## TIDP 440+480_Rev 02
PROJECT: DCMvn Annotation
DOCUMENT: DCMvn_ELT_MSR_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP)
NO: | NAME | Category | DESCRIPTION | FILE TYPE | CREATED BY | AUTHORISED BY | Batch | 2026-01-30 | 2026-02-27 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16
[8 empty] | CW: 05 | CW: 09 | CW: 19 | CW: 20 | CW: 21 | CW: 22 | CW: 23 | CW: 24 | CW: 25 | CW: 26 | CW: 27 | CW: 28 | CW: 29 | CW: 30 | CW: 31 | CW: 32 | CW: 33 | CW: 34 | CW: 35 | CW: 36 | CW: 37 | CW: 38 | CW: 39 | CW: 40 | CW: 41 | CW: 42
A | Framework deliverables (apply to SAN ) |  |  |  | MEP | DIG
1 | Define the "Graphical Annotation Framework" (ELT + MSR)
|  |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 0 | CW: 05: TRM
|  |  | Fill the content for ELT and MSR disciplines | .xlsx | MEP | DIG | 0 | CW: 05: TRM
|  |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | CW: 05: TRM
2 | Define the "Data Requirement Framework" (ELT + MSR)
|  |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 0 | CW: 05: TRM
|  |  | Fill the content for ELT and MSR disciplines | .xlsx | MEP | DIG | 0 | CW: 05: TRM
|  |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | CW: 05: TRM
3 | Define the process to revise the RFA library
|  |  | Confirm and sign the process document | .pdf | MEP | DIG | 0 | CW: 05: TRM
|  |  | Workshop the process with delivery team | .pptx | DIG | DIG | 0 | CW: 09: TRM
4 | Define the desired outcome (ELT + MSR)
|  |  | Produce the sample layouts as multiple scales for LPH3 - ELT Cable trays | .pdf | MEP | MEP | 0 | CW: 19: TRM
|  |  | Produce the sample layouts as multiple scales for LPH3 - ELT Installations | .pdf | MEP | MEP | 0 | CW: 19: TRM
|  |  | Produce the sample layouts as multiple scales for LPH3 - ELT Lightning protection & Earthing system | .pdf | MEP | MEP | 0 | CW: 19: TRM
|  |  | Produce the sample schematics as multiple scales for LPH3 - ELT | .pdf | MEP | MEP | 0 | CW: 19: TRM
|  |  | Produce the sample layouts as multiple scales for LPH5 - ELT Cable trays | .pdf | MEP | MEP | 0 | CW: 20: TRM
|  |  | Produce the sample layouts as multiple scales for LPH5 - ELT Installations | .pdf | MEP | MEP | 0 | CW: 20: TRM
|  |  | Produce the sample layouts as multiple scales for LPH5 - ELT Lightning protection & Earthing system | .pdf | MEP | MEP | 0 | CW: 20: TRM
|  |  | Produce the sample schematics as multiple scales for LPH5 - ELT | .pdf | MEP | MEP | 0 | CW: 20: TRM
|  |  | Produce the sample layouts as multiple scales for LPH8 - ELT Cable trays | .pdf | MEP | MEP | 0 | CW: 21: TRM
|  |  | Produce the sample layouts as multiple scales for LPH8 - ELT Installations | .pdf | MEP | MEP | 0 | CW: 21: TRM
|  |  | Produce the sample layouts as multiple scales for LPH8 - ELT Lightning protection & Earthing system | .pdf | MEP | MEP | 0 | CW: 21: TRM
|  |  | Produce the sample schematics as multiple scales for LPH8 - ELT | .pdf | MEP | MEP | 0 | CW: 21: TRM
|  |  | Produce the sample layouts as multiple scales for LPH3 - MSR | .pdf | MEP | MEP | 0 | CW: 22: TRM
|  |  | Produce the sample schematics as multiple scales for LPH3 - MSR | .pdf | MEP | MEP | 0 | CW: 22: TRM
|  |  | Produce the sample layouts as multiple scales for LPH5 - MSR | .pdf | MEP | MEP | 0 | CW: 22: TRM
|  |  | Produce the sample schematics as multiple scales for LPH5 - MSR | .pdf | MEP | MEP | 0 | CW: 22: TRM
|  |  | Produce the sample layouts as multiple scales for LPH8 - MSR | .pdf | MEP | MEP | 0 | CW: 22: TRM
|  |  | Produce the sample schematics as multiple scales for LPH8 - MSR | .pdf | MEP | MEP | 0 | CW: 22: TRM
B | Revise the RFA library for ELT + MSR system | 413 |  |  | MEP | DIG
B1 | ELT Discipline | 325 | 326 Families need to revise
B.1.1 | EE_Electrical Equipment |  | 46 | .rfa | MEP | DIG
1 | 440_EE_AutomaticTranferSwitchPanel.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
2 | 440_EE_BatteryStorage.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
3 | 442_EE_ChargeController.rfa | 442_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
4 | 440_EE_CircuitBreakerEnclosure.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
5 | 440_EE_DCtoAC_Inverter.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
6 | 440_EE_DieselGenerator.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
7 | 440_EE_DieselTankGenerator.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
8 | 440_EE_DistributionBox_DALI.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
9 | 440_EE_DryTransformer.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
10 | 440_EE_ElectricalCabinet_Standard.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
11 | 440_EE_FlatRoofSolar.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
12 | 440_EE_FlatRoofSolarFrameWithRoot_NoSystem.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
13 | 440_EE_FlatRoofSolarFrame_NoSystem.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
14 | 440_EE_FlatRoofSolarModule.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
15 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSEVU.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
16 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSKälte.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
17 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSNord.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
18 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MsPvAnlage.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
19 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSSüd.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
20 | 440_EE_Generator_Standard.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
21 | 440_EE_IndoorTransformer.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
22 | 440_EE_kwhMeter_3Phases.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
23 | 440_EE_LowVoltagePanel.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | CW: 23: TRM; CW: 24: AUD; CW: 25: REV; CW: 26: CFM
24 | 440_EE_LowVoltageSwitchboard_GHVNord_HOST.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
25 | 440_EE_LowVoltageSwitchboard_GHVSüd_HOST.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
26 | 440_EE_LowVoltageSwitchboard_NshvKälte_HOST.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
27 | 440_EE_LowVoltageSwitchboard_NshvPV_HOST.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
28 | 440_EE_MainDistributionBoard_WallMounted.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
29 | 440_EE_MainSupply_GEVBnetwork.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
30 | 440_EE_MainSupply_UPSmains.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
31 | 440_EE_MainSwitchBoard.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
32 | 440_EE_Manhole_Standard.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
33 | 440_EE_MediumVoltageSwitchgear.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
34 | 440_EE_MotorControlCenter_SwitchBoard.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
35 | 440_EE_OilTransformer.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
36 | 440_EE_OutdoorTransformer.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
37 | 440_EE_PanelBoard.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
38 | 440_EE_SilentDieselGenerator.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
39 | 440_EE_SinglePhase_Panel.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
40 | 440_EE_SpringVibration.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
41 | 440_EE_SubmainSwitchBoard.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
42 | 440_EE_SwitchCabinet_OutgoingPanel.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
43 | 440_EE_SwitchCabinet_SupplyPanel.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
44 | 440_EE_SynchronizationPanel.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
45 | 440_EE_TransferDistributor.rfa | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
46 | 456_EE_BMABusCoupler.rfa | 456_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
B.1.2 | EF_Electrical Fixtures |  | 88 | .rfa | MEP | DIG
1 | 440_EF_360DegreeRadiusMotionDetector_CeilingMounted.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
2 | 446_EF_AirTerminationRodsForMetalRoofs.rfa | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
3 | 446_EF_AirTerminationRods_FloorStand.rfa | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
4 | 440_EF_AL_SideFeedingUnitForTransformer_Busway.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
5 | 440_EF_AL_TakeOffUnitWithFuseSwitch_Busway.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
6 | 440_EF_AL_TopFeedingUnitForTransformer_Busway.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
7 | 481_EF_OutdoorAirTemperatureSensor.rfa | 481_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | CW: 24: TRM; CW: 25: AUD; CW: 26: REV; CW: 27: CFM
8 | 440_EF_CableConnection_PluginSystem.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
9 | 440_EF_ConnectionBrackets.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
10 | 440_EF_DALIPresenceDetectorCombineLightingSensor_CeilingSurface.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
11 | 440_EF_DALIPresenceDetector_CeilingSurface.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
12 | 440_EF_DataConnectionSocket_Audio_Out_HDMI.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
13 | 440_EF_DataConnectionSocket_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
14 | 457_EF_DataConnectionSocket_CeilingMounted_WaterProof.rfa | 457_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
15 | 440_EF_DataConnectionSocket_Floor.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
16 | 440_EF_DataConnectionSocket_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
17 | 440_EF_DaylightSensor_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
18 | 440_EF_DaylightSensor_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
19 | 440_EF_DimmerSwitch_WallRecessed.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
20 | 440_EF_DoorbellPushButton_WallMounted.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
21 | 440_EF_DoubleSocketOutletHorizontal_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
22 | 440_EF_DoubleSocketOutletUSBTypeAC_WallSurface.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
23 | 440_EF_DoubleSocketOutletVertical_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
24 | 440_EF_DoubleSocketOutletVertical_WallFlush.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
25 | 440_EF_DoubleSocketOutlet_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
26 | 440_EF_DoubleSocketOutlet_Floor.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
27 | 440_EF_DoubleSocketOutlet_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
28 | 446_EF_EarthingFixedPoint_WallSurface.rfa | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
29 | 446_EF_Earthing_WallSurface.rfa | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
30 | 440_EF_EarthPit.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
31 | 440_EF_EarthRod.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
32 | 446_EF_EarthTestBox.rfa | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
33 | 440_EF_EmergencyStopPushButtons.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
34 | 440_EF_EnergyBollard.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
35 | 440_EF_Equipotentialbondingbar.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
36 | 446_EF_EquipotentialBondingBusbars_WallMounted.rfa | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
37 | 440_EF_FixedConnection_1Pole.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
38 | 440_EF_FixedConnection_400V.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
39 | 444_EF_GooseneckBushing_NoSystem.rfa | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
40 | 481_EF_Hygrostat.rfa | 481_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
41 | 444_EF_InstallationTrunking.rfa | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
42 | 440_EF_Isolator_3Phases.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
43 | 440_EF_Isolator_SinglePhase.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
44 | 440_EF_JunctionBox_Ceiling_3Pole.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
45 | 440_EF_JunctionBox_Floor_3Pole.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
46 | 440_EF_BasementVentilationControl.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
47 | 440_EF_KeySwitch_WallRecessed.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | CW: 25: TRM; CW: 26: AUD; CW: 27: REV; CW: 28: CFM
48 | 440_EF_KNXPresenceDetection_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
49 | 440_EF_KNX_PushButtonSensor_2gang.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
50 | 440_EF_MainEquipotentialBondingBar.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
51 | 440_EF_PanelBoard.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
52 | 440_EF_PresenceDetector_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
53 | 440_EF_PresenceDetector_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
54 | 440_EF_PushButtonSensorKNX_4gang.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
55 | 440_EF_Raumluftfühler.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
56 | 440_EF_RoomSignallight.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
57 | 440_EF_RotaryDimmer.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
58 | 440_EF_ShaverSocketOutlet_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
59 | 440_EF_SocketDistributionBox_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
60 | 440_EF_SocketDistributionBox_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
61 | 440_EF_SocketOutletCombination_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
62 | 440_EF_SocketOutletRound_Floor.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
63 | 440_EF_SocketOutlet_FloorRecessed_Round.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
64 | 440_EF_SocketOutlet_Horizontal_4Gangs_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
65 | 444_EF_SocketOutlet_Rec_Floor.rfa | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
66 | 444_EF_USBSocketOutlet_WallFlush.rfa | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
67 | 444_EF_SocketOutlet_VerticalWallSurface_4Gangs.rfa | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
68 | 440_EF_SocketOutlet_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
69 | 440_EF_SocketOutlet_WallMounted_WaterProof.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
70 | 440_EF_SocketOutlet_Wall_3Phase.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
71 | 440_EF_SocketOutlet_Wall_4Gangs.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
72 | 440_EF_SocketOutlet_Wall_Combination.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
73 | 440_EF_SwitchableSocketOutlet_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
74 | 440_EF_SwitchableSocketOutlet_Floor.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
75 | 444_EF_SwitchableSocketOutlet_WallSurface.rfa | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
76 | 440_EF_SwitchPushButton_FlushMounted.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
77 | 440_EF_Switch_1Gang.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
78 | 440_EF_Switch_2Gang.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
79 | 440_EF_Switch_2Gang2Way.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
80 | 440_EF_Switch_3Gang.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
81 | 451_EF_TelephoneOutlet_Single.rfa | 451_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | CW: 26: TRM; CW: 27: AUD; CW: 28: REV; CW: 29: CFM
82 | 440_EF_Thermosat.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
83 | 440_EF_TouchPanelRoomOperating_WallMounted.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
84 | 440_EF_TripleSocketOutlet_Ceiling.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
85 | 440_EF_TripleSocketOutlet_Floor.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
86 | 440_EF_TripleSocketOutlet_Wall.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
87 | 440_EF_WindowMotor_WallMounted.rfa | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
88 | 457_EF_VideoModul.rfa | 457_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
B.1.3 | LF_Lighting Fixtures |  | 65 | .rfa | MEP | DIG
1 | 445_LF_3FoldPendantLight_CeilingSuspended.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
2 | 445_LF_BathroomLuminaire_WallMounted_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
3 | 445_LF_CoreLineLEDLight_CeilingSuspended.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
4 | 445_LF_CoreLineLEDLight_WallSurface.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
5 | 445_LF_CorelineSlimDownlight_CeilingMounted.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
6 | 445_LF_CorelineSlimDownlight_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
7 | 445_LF_CorelineSpotlight_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
8 | 445_LF_DownlightLEDrigid_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
9 | 445_LF_DownlightLEDSwivelling_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
10 | 445_LF_EscapeSign_CeilingMounted.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
11 | 445_LF_EscapeSign_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
12 | 445_LF_EscapeSign_WallMounted.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
13 | 445_LF_ExitCube_Ceiling.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
14 | 445_LF_FixedOpticSmallBodyIroundOutdoorlight_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
15 | 445_LF_GreenSpaceAccentSpotlightRigid_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
16 | 445_LF_LaserBladeLightXSWallWasher_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
17 | 445_LF_LaserBladeLightXS_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
18 | 445_LF_LeadSacidTwinHeadEmergencyLight_WallSurface.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
19 | 445_LF_LEDAccentRigidlight_CeilingRecessed_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
20 | 445_LF_LEDBAPPendantLightWithAdjustableRod_CeilingSuspended.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
21 | 445_LF_LEDDeckeneinbauMontage_CeilingMounted_LG6E.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
22 | 445_LF_LEDDoubleHeadEmergencyLight_WallSurface.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
23 | 445_LF_LEDDownlightForWC_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | CW: 30: TRM; CW: 31: AUD; CW: 32: REV; CW: 33: CFM
24 | 445_LF_LEDDownlightSM_CeilingRecessed_Round.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
25 | 445_LF_LEDHighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
26 | 445_LF_LedinaireHighbayPendantLightWithAdjustableRod_CeilingSuspended.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
27 | 445_LF_LedinaireSlimDownlight_CeilingSuspended.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
28 | 445_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
29 | 445_LF_LEDMasterEmergencyLightingLuminaire_WallMounted.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
30 | 445_LF_LEDPanel_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
31 | 445_LF_LEDPendantLightWithAdjustableRod_CeilingSuspended.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
32 | 445_LF_LEDPendantRingLight.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
33 | 445_LF_LEDSignalLightForWC_WallMounted.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
34 | 445_LF_LEDSpotEmergencyLightingLuminaireInFireResistantCeiling_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
35 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
36 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square_SQ5D.rfa | 440_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
37 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round.rfa | 440_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
38 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round_SQ6.rfa | 440_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
39 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Square_SQ5E.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
40 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Round.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
41 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Square.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
42 | 445_LF_LEDSpotEmergencyLightingLuminaire_WallMounted_Square_SQ5A.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
43 | 445_LF_LEDStairEmergencyLight_WallSurface.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
44 | 445_LF_LEDStripLight_CeilingMounted_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
45 | 445_LF_LEDStripLight_CeilingRecessed_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
46 | 445_LF_LEDStripLight_WallSurface_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
47 | 445_LF_LEDTwinHeadsFastChargingIP30EmergencyLight_WallSurface.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
48 | 445_LF_LEDTwoHeadWaterProofIP65EmergencyLight_WallSurface.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
49 | 445_LF_LEDUplight_FloorRecessed_Round.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
50 | 445_LF_LED_HighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
51 | 445_LF_LuxSpaceAccentPerformanceSpotlightSwiveling_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | CW: 31: TRM; CW: 32: AUD; CW: 33: REV; CW: 34: CFM
52 | 445_LF_LuxSpaceCompactAnbaudownlight_CeilingSuspended.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
53 | 445_LF_LuxSpaceDownlight_CeilingRecessed_Square.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
54 | 445_LF_MoistureProofLuminaire_CeilingSuspended_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
55 | 445_LF_OpticalLight_CeilingRecessed_Round_Outdoor.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
56 | 445_LF_TrackSpot-S_CeilingMounted.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
57 | 445_LF_TruelineLinearLuminaire_CeilingRecessed.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
58 | 445_LF_UVCAirDisinfectionLight_WallSurface.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
59 | 445_LF_InteriorLuminaireBL_CeilingRecessed_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
60 | 445_LF_InteriorLuminaireINDMP_CeilingRecessed_Round.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
61 | 445_LF_LEDDownlightOP_CeilingRecessed_Round.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
62 | 445_LF_LEDDownlightSFNB_CeilingRecessed_Round.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
63 | 445_LF_LEDLuminaireMP_CeilingMounted_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
64 | 445_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
65 | 445_LF_MoistureProofLuminaire_WallSurface_Rectangular.rfa | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.4 | FA_Fire Alarm Devices |  | 2 | .rfa | MEP | DIG
1 | 456_FA_AspiratingSmokesSystem2Channel_WallMounted.rfa | 456_FA | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
2 | 456_FA_SmokeSamplingHead_Ceiling.rfa | 456_FA | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.5 | LD_Lighting Devices |  | 2 | .rfa | MEP | DIG
1 | 440_LD_DoubleSwitchSocket_WallMounted.rfa | 440_LD | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
2 | 440_LD_SingleSwitchSocket_WallMounted.rfa | 440_LD | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.6 | DD_Data Devices |  | 1 | .rfa | MEP | DIG
1 | 481_EE_SmartHomeAccessPoint_WLAN.rfa | 481_EE | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.7 | SD_Security Devices |  | 1 | .rfa | MEP | DIG
1 | 457_SD_DomeCamera_Outdoor.rfa | 457_SD | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.8 | SE |  | 2 | .rfa | MEP | DIG
1 | 440_SE_AccessPanel_Ceiling.rfa | 440_SE | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
2 | 440_SE_Penetration_CuraFlex.rfa | 440_SE | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.9 | CD_Communication Devices |  | 1 | .rfa | MEP | DIG
1 | 455_CD_IndoorAntenna_Ceiling.rfa | 455_CD | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.10 | NC |  | 1 | .rfa | MEP | DIG
1 | 440_NC_EmergencyPullCordSwitch_Wall.rfa | 440_NC | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B.1.11 | CF_Cable Tray Fittings |  | 66 | .rfa | MEP | DIG
1 | 440_CF_AL_eHorizontalElbow_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
2 | 440_CF_AL_eVerticalElbow90Deg_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
3 | 440_CF_AL_eVerticalOffsetElbow90Deg_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
4 | 440_CF_AL_mHorizontalOffsetZShade_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
5 | 440_CF_AL_mVerticalOffsetZShade_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
6 | 440_CF_AL_StraightLength_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
7 | 440_CF_AL_tVerticalTee_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
8 | 440_CF_AL_uEndFlange_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
9 | 440_CF_wChannelHorizontalWye_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
10 | 440_CF_CO_eDoubleLeftElbow_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
11 | 440_CF_CO_eEdgewiseElbowWithAngle_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
12 | 440_CF_CO_eEdgewiseElbow_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
13 | 440_CF_CO_eEdgewiseOffet_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
14 | 440_CF_CO_eFlatwiseOffsetElbow_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
15 | 440_CF_CO_eFlatwise_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
16 | 440_CF_CO_mChannelMultiPort_Standard_FeedUnitForDryTransformer.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
17 | 440_CF_CO_uFlangedEnd_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
18 | 440_CF_CS_eCavityFloorBoxWithHeatResistantRoundFormworkBodyElbow_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
19 | 440_CF_CS_eCavityFloorBoxWithHeatResistantSquareFormworkBodyElbow_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
20 | 440_CF_CS_eCavityFloorBoxWithRoundFormworkBodyElbow_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
21 | 440_CF_CS_eCavityFloorBoxWithSquareFormworkBodyElbow_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
22 | 440_CF_CS_eScreedCovered_Standard_ChannelThreePartVerticalBend.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
23 | 440_CF_CS_eScreedCovered_Standard_ChannelTwoPartVerticalBend.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
24 | 440_CF_CS_tCavityFloorBoxWithHeatResistantRoundFormworkBodyTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
25 | 440_CF_CS_tCavityFloorBoxWithHeatResistantSquareFormworkBodyTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
26 | 440_CF_CS_tCavityFloorBoxWithRoundFormworkBodyTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
27 | 440_CF_CS_tCavityFloorBoxWithSquareFormworkBodyTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
28 | 440_CF_CS_uCavityFloorBoxWithHeatResistantRoundFormworkBodyEnd_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
29 | 440_CF_CS_uCavityFloorBoxWithHeatResistantSquareFormworkBodyEnd_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
30 | 440_CF_CS_uCavityFloorBoxWithRoundFormworkBodyEnd_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
31 | 440_CF_CS_uCavityFloorBoxWithSquareFormworkBodyEnd_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
32 | 440_CF_CS_xCavityFloorBoxWithHeatResistantRoundFormworkBodyCross_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
33 | 440_CF_CS_xCavityFloorBoxWithHeatResistantSquareFormworkBodyCross_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
34 | 440_CF_CS_xCavityFloorBoxWithRoundFormworkBodyCross_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
35 | 440_CF_CS_xCavityFloorBoxWithSquareFormworkBodyCross_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
36 | 440_CF_ehFlatwiseElbowFlangeEnd_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
37 | 440_CF_ehFlatwiseElbowWithAngle_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
38 | 440_CF_mFlatwiseTee_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
39 | 440_CF_mPhaseTransition_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
40 | 440_CF_mPotentialEqualisationBusbar.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
41 | 440_CF_mStraightLength_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
42 | 440_CF_ST_ehChannelHorizontalBend_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 27: TRM; CW: 28: AUD; CW: 29: REV; CW: 30: CFM
43 | 440_CF_ST_xChannelHorizontalCross_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
44 | 440_CF_ST_ehChannelHorizontalMiteredBend_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
45 | 440_CF_ST_tChannelHorizontalTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
46 | 440_CF_ST_rChannelTransition_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
47 | 440_CF_ST_uChannelUnion_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
48 | 440_CF_ST_xvChannelVerticalCross_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
49 | 440_CF_ST_tvChannelVerticalDownTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
50 | 440_CF_ST_eiChannelVerticalInsideBend_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
51 | 440_CF_ST_eoChannelVerticalOutsideBend_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
52 | 440_CF_ST_ehLadderHorizontalBend_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
53 | 440_CF_ST_xLadderHorizontalCross_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
54 | 440_CF_ST_tLadderHorizontalTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
55 | 440_CF_ST_rLadderTransition_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
56 | 440_CF_ST_uLadderUnion_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
57 | 440_CF_ST_tvLadderUTypeVerticalTee_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
58 | 440_CF_ST_xvLadderVerticalCross_Standard | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
59 | 440_CF_ST_eiLadderVerticalInsideBend_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
60 | 440_CF_ST_eoLadderVerticalOutsideBend_Standard.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
61 | 440_CF_uCableTapBoxCenter_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
62 | 440_CF_uCableTapBoxEnd_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
63 | 440_CF_uEndClosure_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
64 | 440_CF_uFlexibleLink_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
65 | 440_CF_UnfusedReducer_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
66 | 440_CF_uWallFloorFlange_Busway.rfa | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
B.1.12 | CI_Conduit Fittings |  | 50 | .rfa | MEP | DIG
1 | 440_CI_CS_tClamps_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
2 | 440_CI_CS_tExpansionPiecesRound_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
3 | 440_CI_CS_xClamps_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
4 | 440_CI_CS_xExpansionPiecesRound_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
5 | 440_CI_PC_mJunctionBox_Standard_Weatherproof.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
6 | 440_CI_PVC_e30DegreeElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
7 | 440_CI_PVC_e45DegreeElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
8 | 440_CI_PVC_e90DegreeElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
9 | 440_CI_PVC_eAngledTwoWayBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
10 | 440_CI_PVC_cMarkerforConnectionLugs.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
11 | 440_CI_PVC_uConduitBodiesTypeC_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
12 | 440_CI_PVC_cConduitBodiesTypeE_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
13 | 440_CI_PVC_eConduitBodiesTypeLB_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
14 | 440_CI_PVC_eConduitBodiesTypeLL_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
15 | 440_CI_PVC_eConduitBodiesTypeLR_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
16 | 440_CI_PVC_tConduitBodiesTypeT_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
17 | 440_CI_PVC_ConduitSleeveCoupling_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
18 | 440_CI_PVC_fCoupling_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
19 | 440_CI_PVC_mHWayJuntionBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
20 | 440_CI_PVC_eInspectionBend_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 28: TRM; CW: 29: AUD; CW: 30: REV; CW: 31: CFM
21 | 440_CI_PVC_e90DegreeInspectionElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
22 | 440_CI_PVC_tInspectionTee_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
23 | 440_CI_PVC_xIntersectionFourWayBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
24 | 440_CI_PVC_uJunctionBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
25 | 440_CI_PVC_mJunctionBox_Standard_ThreeWay.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
26 | 440_CI_PVC_rReducer_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
27 | 440_CI_PVC_tTeeThreeWayBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
28 | 440_CI_PVC_cTerminalOneWayBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
29 | 440_CI_PVC_uThroughTwoWayBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
30 | 440_CI_PVC_mUWayBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
31 | 440_CI_PVC_mYWayBox_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
32 | 440_CI_SS_cDeviceBoxes_Threaded.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
33 | 440_CI_SS_e45DegreeElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
34 | 440_CI_SS_e45DegreeElbow_Threaded.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
35 | 440_CI_SS_e90DegreeElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
36 | 440_CI_SS_e90DegreeElbow_Threaded.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
37 | 440_CI_SS_eConduitBodies_Threaded_TypeLB.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
38 | 440_CI_SS_eConduitBodies_Threaded_TypeLR.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
39 | 440_CI_SS_eConduitBodies_Threaded_TypeLU.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
40 | 440_CI_SS_eConduitBodies_TypeLL_Threaded.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
41 | 440_CI_SS_eFlatConductorsElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
42 | 440_CI_SS_eInspectionElbow_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
43 | 440_CI_SS_FlatStrip_Standard.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
44 | 440_CI_SS_tConduitBodies_Threaded_TypeT.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
45 | 440_CI_SS_tConduitBodies_Threaded_TypeTB.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
46 | 440_CI_SS_uCFormConduitUnion_Threaded.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
47 | 440_CI_SS_xConduitBodies_Threaded_TypeX.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
48 | 440_CI_SS_xCrossConductorFlatToRound.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
49 | 440_CI_SS_xFlatConductorCross.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 29: TRM; CW: 30: AUD; CW: 31: REV; CW: 32: CFM
50 | 440_CI_ST_mJunctionBox_Explosionproof.rfa | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | CW: 32: TRM; CW: 33: AUD; CW: 34: REV; CW: 35: CFM
B2 | MSR Discipline | 88 | 89 Families need to revise
B.2.1 | FA_Fire Alarm Devices |  | 37 | .rfa | MEP | DIG
1 | 480_FA_AddressableManualPullStation.rfa | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
2 | 456_FA_AddressableSensor.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
3 | 480_FA_AnnunciatorPanel.rfa | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
4 | 456_FA_AspiratingSmokeDetector_WallMounted.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
5 | 456_FA_BeamSensor_WallSurface_Rectangular.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
6 | 480_FA_Bell.rfa | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
7 | 456_FA_CouplerUnit.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
8 | 456_FA_DetectorWithHorn.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
9 | 456_FA_Detector_CO1224A.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
10 | 456_FA_Detector_CO1224TR.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
11 | 456_FA_EmegencyDoorRelease_WallMounted.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
12 | 456_FA_FireAlarmCenter.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
13 | 456_FA_FireAlarmControlPanel.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
14 | 456_FA_FireAlarmZoneModuleControl.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
15 | 456_FA_FireBrigadeInformationCenter_WallMounted.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
16 | 456_FA_FireDepartmentKeyDepot.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
17 | 480_FA_FireDoorHolder.rfa | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
18 | 456_FA_HeatSensor.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
19 | 480_FA_LEDIndicator_WallMounted.rfa | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
20 | 456_FA_LinearHeatDetector.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
21 | 456_FA_MultiSensorDetector_Ceiling.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
22 | 456_FA_O2TMultisensordetector.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
23 | 456_FA_O2TMultisensordetector_BottomSlab.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
24 | 456_FA_PhotoelectricSmokeDetector.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
25 | 456_FA_PhotoThermalSensor_CeilingMouted_Round.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
26 | 456_FA_PresenceDetector24m_Ceiling.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
27 | 456_FA_PresenceDetectorHTS_Ceiling.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
28 | 456_FA_PushButton_WallMounted_RWA.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
29 | 480_FA_SmokeDectectorOpticalSignal_Ceiling.rfa | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
30 | 456_FA_SmokeSensor_BottomSlab.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
31 | 456_FA_SmokeSensor_Ceiling.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
32 | 456_FA_SmokeSensor_RaiseFloor.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
33 | 456_FA_ManualCallPoint_WallMounted_Square.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
34 | 456_FA_ManualCallPoint_WallMounted_Square_Waterproof.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
35 | 480_FA_TransferUnit.rfa | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
36 | 454_FA_VandalResistantLoudSpeaker.rfa | 454_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
37 | 456_FA_WindandRainDetector_WallMounted_RWA.rfa | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 33: TRM; CW: 34: AUD; CW: 35: REV; CW: 36: CFM
B.2.2 | EE_Electrical Equipment |  | 11 | .rfa | MEP | DIG
1 | 482_EE_ControlDistribution_WallMounted.rfa | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
2 | 456_EE_ConventionalControlPanel_WallSurface_Rectangular.rfa | 456_EE | MSR Revit Family | .rfa | MEP | DIG | 11 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
3 | 457_EE_DataCabinet.rfa | 457_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
4 | 457_EE_DataServerCabinet_FloorStand_Rectangular.rfa | 457_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
5 | 482_EE_Distribution_FloorStanding_Indoor.rfa | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
6 | 482_EE_Distribution_FloorStanding_Outdoor.rfa | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
7 | 456_EE_PowerSupplyUnitAccessControl_WallMounted.rfa | 456_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
8 | 454_EE_PublicAddressSystemPanel_FloorMounted.rfa | 454_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
9 | 482_EE_RackCabinet_WallMounted.rfa | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
10 | 482_EE_SwitchCabinet_FloorStand_Rectangular.rfa | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
11 | 480_EE_WallControlPanel_WallMounted.rfa | 480_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
B.2.3 | EF_Electrical Fixtures |  | 8 | .rfa | MEP | DIG
1 | 480_EF_IndividualRoomController.rfa | 480_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
2 | 444_CI_ABS_mIndustrialBox.rfa | 444_CI | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
3 | 446_EF_LightningCounterDevice.rfa | 446_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
4 | 446_EF_LightningRod_NoSystem.rfa | 446_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
5 | 443_EF_OvervoltageProtection_WallFlush.rfa | 443_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
6 | 442_EF_SealedBatteries.rfa | 442_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
7 | 452_EF_TouchButton_WallMounted.rfa | 452_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
8 | 484_EF_Transferbox.rfa | 484_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
B.2.4 | CD_Communication Devices |  | 10 | .rfa | MEP | DIG
1 | 454_CD_CabinetLoudspeaker6W_WallMounted_Circular.rfa | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
2 | 454_CD_CabinetLoudspeaker6W_WallMounted_Rectangular.rfa | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
3 | 454_CD_CabinetLoudspeaker6W_WallMounted_Square.rfa | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
4 | 452_CD_CallButtonPullCord.rfa | 452_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
5 | 456_CD_DeskIntercomStation.rfa | 456_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
6 | 454_CD_FireDepartmentContactPoint_WallMounted.rfa | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
7 | 454_CD_HornLoudspeaker15W_WallMounted.rfa | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
8 | 454_CD_Loudspeaker6W_CeilingRecessed.rfa | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
9 | 457_CD_Router_Indoor.rfa | 457_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
10 | 456_CD_Siren.rfa | 456_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 34: TRM; CW: 35: AUD; CW: 36: REV; CW: 37: CFM
B.2.5 | SD_Security Devices |  | 17 | .rfa | MEP | DIG
1 | 456_SD_AnalogCamera.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
2 | 456_SD_CameraHub_16Port.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
3 | 456_SD_CameraHub_8Port.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
4 | 456_SD_CardReader.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
5 | 456_SD_DomeCamera_Indoor.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
6 | 456_SD_DomeCamera_Outdoor.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
7 | 456_SD_ElectricalLock_DoorMounted.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
8 | 456_SD_FingerScan.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
9 | 456_SD_FingerScanFace_WallMounted.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
10 | 456_SD_FixCameraIP_Indoor.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
11 | 456_SD_FixCameraIP_Outdoor.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
12 | 456_SD_Monitor.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
13 | 456_SD_PTZCamera_Indoor.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
14 | 456_SD_PTZCamera_Outdoor.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
15 | 456_SD_SecurityAlarmBell.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
16 | 456_SD_ThermalCamera.rfa | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
17 | 442_SD_UPSBattery_FloorStand_Rectangular.rfa | 442_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
B.2.6 | DD_Data Devices |  | 5 | .rfa | MEP | DIG
1 | 481_DD_BACnetGateway.rfa | 481_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
2 | 457_DD_LanAndTelOutlet_WallSurface.rfa | 457_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
3 | 457_DD_LanOutlet_WallMounted_2Gangs.rfa | 457_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
4 | 451_DD_TelOutlet_WallMounted_2Gangs.rfa | 451_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
5 | 455_DD_TVOutlet_WallMounted_1Gang.rfa | 455_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | CW: 35: TRM; CW: 36: AUD; CW: 37: REV; CW: 38: CFM
C | Create the Revit templates for each LPH (ELT + MSR)
1 | Revit Template for ELT in LPH3 | ELT | Revit Template | .rte | MEP | DIG | 13 | CW: 39: TRM; CW: 40: CFM
2 | Revit Template for ELT in LPH5 | ELT | Revit Template | .rte | MEP | DIG | 13 | CW: 39: TRM; CW: 40: CFM
3 | Revit Template for ELT in LPH8 | ELT | Revit Template | .rte | MEP | DIG | 13 | CW: 39: TRM; CW: 40: CFM
4 | Revit Template for MSR in LPH3 | MSR | Revit Template | .rte | MEP | DIG | 13 | CW: 39: TRM; CW: 40: CFM
5 | Revit Template for MSR in LPH5 | MSR | Revit Template | .rte | MEP | DIG | 13 | CW: 39: TRM; CW: 40: CFM
6 | Revit Template for MSR in LPH8 | MSR | Revit Template | .rte | MEP | DIG | 13 | CW: 39: TRM; CW: 40: CFM
D | Create the Output Checklists for each LPH (ELT + MSR)
D1 | LPH3 Check list for ELT discipline | ELT |  | .xlsx | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH3_Check list_ELT 01 | ELT | Checklist_Layout Plan. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH3_Check list_ELT 02 | ELT | Checklist_Section. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH3_Check list_ELT 03 | ELT | Checklist_Schematic Diagram. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
D2 | LPH5 Check list for ELT discipline | ELT |  | .xlsx | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH5_Check list_ELT 01 | ELT | Checklist_Layout Plan. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH5_Check list_ELT 02 | ELT | Checklist_Section. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH5_Check list_ELT 03 | ELT | Checklist_Schematic Diagram. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
D3 | LPH8 Check list for ELT discipline | ELT |  | .xlsx | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH8_Check list_ELT 01 | ELT | Checklist_Layout Plan. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH8_Check list_ELT 02 | ELT | Checklist_Section. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
| LPH8_Check list_ELT 03 | ELT | Checklist_Schematic Diagram. |  | MEP | DIG | 14 | CW: 40: TRM; CW: 41: CFM
D4 | LPH3 Check list for MSR discipline | MSR |  | .xlsx | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH3_Check list_MSR 01 | MSR | Checklist_Layout Plan. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH3_Check list_MSR 02 | MSR | Checklist_Section. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH3_Check list_MSR 03 | MSR | Checklist_Schematic Diagram. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
D5 | LPH5 Check list for MSR discipline | MSR |  | .xlsx | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH5_Check list_MSR 01 | MSR | Checklist_Layout Plan. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH5_Check list_MSR 02 | MSR | Checklist_Section. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH5_Check list_MSR 03 | MSR | Checklist_Schematic Diagram. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
D6 | LPH8 Check list for MSR discipline | MSR |  | .xlsx | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH8_Check list_MSR 01 | MSR | Checklist_Layout Plan. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH8_Check list_MSR 02 | MSR | Checklist_Section. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
| LPH8_Check list_MSR 03 | MSR | Checklist_Schematic Diagram. |  | MEP | DIG | 15 | CW: 40: TRM; CW: 41: CFM
E | Sample Model + Output Data
E1 | Sample Model + Output Data For ELT
1 | Delivery 2nd Draft layout for ELT LPH3 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
2 | Delivery 2nd Draft layout for ELT LPH5 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
3 | Delivery 2nd Draft layout for ELT LPH8 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
4 | Delivery 2nd Draft Schematic Drawing Sample for ELT LPH3 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
5 | Delivery 2nd Draft Schematic Drawing Sample for ELT LPH5 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
6 | Delivery 2nd Draft Schematic Drawing Sample for ELT LPH8 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
E2 | Sample Model + Output Data For MSR
1 | Delivery 2nd Draft layout for MSR LPH3 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
2 | Delivery 2nd Draft layout for MSR LPH5 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
3 | Delivery 2nd Draft layout for MSR LPH8 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
4 | Delivery 2nd Draft Schematic Drawing Sample for MSR LPH3 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
5 | Delivery 2nd Draft Schematic Drawing Sample for MSR LPH5 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
6 | Delivery 2nd Draft Schematic Drawing Sample for MSR LPH8 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
F | Export layouts to Revizto & set up 3D Overlay (ELT + MSR)
1 | Export layouts to Revizto & set up 3D Overlay ELT _LPH3 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
2 | Export layouts to Revizto & set up 3D Overlay ELT _LPH5 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
3 | Export layouts to Revizto & set up 3D Overlay ELT _LPH8 | ELT |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
4 | Export layouts to Revizto & set up 3D Overlay MSR _LPH3 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
5 | Export layouts to Revizto & set up 3D Overlay MSR _LPH5 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
6 | Export layouts to Revizto & set up 3D Overlay MSR _LPH8 | MSR |  | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
G | Lesson Learned
1 | Lesson Learned ELT | ELT | What went well. What need to be improved What we learned, Action items / Improvements | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
2 | Lesson Learned MSR | MSR | What went well. What need to be improved What we learned, Action items / Improvements | .pdf | MEP | DIG | 16 | CW: 41: TRM; CW: 42: CFM
Legend:
TRM | Transmistal | MEP
AUD | Auditing | DIG
REV | Revision | MEP
CFM | Confimmation/Final Submision | DIG/MEP

## Sheet1
3.374%
315