## TIDP 410_Rev 02
PROJECT: DCMVN ANNOTATION
DOCUMENT: DCMVN_HKT_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP)
NO: | NAME | Category | DESCRIPTION | FILE TYPE | CREATED BY | AUTHORISED BY | Batch | 2026-01-30 | 2026-02-27 | 2026-05-22 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | 2026-09-04 | 2026-09-10 | 2026-09-16 | 2026-09-22 | 2026-09-28
A | Framework deliverables (apply to HKG ) |  |  |  | MEP | DIG
1 | DeREVe the "Graphical Annotation Framework" HKG
|  |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 0 | TRM
|  |  | Fill the content for HKG disciplines | .xlsx | MEP | DIG | 0 | TRM
|  |  | Confirm and sign the document | .pdf | MEP | DIG | 0
2 | DeREVe the "Data Requirement Framework" HKG
|  |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 0 | TRM
|  |  | Fill the content for HKG discipline | .xlsx | MEP | DIG | 0 |  | TRM
|  |  | Confirm and sign the document | .pdf | MEP | DIG | 0 |  |  | TRM
3 | DeREVe the process to revise the RFA library
|  |  | Confirm and sign the process document | .pdf | MEP | DIG | 0 |  |  | TRM
|  |  | Workshop the process with delivery team | .pptx | DIG | DIG | 0 |  | TRM
B | Revise the RFA library for HKG system |  |  |  | MEP | DIG
| HZG Discipline | [30 empty] | Status | Assigned To | Ticket
1 | 420_PF_Brass_ThreeWayEqualTee_Compression | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72195
2 | 420_PF_Copper_Elbow | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72177
3 | 420_PF_CO_cCap_Soldered | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72196
4 | 420_PF_CO_eElbow_Soldered | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72198
5 | 420_PF_CO_rReducer_Soldered | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | new | hu.dam | 73509
6 | 420_PF_CO_tTee_Soldered | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72586
7 | 420_PF_CO_uUnion_Soldered | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72585
8 | 420_PF_CO_xCross_Soldered | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72584
9 | 420_PF_CS_cCap_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72583
10 | 420_PF_CS_eElbow_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72582
11 | 420_PF_CS_fConnectionFlanged_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72204
12 | 420_PF_CS_rReducer_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72203
13 | 420_PF_CS_sTap_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72202
14 | 420_PF_CS_tTee_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72201
15 | 420_PF_CS_uUnion_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72200
16 | 420_PF_CS_xCross_Welded | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72199
17 | 420_PF_MapressCarbonSteel_Cap_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72176
18 | 420_PF_MapressCarbonSteel_Cross_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72175
19 | 420_PF_MapressCarbonSteel_Elbow_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | ht.tran | 72174
20 | 420_PF_MapressCarbonSteel_FlangeAdaptor_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72173
21 | 420_PF_MapressCarbonSteel_SocketAdaptor_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72172
22 | 420_PF_MapressCarbonSteel_SocketFlangeAdaptor_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72171
23 | 420_PF_MapressCarbonSteel_Tee_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72170
24 | 420_PF_MapressCarbonSteel_Transition_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72169
25 | 420_PF_MapressCarbonSteel_Union_SlipJoin | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72168
26 | 420_PF_PE_eElbow | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 72167
27 | 420_PA_6WayValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | acknowledged | ht.tran | 73832
28 | 420_PA_AirReleaseValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | ht.tran | 73831
29 | 420_PA_AirReleaseValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | ht.tran | 73830
30 | 420_PA_AirValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73829
31 | 420_PA_BalancingValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | acknowledged | ht.tran | 73828
32 | 420_PA_BalancingValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | acknowledged | ht.tran | 73827
33 | 420_PA_BalancingValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73826
34 | 420_PA_BalancingValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | new | ht.tran | 73825
35 | 420_PA_BallValve3Way_LPort | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73824
36 | 420_PA_BallValve3Way_TPort | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73823
37 | 420_PA_BallValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | b.tran | 73822
38 | 420_PA_BallValve_Flanged_LeverStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | qd.nguyen | 73821
39 | 420_PA_BallValve_Flanged_WheelStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | qd.nguyen | 73820
40 | 420_PA_BallValve_FullBore | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73819
41 | 420_PA_BallValve_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73551
42 | 420_PA_BallValve_Thread_LeverStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73553
43 | 420_PA_BallValve_Thread_WheelStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73552
44 | 420_PA_BasketStrainerValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73550
45 | 420_PA_BasketStrainerValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73549
46 | 420_PA_ButterflyValveHandwheel_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73548
47 | 420_PA_ButterflyvalveMotor_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73543
48 | 420_PA_ButterflyValve_Flanged_GearStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73547
49 | 420_PA_ButterflyValve_Flanged_Handle | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73818
50 | 420_PA_ButterflyValve_Flanged_LeverStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73546
51 | 420_PA_ButterflyValve_Thread_GearStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73545
52 | 420_PA_ButterflyValve_Thread_LeverStandard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73544
53 | 420_PA_CapValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73542
54 | 420_PA_CheckValveWithThermometer_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73541
55 | 420_PA_DifferentialPressureControlValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | l.nguyen | 73540
56 | 420_PA_DifferentialPressureGauge_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73539
57 | 420_PA_DifferentialPressureSensor | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | qd.nguyen | 73537
58 | 420_PA_DifferentialPressureSensor_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | dahn.nguyen | 73536
59 | 420_PA_DiscCheckValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73535
60 | 420_PA_DrainValve_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73533
61 | 420_PA_DrainValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73534
62 | 420_PA_ExpansionJoint_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73532
63 | 420_PA_ExpansionJoint_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73531
64 | 420_PA_ExpansionJoint_Weld | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | b.tran | 73530
65 | 420_PA_FillAndDrainBallValve_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73529
66 | 420_PA_FilterValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73528
67 | 420_PA_FilterValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73527
68 | 420_PA_FlexibleConnection_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73526
69 | 420_PA_FlexibleConnection_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73146
70 | 420_PA_FlowSensor | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73145
71 | 420_PA_FlowSensor_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73144
72 | 420_PA_FlowSensor_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73143
73 | 420_PA_GateValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73142
74 | 420_PA_GateValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73141
75 | 420_PA_GateValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73140
76 | 420_PA_GateValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73139
77 | 420_PA_GlobeValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73138
78 | 420_PA_GlobeValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | ht.tran | 73136
79 | 420_PA_GlobeValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | ht.tran | 73135
80 | 420_PA_GlobeValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | ht.tran | 73134
81 | 420_PA_HeatingBallValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73130
82 | 420_PA_HeatMeter_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73133
83 | 420_PA_HeatMeter_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73132
84 | 420_PA_HeatMeter_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73131
85 | 420_PA_LiftCheckValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73129
86 | 420_PA_LiftCheckValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73128
87 | 420_PA_ManifoldConnection_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73525
88 | 420_PA_MotorizedBallValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | lk.dang | 73127
89 | 420_PA_MotorizedBallValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | nd.huynh | 73126
90 | 420_PA_MotorizedButterflyValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73125
91 | 420_PA_MotorizedGateValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73124
92 | 420_PA_MotorizedGateValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73123
93 | 420_PA_MotorizedGlobeValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73122
94 | 420_PA_MotorizedGlobeValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73121
95 | 420_PA_MotorizedThreeWayValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73120
96 | 420_PA_MotorizedThreeWayvalve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73119
97 | 420_PA_NonReturnFlap_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | assigned | kd.doan | 73118
98 | 420_PA_PICCV2WayValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73117
99 | 420_PA_PICCV3WayValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73116
100 | 420_PA_PICVValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 |  |  |  | TRM | AUD | REV | CFM | [17 empty] | closed | hu.dam | 73524
101 | 420_PA_PIQCV6WayValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | ht.tran | 73115
102 | 420_PA_PIQCVValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | b.tran | 73522
103 | 420_PA_PneumaticControlValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | kd.doan | 73114
104 | 420_PA_PneumaticGlobeControlValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | kd.doan | 73113
105 | 420_PA_PneumaticGlobeControlValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 73112
106 | 420_PA_PressureGauge | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | b.tran | 73111
107 | 420_PA_PressureGauge_2Connection | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | b.tran | 73110
108 | 420_PA_PressureGauge_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | b.tran | 73109
109 | 420_PA_PressureIndependentControlValveCompact_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 73108
110 | 420_PA_PressureIndependentControlValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 73107
111 | 420_PA_PressureIndependentControlValve_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 73106
112 | 420_PA_PressureReducingValveWithGauge_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 73105
113 | 420_PA_PressureSensor | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 72695
114 | 420_PA_PressureSensor_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | ht.pham | 72694
115 | 420_PA_RadiatorLockshield_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 72693
116 | 420_PA_RadiatorShutOffValveAngle_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 72691
117 | 420_PA_RadiatorShutOffValveStraight_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 72690
118 | 420_PA_RadiatorThermostatic2PointAngleValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 72688
119 | 420_PA_RadiatorThermostaticAngleValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | hu.dam | 72687
120 | 420_PA_RadiatorThermostaticStraightValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | n.le | 72686
121 | 420_PA_RegulatingValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | nd.huynh | 72684
122 | 420_PA_RegulatingValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | nd.huynh | 72683
123 | 420_PA_RegulatingValve_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72662
124 | 420_PA_RegulatingValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72663
125 | 420_PA_SafetyReliefValveConer_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72660
126 | 420_PA_SafetyReliefValveCorner_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72659
127 | 420_PA_SafetyReliefValveStraight_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | kd.doan | 72658
128 | 420_PA_SafetyValveCorner_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72657
129 | 420_PA_SafetyValveCorner_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72655
130 | 420_PA_ShutOffValveWithSafetyFunction_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 73521
131 | 420_PA_ShutoffValve_Motorized | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | d.phan | 73520
132 | 420_PA_SixWayMotorisedControlValve_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | qd.nguyen | 73517
133 | 420_PA_SmartForEnergyManagement_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | qn.ha | 73516
134 | 420_PA_SmartForEnergyManagement_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | qn.ha | 73515
135 | 420_PA_SpringCheckValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72654
136 | 420_PA_SwingcheckValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | ht.tran | 72650
137 | 420_PA_SwingCheckValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | nd.huynh | 72653
138 | 420_PA_SwingcheckValve_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | ht.nguyen | 72604
139 | 420_PA_SwingCheckValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72652
140 | 420_PA_TemperatureGauge_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72603
141 | 420_PA_TemperatureRegulatorValve_SelfOperated | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 73514
142 | 420_PA_TemperatureSensor | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72602
143 | 420_PA_TemperatureSensor_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | #N/A | #N/A | #N/A
144 | 420_PA_Thermometer | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72600
145 | 420_PA_Thermometergauge | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | ht.nguyen | 72599
146 | 420_PA_ThreeWayMotorisedControlValve_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 73513
147 | 420_PA_ThreeWayMotorisedControlValve_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | lk.dang | 73512
148 | 420_PA_ThreeWayvalve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72598
149 | 420_PA_ThreeWayvalve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | ht.tran | 72597
150 | 420_PA_WaferCheckValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | ht.tran | 72595
151 | 420_PA_WaterMeter_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | ht.tran | 72594
152 | 420_PA_WaterMeter_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | ht.tran | 72593
153 | 420_PA_WaterMeter_Threaded | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72591
154 | 420_PA_WaterMeter_Threaded_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | assigned | qn.ha | 73511
155 | 420_PA_YStrainerValve_Flanged_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72590
156 | 420_PA_YStrainerValve_Thread_Standard | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72589
157 | 420_PA_YStrainer_Flanged | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72588
158 | 420_PA_YStrainer_Thread | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | closed | hu.dam | 72587
159 | 420_HeatExchangerTank_VerticalPump | 420_He | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75193
160 | 420_ME_AirCoolHeatPump_MonoBlock | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75194
161 | 420_ME_AirCurtain_StandingType | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75195
162 | 420_ME_AirCurtain_WallMounted | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75196
163 | 420_ME_AirCurtain_WallMounted_Standard | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75197
164 | 420_ME_AirHeater_Top | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75198
165 | 420_ME_AirSoureHeatPump | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75199
166 | 420_ME_BufferHeatingTank | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | ht.tran | 75200
167 | 420_ME_BufferTank_Custom | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | ht.tran | 75201
168 | 420_ME_BufferTank_Standard | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | ht.tran | 75202
169 | 420_ME_BufferTank_StorathermHeat&WithInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | ht.tran | 75203
170 | 420_ME_BufferTank_StorathermHeat1Coil&WithInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | ht.tran | 75204
171 | 420_ME_BufferTank_StorathermHeat1Coil&WithoutInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75205
172 | 420_ME_BufferTank_StorathermHeat2Coil&WithInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75206
173 | 420_ME_BufferTank_StorathermHeatCombi1Coil&WithInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75207
174 | 420_ME_BufferTank_StorathermHeatCombi2Coil&WithInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75208
175 | 420_ME_BufferTank_StorathermHeatFlange&WithInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75209
176 | 420_ME_BufferTank_StorathermHeatFlange&WithoutInsulation | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | th.nguyen | 75210
177 | 420_ME_CeilingPanel_Standard | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | th.nguyen | 75211
178 | 420_ME_CentrifugalPumpWithElectricMotor_Horizontal | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | th.nguyen | 75212
179 | 420_ME_ColdWaterTank | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | th.nguyen | 75213
180 | 420_ME_CompressedAirTank | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | th.nguyen | 75214
181 | 420_ME_ControlValveGroup | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75215
182 | 420_ME_Convector_FloorSurface | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75216
183 | 420_ME_EnergyDistributor_6Pairs | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75217
184 | 420_ME_EnergyDistributor_8Pairs | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75218
185 | 420_ME_ExpansionTank_FloorStand | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | d.phan | 75219
186 | 420_ME_ExpansionTank_Standard | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75220
187 | 420_ME_FacadeHeating_Standard | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75222
188 | 420_ME_Fancoilunit_UnderfloorTrench_KathermNK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75223
189 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQE_NoSystem | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75224
190 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75225
191 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQKnano | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75226
192 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_1Connector | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75227
193 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_2Connector | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75228
194 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_3Connector | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75229
195 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_4Connector | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75230
196 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_5Connector | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75231
197 | 420_ME_FWTransfer | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | acknowledged | b.tran | 75221
198 | 420_ME_HeatExchangerFreeCooling_Flange | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75232
199 | 420_ME_HeatingCoolingSails_Ceiling | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | th.nguyen | 75235
200 | 420_ME_HeatPump_PackageDrooftop_48And50UA&UH | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | [5 empty] | TRM | AUD | REV | CFM | [15 empty] | new | l.nguyen | 75233
201 | 420_ME_HeatTransferStation_Custom | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | th.nguyen | 75234
202 | 420_ME_HomeStation_DHK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | th.nguyen | 75236
203 | 420_ME_HomeStation_GHK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | th.nguyen | 75237
204 | 420_ME_HomeStation_GHKFBH | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | th.nguyen | 75238
205 | 420_ME_HotWaterBoiler | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | th.nguyen | 75239
206 | 420_ME_HotWaterStorageTank_Standard | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | th.nguyen | 75240
207 | 420_ME_HotWaterStorageTank_StorathermAqua | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
208 | 420_ME_HotWaterStorageTank_StorathermAquaCompact&Electricheater | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
209 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil&Electricheater | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
210 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
211 | 420_ME_HotWaterStorageTank_StorathermAquaCompactHorizontal | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
212 | 420_ME_HotWaterStorageTank_StorathermAquaCompactWallHung | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
213 | 420_ME_HotWaterStorageTank_StorathermAquaEEC | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
214 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump1Coil | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
215 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump2Coil | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
216 | 420_ME_HotWaterStorageTank_StorathermAquaInox | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
217 | 420_ME_HotWaterStorageTank_StorathermAquaLoad1Flange | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
218 | 420_ME_HotWaterStorageTank_StorathermAquaLoad2Flange | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
219 | 420_ME_HotWaterStorageTank_StorathermAquaLoad3Flange | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
220 | 420_ME_HotWaterStorageTank_StorathermAquaLoad4Flange | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
221 | 420_ME_HotWaterStorageTank_StorathermAquaSolar | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
222 | 420_ME_HotWaterStorageTank_StorathermAquaSolarEEC | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
223 | 420_ME_HotWaterTank | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
224 | 420_ME_HydraulicSeparator_Flanged | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
225 | 420_ME_HydraulicSeparator_Threaded | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
226 | 420_ME_KTS_ThermoBox | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
227 | 420_ME_LargeBecomixVessel_Vertical | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
228 | 420_ME_Manifold12Connection_Custom | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
229 | 420_ME_ManifoldCabinet_UP110 | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
230 | 420_ME_MixedBecomixVessel_Vertical | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
231 | 420_ME_MultiOutdoorUnit_SingleFan | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
232 | 420_ME_PlateHeatExchanger | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
233 | 420_ME_Pump_WaterJetPump_3Way_Flanged | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
234 | 420_ME_Pump_WaterJetPump_3Way_Threaded | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
235 | 420_ME_QuantumW500_DoubleCapacitor | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
236 | 420_ME_RadiatorBathroom_WallMounted_Basic | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
237 | 420_ME_RadiatorBathroom_WallMounted_BasicR | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
238 | 420_ME_RadiatorBathroom_WallMounted_Casteo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
239 | 420_ME_RadiatorBathroom_WallMounted_Credohalf | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
240 | 420_ME_RadiatorBathroom_WallMounted_Credohalfflat | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | d.phan | 74719
241 | 420_ME_RadiatorBathroom_WallMounted_Credohalfround | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | #N/A | #N/A | #N/A
242 | 420_ME_RadiatorBathroom_WallMounted_Credoplus | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | th.nguyen | 74718
243 | 420_ME_RadiatorBathroom_WallMounted_DecorArteLine | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74717
244 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePlan | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74716
245 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureHorizontal | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 74715
246 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureVertical | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 74714
247 | 420_ME_RadiatorBathroom_WallMounted_Diveo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 74713
248 | 420_ME_RadiatorBathroom_WallMounted_Duett | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74712
249 | 420_ME_RadiatorBathroom_WallMounted_Elveo_NoSystem | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74711
250 | 420_ME_RadiatorBathroom_WallMounted_Fineo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | l.nguyen | 74710
251 | 420_ME_RadiatorBathroom_WallMounted_Geneocircle | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | l.nguyen | 74709
252 | 420_ME_RadiatorBathroom_WallMounted_Geneoquadris | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | l.nguyen | 74708
253 | 420_ME_RadiatorBathroom_WallMounted_Icaro | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74707
254 | 420_ME_RadiatorBathroom_WallMounted_Ideos | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | d.phan | 74706
255 | 420_ME_RadiatorBathroom_WallMounted_Ineo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74705
256 | 420_ME_RadiatorBathroom_WallMounted_Leveo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74704
257 | 420_ME_RadiatorBathroom_WallMounted_Pateo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | l.nguyen | 74703
258 | 420_ME_RadiatorBathroom_WallMounted_Pio1layer | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | d.phan | 74702
259 | 420_ME_RadiatorBathroom_WallMounted_Pio2layer | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qd.nguyen | 74664
260 | 420_ME_RadiatorBathroom_WallMounted_PioPlus | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qd.nguyen | 74663
261 | 420_ME_RadiatorBathroom_WallMounted_Rubeo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 74662
262 | 420_ME_RadiatorBathroom_WallMounted_Signo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74661
263 | 420_ME_RadiatorBathroom_WallMounted_Tabeo | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | ht.nguyen | 74660
264 | 420_ME_RadiatorBathroom_WallMounted_TabeoV | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | ht.nguyen | 74659
265 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanHorizontal_NoSystem | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qd.nguyen | 74657
266 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanVertical_NoSystem | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74656
267 | 420_ME_RadiatorElectricPanel_WallMounted_xThermProfileHorizontal_NoSystem | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74655
268 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74654
269 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKHygiene | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | l.nguyen | 74653
270 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKReplacement | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | l.nguyen | 74652
271 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74651
272 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVHygiene | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | b.tran | 74650
273 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlus | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 74649
274 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlusHygiene | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | b.tran | 74648
275 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 74647
276 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKHygiene | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | d.phan | 74646
277 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKReplacement | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | d.phan | 74645
278 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileV | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | ht.nguyen | 74644
279 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVHygiene | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 74643
280 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlus | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | ht.nguyen | 74642
281 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlusHygiene | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 74641
282 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoPlan | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 73848
283 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoProfile | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qn.ha | 73847
284 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 73846
285 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanV | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | new | hu.dam | 73845
286 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanVPlus | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | acknowledged | th.nguyen | 73844
287 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileK | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | ht.nguyen | 73843
288 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileV | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | ht.nguyen | 73842
289 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileVPlus | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | nd.huynh | 73841
290 | 420_ME_RadiatorHeatingWall_WallMounted_Horizontal | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | closed | hu.dam | 73840
291 | 420_ME_RadiatorHeatingWall_WallMounted_ValveHorizontal | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | closed | l.nguyen | 73839
292 | 420_ME_RadiatorHeatingWall_WallMounted_ValveVertical | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | closed | hu.dam | 73838
293 | 420_ME_RadiatorHeatingWall_WallMounted_Vertical | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | nd.huynh | 73837
294 | 420_ME_Radiator_WallMounted_Standard | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | qd.nguyen | 73836
295 | 420_ME_RectangularTubeManifold_8Connection | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | closed | hu.dam | 73835
296 | 420_ME_SinglePassTubeHeatExchanger_Horizontal | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | nd.huynh | 73834
297 | 420_ME_WaterHeater_Vertical | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | [7 empty] | TRM | AUD | REV | CFM | [13 empty] | assigned | nd.huynh | 73833
| KLT | [30 empty] | #N/A | #N/A | #N/A
1 | 434_PF_CO_30Cross_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72627
2 | 434_PF_CO_AdaptorMultiPort_MapressAndNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72626
3 | 434_PF_CO_AdaptorUnion_FemaleThreadAndMeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72625
4 | 434_PF_CO_AdaptorUnion_MapressAndFlangeGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 72624
5 | 434_PF_CO_AdaptorUnion_PlainEndAndFlange | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72623
6 | 434_PF_CO_Bend_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72622
7 | 434_PF_CO_Bend_MapressFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72621
8 | 434_PF_CO_Bend_MapressGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72581
9 | 434_PF_CO_BridgeBendMultiPort_MapressGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | ht.nguyen | 72580
10 | 434_PF_CO_Cap_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72579
11 | 434_PF_CO_Cap_MapressFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72578
12 | 434_PF_CO_Cap_MapressGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72577
13 | 434_PF_CO_e90Elbow_ThreadAndMeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73489
14 | 434_PF_CO_eAdaptorBend_MapressAndFemaleThread_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73488
15 | 434_PF_CO_eAdaptorBend_MapressAndMeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73487
16 | 434_PF_CO_eAdaptorBend_MapressAndThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72484
17 | 434_PF_CO_eAdaptorBend_MapressAndThreadFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72483
18 | 434_PF_CO_eAdaptorBend_MapressAndThreadGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72482
19 | 434_PF_CO_eDouble90ElbowMultiPort_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73486
20 | 434_PF_CO_eElbow90Deg_MaleThread_MeplaFixAndPremounted | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73485
21 | 434_PF_CO_eElbowDouble90Deg_MaleThread_MeplaFixAndPremounted | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73484
22 | 434_PF_CO_fFlange_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73483
23 | 434_PF_CO_mBridgeBend_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 73314
24 | 434_PF_CO_mDouble90Elbow_Mapress_PreMounted | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 73313
25 | 434_PF_CO_mElbowOffset_MapressAndFemaleThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73312
26 | 434_PF_CO_mElbow_MapressAndFemaleThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 73311
27 | 434_PF_CO_mTeeCrossing_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 73310
28 | 434_PF_CO_mTeeInletReturnUnion_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 73309
29 | 434_PF_CO_mTeeInletReturn_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73308
30 | 434_PF_CO_mTeeReturn_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 73307
31 | 434_PF_CO_ReducerAdaptor_PlainEndAndClampingRing | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72576
32 | 434_PF_CO_rReducerAdaptor_MaleThread_MeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73306
33 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThreadFKMBlue_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73305
34 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThread_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73304
35 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThreadFKMBlue_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73303
36 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThread_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73302
37 | 434_PF_CO_rReducerAdaptor_MapressAndThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73301
38 | 434_PF_CO_rReducerAdaptor_MapressAndThreadFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | ht.nguyen | 73300
39 | 434_PF_CO_rReducerAdaptor_MapressAndThreadGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73299
40 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73298
41 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFixAdaptor | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72481
42 | 434_PF_CO_rReducerAdaptor_PlainEndAndThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73297
43 | 434_PF_CO_rReducerAdaptor_PlainEndAndThreadGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73296
44 | 434_PF_CO_rReducerAdaptor_PlainEnd_WithMeplaFixAdaptor | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72480
45 | 434_PF_CO_Tee_Mapress&FemaleThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72575
46 | 434_PF_CO_Tee_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72574
47 | 434_PF_CO_Tee_MapressFKMBlue&FemaleThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72573
48 | 434_PF_CO_Tee_MapressFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72572
49 | 434_PF_CO_Tee_MapressGas&FemaleThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72571
50 | 434_PF_CO_Tee_MapressGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72570
51 | 434_PF_CO_Transition_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72569
52 | 434_PF_CO_Transition_MapressFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72568
53 | 434_PF_CO_Transition_MapressGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72567
54 | 434_PF_CO_uAdaptorUnion_MaleThreadAndMeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73295
55 | 434_PF_CO_uAdaptorUnion_MaleThread_MeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73294
56 | 434_PF_CO_uAdaptorUnion_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | ht.nguyen | 72479
57 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThreadFKMBlue_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72478
58 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThread_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 73293
59 | 434_PF_CO_uAdaptorUnion_MapressAndMaleThreadFKMBlue_WithNut | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | hu.dam | 73292
60 | 434_PF_CO_uAdaptorUnion_MapressAndNutGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | hu.dam | 73291
61 | 434_PF_CO_uAdaptorUnion_MapressAndThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72471
62 | 434_PF_CO_uAdaptorUnion_MapressAndThreadFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72468
63 | 434_PF_CO_uAdaptorUnion_MapressAndThreadGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72467
64 | 434_PF_CO_uAdaptorUnion_PlainEndAndClampingRing | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | tm.doan | 73290
65 | 434_PF_CO_uAdaptorUnion_PlainEndAndThread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | tm.doan | 73289
66 | 434_PF_CO_uAdaptorUnion_PlainEndAndThreadGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | dx.quach | 72466
67 | 434_PF_CO_uAdaptorUnion_PlainEnd_WithMeplaFix | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72465
68 | 434_PF_CO_Union_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72566
69 | 434_PF_CO_Union_MapressFKMBlue | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72565
70 | 434_PF_CO_Union_MapressGas | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72485
71 | 434_PF_CO_uTap_Thread | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | hu.dam | 73288
72 | 434_PF_CO_xOffsetCross_Mapress | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | hu.dam | 73287
73 | 434_PA_BranchProviderBox_BPMKS2Port | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72643
74 | 434_PA_BranchProviderBox_BPMKS3Port | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72642
75 | 434_PA_MultiConnectionPipingKit1_BHFPGas | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72640
76 | 434_PA_MultiConnectionPipingKit1_BHFPLiquid | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72639
77 | 434_PA_MultiConnectionPipingKit2_BHFPGas | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | #N/A | #N/A | #N/A
78 | 434_PA_MultiConnectionPipingKit2_BHFPLiquid | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72636
79 | 434_PA_RefnetHeader_KHRPGas4Branches | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72635
80 | 434_PA_RefnetHeader_KHRPGas8Branches | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | kd.doan | 72634
81 | 434_PA_RefnetHeader_KHRPHP&LPGas | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | ht.nguyen | 72633
82 | 434_PA_RefnetHeader_KHRPLiquid4Branches | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | closed | hu.dam | 72632
83 | 434_PA_RefnetHeader_KHRPLiquid8Branches | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | dahn.nguyen | 72631
84 | 434_PA_RefnetJoint_KHRPDischarge | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | tm.doan | 72630
85 | 434_PA_RefnetJoint_KHRPGas | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | assigned | nd.huynh | 72629
86 | 434_PA_RefnetJoint_KHRPLiquid | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | tm.doan | 72628
87 | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | acknowledged | dx.quach | 75241
88 | 434_ME_AirCooledChillers_30AWH | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | acknowledged | dx.quach | 75242
89 | 434_ME_AirCooledCondensingUnits_38RBS_2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | acknowledged | dx.quach | 75243
90 | 434_ME_AirCooledCondensingUnits_38RBS_4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | acknowledged | dx.quach | 75244
91 | 434_ME_AirCooledCondensingUnits_38RBS_LeftConnector | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | acknowledged | dx.quach | 75246
92 | 434_ME_AirCooledLiquidChillers_30RB | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | acknowledged | dx.quach | 75247
93 | 434_ME_AirCooledLiquidChillers_30RBS | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | h.huynh | 75248
94 | 434_ME_AirCooledLiquidChillers_30XA | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | h.huynh | 75249
95 | 434_ME_AirCooledLiquidChillers_30XAS | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | h.huynh | 75250
96 | 434_ME_AirCooledLiquidChillers_30XAV | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | h.huynh | 75251
97 | 434_ME_AirCooledLiquidChillers_HeatReclaimUnit30XAS | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | h.huynh | 75252
98 | 434_ME_AirCooledScrollChillers_30RBP | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | tm.doan | 75253
99 | 434_ME_CirculatorPump_CronoTwinDL | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | tm.doan | 75254
100 | 434_ME_ConvectionElementsCeillings_CeilingMounted_KN | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | [9 empty] | TRM | AUD | REV | CFM | [11 empty] | new | tm.doan | 75255
101 | 434_ME_Convector_UnderFloorTrench_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75256
102 | 434_ME_CyclonicVacuumDegasser_VentoVEC | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75257
103 | 434_ME_CyclonicVacuumDegasser_VentoVIEC | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | ht.pham | 75258
104 | 434_ME_DegassingSystem | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | ht.pham | 75259
105 | 434_ME_Ductableaircooledliquidchillers_30RBSY_LeftConnection | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | t.tran | 75263
106 | 434_ME_DuctableAirCooledLiquidChillers_30RBY | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | ht.pham | 75260
107 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | ht.pham | 75262
108 | 434_ME_EndSuctionPump_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | t.tran | 75264
109 | 434_ME_ExpansionVessel_IntermediateDD | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | t.tran | 75265
110 | 434_ME_ExpansionVessel_IntermediateDG | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | t.tran | 75266
111 | 434_ME_ExpansionVessel_IntermediateDU | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | t.tran | 75267
112 | 434_ME_ExpansionVessel_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75268
113 | 434_ME_ExpansionVessel_StaticoSD | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75269
114 | 434_ME_ExpansionVessel_StaticoSG | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | dx.quach | 75270
115 | 434_ME_ExpansionVessel_StaticoSU | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | dx.quach | 75271
116 | 434_ME_FanCoilUnit_AirTreatmentModules42GM2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | dx.quach | 75272
117 | 434_ME_FanCoilUnit_AirTreatmentModules42GM4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | dx.quach | 75274
118 | 434_ME_FanCoilUnit_AirTreatmentModules42GR2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | dx.quach | 75275
119 | 434_ME_FanCoilUnit_AirTreatmentModules42GR4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | h.huynh | 75276
120 | 434_ME_FanCoilUnit_CeilingCassette_2pipes&42GW | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | h.huynh | 75277
121 | 434_ME_FanCoilUnit_CeilingCassette_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | h.huynh | 75278
122 | 434_ME_Fancoilunit_CeilingMounted_4wayblowcassetteFWFBF4pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
123 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFBT2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | h.huynh | 75279
124 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFCT2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | h.huynh | 75280
125 | 434_ME_FanCoilUnit_CeilingMounted_CompactChassis42GW4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75281
126 | 434_ME_FanCoilUnit_CeilingMounted_HybridTerminal36XB | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75282
127 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC2Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75283
128 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC4Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75284
129 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWD2Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75285
130 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH2Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75286
131 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH4Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 75287
132 | 434_ME_FanCoilUnit_CeilingMounted_LargeChassis42GW4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | t.tran | 75288
133 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBF4pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
134 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBT2pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
135 | 434_ME_FanCoilUnit_CeilingMounted_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | t.tran | 75289
136 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJF4pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
137 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJT2pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
138 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAF4pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
139 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAT2pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
140 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDF4pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
141 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDT2pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
142 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAF4pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
143 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAT2pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
144 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE2Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
145 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE4Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
146 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS2Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
147 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS4Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
148 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize0x | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
149 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize1x | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
150 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize2x&3x | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
151 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize0x | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
152 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize1x | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
153 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize2x&3x | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
154 | 434_ME_FanCoilUnit_CeilingPlenum_Ultra | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
155 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
156 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
157 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAF4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
158 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAT2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
159 | 434_ME_FanCoilUnit_FloorStanding_FWVDAF4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
160 | 434_ME_FanCoilUnit_FloorStanding_FWVDAT2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
161 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK2Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
162 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK4Pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
163 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHKE | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
164 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermID | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
165 | 434_ME_FanCoilUnit_WallMounted_FWBBT2pipe | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
166 | 434_ME_FanCoilUnit_WallMounted_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
167 | 434_ME_FillsoftI | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | #N/A | #N/A | #N/A
168 | 434_ME_FlatCompactDryCooler | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74701
169 | 434_ME_HeatedAndChilledBaffleCeilings_CeilingMounted_L608 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | ht.pham | 74693
170 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD315 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | hu.dam | 74692
171 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD320 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | hu.dam | 74691
172 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs125_NoSystem | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | hu.dam | 74690
173 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs78_NoSystem | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | tm.doan | 74689
174 | 434_ME_HeatedAndChilledCorridorCeilings_CeilingMounted_E312 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | h.huynh | 74688
175 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E200 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | h.huynh | 74687
176 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E210 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | h.huynh | 74686
177 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E213 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | h.huynh | 74685
178 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E214 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | hu.dam | 74684
179 | 434_ME_HeatedAndChilledHybridCeilings_CeilingMounted_DSTAS | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | hu.dam | 74683
180 | 434_ME_HeatedAndChilledPlasterboardCeilings_CeilingMounted_GKHEKDA2Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | dahn.nguyen | 74682
181 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | dahn.nguyen | 74681
182 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100SD | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | h.huynh | 74680
183 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B110 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | ht.pham | 74679
184 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B147SD | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | hu.dam | 74678
185 | 434_ME_HeatExchanger_Brazed&DoublePass&Flanged | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74700
186 | 434_ME_HeatExchanger_BrazedSinglePass&Thread | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74699
187 | 434_ME_HeatExchanger_Brazed_DoublePass | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74698
188 | 434_ME_HeatExchanger_Brazed_SinglePass&Flanged | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74697
189 | 434_ME_HeatExchanger_Gasketed&Flanged | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | ht.pham | 74696
190 | 434_ME_HeatExchanger_Gasketed&Thread | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | ht.pham | 74695
191 | 434_ME_HeatExchanger_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | ht.pham | 74694
192 | 434_ME_InLinePump_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74640
193 | 434_ME_ManifoldWithFlowMeter_10Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74639
194 | 434_ME_ManifoldWithFlowMeter_11Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74638
195 | 434_ME_ManifoldWithFlowMeter_12Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | acknowledged | t.tran | 74637
196 | 434_ME_ManifoldWithFlowMeter_2Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | ht.pham | 74636
197 | 434_ME_ManifoldWithFlowMeter_3Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | ht.pham | 74635
198 | 434_ME_ManifoldWithFlowMeter_4Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | dx.quach | 74634
199 | 434_ME_ManifoldWithFlowMeter_5Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | assigned | dx.quach | 74633
200 | 434_ME_ManifoldWithFlowMeter_6Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | [11 empty] | TRM | AUD | REV | CFM | [9 empty] | new | tm.doan | 74632
201 | 434_ME_ManifoldWithFlowMeter_7Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qn.ha | 74631
202 | 434_ME_ManifoldWithFlowMeter_8Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qn.ha | 74630
203 | 434_ME_ManifoldWithFlowMeter_9Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qn.ha | 74629
204 | 434_ME_ManifoldWithPump_1Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qn.ha | 74628
205 | 434_ME_ManifoldWithPump_2Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 74627
206 | 434_ME_ManifoldWithPump_3Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 74626
207 | 434_ME_ManifoldWithPump_4Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 74625
208 | 434_ME_ManifoldWithPump_5Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.nguyen | 74624
209 | 434_ME_ManifoldWithPump_6Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 74623
210 | 434_ME_ManifoldWithPump_7Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qn.ha | 74622
211 | 434_ME_ManifoldWithPump_8Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qn.ha | 74621
212 | 434_ME_Manifold_10Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | t.tran | 73890
213 | 434_ME_Manifold_11Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | t.tran | 73889
214 | 434_ME_Manifold_12Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | new | hu.dam | 73888
215 | 434_ME_Manifold_2Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qn.ha | 73887
216 | 434_ME_Manifold_3Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73886
217 | 434_ME_Manifold_4Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73885
218 | 434_ME_Manifold_5Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73884
219 | 434_ME_Manifold_6Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73883
220 | 434_ME_Manifold_7Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73882
221 | 434_ME_Manifold_8Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | ht.pham | 73880
222 | 434_ME_Manifold_9Circuits | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | ht.pham | 73879
223 | 434_ME_OutDoorUnit_VRV5HeatRecoveryREYA | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.pham | 73878
224 | 434_ME_PrecisionPressureMaintenance_TransferoTI | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73877
225 | 434_ME_PrecisionPressureMaintenance_TransferoTV1 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73876
226 | 434_ME_PrecisionPressureMaintenance_TransferoTV2 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73875
227 | 434_ME_PrecisionPressureMaintenance_TransferoTVI1 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73874
228 | 434_ME_PrecisionPressuremaintenance_TransferoTVI2 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73873
229 | 434_ME_PrecisionPressurisation_CompressoC | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73872
230 | 434_ME_PrecisionPressurisation_CompressoF | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73871
231 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73870
232 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9F | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73868
233 | 434_ME_PressureMaintenanceMonitoring_PlenoPIX | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73867
234 | 434_ME_PressureMaintenanceMonitoring_PlenoPX | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73866
235 | 434_ME_PumpCirculator_FloorStand_Round_CronoLineILE | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | h.huynh | 73865
236 | 434_ME_Pump_CirculatorAtmosGIGA&B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73864
237 | 434_ME_Pump_CirculatorStratosGIGA&B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73863
238 | 434_ME_Pump_CirculatorStratosGIGA&D | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | #N/A | #N/A | #N/A
239 | 434_ME_Pump_CirculatorStratosGIGA | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73862
240 | 434_ME_Pump_CirculatorStratosGIGA20&D | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73861
241 | 434_ME_Pump_CirculatorStratosGIGA20&I | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | h.huynh | 73860
242 | 434_ME_Pump_CirculatorStratosMAXO&D | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | #N/A | #N/A | #N/A
243 | 434_ME_Pump_CirculatorStratosMAXO | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73859
244 | 434_ME_Pump_CirculatorStratosPICO | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73858
245 | 434_ME_Pump_CirculatorVeroLineIPL | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73857
246 | 434_ME_Pump_CirculatorYonosMAXO&D | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | #N/A | #N/A | #N/A
247 | 434_ME_Pump_CirculatorYonosMAXO | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73856
248 | 434_ME_Pump_CirculatorYonosPICO&D | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | #N/A | #N/A | #N/A
249 | 434_ME_Pump_CirculatorYonosPICO | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | dx.quach | 73855
250 | 434_ME_Pump_Circulator_CronoTwin_DL_E | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | dx.quach | 73854
251 | 434_ME_Pump_Circulator_VeroTwinDPL_DN100 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73853
252 | 434_ME_Pump_Circulator_VeroTwinDPL_DN32 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | dx.quach | 73852
253 | 434_ME_Pump_Circulator_VeroTwinDPL_DN40 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | qd.nguyen | 73851
254 | 434_ME_Pump_Circulator_VeroTwinDPL_DN50 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | dx.quach | 73850
255 | 434_ME_Pump_Circulator_VeroTwinDPL_DN65 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | new | hu.dam | 73849
256 | 434_ME_Pump_Circulator_VeroTwinDPL_DN80 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73147
257 | 434_ME_Pump_Circulator_YonosGIGA20D | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73508
258 | 434_ME_Pump_Circulator_YonosGIGA20_I | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73104
259 | 434_ME_Pump_SingleStageGlandedBM | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73507
260 | 434_ME_Pump_SingleStageLowPressureBAC | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73506
261 | 434_ME_Pump_SingleStageLowPressureBAC65 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73103
262 | 434_ME_Pump_WaterSupplyAtmosGIGA&N | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73505
263 | 434_ME_Pump_WaterSupplyAtmosI | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73504
264 | 434_ME_Pump_WaterSupplyAtmosTERA&SCH | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73503
265 | 434_ME_Pump_WaterSupplyCronoBlocBLE | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73502
266 | 434_ME_Pump_WaterSupplyCronoNorm&NLG | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73501
267 | 434_ME_Pump_WaterSupplySCP | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.nguyen | 73500
268 | 434_ME_Pump_WaterSupplyVeroLineIPE | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73499
269 | 434_ME_Pump_WaterSupplyVeroTwinDPE | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.nguyen | 73498
270 | 434_ME_Pump_WaterSupplyYonosGIGA&N | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73497
271 | 434_ME_SplitCasePump_Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73102
272 | 434_ME_TwoOutletPump_Flanged | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73101
273 | 434_ME_VariableSpeedWaterCooledLiquidChiller_SingleCompressor30XW&V | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73495
274 | 434_ME_VRVInDoorUnit_CeilingMouted_FXFA&A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73100
275 | 434_ME_VRVInDoorUnit_CeilingMouted_FXZA&A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73099
276 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXHA&A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73098
277 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXUA&A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73097
278 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXDA | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.pham | 73096
279 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.pham | 73095
280 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA200and250A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.pham | 73094
281 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXSA | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73093
282 | 434_ME_VRVInDoorUnit_WallMounted_FXAA&A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73092
283 | 434_ME_VRVMultiBranchSelector_BS&10A14AV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | new | tm.doan | 73091
284 | 434_ME_VRVMultiBranchSelector_BS&12A14AV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73090
285 | 434_ME_VRVMultiBranchSelector_BS&4A14AV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73089
286 | 434_ME_VRVMultiBranchSelector_BS&6A14AV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73088
287 | 434_ME_VRVMultiBranchSelector_BS&8A14AV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.nguyen | 73087
288 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA14&20A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.nguyen | 73086
289 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA8&12A | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 73085
290 | 434_ME_VRVOutDoorUnit_HeatPumpRXYSA&AV1&AY1 | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73084
291 | 434_ME_VRVShutOffValveBox_SV1A25AJV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73083
292 | 434_ME_VRVShutOffValveBox_SV4A14AJV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73082
293 | 434_ME_VRVShutOffValveBox_SV6A14AJV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73081
294 | 434_ME_VRVShutOffValveBox_SV8A14AJV1B | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73080
295 | 434_ME_WateCooledCondenserlessLiquidChillers_WithHydraulicModule_30RW | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73494
296 | 434_ME_WatercooledCondenserlessliquidchillers_30RW_WithoutHydraulicModule | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | lk.dang | 73490
297 | 434_ME_WaterCooledCondenserlessLiquidChillers_30WG | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73493
298 | 434_ME_WaterCooledCondenserlessLiquidchillers_30WGA | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | nd.huynh | 73492
299 | 434_ME_WaterCooledLiquidChillers_30XW | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | lk.dang | 73079
300 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC4Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | closed | hu.dam | 73491
301 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC5Pipes | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | ht.nguyen | 73078
302 | 434_ME_Watercooled_Condenserlessliquidchillers_30RW_30RWA_VerticalConnection | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | assigned | dahn.nguyen | 72644
303 | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | [13 empty] | TRM | AUD | REV | CFM | [7 empty] | acknowledged | dx.quach | 75241
| HGR | [31 empty] | #N/A | #N/A
1 | 491_NF_GussetPlate90dHexagon | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
2 | 491_NF_GussetPlate90dRectangular | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
3 | 491_NF_GussetPlate90dTCenter | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
4 | 491_NF_GussetPlate90dTSide | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
5 | 491_NF_GussetPlateAngularAxial | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
6 | 491_NF_GussetPlateAngularDoubleAdjustableBrace | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
7 | 491_NF_GussetPlateAngularRectangular | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
8 | 491_NF_GussetPlateAngularSingleAdjustableBrace | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
9 | 491_NF_GussetPlateBase | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
10 | 491_NF_GussetPlateCantileverBracket | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
11 | 491_NF_GussetPlateFlatHexagon | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
12 | 491_NF_GussetPlateFlatRectangular | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
13 | 491_NF_GussetPlateFlatSemiCircle | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
14 | 491_NF_GussetPlateFlatT | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
15 | 491_NF_GussetPlateTrailingArm | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
16 | 491_NF_GussetPlateTrailingArmBrace | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
17 | 491_NF_GussetPlateUShape | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
18 | 491_NF_GussetPlateUShape_2Layers | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
19 | 491_NF_GussetPlateUShape_Hanger | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
20 | 491_NF_GussetPlateUShape_Omega | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
21 | 491_NF_GussetPlateUShape_Side | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
22 | 491_NF_GussetPlateWingShape | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
23 | 491_NF_GussetPlateWShape | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
24 | 491_NF_GussetPlateZShape | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
25 | 491_NF_GussetPlate_StairTreadSupport | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
26 | 491_NF_PipeClampAccessoriesPunchedAngle | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
27 | 491_NF_PipeClampAccessoriesSquareWasher | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
28 | 491_NF_PipeClampAccessories_BladeEnd | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
29 | 491_NF_PipeClampAccessories_Clevis | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
30 | 491_NF_PipeClampAccessories_EyeNut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
31 | 491_NF_PipeClampAccessories_HangerStrap | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
32 | 491_NF_PipeClampAccessories_LinkPlate | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
33 | 491_NF_PipeClampAccessories_Turnbuckle | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
34 | 491_NF_PipeClampBeamAttachmentsPurlinClip | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
35 | 491_NF_PipeClampBeamAttachmentsSwivelFlangeClamp | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
36 | 491_NF_PipeClampBeamAttachmentsUBracket | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
37 | 491_NF_PipeClampBeamAttachmentsWeldOnBracket | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
38 | 491_NF_PipeClampBeamAttachments_AngleBracket | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
39 | 491_NF_PipeClampBeamAttachments_BeamClip | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
40 | 491_NF_PipeClampBeamAttachments_FlangeClamp | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
41 | 491_NF_PipeClampBeamAttachments_PipeBeamClip | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
42 | 491_NF_PipeClampBeamAttachments_SphericalWasher | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
43 | 491_NF_PipeClampBeamAttachments_SwivelCage | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
44 | 491_NF_PipeClampDoubleBoltStrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
45 | 491_NF_PipeClampFourBolt | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
46 | 491_NF_PipeClampHangedSaddle | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
47 | 491_NF_PipeClampPearHanger | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
48 | 491_NF_PipeClampSingleBoltStrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
49 | 491_NF_PipeClampThreeBolt | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
50 | 491_NF_PipeClampTwistClip | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
51 | 491_NF_PipeClampTwoPiece | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
52 | 491_NF_PipeClampTwoPieceWithYoke | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
53 | 491_NF_PipeClampUBolt | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
54 | 491_NF_PipeClamp_OnePiece | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
55 | 491_NF_PipeClamp_StandOffBracket | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
56 | 491_NF_Steel_A1000_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
57 | 491_NF_Steel_AnchorScrew | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
58 | 491_NF_Steel_CantileverBrackets_Triangle | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
59 | 491_NF_Steel_FlatWashers | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
60 | 491_NF_Steel_HexagonHeadScrew | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
61 | 491_NF_Steel_HexagonNut_Threaded | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
62 | 491_NF_Steel_P1000B_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
63 | 491_NF_Steel_P1000C41_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
64 | 491_NF_Steel_P1000C_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
65 | 491_NF_Steel_P1000_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
66 | 491_NF_Steel_P10013_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
67 | 491_NF_Steel_P1001A_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
68 | 491_NF_Steel_P1001C3_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
69 | 491_NF_Steel_P1001D3_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
70 | 491_NF_Steel_P1001_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
71 | 491_NF_Steel_P1003_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
72 | 491_NF_Steel_P1004A_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
73 | 491_NF_Steel_P2001A_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
74 | 491_NF_Steel_P2001B_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
75 | 491_NF_Steel_P2001C3_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
76 | 491_NF_Steel_P3300_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
77 | 491_NF_Steel_P4000_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
78 | 491_NF_Steel_P40021_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
79 | 491_NF_Steel_P4003_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
80 | 491_NF_Steel_P5500_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
81 | 491_NF_Steel_P5501_Unistrut | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
82 | 491_NF_Steel_UnirodThreadedRod | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
83 | 491_SE_ArmFromDoublePerpendicularArm | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
84 | 491_SE_ArmWithAngleBracket | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
85 | 491_SE_BracingArmSKOF80 | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
86 | 491_SE_CantileverBracketAKF80 | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
87 | 491_SE_ClampDoublePiece | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
88 | 491_SE_ConductorHolders_FloorStand | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
89 | 491_SE_DoublePillarWithPlate | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
90 | 491_SE_DouleClampWithFoundationPlate | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
91 | 491_SE_EndSupportSTAF80 | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
92 | 491_SE_FixedpointsetXS | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
93 | 491_SE_FrameHangerTopBase | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
94 | 491_SE_GuidingBracketFWF | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
95 | 491_SE_PillarOnTopAndDoubleArmWithThread | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
96 | 491_SE_PillarOnTopAndSingleArmWithThread | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
97 | 491_SE_PillarWithPlate | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
98 | 491_SE_PipeClampWithRubberRing | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
99 | 491_SE_PipeClampWithShadeNut | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
100 | 491_SE_PipeStrapWithUType | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
101 | 491_SE_PipeSupport_FloorStandingType | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
102 | 491_SE_PipeSupport_RiserType | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
103 | 491_SE_PipeSupport_Riser_ClampType | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
104 | 491_SE_PipeTrapezeHangerDoubleFrame | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
105 | 491_SE_PipeTrapezeHangerSingleFrame | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
106 | 491_SE_RectangularDuctHanger_Standard | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
107 | 491_SE_RoundDuctHanger_Standard | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
108 | 491_SE_ShouderWithDoubleArm | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
109 | 491_SE_SingleArmWithDoubleBracket | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
110 | 491_SE_SingleArmWithPillarOnTop | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
111 | 491_SE_SingleArmWithPlate | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
112 | 491_SE_SlidesetFS | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | [15 empty] | TRM | AUD | REV | CFM | [6 empty] | #N/A | #N/A
| Create the Revit templates for each LPH HKG |  |  |  |  | DIG | [26 empty] | #N/A | #N/A
| TGA_Revit Template | [31 empty] | #N/A | #N/A
1 | LPH3 | HKG | Revit Template | .rte | MEP | DIG | 8 | [16 empty] | TRM | AUD | REV | CFM | [5 empty] | #N/A | #N/A
2 | LPH5 | HKG | Revit Template | .rte | MEP | DIG | 8 | [16 empty] | TRM | AUD | REV | CFM | [5 empty] | #N/A | #N/A
3 | LPH8 | HKG | Revit Template | .rte | MEP | DIG | 8 | [16 empty] | TRM | AUD | REV | CFM | [5 empty] | #N/A | #N/A
D | TGA_Output Checklists | [31 empty] | #N/A | #N/A
1 | LPH3 Check list for HKG discipline |  |  | .xlsx | MEP | DIG | 9 | [17 empty] | TRM | AUD | REV | CFM |  |  |  |  | #N/A | #N/A
2 | LPH3_Check list_HKG 01 |  | Define Checklist_layout Plan |  | MEP | DIG | 9 | [17 empty] | TRM | AUD | REV | CFM |  |  |  |  | #N/A | #N/A
3 | LPH3_Check list_HKG 02 |  | Define Checklist_Section |  | MEP | DIG | 9 | [17 empty] | TRM | AUD | REV | CFM |  |  |  |  | #N/A | #N/A
4 | LPH3_Check list_HKG 03 |  | Define Checklist_Isometric Drawing |  | MEP | DIG | 9 | [17 empty] | TRM | AUD | REV | CFM |  |  |  |  | #N/A | #N/A
5 | LPH3_Check list_HKG 04 |  | Define Checklist_Schematic Diagram |  | MEP | DIG | 9 | [17 empty] | TRM | AUD | REV | CFM |  |  |  |  | #N/A | #N/A
E | Sample Model + Out Put Data |  |  |  | MEP | DIG | [26 empty] | #N/A | #N/A
| Sample Model + Out Put Data For HKG | [31 empty] | #N/A | #N/A
1 | Delivery layout Sample for HKG LPH3 |  | Execute a sample layout for the HKG discipline | .pdf | MEP | DIG | 10 | [18 empty] | TRM | AUD | REV | CFM |  |  |  | #N/A | #N/A
2 | Delivery layout Sample for HKG LPH5 |  | Execute a sample layout for the HKG discipline | .pdf | MEP | DIG | 10 | [18 empty] | TRM | AUD | REV | CFM |  |  |  | #N/A | #N/A
3 | Delivery layout Sample for HKG LPH8 |  | Execute a sample layout for the HKG discipline | .pdf | MEP | DIG | 10 | [18 empty] | TRM | AUD | REV | CFM |  |  |  | #N/A | #N/A
4 | Delivery Schematic Drawing Sample for HKG LPH3 |  | Execute a sample schematic for the HKG discipline | .pdf | MEP | DIG | 10 | [18 empty] | TRM | AUD | REV | CFM |  |  |  | #N/A | #N/A
5 | Delivery Schematic Drawing Sample for HKG LPH5 |  | Execute a sample schematic for the HKG discipline | .pdf | MEP | DIG | 10 | [18 empty] | TRM | AUD | REV | CFM |  |  |  | #N/A | #N/A
F | Export layouts to Revizto & set up 3D Review HKG |  |  |  | MEP | DIG | [26 empty] | #N/A | #N/A
1 | Export layouts to Revizto & set up 3D Review HKG _LPH3 |  |  | .pdf | MEP | DIG | 11 | [19 empty] | TRM | AUD | REV | CFM |  |  | #N/A | #N/A
2 | Export layouts to Revizto & set up 3D Review HKG _LPH5 |  |  | .pdf | MEP | DIG | 11 | [19 empty] | TRM | AUD | REV | CFM |  |  | #N/A | #N/A
3 | Export layouts to Revizto & set up 3D Review HKG _LPH8 |  |  | .pdf | MEP | DIG | 11 | [19 empty] | TRM | AUD | REV | CFM |  |  | #N/A | #N/A
G | Lesson Learned |  |  |  | MEP | DIG | [26 empty] | #N/A | #N/A
| Lesson Learned HKG |  |  | .pdf | MEP | DIG | 12 | [20 empty] | TRM | AUD | REV | CFM |  | #N/A | #N/A
1 | What went well. |  | What went well. | .pdf | MEP | DIG | 12 | [20 empty] | TRM | AUD | REV | CFM |  | #N/A | #N/A
2 | What need to be improved |  | What didn’t go well | .pdf | MEP | DIG | 12 | [20 empty] | TRM | AUD | REV | CFM |  | #N/A | #N/A
3 | What we learned, |  | What we learned | .pdf | MEP | DIG | 12 | [20 empty] | TRM | AUD | REV | CFM |  | #N/A | #N/A
4 | Action items / Improvements |  | Action items / Improvements | .pdf | MEP | DIG | 12 | [20 empty] | TRM | AUD | REV | CFM |  | #N/A | #N/A
Legend:
TRM | Transmital | MEP
AUD | Auditting | DIG
REV | Revision | MEP
CFM | Confirmation/REVal Submission | MEP/DIG

## Ticket Data
Id | Reporter | Assigned To | Date Submitted | Summary | Status | Check | Status | Assigned To | Ticket
75225 | n.le | b.tran | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQK.rfa | acknowledged | 420_ME_Fancoilunit_UnderfloorTrench_KathermQK | acknowledged | b.tran | 75225
75224 | n.le | b.tran | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQE_NoSystem.rfa | acknowledged | 420_ME_Fancoilunit_UnderfloorTrench_KathermQE_NoSystem | acknowledged | b.tran | 75224
75223 | n.le | b.tran | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermNK.rfa | acknowledged | 420_ME_Fancoilunit_UnderfloorTrench_KathermNK | acknowledged | b.tran | 75223
75222 | n.le | b.tran | 2026-08-13 | 420_ME_FacadeHeating_Standard.rfa | acknowledged | 420_ME_FacadeHeating_Standard | acknowledged | b.tran | 75222
75221 | n.le | b.tran | 2026-08-13 | 420_ME_FWTransfer.rfa | acknowledged | 420_ME_FWTransfer | acknowledged | b.tran | 75221
75220 | n.le | b.tran | 2026-08-13 | 420_ME_ExpansionTank_Standard.rfa | acknowledged | 420_ME_ExpansionTank_Standard | acknowledged | b.tran | 75220
75199 | n.le | b.tran | 2026-08-13 | 420_ME_AirSoureHeatPump.rfa | acknowledged | 420_ME_AirSoureHeatPump | acknowledged | b.tran | 75199
75198 | n.le | b.tran | 2026-08-13 | 420_ME_AirHeater_Top.rfa | acknowledged | 420_ME_AirHeater_Top | acknowledged | b.tran | 75198
75197 | n.le | b.tran | 2026-08-13 | 420_ME_AirCurtain_WallMounted_Standard.rfa | acknowledged | 420_ME_AirCurtain_WallMounted_Standard | acknowledged | b.tran | 75197
75196 | n.le | b.tran | 2026-08-13 | 420_ME_AirCurtain_WallMounted.rfa | acknowledged | 420_ME_AirCurtain_WallMounted | acknowledged | b.tran | 75196
74707 | n.le | hu.dam | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Icaro.rfa | new | 420_ME_RadiatorBathroom_WallMounted_Icaro | new | hu.dam | 74707
73287 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_xOffsetCross_Mapress | new | 434_PF_CO_xOffsetCross_Mapress | new | hu.dam | 73287
73108 | n.le | hu.dam | 2026-06-08 | 420_PA_PressureIndependentControlValveCompact_Threaded | new | 420_PA_PressureIndependentControlValveCompact_Threaded | new | hu.dam | 73108
74627 | n.le | hu.dam | 2026-07-21 | 434_ME_ManifoldWithPump_2Circuits.rfa | closed | 434_ME_ManifoldWithPump_2Circuits | closed | hu.dam | 74627
75195 | n.le | d.phan | 2026-08-13 | 420_ME_AirCurtain_StandingType.rfa | acknowledged | 420_ME_AirCurtain_StandingType | acknowledged | d.phan | 75195
75194 | n.le | d.phan | 2026-08-13 | 420_ME_AirCoolHeatPump_MonoBlock.rfa | acknowledged | 420_ME_AirCoolHeatPump_MonoBlock | acknowledged | d.phan | 75194
75193 | n.le | d.phan | 2026-08-13 | 420_HeatExchangerTank_VerticalPump.rfa | acknowledged | 420_HeatExchangerTank_VerticalPump | acknowledged | d.phan | 75193
75275 | n.le | dx.quach | 2026-08-13 | 434_ME_FanCoilUnit_AirTreatmentModules42GR2Pipes.rfa | acknowledged | 434_ME_FanCoilUnit_AirTreatmentModules42GR2Pipes | acknowledged | dx.quach | 75275
75274 | n.le | dx.quach | 2026-08-13 | 434_ME_FanCoilUnit_AirTreatmentModules42GM4Pipes.rfa | acknowledged | 434_ME_FanCoilUnit_AirTreatmentModules42GM4Pipes | acknowledged | dx.quach | 75274
75272 | n.le | dx.quach | 2026-08-13 | 434_ME_FanCoilUnit_AirTreatmentModules42GM2Pipes.rfa | acknowledged | 434_ME_FanCoilUnit_AirTreatmentModules42GM2Pipes | acknowledged | dx.quach | 75272
75271 | n.le | dx.quach | 2026-08-13 | 434_ME_ExpansionVessel_StaticoSU.rfa | acknowledged | 434_ME_ExpansionVessel_StaticoSU | acknowledged | dx.quach | 75271
75270 | n.le | dx.quach | 2026-08-13 | 434_ME_ExpansionVessel_StaticoSG.rfa | acknowledged | 434_ME_ExpansionVessel_StaticoSG | acknowledged | dx.quach | 75270
75247 | n.le | dx.quach | 2026-08-13 | 434_ME_AirCooledLiquidChillers_30RB.rfa | acknowledged | 434_ME_AirCooledLiquidChillers_30RB | acknowledged | dx.quach | 75247
75246 | n.le | dx.quach | 2026-08-13 | 434_ME_AirCooledCondensingUnits_38RBS_LeftConnector.rfa | acknowledged | 434_ME_AirCooledCondensingUnits_38RBS_LeftConnector | acknowledged | dx.quach | 75246
75244 | n.le | dx.quach | 2026-08-13 | 434_ME_AirCooledCondensingUnits_38RBS_4Pipes.rfa | acknowledged | 434_ME_AirCooledCondensingUnits_38RBS_4Pipes | acknowledged | dx.quach | 75244
75243 | n.le | dx.quach | 2026-08-13 | 434_ME_AirCooledCondensingUnits_38RBS_2Pipes.rfa | acknowledged | 434_ME_AirCooledCondensingUnits_38RBS_2Pipes | acknowledged | dx.quach | 75243
75242 | n.le | dx.quach | 2026-08-13 | 434_ME_AirCooledChillers_30AWH.rfa | acknowledged | 434_ME_AirCooledChillers_30AWH | acknowledged | dx.quach | 75242
75241 | n.le | dx.quach | 2026-08-13 | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard.rfa | acknowledged | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard | acknowledged | dx.quach | 75241
75204 | n.le | ht.tran | 2026-08-13 | 420_ME_BufferTank_StorathermHeat1Coil&WithInsulation.rfa | new | 420_ME_BufferTank_StorathermHeat1Coil&WithInsulation | new | ht.tran | 75204
75203 | n.le | ht.tran | 2026-08-13 | 420_ME_BufferTank_StorathermHeat&WithInsulation.rfa | new | 420_ME_BufferTank_StorathermHeat&WithInsulation | new | ht.tran | 75203
75202 | n.le | ht.tran | 2026-08-13 | 420_ME_BufferTank_Standard.rfa | new | 420_ME_BufferTank_Standard | new | ht.tran | 75202
75201 | n.le | ht.tran | 2026-08-13 | 420_ME_BufferTank_Custom.rfa | new | 420_ME_BufferTank_Custom | new | ht.tran | 75201
75200 | n.le | ht.tran | 2026-08-13 | 420_ME_BufferHeatingTank.rfa | new | 420_ME_BufferHeatingTank | new | ht.tran | 75200
75209 | n.le | l.nguyen | 2026-08-13 | 420_ME_BufferTank_StorathermHeatFlange&WithInsulation.rfa | new | 420_ME_BufferTank_StorathermHeatFlange&WithInsulation | new | l.nguyen | 75209
75208 | n.le | l.nguyen | 2026-08-13 | 420_ME_BufferTank_StorathermHeatCombi2Coil&WithInsulation.rfa | new | 420_ME_BufferTank_StorathermHeatCombi2Coil&WithInsulation | new | l.nguyen | 75208
75207 | n.le | l.nguyen | 2026-08-13 | 420_ME_BufferTank_StorathermHeatCombi1Coil&WithInsulation.rfa | new | 420_ME_BufferTank_StorathermHeatCombi1Coil&WithInsulation | new | l.nguyen | 75207
75206 | n.le | l.nguyen | 2026-08-13 | 420_ME_BufferTank_StorathermHeat2Coil&WithInsulation.rfa | new | 420_ME_BufferTank_StorathermHeat2Coil&WithInsulation | new | l.nguyen | 75206
75205 | n.le | l.nguyen | 2026-08-13 | 420_ME_BufferTank_StorathermHeat1Coil&WithoutInsulation.rfa | new | 420_ME_BufferTank_StorathermHeat1Coil&WithoutInsulation | new | l.nguyen | 75205
75214 | n.le | th.nguyen | 2026-08-13 | 420_ME_CompressedAirTank.rfa | new | 420_ME_CompressedAirTank | new | th.nguyen | 75214
75213 | n.le | th.nguyen | 2026-08-13 | 420_ME_ColdWaterTank.rfa | new | 420_ME_ColdWaterTank | new | th.nguyen | 75213
75212 | n.le | th.nguyen | 2026-08-13 | 420_ME_CentrifugalPumpWithElectricMotor_Horizontal.rfa | new | 420_ME_CentrifugalPumpWithElectricMotor_Horizontal | new | th.nguyen | 75212
75211 | n.le | th.nguyen | 2026-08-13 | 420_ME_CeilingPanel_Standard.rfa | new | 420_ME_CeilingPanel_Standard | new | th.nguyen | 75211
75210 | n.le | th.nguyen | 2026-08-13 | 420_ME_BufferTank_StorathermHeatFlange&WithoutInsulation.rfa | new | 420_ME_BufferTank_StorathermHeatFlange&WithoutInsulation | new | th.nguyen | 75210
75269 | n.le | tm.doan | 2026-08-13 | 434_ME_ExpansionVessel_StaticoSD.rfa | new | 434_ME_ExpansionVessel_StaticoSD | new | tm.doan | 75269
75268 | n.le | tm.doan | 2026-08-13 | 434_ME_ExpansionVessel_Standard.rfa | new | 434_ME_ExpansionVessel_Standard | new | tm.doan | 75268
75252 | n.le | h.huynh | 2026-08-13 | 434_ME_AirCooledLiquidChillers_HeatReclaimUnit30XAS.rfa | new | 434_ME_AirCooledLiquidChillers_HeatReclaimUnit30XAS | new | h.huynh | 75252
75251 | n.le | h.huynh | 2026-08-13 | 434_ME_AirCooledLiquidChillers_30XAV.rfa | new | 434_ME_AirCooledLiquidChillers_30XAV | new | h.huynh | 75251
75250 | n.le | h.huynh | 2026-08-13 | 434_ME_AirCooledLiquidChillers_30XAS.rfa | new | 434_ME_AirCooledLiquidChillers_30XAS | new | h.huynh | 75250
75249 | n.le | h.huynh | 2026-08-13 | 434_ME_AirCooledLiquidChillers_30XA.rfa | new | 434_ME_AirCooledLiquidChillers_30XA | new | h.huynh | 75249
75248 | n.le | h.huynh | 2026-08-13 | 434_ME_AirCooledLiquidChillers_30RBS.rfa | new | 434_ME_AirCooledLiquidChillers_30RBS | new | h.huynh | 75248
75257 | n.le | tm.doan | 2026-08-13 | 434_ME_CyclonicVacuumDegasser_VentoVEC.rfa | new | 434_ME_CyclonicVacuumDegasser_VentoVEC | new | tm.doan | 75257
75256 | n.le | tm.doan | 2026-08-13 | 434_ME_Convector_UnderFloorTrench_Standard.rfa | new | 434_ME_Convector_UnderFloorTrench_Standard | new | tm.doan | 75256
75255 | n.le | tm.doan | 2026-08-13 | 434_ME_ConvectionElementsCeillings_CeilingMounted_KN.rfa | new | 434_ME_ConvectionElementsCeillings_CeilingMounted_KN | new | tm.doan | 75255
75254 | n.le | tm.doan | 2026-08-13 | 434_ME_CirculatorPump_CronoTwinDL.rfa | new | 434_ME_CirculatorPump_CronoTwinDL | new | tm.doan | 75254
75253 | n.le | tm.doan | 2026-08-13 | 434_ME_AirCooledScrollChillers_30RBP.rfa | new | 434_ME_AirCooledScrollChillers_30RBP | new | tm.doan | 75253
75262 | n.le | ht.pham | 2026-08-13 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY.rfa | new | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY | new | ht.pham | 75262
75261 | n.le | ht.pham | 2026-08-13 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY.rfa | new | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY | new | ht.pham | 75261
75260 | n.le | ht.pham | 2026-08-13 | 434_ME_DuctableAirCooledLiquidChillers_30RBY.rfa | new | 434_ME_DuctableAirCooledLiquidChillers_30RBY | new | ht.pham | 75260
75259 | n.le | ht.pham | 2026-08-13 | 434_ME_DegassingSystem.rfa | new | 434_ME_DegassingSystem | new | ht.pham | 75259
75258 | n.le | ht.pham | 2026-08-13 | 434_ME_CyclonicVacuumDegasser_VentoVIEC.rfa | new | 434_ME_CyclonicVacuumDegasser_VentoVIEC | new | ht.pham | 75258
75267 | n.le | t.tran | 2026-08-13 | 434_ME_ExpansionVessel_IntermediateDU.rfa | new | 434_ME_ExpansionVessel_IntermediateDU | new | t.tran | 75267
75266 | n.le | t.tran | 2026-08-13 | 434_ME_ExpansionVessel_IntermediateDG.rfa | new | 434_ME_ExpansionVessel_IntermediateDG | new | t.tran | 75266
75265 | n.le | t.tran | 2026-08-13 | 434_ME_ExpansionVessel_IntermediateDD.rfa | new | 434_ME_ExpansionVessel_IntermediateDD | new | t.tran | 75265
75264 | n.le | t.tran | 2026-08-13 | 434_ME_EndSuctionPump_Standard.rfa | new | 434_ME_EndSuctionPump_Standard | new | t.tran | 75264
75263 | n.le | t.tran | 2026-08-13 | 434_ME_Ductableaircooledliquidchillers_30RBSY_LeftConnection.rfa | new | 434_ME_Ductableaircooledliquidchillers_30RBSY_LeftConnection | new | t.tran | 75263
73078 | n.le | ht.nguyen | 2026-06-08 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC5Pipes | assigned | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC5Pipes | assigned | ht.nguyen | 73078
73086 | n.le | ht.nguyen | 2026-06-08 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA14&20A | assigned | 434_ME_VRVOutDoorUnit_HeatPumpRXYA14&20A | assigned | ht.nguyen | 73086
73087 | n.le | ht.nguyen | 2026-06-08 | 434_ME_VRVMultiBranchSelector_BS&8A14AV1B | assigned | 434_ME_VRVMultiBranchSelector_BS&8A14AV1B | assigned | ht.nguyen | 73087
75219 | n.le | d.phan | 2026-08-13 | 420_ME_ExpansionTank_FloorStand.rfa | acknowledged | 420_ME_ExpansionTank_FloorStand | acknowledged | d.phan | 75219
75218 | n.le | d.phan | 2026-08-13 | 420_ME_EnergyDistributor_8Pairs.rfa | acknowledged | 420_ME_EnergyDistributor_8Pairs | acknowledged | d.phan | 75218
75217 | n.le | d.phan | 2026-08-13 | 420_ME_EnergyDistributor_6Pairs.rfa | acknowledged | 420_ME_EnergyDistributor_6Pairs | acknowledged | d.phan | 75217
75216 | n.le | d.phan | 2026-08-13 | 420_ME_Convector_FloorSurface.rfa | acknowledged | 420_ME_Convector_FloorSurface | acknowledged | d.phan | 75216
75215 | n.le | d.phan | 2026-08-13 | 420_ME_ControlValveGroup.rfa | acknowledged | 420_ME_ControlValveGroup | acknowledged | d.phan | 75215
75280 | n.le | h.huynh | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFCT2Pipes.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFCT2Pipes | new | h.huynh | 75280
75279 | n.le | h.huynh | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFBT2Pipes.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFBT2Pipes | new | h.huynh | 75279
75278 | n.le | h.huynh | 2026-08-13 | 434_ME_FanCoilUnit_CeilingCassette_Standard.rfa | new | 434_ME_FanCoilUnit_CeilingCassette_Standard | new | h.huynh | 75278
75277 | n.le | h.huynh | 2026-08-13 | 434_ME_FanCoilUnit_CeilingCassette_2pipes&42GW.rfa | new | 434_ME_FanCoilUnit_CeilingCassette_2pipes&42GW | new | h.huynh | 75277
75276 | n.le | h.huynh | 2026-08-13 | 434_ME_FanCoilUnit_AirTreatmentModules42GR4Pipes.rfa | new | 434_ME_FanCoilUnit_AirTreatmentModules42GR4Pipes | new | h.huynh | 75276
75287 | n.le | tm.doan | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH4Pipe.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH4Pipe | new | tm.doan | 75287
75286 | n.le | tm.doan | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH2Pipe.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH2Pipe | new | tm.doan | 75286
75285 | n.le | tm.doan | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWD2Pipe.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWD2Pipe | new | tm.doan | 75285
75284 | n.le | tm.doan | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC4Pipe.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC4Pipe | new | tm.doan | 75284
75283 | n.le | tm.doan | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC2Pipe.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC2Pipe | new | tm.doan | 75283
75282 | n.le | tm.doan | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_HybridTerminal36XB.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_HybridTerminal36XB | new | tm.doan | 75282
75281 | n.le | tm.doan | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_CompactChassis42GW4Pipes.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_CompactChassis42GW4Pipes | new | tm.doan | 75281
75289 | n.le | t.tran | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_Standard.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_Standard | new | t.tran | 75289
75288 | n.le | t.tran | 2026-08-13 | 434_ME_FanCoilUnit_CeilingMounted_LargeChassis42GW4Pipes.rfa | new | 434_ME_FanCoilUnit_CeilingMounted_LargeChassis42GW4Pipes | new | t.tran | 75288
75233 | n.le | l.nguyen | 2026-08-13 | 420_ME_HeatPump_PackageDrooftop_48And50UA&UH.rfa | new | 420_ME_HeatPump_PackageDrooftop_48And50UA&UH | new | l.nguyen | 75233
75232 | n.le | l.nguyen | 2026-08-13 | 420_ME_HeatExchangerFreeCooling_Flange.rfa | new | 420_ME_HeatExchangerFreeCooling_Flange | new | l.nguyen | 75232
75231 | n.le | l.nguyen | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_5Connector.rfa | new | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_5Connector | new | l.nguyen | 75231
75230 | n.le | l.nguyen | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_4Connector.rfa | new | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_4Connector | new | l.nguyen | 75230
75229 | n.le | l.nguyen | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_3Connector.rfa | new | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_3Connector | new | l.nguyen | 75229
75228 | n.le | l.nguyen | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_2Connector.rfa | new | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_2Connector | new | l.nguyen | 75228
75227 | n.le | l.nguyen | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_1Connector.rfa | new | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_1Connector | new | l.nguyen | 75227
75226 | n.le | l.nguyen | 2026-08-13 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQKnano.rfa | new | 420_ME_Fancoilunit_UnderfloorTrench_KathermQKnano | new | l.nguyen | 75226
75240 | n.le | th.nguyen | 2026-08-13 | 420_ME_HotWaterStorageTank_Standard.rfa | new | 420_ME_HotWaterStorageTank_Standard | new | th.nguyen | 75240
75239 | n.le | th.nguyen | 2026-08-13 | 420_ME_HotWaterBoiler.rfa | new | 420_ME_HotWaterBoiler | new | th.nguyen | 75239
75238 | n.le | th.nguyen | 2026-08-13 | 420_ME_HomeStation_GHKFBH.rfa | new | 420_ME_HomeStation_GHKFBH | new | th.nguyen | 75238
75237 | n.le | th.nguyen | 2026-08-13 | 420_ME_HomeStation_GHK.rfa | new | 420_ME_HomeStation_GHK | new | th.nguyen | 75237
75236 | n.le | th.nguyen | 2026-08-13 | 420_ME_HomeStation_DHK.rfa | new | 420_ME_HomeStation_DHK | new | th.nguyen | 75236
75235 | n.le | th.nguyen | 2026-08-13 | 420_ME_HeatingCoolingSails_Ceiling.rfa | new | 420_ME_HeatingCoolingSails_Ceiling | new | th.nguyen | 75235
75234 | n.le | th.nguyen | 2026-08-13 | 420_ME_HeatTransferStation_Custom.rfa | new | 420_ME_HeatTransferStation_Custom | new | th.nguyen | 75234
74701 | n.le | t.tran | 2026-07-22 | 434_ME_FlatCompactDryCooler.rfa | acknowledged | 434_ME_FlatCompactDryCooler | acknowledged | t.tran | 74701
74718 | n.le | th.nguyen | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Credoplus.rfa | acknowledged | 420_ME_RadiatorBathroom_WallMounted_Credoplus | acknowledged | th.nguyen | 74718
74633 | n.le | dx.quach | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_5Circuits.rfa | assigned | 434_ME_ManifoldWithFlowMeter_5Circuits | assigned | dx.quach | 74633
73825 | n.le | ht.tran | 2026-06-25 | 420_PA_BalancingValve_Thread_Standard.rfa | new | 420_PA_BalancingValve_Thread_Standard | new | ht.tran | 73825
73534 | n.le | nd.huynh | 2026-06-19 | 420_PA_DrainValve_Thread_Standard | assigned | 420_PA_DrainValve_Thread_Standard | assigned | nd.huynh | 73534
73147 | n.le | nd.huynh | 2026-06-08 | 434_ME_Pump_Circulator_VeroTwinDPL_DN80 | assigned | 434_ME_Pump_Circulator_VeroTwinDPL_DN80 | assigned | nd.huynh | 73147
73533 | n.le | nd.huynh | 2026-06-19 | 420_PA_DrainValve_Threaded | assigned | 420_PA_DrainValve_Threaded | assigned | nd.huynh | 73533
73844 | n.le | th.nguyen | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanVPlus.rfa | acknowledged | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanVPlus | acknowledged | th.nguyen | 73844
73822 | n.le | b.tran | 2026-06-25 | 420_PA_BallValve_Flanged.rfa | assigned | 420_PA_BallValve_Flanged | assigned | b.tran | 73822
73522 | n.le | b.tran | 2026-06-19 | 420_PA_PIQCVValve_Thread | assigned | 420_PA_PIQCVValve_Thread | assigned | b.tran | 73522
73084 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVOutDoorUnit_HeatPumpRXYSA&AV1&AY1 | assigned | 434_ME_VRVOutDoorUnit_HeatPumpRXYSA&AV1&AY1 | assigned | nd.huynh | 73084
73535 | n.le | nd.huynh | 2026-06-19 | 420_PA_DiscCheckValve_Flanged_Standard | assigned | 420_PA_DiscCheckValve_Flanged_Standard | assigned | nd.huynh | 73535
73100 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVInDoorUnit_CeilingMouted_FXFA&A | assigned | 434_ME_VRVInDoorUnit_CeilingMouted_FXFA&A | assigned | nd.huynh | 73100
73884 | n.le | nd.huynh | 2026-06-25 | 434_ME_Manifold_5Circuits.rfa | assigned | 434_ME_Manifold_5Circuits | assigned | nd.huynh | 73884
73883 | n.le | nd.huynh | 2026-06-25 | 434_ME_Manifold_6Circuits.rfa | assigned | 434_ME_Manifold_6Circuits | assigned | nd.huynh | 73883
73882 | n.le | nd.huynh | 2026-06-25 | 434_ME_Manifold_7Circuits.rfa | assigned | 434_ME_Manifold_7Circuits | assigned | nd.huynh | 73882
73868 | n.le | nd.huynh | 2026-06-25 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9F.rfa | assigned | 434_ME_PressureMaintenanceMonitoring_PlenoPI9F | assigned | nd.huynh | 73868
73532 | n.le | nd.huynh | 2026-06-19 | 420_PA_ExpansionJoint_Flanged | assigned | 420_PA_ExpansionJoint_Flanged | assigned | nd.huynh | 73532
73130 | n.le | nd.huynh | 2026-06-08 | 420_PA_HeatingBallValve_Thread | assigned | 420_PA_HeatingBallValve_Thread | assigned | nd.huynh | 73130
73553 | n.le | nd.huynh | 2026-06-19 | 420_PA_BallValve_Thread_LeverStandard | assigned | 420_PA_BallValve_Thread_LeverStandard | assigned | nd.huynh | 73553
73552 | n.le | nd.huynh | 2026-06-19 | 420_PA_BallValve_Thread_WheelStandard | assigned | 420_PA_BallValve_Thread_WheelStandard | assigned | nd.huynh | 73552
73528 | n.le | nd.huynh | 2026-06-19 | 420_PA_FilterValve_Flanged | assigned | 420_PA_FilterValve_Flanged | assigned | nd.huynh | 73528
73501 | n.le | nd.huynh | 2026-06-19 | 434_ME_Pump_WaterSupplyCronoNorm&NLG | assigned | 434_ME_Pump_WaterSupplyCronoNorm&NLG | assigned | nd.huynh | 73501
73139 | n.le | nd.huynh | 2026-06-08 | 420_PA_GateValve_Thread_Standard | assigned | 420_PA_GateValve_Thread_Standard | assigned | nd.huynh | 73139
73126 | n.le | nd.huynh | 2026-06-08 | 420_PA_MotorizedBallValve_Thread_Standard | assigned | 420_PA_MotorizedBallValve_Thread_Standard | assigned | nd.huynh | 73126
73099 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVInDoorUnit_CeilingMouted_FXZA&A | assigned | 434_ME_VRVInDoorUnit_CeilingMouted_FXZA&A | assigned | nd.huynh | 73099
73082 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVShutOffValveBox_SV4A14AJV1B | assigned | 434_ME_VRVShutOffValveBox_SV4A14AJV1B | assigned | nd.huynh | 73082
73543 | n.le | nd.huynh | 2026-06-19 | 420_PA_ButterflyvalveMotor_Flanged | assigned | 420_PA_ButterflyvalveMotor_Flanged | assigned | nd.huynh | 73543
73129 | n.le | nd.huynh | 2026-06-08 | 420_PA_LiftCheckValve_Flanged_Standard | assigned | 420_PA_LiftCheckValve_Flanged_Standard | assigned | nd.huynh | 73129
73128 | n.le | nd.huynh | 2026-06-08 | 420_PA_LiftCheckValve_Thread_Standard | assigned | 420_PA_LiftCheckValve_Thread_Standard | assigned | nd.huynh | 73128
73090 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVMultiBranchSelector_BS&12A14AV1B | assigned | 434_ME_VRVMultiBranchSelector_BS&12A14AV1B | assigned | nd.huynh | 73090
73089 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVMultiBranchSelector_BS&4A14AV1B | assigned | 434_ME_VRVMultiBranchSelector_BS&4A14AV1B | assigned | nd.huynh | 73089
73083 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVShutOffValveBox_SV1A25AJV1B | assigned | 434_ME_VRVShutOffValveBox_SV1A25AJV1B | assigned | nd.huynh | 73083
73493 | n.le | nd.huynh | 2026-06-19 | 434_ME_WaterCooledCondenserlessLiquidChillers_30WG | assigned | 434_ME_WaterCooledCondenserlessLiquidChillers_30WG | assigned | nd.huynh | 73493
73492 | n.le | nd.huynh | 2026-06-19 | 434_ME_WaterCooledCondenserlessLiquidchillers_30WGA | assigned | 434_ME_WaterCooledCondenserlessLiquidchillers_30WGA | assigned | nd.huynh | 73492
73143 | n.le | nd.huynh | 2026-06-08 | 420_PA_FlowSensor_Thread_Standard | assigned | 420_PA_FlowSensor_Thread_Standard | assigned | nd.huynh | 73143
72653 | n.le | nd.huynh | 2026-06-01 | 420_PA_SwingCheckValve_Flanged_Standard | assigned | 420_PA_SwingCheckValve_Flanged_Standard | assigned | nd.huynh | 72653
73833 | n.le | nd.huynh | 2026-06-25 | 420_ME_WaterHeater_Vertical.rfa | assigned | 420_ME_WaterHeater_Vertical | assigned | nd.huynh | 73833
73823 | n.le | nd.huynh | 2026-06-25 | 420_PA_BallValve3Way_TPort.rfa | assigned | 420_PA_BallValve3Way_TPort | assigned | nd.huynh | 73823
73494 | n.le | nd.huynh | 2026-06-19 | 434_ME_WateCooledCondenserlessLiquidChillers_WithHydraulicModule_30RW | assigned | 434_ME_WateCooledCondenserlessLiquidChillers_WithHydraulicModule_30RW | assigned | nd.huynh | 73494
73853 | n.le | nd.huynh | 2026-06-25 | 434_ME_Pump_Circulator_VeroTwinDPL_DN100.rfa | assigned | 434_ME_Pump_Circulator_VeroTwinDPL_DN100 | assigned | nd.huynh | 73853
73886 | n.le | nd.huynh | 2026-06-25 | 434_ME_Manifold_3Circuits.rfa | assigned | 434_ME_Manifold_3Circuits | assigned | nd.huynh | 73886
73885 | n.le | nd.huynh | 2026-06-25 | 434_ME_Manifold_4Circuits.rfa | assigned | 434_ME_Manifold_4Circuits | assigned | nd.huynh | 73885
73545 | n.le | nd.huynh | 2026-06-19 | 420_PA_ButterflyValve_Thread_GearStandard | assigned | 420_PA_ButterflyValve_Thread_GearStandard | assigned | nd.huynh | 73545
73544 | n.le | nd.huynh | 2026-06-19 | 420_PA_ButterflyValve_Thread_LeverStandard | assigned | 420_PA_ButterflyValve_Thread_LeverStandard | assigned | nd.huynh | 73544
73841 | n.le | nd.huynh | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileVPlus.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileVPlus | assigned | nd.huynh | 73841
73837 | n.le | nd.huynh | 2026-06-25 | 420_ME_RadiatorHeatingWall_WallMounted_Vertical.rfa | assigned | 420_ME_RadiatorHeatingWall_WallMounted_Vertical | assigned | nd.huynh | 73837
73834 | n.le | nd.huynh | 2026-06-25 | 420_ME_SinglePassTubeHeatExchanger_Horizontal.rfa | assigned | 420_ME_SinglePassTubeHeatExchanger_Horizontal | assigned | nd.huynh | 73834
73551 | n.le | nd.huynh | 2026-06-19 | 420_PA_BallValve_Threaded | assigned | 420_PA_BallValve_Threaded | assigned | nd.huynh | 73551
73549 | n.le | nd.huynh | 2026-06-19 | 420_PA_BasketStrainerValve_Thread_Standard | assigned | 420_PA_BasketStrainerValve_Thread_Standard | assigned | nd.huynh | 73549
73539 | n.le | nd.huynh | 2026-06-19 | 420_PA_DifferentialPressureGauge_Standard | assigned | 420_PA_DifferentialPressureGauge_Standard | assigned | nd.huynh | 73539
73145 | n.le | nd.huynh | 2026-06-08 | 420_PA_FlowSensor | assigned | 420_PA_FlowSensor | assigned | nd.huynh | 73145
73104 | n.le | nd.huynh | 2026-06-08 | 434_ME_Pump_Circulator_YonosGIGA20_I | assigned | 434_ME_Pump_Circulator_YonosGIGA20_I | assigned | nd.huynh | 73104
73103 | n.le | nd.huynh | 2026-06-08 | 434_ME_Pump_SingleStageLowPressureBAC65 | assigned | 434_ME_Pump_SingleStageLowPressureBAC65 | assigned | nd.huynh | 73103
73098 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXHA&A | assigned | 434_ME_VRVInDoorUnit_CeilingSuspended_FXHA&A | assigned | nd.huynh | 73098
72629 | n.le | nd.huynh | 2026-06-01 | 434_PA_RefnetJoint_KHRPGas | assigned | 434_PA_RefnetJoint_KHRPGas | assigned | nd.huynh | 72629
73088 | n.le | nd.huynh | 2026-06-08 | 434_ME_VRVMultiBranchSelector_BS&6A14AV1B | assigned | 434_ME_VRVMultiBranchSelector_BS&6A14AV1B | assigned | nd.huynh | 73088
73495 | n.le | nd.huynh | 2026-06-19 | 434_ME_VariableSpeedWaterCooledLiquidChiller_SingleCompressor30XW&V | assigned | 434_ME_VariableSpeedWaterCooledLiquidChiller_SingleCompressor30XW&V | assigned | nd.huynh | 73495
74689 | n.le | tm.doan | 2026-07-22 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs78_NoSystem.rfa | assigned | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs78_NoSystem | assigned | tm.doan | 74689
74634 | n.le | dx.quach | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_4Circuits.rfa | assigned | 434_ME_ManifoldWithFlowMeter_4Circuits | assigned | dx.quach | 74634
74717 | n.le | hu.dam | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_DecorArteLine.rfa | new | 420_ME_RadiatorBathroom_WallMounted_DecorArteLine | new | hu.dam | 74717
74716 | n.le | hu.dam | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePlan.rfa | new | 420_ME_RadiatorBathroom_WallMounted_DecorArtePlan | new | hu.dam | 74716
74711 | n.le | hu.dam | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Elveo_NoSystem.rfa | new | 420_ME_RadiatorBathroom_WallMounted_Elveo_NoSystem | new | hu.dam | 74711
74690 | n.le | hu.dam | 2026-07-22 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs125_NoSystem.rfa | new | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs125_NoSystem | new | hu.dam | 74690
74678 | n.le | hu.dam | 2026-07-22 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B147SD.rfa | new | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B147SD | new | hu.dam | 74678
73849 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_Circulator_VeroTwinDPL_DN65.rfa | new | 434_ME_Pump_Circulator_VeroTwinDPL_DN65 | new | hu.dam | 73849
73819 | n.le | hu.dam | 2026-06-25 | 420_PA_BallValve_FullBore | closed | 420_PA_BallValve_FullBore | closed | hu.dam | 73819
73096 | n.le | ht.pham | 2026-06-08 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXDA | assigned | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXDA | assigned | ht.pham | 73096
74719 | n.le | d.phan | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Credohalfflat.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_Credohalfflat | assigned | d.phan | 74719
74706 | n.le | d.phan | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Ideos.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_Ideos | assigned | d.phan | 74706
74702 | n.le | d.phan | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Pio1layer.rfa | acknowledged | 420_ME_RadiatorBathroom_WallMounted_Pio1layer | acknowledged | d.phan | 74702
73855 | n.le | dx.quach | 2026-06-25 | 434_ME_Pump_CirculatorYonosPICO.rfa | acknowledged | 434_ME_Pump_CirculatorYonosPICO | acknowledged | dx.quach | 73855
73854 | n.le | dx.quach | 2026-06-25 | 434_ME_Pump_Circulator_CronoTwin_DL_E.rfa | acknowledged | 434_ME_Pump_Circulator_CronoTwin_DL_E | acknowledged | dx.quach | 73854
73852 | n.le | dx.quach | 2026-06-25 | 434_ME_Pump_Circulator_VeroTwinDPL_DN32.rfa | acknowledged | 434_ME_Pump_Circulator_VeroTwinDPL_DN32 | acknowledged | dx.quach | 73852
73850 | n.le | dx.quach | 2026-06-25 | 434_ME_Pump_Circulator_VeroTwinDPL_DN50.rfa | acknowledged | 434_ME_Pump_Circulator_VeroTwinDPL_DN50 | acknowledged | dx.quach | 73850
73865 | n.le | h.huynh | 2026-06-25 | 434_ME_PumpCirculator_FloorStand_Round_CronoLineILE.rfa | assigned | 434_ME_PumpCirculator_FloorStand_Round_CronoLineILE | assigned | h.huynh | 73865
73860 | n.le | h.huynh | 2026-06-25 | 434_ME_Pump_CirculatorStratosGIGA20&I.rfa | assigned | 434_ME_Pump_CirculatorStratosGIGA20&I | assigned | h.huynh | 73860
73095 | n.le | ht.pham | 2026-06-08 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA | assigned | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA | assigned | ht.pham | 73095
73094 | n.le | ht.pham | 2026-06-08 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA200and250A | assigned | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA200and250A | assigned | ht.pham | 73094
72628 | n.le | tm.doan | 2026-06-01 | 434_PA_RefnetJoint_KHRPLiquid | new | 434_PA_RefnetJoint_KHRPLiquid | new | tm.doan | 72628
72630 | n.le | tm.doan | 2026-06-01 | 434_PA_RefnetJoint_KHRPDischarge | new | 434_PA_RefnetJoint_KHRPDischarge | new | tm.doan | 72630
73091 | n.le | tm.doan | 2026-06-08 | 434_ME_VRVMultiBranchSelector_BS&10A14AV1B | new | 434_ME_VRVMultiBranchSelector_BS&10A14AV1B | new | tm.doan | 73091
74649 | n.le | hu.dam | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlus.rfa | new | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlus | new | hu.dam | 74649
73107 | n.le | hu.dam | 2026-06-08 | 420_PA_PressureIndependentControlValve_Flanged | new | 420_PA_PressureIndependentControlValve_Flanged | new | hu.dam | 73107
73106 | n.le | hu.dam | 2026-06-08 | 420_PA_PressureIndependentControlValve_Threaded | new | 420_PA_PressureIndependentControlValve_Threaded | new | hu.dam | 73106
72693 | n.le | hu.dam | 2026-06-01 | 420_PA_RadiatorLockshield_Thread | new | 420_PA_RadiatorLockshield_Thread | new | hu.dam | 72693
72690 | n.le | hu.dam | 2026-06-01 | 420_PA_RadiatorShutOffValveStraight_Thread | new | 420_PA_RadiatorShutOffValveStraight_Thread | new | hu.dam | 72690
74683 | n.le | hu.dam | 2026-07-22 | 434_ME_HeatedAndChilledHybridCeilings_CeilingMounted_DSTAS.rfa | new | 434_ME_HeatedAndChilledHybridCeilings_CeilingMounted_DSTAS | new | hu.dam | 74683
74651 | n.le | hu.dam | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV.rfa | new | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV | new | hu.dam | 74651
72688 | n.le | hu.dam | 2026-06-01 | 420_PA_RadiatorThermostatic2PointAngleValve_Thread | new | 420_PA_RadiatorThermostatic2PointAngleValve_Thread | new | hu.dam | 72688
72687 | n.le | hu.dam | 2026-06-01 | 420_PA_RadiatorThermostaticAngleValve_Thread | new | 420_PA_RadiatorThermostaticAngleValve_Thread | new | hu.dam | 72687
73829 | n.le | hu.dam | 2026-06-25 | 420_PA_AirValve_Thread.rfa | closed | 420_PA_AirValve_Thread | closed | hu.dam | 73829
73826 | n.le | hu.dam | 2026-06-25 | 420_PA_BalancingValve_Thread.rfa | closed | 420_PA_BalancingValve_Thread | closed | hu.dam | 73826
74661 | n.le | hu.dam | 2026-07-21 | 420_ME_RadiatorBathroom_WallMounted_Signo.rfa | new | 420_ME_RadiatorBathroom_WallMounted_Signo | new | hu.dam | 74661
73845 | n.le | hu.dam | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanV.rfa | new | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanV | new | hu.dam | 73845
73105 | n.le | hu.dam | 2026-06-08 | 420_PA_PressureReducingValveWithGauge_Thread | new | 420_PA_PressureReducingValveWithGauge_Thread | new | hu.dam | 73105
72695 | n.le | hu.dam | 2026-06-01 | 420_PA_PressureSensor | new | 420_PA_PressureSensor | new | hu.dam | 72695
72659 | n.le | hu.dam | 2026-06-01 | 420_PA_SafetyReliefValveCorner_Flanged | closed | 420_PA_SafetyReliefValveCorner_Flanged | closed | hu.dam | 72659
72588 | n.le | hu.dam | 2026-06-01 | 420_PA_YStrainer_Flanged | closed | 420_PA_YStrainer_Flanged | closed | hu.dam | 72588
73878 | n.le | ht.pham | 2026-06-25 | 434_ME_OutDoorUnit_VRV5HeatRecoveryREYA.rfa | assigned | 434_ME_OutDoorUnit_VRV5HeatRecoveryREYA | assigned | ht.pham | 73878
72599 | n.le | ht.nguyen | 2026-06-01 | 420_PA_Thermometergauge | assigned | 420_PA_Thermometergauge | assigned | ht.nguyen | 72599
73877 | n.le | qd.nguyen | 2026-06-25 | 434_ME_PrecisionPressureMaintenance_TransferoTI.rfa | assigned | 434_ME_PrecisionPressureMaintenance_TransferoTI | assigned | qd.nguyen | 73877
72604 | n.le | ht.nguyen | 2026-06-01 | 420_PA_SwingcheckValve_Threaded | assigned | 420_PA_SwingcheckValve_Threaded | assigned | ht.nguyen | 72604
72631 | n.le | dahn.nguyen | 2026-06-01 | 434_PA_RefnetHeader_KHRPLiquid8Branches | assigned | 434_PA_RefnetHeader_KHRPLiquid8Branches | assigned | dahn.nguyen | 72631
73536 | n.le | dahn.nguyen | 2026-06-19 | 420_PA_DifferentialPressureSensor_Standard | assigned | 420_PA_DifferentialPressureSensor_Standard | assigned | dahn.nguyen | 73536
73537 | n.le | qd.nguyen | 2026-06-19 | 420_PA_DifferentialPressureSensor | assigned | 420_PA_DifferentialPressureSensor | assigned | qd.nguyen | 73537
73874 | n.le | qd.nguyen | 2026-06-25 | 434_ME_PrecisionPressureMaintenance_TransferoTVI1.rfa | assigned | 434_ME_PrecisionPressureMaintenance_TransferoTVI1 | assigned | qd.nguyen | 73874
73875 | n.le | qd.nguyen | 2026-06-25 | 434_ME_PrecisionPressureMaintenance_TransferoTV2.rfa | assigned | 434_ME_PrecisionPressureMaintenance_TransferoTV2 | assigned | qd.nguyen | 73875
73876 | n.le | qd.nguyen | 2026-06-25 | 434_ME_PrecisionPressureMaintenance_TransferoTV1.rfa | assigned | 434_ME_PrecisionPressureMaintenance_TransferoTV1 | assigned | qd.nguyen | 73876
74705 | n.le | hu.dam | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Ineo.rfa | new | 420_ME_RadiatorBathroom_WallMounted_Ineo | new | hu.dam | 74705
74704 | n.le | hu.dam | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Leveo.rfa | new | 420_ME_RadiatorBathroom_WallMounted_Leveo | new | hu.dam | 74704
74692 | n.le | hu.dam | 2026-07-22 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD315.rfa | new | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD315 | new | hu.dam | 74692
74691 | n.le | hu.dam | 2026-07-22 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD320.rfa | new | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD320 | new | hu.dam | 74691
74655 | n.le | hu.dam | 2026-07-21 | 420_ME_RadiatorElectricPanel_WallMounted_xThermProfileHorizontal_NoSystem.rfa | new | 420_ME_RadiatorElectricPanel_WallMounted_xThermProfileHorizontal_NoSystem | new | hu.dam | 74655
74654 | n.le | hu.dam | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanK.rfa | new | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanK | new | hu.dam | 74654
73292 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_uAdaptorUnion_MapressAndMaleThreadFKMBlue_WithNut | new | 434_PF_CO_uAdaptorUnion_MapressAndMaleThreadFKMBlue_WithNut | new | hu.dam | 73292
73291 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_uAdaptorUnion_MapressAndNutGas | new | 434_PF_CO_uAdaptorUnion_MapressAndNutGas | new | hu.dam | 73291
73288 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_uTap_Thread | new | 434_PF_CO_uTap_Thread | new | hu.dam | 73288
72691 | n.le | hu.dam | 2026-06-01 | 420_PA_RadiatorShutOffValveAngle_Thread | new | 420_PA_RadiatorShutOffValveAngle_Thread | new | hu.dam | 72691
73866 | n.le | hu.dam | 2026-06-25 | 434_ME_PressureMaintenanceMonitoring_PlenoPX.rfa | closed | 434_ME_PressureMaintenanceMonitoring_PlenoPX | closed | hu.dam | 73866
73867 | n.le | hu.dam | 2026-06-25 | 434_ME_PressureMaintenanceMonitoring_PlenoPIX.rfa | closed | 434_ME_PressureMaintenanceMonitoring_PlenoPIX | closed | hu.dam | 73867
73838 | n.le | hu.dam | 2026-06-25 | 420_ME_RadiatorHeatingWall_WallMounted_ValveVertical.rfa | closed | 420_ME_RadiatorHeatingWall_WallMounted_ValveVertical | closed | hu.dam | 73838
73835 | n.le | hu.dam | 2026-06-25 | 420_ME_RectangularTubeManifold_8Connection.rfa | closed | 420_ME_RectangularTubeManifold_8Connection | closed | hu.dam | 73835
73488 | n.le | hu.dam | 2026-06-19 | 434_PF_CO_eAdaptorBend_MapressAndFemaleThread_WithNut | closed | 434_PF_CO_eAdaptorBend_MapressAndFemaleThread_WithNut | closed | hu.dam | 73488
72663 | n.le | hu.dam | 2026-06-01 | 420_PA_RegulatingValve_Thread_Standard | closed | 420_PA_RegulatingValve_Thread_Standard | closed | hu.dam | 72663
72660 | n.le | hu.dam | 2026-06-01 | 420_PA_SafetyReliefValveConer_Thread | closed | 420_PA_SafetyReliefValveConer_Thread | closed | hu.dam | 72660
72686 | n.le | n.le | 2026-06-01 | 420_PA_RadiatorThermostaticStraightValve_Thread | assigned | 420_PA_RadiatorThermostaticStraightValve_Thread | assigned | n.le | 72686
73511 | n.le | qn.ha | 2026-06-19 | 420_PA_WaterMeter_Threaded_Standard | assigned | 420_PA_WaterMeter_Threaded_Standard | assigned | qn.ha | 73511
73300 | n.le | ht.nguyen | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MapressAndThreadFKMBlue | assigned | 434_PF_CO_rReducerAdaptor_MapressAndThreadFKMBlue | assigned | ht.nguyen | 73300
73859 | n.le | qd.nguyen | 2026-06-25 | 434_ME_Pump_CirculatorStratosMAXO.rfa | assigned | 434_ME_Pump_CirculatorStratosMAXO | assigned | qd.nguyen | 73859
74688 | n.le | h.huynh | 2026-07-22 | 434_ME_HeatedAndChilledCorridorCeilings_CeilingMounted_E312.rfa | assigned | 434_ME_HeatedAndChilledCorridorCeilings_CeilingMounted_E312 | assigned | h.huynh | 74688
74687 | n.le | h.huynh | 2026-07-22 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E200.rfa | assigned | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E200 | assigned | h.huynh | 74687
74680 | n.le | h.huynh | 2026-07-22 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100SD.rfa | assigned | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100SD | assigned | h.huynh | 74680
73079 | n.le | lk.dang | 2026-06-08 | 434_ME_WaterCooledLiquidChillers_30XW | assigned | 434_ME_WaterCooledLiquidChillers_30XW | assigned | lk.dang | 73079
73888 | n.le | hu.dam | 2026-06-25 | 434_ME_Manifold_12Circuits.rfa | new | 434_ME_Manifold_12Circuits | new | hu.dam | 73888
73127 | n.le | lk.dang | 2026-06-08 | 420_PA_MotorizedBallValve_Flanged_Standard | assigned | 420_PA_MotorizedBallValve_Flanged_Standard | assigned | lk.dang | 73127
74656 | n.le | hu.dam | 2026-07-21 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanVertical_NoSystem.rfa | new | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanVertical_NoSystem | new | hu.dam | 74656
73112 | n.le | hu.dam | 2026-06-08 | 420_PA_PneumaticGlobeControlValve_Thread | new | 420_PA_PneumaticGlobeControlValve_Thread | new | hu.dam | 73112
72158 | n.le | n.le | 2026-05-27 | Revise the RFA library for the HGR system | assigned | Revise the RFA library for the HGR system | assigned | n.le | 72158
72157 | n.le | n.le | 2026-05-27 | Revise the RFA library for the KLT system | assigned | Revise the RFA library for the KLT system | assigned | n.le | 72157
72156 | n.le | n.le | 2026-05-27 | Revise the RFA library for the HZG system | assigned | Revise the RFA library for the HZG system | assigned | n.le | 72156
74712 | n.le | hu.dam | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Duett.rfa | new | 420_ME_RadiatorBathroom_WallMounted_Duett | new | hu.dam | 74712
74684 | n.le | hu.dam | 2026-07-22 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E214.rfa | new | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E214 | new | hu.dam | 74684
73846 | n.le | hu.dam | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanK.rfa | new | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanK | new | hu.dam | 73846
73509 | n.le | hu.dam | 2026-06-19 | 420_PF_CO_rReducer_Soldered | new | 420_PF_CO_rReducer_Soldered | new | hu.dam | 73509
73524 | n.le | hu.dam | 2026-06-19 | 420_PA_PICVValve_Thread | closed | 420_PA_PICVValve_Thread | closed | hu.dam | 73524
73144 | n.le | hu.dam | 2026-06-08 | 420_PA_FlowSensor_Flanged_Standard | closed | 420_PA_FlowSensor_Flanged_Standard | closed | hu.dam | 73144
74622 | n.le | qn.ha | 2026-07-21 | 434_ME_ManifoldWithPump_7Circuits.rfa | assigned | 434_ME_ManifoldWithPump_7Circuits | assigned | qn.ha | 74622
74621 | n.le | qn.ha | 2026-07-21 | 434_ME_ManifoldWithPump_8Circuits.rfa | assigned | 434_ME_ManifoldWithPump_8Circuits | assigned | qn.ha | 74621
74715 | n.le | qn.ha | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureHorizontal.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureHorizontal | assigned | qn.ha | 74715
74714 | n.le | qn.ha | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureVertical.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureVertical | assigned | qn.ha | 74714
74713 | n.le | qn.ha | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Diveo.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_Diveo | assigned | qn.ha | 74713
74662 | n.le | qn.ha | 2026-07-21 | 420_ME_RadiatorBathroom_WallMounted_Rubeo.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_Rubeo | assigned | qn.ha | 74662
74647 | n.le | qn.ha | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileK.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileK | assigned | qn.ha | 74647
74643 | n.le | qn.ha | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVHygiene.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVHygiene | assigned | qn.ha | 74643
74641 | n.le | qn.ha | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlusHygiene.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlusHygiene | assigned | qn.ha | 74641
74631 | n.le | qn.ha | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_7Circuits.rfa | assigned | 434_ME_ManifoldWithFlowMeter_7Circuits | assigned | qn.ha | 74631
74630 | n.le | qn.ha | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_8Circuits.rfa | assigned | 434_ME_ManifoldWithFlowMeter_8Circuits | assigned | qn.ha | 74630
74629 | n.le | qn.ha | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_9Circuits.rfa | assigned | 434_ME_ManifoldWithFlowMeter_9Circuits | assigned | qn.ha | 74629
74628 | n.le | qn.ha | 2026-07-21 | 434_ME_ManifoldWithPump_1Circuits.rfa | assigned | 434_ME_ManifoldWithPump_1Circuits | assigned | qn.ha | 74628
73887 | n.le | qn.ha | 2026-06-25 | 434_ME_Manifold_2Circuits.rfa | assigned | 434_ME_Manifold_2Circuits | assigned | qn.ha | 73887
73848 | n.le | qn.ha | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoPlan.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_VerteoPlan | assigned | qn.ha | 73848
73847 | n.le | qn.ha | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoProfile.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_VerteoProfile | assigned | qn.ha | 73847
74696 | n.le | ht.pham | 2026-07-22 | 434_ME_HeatExchanger_Gasketed&Flanged.rfa | assigned | 434_ME_HeatExchanger_Gasketed&Flanged | assigned | ht.pham | 74696
74695 | n.le | ht.pham | 2026-07-22 | 434_ME_HeatExchanger_Gasketed&Thread.rfa | assigned | 434_ME_HeatExchanger_Gasketed&Thread | assigned | ht.pham | 74695
74694 | n.le | ht.pham | 2026-07-22 | 434_ME_HeatExchanger_Standard.rfa | assigned | 434_ME_HeatExchanger_Standard | assigned | ht.pham | 74694
74693 | n.le | ht.pham | 2026-07-22 | 434_ME_HeatedAndChilledBaffleCeilings_CeilingMounted_L608.rfa | assigned | 434_ME_HeatedAndChilledBaffleCeilings_CeilingMounted_L608 | assigned | ht.pham | 74693
74679 | n.le | ht.pham | 2026-07-22 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B110.rfa | assigned | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B110 | assigned | ht.pham | 74679
74636 | n.le | ht.pham | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_2Circuits.rfa | assigned | 434_ME_ManifoldWithFlowMeter_2Circuits | assigned | ht.pham | 74636
74635 | n.le | ht.pham | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_3Circuits.rfa | assigned | 434_ME_ManifoldWithFlowMeter_3Circuits | assigned | ht.pham | 74635
73512 | n.le | lk.dang | 2026-06-19 | 420_PA_ThreeWayMotorisedControlValve_Thread | assigned | 420_PA_ThreeWayMotorisedControlValve_Thread | assigned | lk.dang | 73512
73490 | n.le | lk.dang | 2026-06-19 | 434_ME_WatercooledCondenserlessliquidchillers_30RW_WithoutHydraulicModule | assigned | 434_ME_WatercooledCondenserlessliquidchillers_30RW_WithoutHydraulicModule | assigned | lk.dang | 73490
73136 | n.le | ht.tran | 2026-06-08 | 420_PA_GlobeValve_Flanged_Standard | assigned | 420_PA_GlobeValve_Flanged_Standard | assigned | ht.tran | 73136
73135 | n.le | ht.tran | 2026-06-08 | 420_PA_GlobeValve_Thread | assigned | 420_PA_GlobeValve_Thread | assigned | ht.tran | 73135
73134 | n.le | ht.tran | 2026-06-08 | 420_PA_GlobeValve_Thread_Standard | assigned | 420_PA_GlobeValve_Thread_Standard | assigned | ht.tran | 73134
73115 | n.le | ht.tran | 2026-06-08 | 420_PA_PIQCV6WayValve_Thread | assigned | 420_PA_PIQCV6WayValve_Thread | assigned | ht.tran | 73115
72174 | n.le | ht.tran | 2026-05-27 | 420_PF_MapressCarbonSteel_Elbow_SlipJoin | assigned | 420_PF_MapressCarbonSteel_Elbow_SlipJoin | assigned | ht.tran | 72174
74650 | n.le | b.tran | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVHygiene.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVHygiene | assigned | b.tran | 74650
74648 | n.le | b.tran | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlusHygiene.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlusHygiene | assigned | b.tran | 74648
73880 | n.le | ht.pham | 2026-06-25 | 434_ME_Manifold_8Circuits.rfa | acknowledged | 434_ME_Manifold_8Circuits | acknowledged | ht.pham | 73880
73879 | n.le | ht.pham | 2026-06-25 | 434_ME_Manifold_9Circuits.rfa | acknowledged | 434_ME_Manifold_9Circuits | acknowledged | ht.pham | 73879
72479 | n.le | ht.nguyen | 2026-05-28 | 434_PF_CO_uAdaptorUnion_Mapress | assigned | 434_PF_CO_uAdaptorUnion_Mapress | assigned | ht.nguyen | 72479
72580 | n.le | ht.nguyen | 2026-06-01 | 434_PF_CO_BridgeBendMultiPort_MapressGas | assigned | 434_PF_CO_BridgeBendMultiPort_MapressGas | assigned | ht.nguyen | 72580
72633 | n.le | ht.nguyen | 2026-06-01 | 434_PA_RefnetHeader_KHRPHP&LPGas | assigned | 434_PA_RefnetHeader_KHRPHP&LPGas | assigned | ht.nguyen | 72633
74682 | n.le | dahn.nguyen | 2026-07-22 | 434_ME_HeatedAndChilledPlasterboardCeilings_CeilingMounted_GKHEKDA2Pipes.rfa | assigned | 434_ME_HeatedAndChilledPlasterboardCeilings_CeilingMounted_GKHEKDA2Pipes | assigned | dahn.nguyen | 74682
74681 | n.le | dahn.nguyen | 2026-07-22 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100.rfa | assigned | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100 | assigned | dahn.nguyen | 74681
72583 | n.le | hu.dam | 2026-06-01 | 420_PF_CS_cCap_Welded | closed | 420_PF_CS_cCap_Welded | closed | hu.dam | 72583
72582 | n.le | hu.dam | 2026-06-01 | 420_PF_CS_eElbow_Welded | closed | 420_PF_CS_eElbow_Welded | closed | hu.dam | 72582
72585 | n.le | hu.dam | 2026-06-01 | 420_PF_CO_uUnion_Soldered | closed | 420_PF_CO_uUnion_Soldered | closed | hu.dam | 72585
74646 | n.le | d.phan | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKHygiene.rfa | acknowledged | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKHygiene | acknowledged | d.phan | 74646
74645 | n.le | d.phan | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKReplacement.rfa | acknowledged | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKReplacement | acknowledged | d.phan | 74645
73111 | n.le | b.tran | 2026-06-08 | 420_PA_PressureGauge | assigned | 420_PA_PressureGauge | assigned | b.tran | 73111
73110 | n.le | b.tran | 2026-06-08 | 420_PA_PressureGauge_2Connection | assigned | 420_PA_PressureGauge_2Connection | assigned | b.tran | 73110
73109 | n.le | b.tran | 2026-06-08 | 420_PA_PressureGauge_Standard | assigned | 420_PA_PressureGauge_Standard | assigned | b.tran | 73109
74686 | n.le | h.huynh | 2026-07-22 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E210.rfa | acknowledged | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E210 | acknowledged | h.huynh | 74686
74685 | n.le | h.huynh | 2026-07-22 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E213.rfa | acknowledged | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E213 | acknowledged | h.huynh | 74685
73832 | n.le | ht.tran | 2026-06-25 | 420_PA_6WayValve_Thread.rfa | acknowledged | 420_PA_6WayValve_Thread | acknowledged | ht.tran | 73832
73828 | n.le | ht.tran | 2026-06-25 | 420_PA_BalancingValve_Flanged.rfa | acknowledged | 420_PA_BalancingValve_Flanged | acknowledged | ht.tran | 73828
73827 | n.le | ht.tran | 2026-06-25 | 420_PA_BalancingValve_Flanged_Standard.rfa | acknowledged | 420_PA_BalancingValve_Flanged_Standard | acknowledged | ht.tran | 73827
72650 | n.le | ht.tran | 2026-06-01 | 420_PA_SwingcheckValve_Flanged | acknowledged | 420_PA_SwingcheckValve_Flanged | acknowledged | ht.tran | 72650
72597 | n.le | ht.tran | 2026-06-01 | 420_PA_ThreeWayvalve_Thread_Standard | acknowledged | 420_PA_ThreeWayvalve_Thread_Standard | acknowledged | ht.tran | 72597
72595 | n.le | ht.tran | 2026-06-01 | 420_PA_WaferCheckValve_Flanged_Standard | acknowledged | 420_PA_WaferCheckValve_Flanged_Standard | acknowledged | ht.tran | 72595
72594 | n.le | ht.tran | 2026-06-01 | 420_PA_WaterMeter_Flanged | acknowledged | 420_PA_WaterMeter_Flanged | acknowledged | ht.tran | 72594
72593 | n.le | ht.tran | 2026-06-01 | 420_PA_WaterMeter_Flanged_Standard | acknowledged | 420_PA_WaterMeter_Flanged_Standard | acknowledged | ht.tran | 72593
74640 | n.le | t.tran | 2026-07-21 | 434_ME_InLinePump_Standard.rfa | acknowledged | 434_ME_InLinePump_Standard | acknowledged | t.tran | 74640
74639 | n.le | t.tran | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_10Circuits.rfa | acknowledged | 434_ME_ManifoldWithFlowMeter_10Circuits | acknowledged | t.tran | 74639
74638 | n.le | t.tran | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_11Circuits.rfa | acknowledged | 434_ME_ManifoldWithFlowMeter_11Circuits | acknowledged | t.tran | 74638
74637 | n.le | t.tran | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_12Circuits.rfa | acknowledged | 434_ME_ManifoldWithFlowMeter_12Circuits | acknowledged | t.tran | 74637
73890 | n.le | t.tran | 2026-06-25 | 434_ME_Manifold_10Circuits.rfa | acknowledged | 434_ME_Manifold_10Circuits | acknowledged | t.tran | 73890
73889 | n.le | t.tran | 2026-06-25 | 434_ME_Manifold_11Circuits.rfa | acknowledged | 434_ME_Manifold_11Circuits | acknowledged | t.tran | 73889
73873 | n.le | hu.dam | 2026-06-25 | 434_ME_PrecisionPressuremaintenance_TransferoTVI2.rfa | closed | 434_ME_PrecisionPressuremaintenance_TransferoTVI2 | closed | hu.dam | 73873
73818 | n.le | hu.dam | 2026-06-25 | 420_PA_ButterflyValve_Flanged_Handle | closed | 420_PA_ButterflyValve_Flanged_Handle | closed | hu.dam | 73818
73546 | n.le | hu.dam | 2026-06-19 | 420_PA_ButterflyValve_Flanged_LeverStandard | closed | 420_PA_ButterflyValve_Flanged_LeverStandard | closed | hu.dam | 73546
73514 | n.le | hu.dam | 2026-06-19 | 420_PA_TemperatureRegulatorValve_SelfOperated | closed | 420_PA_TemperatureRegulatorValve_SelfOperated | closed | hu.dam | 73514
73295 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_uAdaptorUnion_MaleThreadAndMeplaFix | closed | 434_PF_CO_uAdaptorUnion_MaleThreadAndMeplaFix | closed | hu.dam | 73295
73293 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThread_WithNut | closed | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThread_WithNut | closed | hu.dam | 73293
73851 | n.le | qd.nguyen | 2026-06-25 | 434_ME_Pump_Circulator_VeroTwinDPL_DN40.rfa | assigned | 434_ME_Pump_Circulator_VeroTwinDPL_DN40 | assigned | qd.nguyen | 73851
73870 | n.le | qd.nguyen | 2026-06-25 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9.rfa | assigned | 434_ME_PressureMaintenanceMonitoring_PlenoPI9 | assigned | qd.nguyen | 73870
73820 | n.le | qd.nguyen | 2026-06-25 | 420_PA_BallValve_Flanged_WheelStandard | assigned | 420_PA_BallValve_Flanged_WheelStandard | assigned | qd.nguyen | 73820
73821 | n.le | qd.nguyen | 2026-06-25 | 420_PA_BallValve_Flanged_LeverStandard | assigned | 420_PA_BallValve_Flanged_LeverStandard | assigned | qd.nguyen | 73821
73871 | n.le | qd.nguyen | 2026-06-25 | 434_ME_PrecisionPressurisation_CompressoF.rfa | assigned | 434_ME_PrecisionPressurisation_CompressoF | assigned | qd.nguyen | 73871
73872 | n.le | qd.nguyen | 2026-06-25 | 434_ME_PrecisionPressurisation_CompressoC.rfa | assigned | 434_ME_PrecisionPressurisation_CompressoC | assigned | qd.nguyen | 73872
73302 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThread_WithNut | closed | 434_PF_CO_rReducerAdaptor_MapressAndMaleThread_WithNut | closed | hu.dam | 73302
72644 | n.le | dahn.nguyen | 2026-06-01 | 434_ME_Watercooled_Condenserlessliquidchillers_30RW_30RWA_VerticalConnection | assigned | 434_ME_Watercooled_Condenserlessliquidchillers_30RW_30RWA_VerticalConnection | assigned | dahn.nguyen | 72644
73085 | n.le | dahn.nguyen | 2026-06-08 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA8&12A | assigned | 434_ME_VRVOutDoorUnit_HeatPumpRXYA8&12A | assigned | dahn.nguyen | 73085
73092 | n.le | dahn.nguyen | 2026-06-08 | 434_ME_VRVInDoorUnit_WallMounted_FXAA&A | assigned | 434_ME_VRVInDoorUnit_WallMounted_FXAA&A | assigned | dahn.nguyen | 73092
73093 | n.le | dahn.nguyen | 2026-06-08 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXSA | assigned | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXSA | assigned | dahn.nguyen | 73093
73097 | n.le | dahn.nguyen | 2026-06-08 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXUA&A | assigned | 434_ME_VRVInDoorUnit_CeilingSuspended_FXUA&A | assigned | dahn.nguyen | 73097
73101 | n.le | dahn.nguyen | 2026-06-08 | 434_ME_TwoOutletPump_Flanged | assigned | 434_ME_TwoOutletPump_Flanged | assigned | dahn.nguyen | 73101
73102 | n.le | dahn.nguyen | 2026-06-08 | 434_ME_SplitCasePump_Standard | assigned | 434_ME_SplitCasePump_Standard | assigned | dahn.nguyen | 73102
73497 | n.le | dahn.nguyen | 2026-06-19 | 434_ME_Pump_WaterSupplyYonosGIGA&N | assigned | 434_ME_Pump_WaterSupplyYonosGIGA&N | assigned | dahn.nguyen | 73497
73499 | n.le | dahn.nguyen | 2026-06-19 | 434_ME_Pump_WaterSupplyVeroLineIPE | assigned | 434_ME_Pump_WaterSupplyVeroLineIPE | assigned | dahn.nguyen | 73499
74710 | n.le | l.nguyen | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Fineo.rfa | acknowledged | 420_ME_RadiatorBathroom_WallMounted_Fineo | acknowledged | l.nguyen | 74710
74709 | n.le | l.nguyen | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Geneocircle.rfa | acknowledged | 420_ME_RadiatorBathroom_WallMounted_Geneocircle | acknowledged | l.nguyen | 74709
74708 | n.le | l.nguyen | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Geneoquadris.rfa | acknowledged | 420_ME_RadiatorBathroom_WallMounted_Geneoquadris | acknowledged | l.nguyen | 74708
74703 | n.le | l.nguyen | 2026-07-22 | 420_ME_RadiatorBathroom_WallMounted_Pateo.rfa | acknowledged | 420_ME_RadiatorBathroom_WallMounted_Pateo | acknowledged | l.nguyen | 74703
74653 | n.le | l.nguyen | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKHygiene.rfa | acknowledged | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKHygiene | acknowledged | l.nguyen | 74653
74652 | n.le | l.nguyen | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKReplacement.rfa | acknowledged | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKReplacement | acknowledged | l.nguyen | 74652
73831 | n.le | ht.tran | 2026-06-25 | 420_PA_AirReleaseValve_Flanged_Standard.rfa | assigned | 420_PA_AirReleaseValve_Flanged_Standard | assigned | ht.tran | 73831
73830 | n.le | ht.tran | 2026-06-25 | 420_PA_AirReleaseValve_Thread_Standard.rfa | assigned | 420_PA_AirReleaseValve_Thread_Standard | assigned | ht.tran | 73830
72684 | n.le | nd.huynh | 2026-06-01 | 420_PA_RegulatingValve_Flanged | assigned | 420_PA_RegulatingValve_Flanged | assigned | nd.huynh | 72684
72683 | n.le | nd.huynh | 2026-06-01 | 420_PA_RegulatingValve_Flanged_Standard | assigned | 420_PA_RegulatingValve_Flanged_Standard | assigned | nd.huynh | 72683
74625 | n.le | nd.huynh | 2026-07-21 | 434_ME_ManifoldWithPump_4Circuits.rfa | assigned | 434_ME_ManifoldWithPump_4Circuits | assigned | nd.huynh | 74625
74626 | n.le | nd.huynh | 2026-07-21 | 434_ME_ManifoldWithPump_3Circuits.rfa | assigned | 434_ME_ManifoldWithPump_3Circuits | assigned | nd.huynh | 74626
72694 | n.le | ht.pham | 2026-06-01 | 420_PA_PressureSensor_Standard | assigned | 420_PA_PressureSensor_Standard | assigned | ht.pham | 72694
74067 | n.le | n.le | 2026-07-02 | 2026Q3_Annotation Project_TL & TM Time allocation_Nhut Minh Le | acknowledged | 2026Q3_Annotation Project_TL & TM Time allocation_Nhut Minh Le | acknowledged | n.le | 74067
73517 | n.le | qd.nguyen | 2026-06-19 | 420_PA_SixWayMotorisedControlValve_Threaded | assigned | 420_PA_SixWayMotorisedControlValve_Threaded | assigned | qd.nguyen | 73517
74664 | n.le | qd.nguyen | 2026-07-21 | 420_ME_RadiatorBathroom_WallMounted_Pio2layer.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_Pio2layer | assigned | qd.nguyen | 74664
74663 | n.le | qd.nguyen | 2026-07-21 | 420_ME_RadiatorBathroom_WallMounted_PioPlus.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_PioPlus | assigned | qd.nguyen | 74663
74657 | n.le | qd.nguyen | 2026-07-21 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanHorizontal_NoSystem.rfa | assigned | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanHorizontal_NoSystem | assigned | qd.nguyen | 74657
74623 | n.le | qd.nguyen | 2026-07-21 | 434_ME_ManifoldWithPump_6Circuits.rfa | assigned | 434_ME_ManifoldWithPump_6Circuits | assigned | qd.nguyen | 74623
74642 | n.le | ht.nguyen | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlus.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlus | assigned | ht.nguyen | 74642
74644 | n.le | ht.nguyen | 2026-07-21 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileV.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileV | assigned | ht.nguyen | 74644
73516 | n.le | qn.ha | 2026-06-19 | 420_PA_SmartForEnergyManagement_Flanged | assigned | 420_PA_SmartForEnergyManagement_Flanged | assigned | qn.ha | 73516
73515 | n.le | qn.ha | 2026-06-19 | 420_PA_SmartForEnergyManagement_Thread | assigned | 420_PA_SmartForEnergyManagement_Thread | assigned | qn.ha | 73515
73843 | n.le | ht.nguyen | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileK.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileK | assigned | ht.nguyen | 73843
73842 | n.le | ht.nguyen | 2026-06-25 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileV.rfa | assigned | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileV | assigned | ht.nguyen | 73842
74660 | n.le | ht.nguyen | 2026-07-21 | 420_ME_RadiatorBathroom_WallMounted_Tabeo.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_Tabeo | assigned | ht.nguyen | 74660
74659 | n.le | ht.nguyen | 2026-07-21 | 420_ME_RadiatorBathroom_WallMounted_TabeoV.rfa | assigned | 420_ME_RadiatorBathroom_WallMounted_TabeoV | assigned | ht.nguyen | 74659
74624 | n.le | ht.nguyen | 2026-07-21 | 434_ME_ManifoldWithPump_5Circuits.rfa | assigned | 434_ME_ManifoldWithPump_5Circuits | assigned | ht.nguyen | 74624
73123 | n.le | hu.dam | 2026-06-08 | 420_PA_MotorizedGateValve_Thread_Standard | closed | 420_PA_MotorizedGateValve_Thread_Standard | closed | hu.dam | 73123
73122 | n.le | hu.dam | 2026-06-08 | 420_PA_MotorizedGlobeValve_Flanged_Standard | closed | 420_PA_MotorizedGlobeValve_Flanged_Standard | closed | hu.dam | 73122
73548 | n.le | hu.dam | 2026-06-19 | 420_PA_ButterflyValveHandwheel_Flanged | closed | 420_PA_ButterflyValveHandwheel_Flanged | closed | hu.dam | 73548
73547 | n.le | hu.dam | 2026-06-19 | 420_PA_ButterflyValve_Flanged_GearStandard | closed | 420_PA_ButterflyValve_Flanged_GearStandard | closed | hu.dam | 73547
73507 | n.le | hu.dam | 2026-06-19 | 434_ME_Pump_SingleStageGlandedBM | closed | 434_ME_Pump_SingleStageGlandedBM | closed | hu.dam | 73507
73504 | n.le | hu.dam | 2026-06-19 | 434_ME_Pump_WaterSupplyAtmosI | closed | 434_ME_Pump_WaterSupplyAtmosI | closed | hu.dam | 73504
73491 | n.le | hu.dam | 2026-06-19 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC4Pipes | closed | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC4Pipes | closed | hu.dam | 73491
72471 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_uAdaptorUnion_MapressAndThread | closed | 434_PF_CO_uAdaptorUnion_MapressAndThread | closed | hu.dam | 72471
74632 | n.le | tm.doan | 2026-07-21 | 434_ME_ManifoldWithFlowMeter_6Circuits.rfa | new | 434_ME_ManifoldWithFlowMeter_6Circuits | new | tm.doan | 74632
73290 | n.le | tm.doan | 2026-06-12 | 434_PF_CO_uAdaptorUnion_PlainEndAndClampingRing | new | 434_PF_CO_uAdaptorUnion_PlainEndAndClampingRing | new | tm.doan | 73290
73289 | n.le | tm.doan | 2026-06-12 | 434_PF_CO_uAdaptorUnion_PlainEndAndThread | new | 434_PF_CO_uAdaptorUnion_PlainEndAndThread | new | tm.doan | 73289
74700 | n.le | t.tran | 2026-07-22 | 434_ME_HeatExchanger_Brazed&DoublePass&Flanged.rfa | acknowledged | 434_ME_HeatExchanger_Brazed&DoublePass&Flanged | acknowledged | t.tran | 74700
74699 | n.le | t.tran | 2026-07-22 | 434_ME_HeatExchanger_BrazedSinglePass&Thread.rfa | acknowledged | 434_ME_HeatExchanger_BrazedSinglePass&Thread | acknowledged | t.tran | 74699
74698 | n.le | t.tran | 2026-07-22 | 434_ME_HeatExchanger_Brazed_DoublePass.rfa | acknowledged | 434_ME_HeatExchanger_Brazed_DoublePass | acknowledged | t.tran | 74698
74697 | n.le | t.tran | 2026-07-22 | 434_ME_HeatExchanger_Brazed_SinglePass&Flanged.rfa | acknowledged | 434_ME_HeatExchanger_Brazed_SinglePass&Flanged | acknowledged | t.tran | 74697
72568 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Transition_MapressFKMBlue | closed | 434_PF_CO_Transition_MapressFKMBlue | closed | hu.dam | 72568
73485 | n.le | hu.dam | 2026-06-19 | 434_PF_CO_eElbow90Deg_MaleThread_MeplaFixAndPremounted | closed | 434_PF_CO_eElbow90Deg_MaleThread_MeplaFixAndPremounted | closed | hu.dam | 73485
73484 | n.le | hu.dam | 2026-06-19 | 434_PF_CO_eElbowDouble90Deg_MaleThread_MeplaFixAndPremounted | closed | 434_PF_CO_eElbowDouble90Deg_MaleThread_MeplaFixAndPremounted | closed | hu.dam | 73484
73294 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_uAdaptorUnion_MaleThread_MeplaFix | closed | 434_PF_CO_uAdaptorUnion_MaleThread_MeplaFix | closed | hu.dam | 73294
73124 | n.le | hu.dam | 2026-06-08 | 420_PA_MotorizedGateValve_Flanged_Standard | closed | 420_PA_MotorizedGateValve_Flanged_Standard | closed | hu.dam | 73124
72640 | n.le | hu.dam | 2026-06-01 | 434_PA_MultiConnectionPipingKit1_BHFPGas | closed | 434_PA_MultiConnectionPipingKit1_BHFPGas | closed | hu.dam | 72640
72575 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Tee_Mapress&FemaleThread | closed | 434_PF_CO_Tee_Mapress&FemaleThread | closed | hu.dam | 72575
72574 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Tee_Mapress | closed | 434_PF_CO_Tee_Mapress | closed | hu.dam | 72574
72573 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Tee_MapressFKMBlue&FemaleThread | closed | 434_PF_CO_Tee_MapressFKMBlue&FemaleThread | closed | hu.dam | 72573
72570 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Tee_MapressGas | closed | 434_PF_CO_Tee_MapressGas | closed | hu.dam | 72570
72483 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_eAdaptorBend_MapressAndThreadFKMBlue | closed | 434_PF_CO_eAdaptorBend_MapressAndThreadFKMBlue | closed | hu.dam | 72483
73836 | n.le | qd.nguyen | 2026-06-25 | 420_ME_Radiator_WallMounted_Standard.rfa | assigned | 420_ME_Radiator_WallMounted_Standard | assigned | qd.nguyen | 73836
73864 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_CirculatorAtmosGIGA&B.rfa | closed | 434_ME_Pump_CirculatorAtmosGIGA&B | closed | hu.dam | 73864
73863 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_CirculatorStratosGIGA&B.rfa | closed | 434_ME_Pump_CirculatorStratosGIGA&B | closed | hu.dam | 73863
73862 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_CirculatorStratosGIGA.rfa | closed | 434_ME_Pump_CirculatorStratosGIGA | closed | hu.dam | 73862
73861 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_CirculatorStratosGIGA20&D.rfa | closed | 434_ME_Pump_CirculatorStratosGIGA20&D | closed | hu.dam | 73861
73824 | n.le | hu.dam | 2026-06-25 | 420_PA_BallValve3Way_LPort.rfa | closed | 420_PA_BallValve3Way_LPort | closed | hu.dam | 73824
73303 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThreadFKMBlue_WithNut | closed | 434_PF_CO_rReducerAdaptor_MapressAndMaleThreadFKMBlue_WithNut | closed | hu.dam | 73303
73121 | n.le | hu.dam | 2026-06-08 | 420_PA_MotorizedGlobeValve_Thread_Standard | closed | 420_PA_MotorizedGlobeValve_Thread_Standard | closed | hu.dam | 73121
73117 | n.le | hu.dam | 2026-06-08 | 420_PA_PICCV2WayValve_Thread | closed | 420_PA_PICCV2WayValve_Thread | closed | hu.dam | 73117
72662 | n.le | hu.dam | 2026-06-01 | 420_PA_RegulatingValve_Threaded | closed | 420_PA_RegulatingValve_Threaded | closed | hu.dam | 72662
72590 | n.le | hu.dam | 2026-06-01 | 420_PA_YStrainerValve_Flanged_Standard | closed | 420_PA_YStrainerValve_Flanged_Standard | closed | hu.dam | 72590
72565 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Union_MapressFKMBlue | closed | 434_PF_CO_Union_MapressFKMBlue | closed | hu.dam | 72565
72172 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_SocketAdaptor_SlipJoin | closed | 420_PF_MapressCarbonSteel_SocketAdaptor_SlipJoin | closed | hu.dam | 72172
73304 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThread_WithNut | closed | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThread_WithNut | closed | hu.dam | 73304
72589 | n.le | hu.dam | 2026-06-01 | 420_PA_YStrainerValve_Thread_Standard | closed | 420_PA_YStrainerValve_Thread_Standard | closed | hu.dam | 72589
72587 | n.le | hu.dam | 2026-06-01 | 420_PA_YStrainer_Thread | closed | 420_PA_YStrainer_Thread | closed | hu.dam | 72587
73116 | n.le | hu.dam | 2026-06-08 | 420_PA_PICCV3WayValve_Thread | closed | 420_PA_PICCV3WayValve_Thread | closed | hu.dam | 73116
73296 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_PlainEndAndThreadGas | closed | 434_PF_CO_rReducerAdaptor_PlainEndAndThreadGas | closed | hu.dam | 73296
73297 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_PlainEndAndThread | closed | 434_PF_CO_rReducerAdaptor_PlainEndAndThread | closed | hu.dam | 73297
73513 | n.le | hu.dam | 2026-06-19 | 420_PA_ThreeWayMotorisedControlValve_Flanged | closed | 420_PA_ThreeWayMotorisedControlValve_Flanged | closed | hu.dam | 73513
72603 | n.le | hu.dam | 2026-06-01 | 420_PA_TemperatureGauge_Standard | closed | 420_PA_TemperatureGauge_Standard | closed | hu.dam | 72603
73308 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_mTeeInletReturn_Mapress | closed | 434_PF_CO_mTeeInletReturn_Mapress | closed | hu.dam | 73308
72600 | n.le | hu.dam | 2026-06-01 | 420_PA_Thermometer | closed | 420_PA_Thermometer | closed | hu.dam | 72600
73306 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MaleThread_MeplaFix | closed | 434_PF_CO_rReducerAdaptor_MaleThread_MeplaFix | closed | hu.dam | 73306
72598 | n.le | hu.dam | 2026-06-01 | 420_PA_ThreeWayvalve_Flanged_Standard | closed | 420_PA_ThreeWayvalve_Flanged_Standard | closed | hu.dam | 72598
72578 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Cap_MapressFKMBlue | closed | 434_PF_CO_Cap_MapressFKMBlue | closed | hu.dam | 72578
72634 | n.le | kd.doan | 2026-06-01 | 434_PA_RefnetHeader_KHRPGas8Branches | assigned | 434_PA_RefnetHeader_KHRPGas8Branches | assigned | kd.doan | 72634
73310 | n.le | kd.doan | 2026-06-12 | 434_PF_CO_mTeeCrossing_Mapress | assigned | 434_PF_CO_mTeeCrossing_Mapress | assigned | kd.doan | 73310
73309 | n.le | kd.doan | 2026-06-12 | 434_PF_CO_mTeeInletReturnUnion_Mapress | assigned | 434_PF_CO_mTeeInletReturnUnion_Mapress | assigned | kd.doan | 73309
73307 | n.le | kd.doan | 2026-06-12 | 434_PF_CO_mTeeReturn_Mapress | assigned | 434_PF_CO_mTeeReturn_Mapress | assigned | kd.doan | 73307
73314 | n.le | kd.doan | 2026-06-12 | 434_PF_CO_mBridgeBend_Mapress | assigned | 434_PF_CO_mBridgeBend_Mapress | assigned | kd.doan | 73314
73313 | n.le | kd.doan | 2026-06-12 | 434_PF_CO_mDouble90Elbow_Mapress_PreMounted | assigned | 434_PF_CO_mDouble90Elbow_Mapress_PreMounted | assigned | kd.doan | 73313
73311 | n.le | kd.doan | 2026-06-12 | 434_PF_CO_mElbow_MapressAndFemaleThread | assigned | 434_PF_CO_mElbow_MapressAndFemaleThread | assigned | kd.doan | 73311
72624 | n.le | kd.doan | 2026-06-01 | 434_PF_CO_AdaptorUnion_MapressAndFlangeGas | assigned | 434_PF_CO_AdaptorUnion_MapressAndFlangeGas | assigned | kd.doan | 72624
73114 | n.le | kd.doan | 2026-06-08 | 420_PA_PneumaticControlValve_Flanged | assigned | 420_PA_PneumaticControlValve_Flanged | assigned | kd.doan | 73114
73113 | n.le | kd.doan | 2026-06-08 | 420_PA_PneumaticGlobeControlValve_Flanged | assigned | 420_PA_PneumaticGlobeControlValve_Flanged | assigned | kd.doan | 73113
72658 | n.le | kd.doan | 2026-06-01 | 420_PA_SafetyReliefValveStraight_Flanged | assigned | 420_PA_SafetyReliefValveStraight_Flanged | assigned | kd.doan | 72658
73131 | n.le | kd.doan | 2026-06-08 | 420_PA_HeatMeter_Thread_Standard | assigned | 420_PA_HeatMeter_Thread_Standard | assigned | kd.doan | 73131
73120 | n.le | kd.doan | 2026-06-08 | 420_PA_MotorizedThreeWayValve_Flanged_Standard | assigned | 420_PA_MotorizedThreeWayValve_Flanged_Standard | assigned | kd.doan | 73120
73118 | n.le | kd.doan | 2026-06-08 | 420_PA_NonReturnFlap_Flanged | assigned | 420_PA_NonReturnFlap_Flanged | assigned | kd.doan | 73118
73132 | n.le | kd.doan | 2026-06-08 | 420_PA_HeatMeter_Flanged_Standard | assigned | 420_PA_HeatMeter_Flanged_Standard | assigned | kd.doan | 73132
73119 | n.le | kd.doan | 2026-06-08 | 420_PA_MotorizedThreeWayvalve_Thread_Standard | assigned | 420_PA_MotorizedThreeWayvalve_Thread_Standard | assigned | kd.doan | 73119
73142 | n.le | kd.doan | 2026-06-08 | 420_PA_GateValve_Flanged | assigned | 420_PA_GateValve_Flanged | assigned | kd.doan | 73142
73141 | n.le | kd.doan | 2026-06-08 | 420_PA_GateValve_Flanged_Standard | assigned | 420_PA_GateValve_Flanged_Standard | assigned | kd.doan | 73141
73140 | n.le | kd.doan | 2026-06-08 | 420_PA_GateValve_Thread | assigned | 420_PA_GateValve_Thread | assigned | kd.doan | 73140
73133 | n.le | kd.doan | 2026-06-08 | 420_PA_HeatMeter_Flanged | assigned | 420_PA_HeatMeter_Flanged | assigned | kd.doan | 73133
73500 | n.le | ht.nguyen | 2026-06-19 | 434_ME_Pump_WaterSupplySCP | assigned | 434_ME_Pump_WaterSupplySCP | assigned | ht.nguyen | 73500
73498 | n.le | ht.nguyen | 2026-06-19 | 434_ME_Pump_WaterSupplyVeroTwinDPE | assigned | 434_ME_Pump_WaterSupplyVeroTwinDPE | assigned | ht.nguyen | 73498
73839 | n.le | l.nguyen | 2026-06-25 | 420_ME_RadiatorHeatingWall_WallMounted_ValveHorizontal.rfa | closed | 420_ME_RadiatorHeatingWall_WallMounted_ValveHorizontal | closed | l.nguyen | 73839
73525 | n.le | hu.dam | 2026-06-19 | 420_PA_ManifoldConnection_Thread | closed | 420_PA_ManifoldConnection_Thread | closed | hu.dam | 73525
73530 | n.le | b.tran | 2026-06-19 | 420_PA_ExpansionJoint_Weld | closed | 420_PA_ExpansionJoint_Weld | closed | b.tran | 73530
73540 | n.le | l.nguyen | 2026-06-19 | 420_PA_DifferentialPressureControlValve_Thread | closed | 420_PA_DifferentialPressureControlValve_Thread | closed | l.nguyen | 73540
73541 | n.le | hu.dam | 2026-06-19 | 420_PA_CheckValveWithThermometer_Thread | closed | 420_PA_CheckValveWithThermometer_Thread | closed | hu.dam | 73541
73520 | n.le | d.phan | 2026-06-19 | 420_PA_ShutoffValve_Motorized | closed | 420_PA_ShutoffValve_Motorized | closed | d.phan | 73520
72168 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_Union_SlipJoin | closed | 420_PF_MapressCarbonSteel_Union_SlipJoin | closed | hu.dam | 72168
73312 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_mElbowOffset_MapressAndFemaleThread | closed | 434_PF_CO_mElbowOffset_MapressAndFemaleThread | closed | hu.dam | 73312
73486 | n.le | hu.dam | 2026-06-19 | 434_PF_CO_eDouble90ElbowMultiPort_Mapress | closed | 434_PF_CO_eDouble90ElbowMultiPort_Mapress | closed | hu.dam | 73486
72622 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Bend_Mapress | closed | 434_PF_CO_Bend_Mapress | closed | hu.dam | 72622
72655 | n.le | hu.dam | 2026-06-01 | 420_PA_SafetyValveCorner_Thread_Standard | closed | 420_PA_SafetyValveCorner_Thread_Standard | closed | hu.dam | 72655
72626 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_AdaptorMultiPort_MapressAndNut | closed | 434_PF_CO_AdaptorMultiPort_MapressAndNut | closed | hu.dam | 72626
72657 | n.le | hu.dam | 2026-06-01 | 420_PA_SafetyValveCorner_Flanged_Standard | closed | 420_PA_SafetyValveCorner_Flanged_Standard | closed | hu.dam | 72657
73138 | n.le | hu.dam | 2026-06-08 | 420_PA_GlobeValve_Flanged | closed | 420_PA_GlobeValve_Flanged | closed | hu.dam | 73138
73125 | n.le | hu.dam | 2026-06-08 | 420_PA_MotorizedButterflyValve_Flanged_Standard | closed | 420_PA_MotorizedButterflyValve_Flanged_Standard | closed | hu.dam | 73125
73299 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MapressAndThreadGas | closed | 434_PF_CO_rReducerAdaptor_MapressAndThreadGas | closed | hu.dam | 73299
73298 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFix | closed | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFix | closed | hu.dam | 73298
72173 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_FlangeAdaptor_SlipJoin | closed | 420_PF_MapressCarbonSteel_FlangeAdaptor_SlipJoin | closed | hu.dam | 72173
72169 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_Transition_SlipJoin | closed | 420_PF_MapressCarbonSteel_Transition_SlipJoin | closed | hu.dam | 72169
73508 | n.le | hu.dam | 2026-06-19 | 434_ME_Pump_Circulator_YonosGIGA20D | closed | 434_ME_Pump_Circulator_YonosGIGA20D | closed | hu.dam | 73508
73305 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThreadFKMBlue_WithNut | closed | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThreadFKMBlue_WithNut | closed | hu.dam | 73305
73526 | n.le | hu.dam | 2026-06-19 | 420_PA_FlexibleConnection_Flanged_Standard | closed | 420_PA_FlexibleConnection_Flanged_Standard | closed | hu.dam | 73526
73505 | n.le | hu.dam | 2026-06-19 | 434_ME_Pump_WaterSupplyAtmosGIGA&N | closed | 434_ME_Pump_WaterSupplyAtmosGIGA&N | closed | hu.dam | 73505
73483 | n.le | hu.dam | 2026-06-19 | 434_PF_CO_fFlange_Mapress | closed | 434_PF_CO_fFlange_Mapress | closed | hu.dam | 73483
73146 | n.le | hu.dam | 2026-06-08 | 420_PA_FlexibleConnection_Thread_Standard | closed | 420_PA_FlexibleConnection_Thread_Standard | closed | hu.dam | 73146
73521 | n.le | hu.dam | 2026-06-19 | 420_PA_ShutOffValveWithSafetyFunction_Flanged | closed | 420_PA_ShutOffValveWithSafetyFunction_Flanged | closed | hu.dam | 73521
72586 | n.le | hu.dam | 2026-06-01 | 420_PF_CO_tTee_Soldered | closed | 420_PF_CO_tTee_Soldered | closed | hu.dam | 72586
73527 | n.le | hu.dam | 2026-06-19 | 420_PA_FilterValve_Thread | closed | 420_PA_FilterValve_Thread | closed | hu.dam | 73527
73506 | n.le | hu.dam | 2026-06-19 | 434_ME_Pump_SingleStageLowPressureBAC | closed | 434_ME_Pump_SingleStageLowPressureBAC | closed | hu.dam | 73506
73542 | n.le | hu.dam | 2026-06-19 | 420_PA_CapValve_Thread | closed | 420_PA_CapValve_Thread | closed | hu.dam | 73542
73550 | n.le | hu.dam | 2026-06-19 | 420_PA_BasketStrainerValve_Flanged_Standard | closed | 420_PA_BasketStrainerValve_Flanged_Standard | closed | hu.dam | 73550
73489 | n.le | hu.dam | 2026-06-19 | 434_PF_CO_e90Elbow_ThreadAndMeplaFix | closed | 434_PF_CO_e90Elbow_ThreadAndMeplaFix | closed | hu.dam | 73489
73529 | n.le | hu.dam | 2026-06-19 | 420_PA_FillAndDrainBallValve_Threaded | closed | 420_PA_FillAndDrainBallValve_Threaded | closed | hu.dam | 73529
73503 | n.le | hu.dam | 2026-06-19 | 434_ME_Pump_WaterSupplyAtmosTERA&SCH | closed | 434_ME_Pump_WaterSupplyAtmosTERA&SCH | closed | hu.dam | 73503
73487 | n.le | hu.dam | 2026-06-19 | 434_PF_CO_eAdaptorBend_MapressAndMeplaFix | closed | 434_PF_CO_eAdaptorBend_MapressAndMeplaFix | closed | hu.dam | 73487
72654 | n.le | hu.dam | 2026-06-01 | 420_PA_SpringCheckValve_Flanged_Standard | closed | 420_PA_SpringCheckValve_Flanged_Standard | closed | hu.dam | 72654
73301 | n.le | hu.dam | 2026-06-12 | 434_PF_CO_rReducerAdaptor_MapressAndThread | closed | 434_PF_CO_rReducerAdaptor_MapressAndThread | closed | hu.dam | 73301
73080 | n.le | hu.dam | 2026-06-08 | 434_ME_VRVShutOffValveBox_SV8A14AJV1B | closed | 434_ME_VRVShutOffValveBox_SV8A14AJV1B | closed | hu.dam | 73080
73531 | n.le | hu.dam | 2026-06-19 | 420_PA_ExpansionJoint_Threaded | closed | 420_PA_ExpansionJoint_Threaded | closed | hu.dam | 73531
73502 | n.le | hu.dam | 2026-06-19 | 434_ME_Pump_WaterSupplyCronoBlocBLE | closed | 434_ME_Pump_WaterSupplyCronoBlocBLE | closed | hu.dam | 73502
72584 | n.le | hu.dam | 2026-06-01 | 420_PF_CO_xCross_Soldered | closed | 420_PF_CO_xCross_Soldered | closed | hu.dam | 72584
73840 | n.le | hu.dam | 2026-06-25 | 420_ME_RadiatorHeatingWall_WallMounted_Horizontal.rfa | closed | 420_ME_RadiatorHeatingWall_WallMounted_Horizontal | closed | hu.dam | 73840
73856 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_CirculatorYonosMAXO.rfa | closed | 434_ME_Pump_CirculatorYonosMAXO | closed | hu.dam | 73856
73857 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_CirculatorVeroLineIPL.rfa | closed | 434_ME_Pump_CirculatorVeroLineIPL | closed | hu.dam | 73857
73858 | n.le | hu.dam | 2026-06-25 | 434_ME_Pump_CirculatorStratosPICO.rfa | closed | 434_ME_Pump_CirculatorStratosPICO | closed | hu.dam | 73858
73869 | n.le | tm.doan | 2026-06-25 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9.rfa | closed | 434_ME_PressureMaintenanceMonitoring_PlenoPI9 | closed | tm.doan | 73869
72627 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_30Cross_Mapress | closed | 434_PF_CO_30Cross_Mapress | closed | hu.dam | 72627
72602 | n.le | hu.dam | 2026-06-01 | 420_PA_TemperatureSensor | closed | 420_PA_TemperatureSensor | closed | hu.dam | 72602
73081 | n.le | hu.dam | 2026-06-08 | 434_ME_VRVShutOffValveBox_SV6A14AJV1B | closed | 434_ME_VRVShutOffValveBox_SV6A14AJV1B | closed | hu.dam | 73081
72632 | n.le | hu.dam | 2026-06-01 | 434_PA_RefnetHeader_KHRPLiquid4Branches | closed | 434_PA_RefnetHeader_KHRPLiquid4Branches | closed | hu.dam | 72632
72639 | n.le | hu.dam | 2026-06-01 | 434_PA_MultiConnectionPipingKit1_BHFPLiquid | closed | 434_PA_MultiConnectionPipingKit1_BHFPLiquid | closed | hu.dam | 72639
72625 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_AdaptorUnion_FemaleThreadAndMeplaFix | closed | 434_PF_CO_AdaptorUnion_FemaleThreadAndMeplaFix | closed | hu.dam | 72625
72643 | n.le | hu.dam | 2026-06-01 | 434_PA_BranchProviderBox_BPMKS2Port | closed | 434_PA_BranchProviderBox_BPMKS2Port | closed | hu.dam | 72643
72642 | n.le | hu.dam | 2026-06-01 | 434_PA_BranchProviderBox_BPMKS3Port | closed | 434_PA_BranchProviderBox_BPMKS3Port | closed | hu.dam | 72642
73538 | n.le | n.le | 2026-06-19 | 420_PA_DifferentialPressureSensor | closed | 420_PA_DifferentialPressureSensor | closed | n.le | 73538
72482 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_eAdaptorBend_MapressAndThreadGas | closed | 434_PF_CO_eAdaptorBend_MapressAndThreadGas | closed | hu.dam | 72482
72636 | n.le | hu.dam | 2026-06-01 | 434_PA_MultiConnectionPipingKit2_BHFPLiquid | closed | 434_PA_MultiConnectionPipingKit2_BHFPLiquid | closed | hu.dam | 72636
72567 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Transition_MapressGas | closed | 434_PF_CO_Transition_MapressGas | closed | hu.dam | 72567
72635 | n.le | hu.dam | 2026-06-01 | 434_PA_RefnetHeader_KHRPGas4Branches | closed | 434_PA_RefnetHeader_KHRPGas4Branches | closed | hu.dam | 72635
72170 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_Tee_SlipJoin | closed | 420_PF_MapressCarbonSteel_Tee_SlipJoin | closed | hu.dam | 72170
72171 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_SocketFlangeAdaptor_SlipJoin | closed | 420_PF_MapressCarbonSteel_SocketFlangeAdaptor_SlipJoin | closed | hu.dam | 72171
72196 | n.le | hu.dam | 2026-05-27 | 420_PF_CO_cCap_Soldered | closed | 420_PF_CO_cCap_Soldered | closed | hu.dam | 72196
72177 | n.le | hu.dam | 2026-05-27 | 420_PF_Copper_Elbow.rfa | closed | 420_PF_Copper_Elbow | closed | hu.dam | 72177
72621 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Bend_MapressFKMBlue | closed | 434_PF_CO_Bend_MapressFKMBlue | closed | hu.dam | 72621
72637 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_eBend_MapressFKMBlue.rfa | closed | 434_PF_CO_eBend_MapressFKMBlue | closed | hu.dam | 72637
72566 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Union_Mapress | closed | 434_PF_CO_Union_Mapress | closed | hu.dam | 72566
72591 | n.le | hu.dam | 2026-06-01 | 420_PA_WaterMeter_Threaded | closed | 420_PA_WaterMeter_Threaded | closed | hu.dam | 72591
72195 | n.le | hu.dam | 2026-05-27 | 420_PF_Brass_ThreeWayEqualTee_Compression | closed | 420_PF_Brass_ThreeWayEqualTee_Compression | closed | hu.dam | 72195
72623 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_AdaptorUnion_PlainEndAndFlange | closed | 434_PF_CO_AdaptorUnion_PlainEndAndFlange | closed | hu.dam | 72623
72652 | n.le | hu.dam | 2026-06-01 | 420_PA_SwingCheckValve_Thread_Standard | closed | 420_PA_SwingCheckValve_Thread_Standard | closed | hu.dam | 72652
72176 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_Cap_SlipJoin | closed | 420_PF_MapressCarbonSteel_Cap_SlipJoin | closed | hu.dam | 72176
72175 | n.le | hu.dam | 2026-05-27 | 420_PF_MapressCarbonSteel_Cross_SlipJoin | closed | 420_PF_MapressCarbonSteel_Cross_SlipJoin | closed | hu.dam | 72175
72167 | n.le | hu.dam | 2026-05-27 | 420_PF_PE_eElbow.rfa | closed | 420_PF_PE_eElbow | closed | hu.dam | 72167
72572 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Tee_MapressFKMBlue | closed | 434_PF_CO_Tee_MapressFKMBlue | closed | hu.dam | 72572
73137 | n.le | n.le | 2026-06-08 | 420_PA_GlobeValve_Flanged | closed | 420_PA_GlobeValve_Flanged | closed | n.le | 73137
72581 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Bend_MapressGas | closed | 434_PF_CO_Bend_MapressGas | closed | hu.dam | 72581
72579 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Cap_Mapress | closed | 434_PF_CO_Cap_Mapress | closed | hu.dam | 72579
72571 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Tee_MapressGas&FemaleThread | closed | 434_PF_CO_Tee_MapressGas&FemaleThread | closed | hu.dam | 72571
72569 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Transition_Mapress | closed | 434_PF_CO_Transition_Mapress | closed | hu.dam | 72569
72485 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_Union_MapressGas | closed | 434_PF_CO_Union_MapressGas | closed | hu.dam | 72485
72478 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThreadFKMBlue_WithNut | closed | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThreadFKMBlue_WithNut | closed | hu.dam | 72478
72199 | n.le | hu.dam | 2026-05-27 | 420_PF_CS_xCross_Welded | closed | 420_PF_CS_xCross_Welded | closed | hu.dam | 72199
72480 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_rReducerAdaptor_PlainEnd_WithMeplaFixAdaptor | closed | 434_PF_CO_rReducerAdaptor_PlainEnd_WithMeplaFixAdaptor | closed | hu.dam | 72480
72484 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_eAdaptorBend_MapressAndThread | closed | 434_PF_CO_eAdaptorBend_MapressAndThread | closed | hu.dam | 72484
72577 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_Cap_MapressGas | closed | 434_PF_CO_Cap_MapressGas | closed | hu.dam | 72577
72576 | n.le | hu.dam | 2026-06-01 | 434_PF_CO_ReducerAdaptor_PlainEndAndClampingRing | closed | 434_PF_CO_ReducerAdaptor_PlainEndAndClampingRing | closed | hu.dam | 72576
72202 | n.le | hu.dam | 2026-05-27 | 420_PF_CS_sTap_Welded | closed | 420_PF_CS_sTap_Welded | closed | hu.dam | 72202
72465 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_uAdaptorUnion_PlainEnd_WithMeplaFix | closed | 434_PF_CO_uAdaptorUnion_PlainEnd_WithMeplaFix | closed | hu.dam | 72465
72201 | n.le | hu.dam | 2026-05-27 | 420_PF_CS_tTee_Welded | closed | 420_PF_CS_tTee_Welded | closed | hu.dam | 72201
72468 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_uAdaptorUnion_MapressAndThreadFKMBlue | closed | 434_PF_CO_uAdaptorUnion_MapressAndThreadFKMBlue | closed | hu.dam | 72468
72198 | n.le | hu.dam | 2026-05-27 | 420_PF_CO_eElbow_Soldered | closed | 420_PF_CO_eElbow_Soldered | closed | hu.dam | 72198
72481 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFixAdaptor | closed | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFixAdaptor | closed | hu.dam | 72481
72204 | n.le | hu.dam | 2026-05-27 | 420_PF_CS_fConnectionFlanged_Welded | closed | 420_PF_CS_fConnectionFlanged_Welded | closed | hu.dam | 72204
72203 | n.le | hu.dam | 2026-05-27 | 420_PF_CS_rReducer_Welded | closed | 420_PF_CS_rReducer_Welded | closed | hu.dam | 72203
72467 | n.le | hu.dam | 2026-05-28 | 434_PF_CO_uAdaptorUnion_MapressAndThreadGas | closed | 434_PF_CO_uAdaptorUnion_MapressAndThreadGas | closed | hu.dam | 72467
72200 | n.le | hu.dam | 2026-05-27 | 420_PF_CS_uUnion_Welded | closed | 420_PF_CS_uUnion_Welded | closed | hu.dam | 72200
72466 | n.le | dx.quach | 2026-05-28 | 434_PF_CO_uAdaptorUnion_PlainEndAndThreadGas | closed | 434_PF_CO_uAdaptorUnion_PlainEndAndThreadGas | closed | dx.quach | 72466
72116 | n.le | t.tran | 2026-05-25 | KLT_LPH8_Sample Layout_Multiple Scales | closed | KLT_LPH8_Sample Layout_Multiple Scales | closed | t.tran | 72116
72114 | n.le | ht.pham | 2026-05-25 | KLT_LPH3_Sample Layout_Multiple Scales | closed | KLT_LPH3_Sample Layout_Multiple Scales | closed | ht.pham | 72114
72115 | n.le | ht.pham | 2026-05-25 | KLT_LPH5_Sample Layout_Multiple Scales | closed | KLT_LPH5_Sample Layout_Multiple Scales | closed | ht.pham | 72115
72112 | n.le | th.nguyen | 2026-05-25 | HZG_LPH5_Sample Layout_Multiple Scales | closed | HZG_LPH5_Sample Layout_Multiple Scales | closed | th.nguyen | 72112
72113 | n.le | th.nguyen | 2026-05-25 | HZG_LPH3_Sample Layout_Multiple Scales | closed | HZG_LPH3_Sample Layout_Multiple Scales | closed | th.nguyen | 72113
72111 | n.le | ht.tran | 2026-05-25 | HZG_LPH8_Sample Layout_Multiple Scales | closed | HZG_LPH8_Sample Layout_Multiple Scales | closed | ht.tran | 72111

## Ref
No | Name | Name | User | Email | Trade | Position | Note
1 | Mr. Nhut Minh Le | Nhut Le | n.le | nl@dcmvn.com | HVAC | 039 | Nhut Team
2 | Ms. Tham Thi Nguyen | Tham Nguyen | th.nguyen | thn@dcmvn.com | SAN | 013 | Nhut Team
3 | Mr. Luc Van Nguyen | Luc Nguyen | l.nguyen | ln@dcmvn.com | HVAC | 006 | Nhut Team
4 | Mr. Truong Van Tran | Truong Tran | t.tran | tt@dcmvn.com | HVAC | 049 | Nhut Team
5 | Ms. Ha Thi Cam Pham | Ha Pham | ht.pham | htp@dcmvn.com | HVAC | 054 | Nhut Team
6 | Mr. Huy Thanh Dinh Tran | Huy Tran | ht.tran | htt@dcmvn.com | HVAC | 053 | Nhut Team
7 | Tan Minh Doan | Tan Doan | tm.doan | tm.doan@dcmvn.com | ELT | 009 | Nhut Team
8 | Mr. Binh Thanh Tran | Binh Tran | b.tran | bt@dcmvn.com | ELT | 031 | Nhut Team
9 | Ms. Huong Huynh | Huong Huynh | h.huynh | huh@dcmvn.com | SAN | 014 | Nhut Team
10 | Mr. Danh Huu Phan | Danh Phan | d.phan | dp@dcmvn.com | HVAC | 004 | Nhut Team
11 | Mr. Duong Xuan Quach | Duong Quach | dx.quach | dxq@dcmvn.com | ELT | 044 | Nhut Team

## TIDP Detail (hidden)
PROJECT: DCMvn Annotation
DOCUMENT: DCMvn_SAN_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP) | [7 empty] | Milestone
NO: | NAME | Category | DESCRIPTION | FILE TYPE | CREATED BY | AUTHORISED BY | Batch | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-08 | 2026-09-15 | 2026-09-10 | 2026-09-22 | 2026-09-29 | 2026-09-30 | 2026-10-02 | 2026-10-09
| Revise the RFA library SAN | [6 empty] | MEP | DIG | MEP
1 | 410_PF_CastIron_Branch68Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
2 | 410_PF_CastIron_CleaningPipeWithRectangularCover_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
3 | 410_PF_CastIron_CleaningPipeWithRoundCover_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
4 | 410_PF_CastIron_CombinationBranch_88Degree_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
5 | 410_PF_CastIron_DownPipeBracket_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
6 | 410_PF_CastIron_EccentricReducer_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
7 | 410_PF_CastIron_Plug_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
8 | 410_PF_CastIron_RainwaterSiphon_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
9 | 410_PF_CastIron_SMLRainwaterSiphonVertical_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
10 | 410_PF_cHDPE_BlindFlange_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
11 | 410_PF_CI_AngleDoubleBranch88Degree_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
12 | 410_PF_CI_Bearing.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
13 | 410_PF_CI_Branch45Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
14 | 410_PF_CI_Branch45Deg_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
15 | 410_PF_CI_cPushinPlug_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
16 | 410_PF_CI_DoubleBranch_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
17 | 410_PF_CI_eAccessBendLong_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
18 | 410_PF_CI_eAccessBendShort_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
19 | 410_PF_CI_eBend15Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
20 | 410_PF_CI_eBend30Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
21 | 410_PF_CI_eBend68Degree_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
22 | 410_PF_CI_eBend88Degree_SpigotAndClamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
23 | 410_PF_CI_eBend88Deg_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
24 | 410_PF_CI_eBendWC_Clamp_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
25 | 410_PF_CI_eBend_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
26 | 410_PF_CI_eBend_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
27 | 410_PF_CI_eBend_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
28 | 410_PF_CI_eConectionBend_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
29 | 410_PF_CI_eDoubleBend45Deg_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
30 | 410_PF_CI_eDoubleBend88Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
31 | 410_PF_CI_eDoubleBend88Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
32 | 410_PF_CI_eOffsetBend130_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | SUB | REV | FIN
33 | 410_PF_CI_eOffsetBend200_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
34 | 410_PF_CI_eOffsetBend65_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
35 | 410_PF_CI_ePlainTrap_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
36 | 410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
37 | 410_PF_CI_eRestBend88_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
38 | 410_PF_CI_eVentilationBend88Axial_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
39 | 410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
40 | 410_PF_CI_GutterAngleUniversal.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
41 | 410_PF_CI_GutterCap_ExternalStopEnd.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
42 | 410_PF_CI_GutterCap_InternalStopEnd.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
43 | 410_PF_CI_GutterElbow_ExternalDropEndOutlet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
44 | 410_PF_CI_GutterElbow_InternalDropEndOutlet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
45 | 410_PF_CI_GutterHalfRound.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
46 | 410_PF_CI_GutterTee_RunningOutlet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
47 | 410_PF_CI_GutterUnionConnector.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
48 | 410_PF_CI_mShortPipeRectangularAccessDoor_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
49 | 410_PF_CI_mVerticalTrap_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
50 | 410_PF_CI_rEccentricReducer_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
51 | 410_PF_CI_rEccentricReducer_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
52 | 410_PF_CI_rReducingEccentric_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
53 | 410_PF_CI_tBranch45_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
54 | 410_PF_CI_tBranch70_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
55 | 410_PF_CI_tBranch88Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
56 | 410_PF_CI_tBranch88Deg_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
57 | 410_PF_CI_tBranch88Long_Spigot_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
58 | 410_PF_CI_tBranch88_Spigot_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
59 | 410_PF_CI_tCombinationBranch90_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
60 | 410_PF_CI_tCornerBranch88_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
61 | 410_PF_CI_tSweptEntryBranch88_Spigot_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
62 | 410_PF_CI_uShortPipeRoundAccessDoor_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
63 | 410_PF_CI_uTrapHorizontal_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
64 | 410_PF_CI_xDoubleBranch45_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 |  | SUB | REV | FIN
65 | 410_PF_CI_xDoubleBranch70Deg_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
66 | 410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
67 | 410_PF_CS_cEndCaps_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
68 | 410_PF_CS_eLongRadiusElbows_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
69 | 410_PF_CS_eLongRadiusReturnBends_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
70 | 410_PF_CS_eRadiusElbows_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
71 | 410_PF_CS_fPlaneFlange_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
72 | 410_PF_CS_rConcentricReducers_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
73 | 410_PF_CS_rConnector_MapressAndFemaleThread.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
74 | 410_PF_CS_uConnector_MapressAndFemaleThread.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
75 | 410_PF_DI_cBellmouth_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
76 | 410_PF_DI_cBlind_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
77 | 410_PF_DI_cCap_KType.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
78 | 410_PF_DI_cPlug_TType.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
79 | 410_PF_DI_eBend_Flange.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
80 | 410_PF_DI_eBend_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
81 | 410_PF_DI_eDuckfoodBend90Deg_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
82 | 410_PF_DI_fFlange_RFType.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
83 | 410_PF_DI_rFlangedCover.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
84 | 410_PF_DI_rFlangeSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
85 | 410_PF_DI_rFlangeSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
86 | 410_PF_DI_rTapper_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
87 | 410_PF_DI_rTapper_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
88 | 410_PF_DI_tLevelInvertTee_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
89 | 410_PF_DI_tTeeSocketWithFlangedBranch.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
90 | 410_PF_DI_tTeeSocketWithLevelInvertFlangedBranch.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
91 | 410_PF_DI_tTee_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
92 | 410_PF_DI_tTee_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
93 | 410_PF_DI_uAdaptorRestrained_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
94 | 410_PF_DI_uFlangeAdaptor.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
95 | 410_PF_DI_uUnionFlange_RFType.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
96 | 410_PF_DI_uUnionSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 |  |  | SUB | REV | FIN
97 | 410_PF_DuctileIron_DoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
98 | 410_PF_EPDM_mKonfixConnector_PushOnJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
99 | 410_PF_eSweptBendLong_Medium_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
100 | 410_PF_fHDPE_LooseFlange.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
101 | 410_PF_FireCollar_FloorMounted.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
102 | 410_PF_FireCollar_WallMounted.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
103 | 410_PF_GS_cFrogFlap_Socket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
104 | 410_PF_GS_cSealingPlugsWithVentilationSlots.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
105 | 410_PF_GS_eAngleBend_1PushShortSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
106 | 410_PF_GS_eAngleBend_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
107 | 410_PF_GS_eBasinConnector_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
108 | 410_PF_GS_eBendWithCalm_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
109 | 410_PF_GS_eBend_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
110 | 410_PF_GS_eBend_NoSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
111 | 410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
112 | 410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
113 | 410_PF_GS_eReductionAngleBend_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
114 | 410_PF_GS_GutterRound_SocketAndStandard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
115 | 410_PF_GS_mOptimisationPart_1PushSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
116 | 410_PF_GS_mSBendTrap_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
117 | 410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
118 | 410_PF_GS_rAdapterConcentric_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
119 | 410_PF_GS_rAdapterEccentric_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
120 | 410_PF_GS_rConcentricOptimiser_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
121 | 410_PF_GS_rTransitiontoCastIron_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
122 | 410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
123 | 410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
124 | 410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
125 | 410_PF_GS_tTeeBranches_2PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
126 | 410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
127 | 410_PF_GS_uBends_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
128 | 410_PF_GS_uGutterPipes_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 |  |  |  | SUB | REV | FIN
129 | 410_PF_GS_uLongCleaningOpening_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
130 | 410_PF_GS_uLongCleaningOpening_NoSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
131 | 410_PF_GS_uLongUnion_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
132 | 410_PF_GS_uSpigottoPlastic_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
133 | 410_PF_GS_uTransitionSMLtoGMX_1PushSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
134 | 410_PF_GS_uTranstiontoCastIron_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
135 | 410_PF_GS_uUnion_2PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
136 | 410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
137 | 410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
138 | 410_PF_HDPE_cProtectionCap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
139 | 410_PF_HDPE_cProtectionCapForPipeEnd.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
140 | 410_PF_HDPE_cThreadedConnectorWithScrewCap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
141 | 410_PF_HDPE_eBend90Deg_Reducer_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
142 | 410_PF_HDPE_eBend_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
143 | 410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
144 | 410_PF_HDPE_eConnectionBend88Deg_WithLateralSupplementary_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
145 | 410_PF_HDPE_eConnectionBend90DegForSleeve.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
146 | 410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
147 | 410_PF_HDPE_eConnectionBend90Deg_RightOffset_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
148 | 410_PF_HDPE_eScrewCap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
149 | 410_PF_HDPE_eSegmentBend_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
150 | 410_PF_HDPE_mDoubleConnectionBend90Deg_ForSleeve.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
151 | 410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
152 | 410_PF_HDPE_mDoubleConnectionBend90Deg_VerticalForWallHungWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
153 | 410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
154 | 410_PF_HDPE_mRunningTrap_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
155 | 410_PF_HDPE_mSoventFitting_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
156 | 410_PF_HDPE_mSTrap_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
157 | 410_PF_HDPE_mUniversalTrap_WithFlangeBushing.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
158 | 410_PF_HDPE_mWasteManifold.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
159 | 410_PF_HDPE_rAdaptorSocket_DN90xDN100.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
160 | 410_PF_HDPE_rCompressionJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 |  |  |  |  | SUB | REV | FIN
161 | 410_PF_HDPE_rReducer_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
162 | 410_PF_HDPE_rRingSealSocket_ReducedWithLipSeal.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
163 | 410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
164 | 410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
165 | 410_PF_HDPE_tLateralTee_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
166 | 410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
167 | 410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
168 | 410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
169 | 410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
170 | 410_PF_HDPE_uAdapterUnion_FemaleThread.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
171 | 410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
172 | 410_PF_HDPE_uAdapterUnion_MaleThread.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
173 | 410_PF_HDPE_uClampingConnector.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
174 | 410_PF_HDPE_uExpansionSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
175 | 410_PF_HDPE_uFlangeAdapter.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
176 | 410_PF_HDPE_uFlangeBushing.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
177 | 410_PF_HDPE_uFlangeSet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
178 | 410_PF_HDPE_uStraightAdapterToCastIronPipe.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
179 | 410_PF_HDPE_uStraightAdapterToPVCPipe.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
180 | 410_PF_HDPE_uStraightAdapterWithCompressionJoint_Glueing.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
181 | 410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
182 | 410_PF_HDPE_uStraightConnectorWithRingSealSocket_WC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
183 | 410_PF_HDPE_uStraightConnector_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
184 | 410_PF_HDPE_uThreadedConnectorWithCompressionJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
185 | 410_PF_HDPE_uUnionConnection_WeldingJoints.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
186 | 410_PF_HDPE_xDoubleBrandFitting45Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
187 | 410_PF_mGalvanized_PTrap_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
188 | 410_PF_mHDPE_PTrap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
189 | 410_PF_PE_eBendForWandWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
190 | 410_PF_PPR_cEndCap_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
191 | 410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
192 | 410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | [5 empty] | SUB | REV | FIN
193 | 410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
194 | 410_PF_PPR_eElbow_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
195 | 410_PF_PPR_rCoupling_FemaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
196 | 410_PF_PPR_rCoupling_MaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
197 | 410_PF_PPR_rElbow90DegMaleThread_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
198 | 410_PF_PPR_rReducing_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
199 | 410_PF_PPR_tTee_FemaleThreadedAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
200 | 410_PF_PPR_tTee_MaleThreadedAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
201 | 410_PF_PPR_tTee_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
202 | 410_PF_PPR_uCoupling_FemaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
203 | 410_PF_PPR_uCoupling_MaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
204 | 410_PF_PPR_uUnion_BushSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
205 | 410_PF_PPR_uUnion_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
206 | 410_PF_PPSilent_DuctBranch_SocketAndSpigot_SweptEntry88DegLeft.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
207 | 410_PF_PPSilent_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
208 | 410_PF_PPSilent_tDoubleConnectionBend90Deg_Extended.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
209 | 410_PF_PP_AccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
210 | 410_PF_PP_Adaptor_SleeveToCastIronAndSilent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
211 | 410_PF_PP_Bend_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
212 | 410_PF_PP_Branch_SocketSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
213 | 410_PF_PP_CapEnd_Socket_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
214 | 410_PF_PP_CombinedCornerBranch_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
215 | 410_PF_PP_DoubleBranchFitting88Deg_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
216 | 410_PF_PP_DoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
217 | 410_PF_PP_mOdorTrapForSinkHorizontal_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
218 | 410_PF_PP_mOdorTrapForSinkVertical_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
219 | 410_PF_PP_mOdorTrapForSink_VerticalandHorizontal_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
220 | 410_PF_PP_ParallelBrand45Deg_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
221 | 410_PF_PP_ReducerEccentric_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
222 | 410_PF_PP_SlipCoupling_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
223 | 410_PF_SilentPro_cCapEnd_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
224 | 410_PF_SilentPro_eElbow_SocketAndSpigot.rfa.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | [6 empty] | SUB | REV | FIN
225 | 410_PF_SilentPro_mCombinedCornerBranch_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
226 | 410_PF_SilentPro_mCornerBranch88Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
227 | 410_PF_SilentPro_rReducerEccentric_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
228 | 410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
229 | 410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
230 | 410_PF_SilentPro_tTeeBranch_SocketSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
231 | 410_PF_SilentPro_uAccessPipe90Deg_WithRoundServiceOpening&Silent_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
232 | 410_PF_SilentPro_uSlipCoupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
233 | 410_PF_SilentPro_wParallelBrand45Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
234 | 410_PF_SilentPro_xCrossDoubleBranchFitting88Deg_SweptEntry_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
235 | 410_PF_SS _Union_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
236 | 410_PF_SS_cCap_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
237 | 410_PF_SS_cDrainplugWithScrewedPlug.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
238 | 410_PF_SS_cSocketPlug.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
239 | 410_PF_SS_cSocketPlugWithClamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
240 | 410_PF_SS_cVentCowl_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
241 | 410_PF_SS_eBend45Degrees_SocketAndStandard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
242 | 410_PF_SS_eBend87_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
243 | 410_PF_SS_eBendWith250mmOblong_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
244 | 410_PF_SS_eBend_15_1Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
245 | 410_PF_SS_eBend_30_1Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
246 | 410_PF_SS_eElbow90DegAdaptor_FemaleThreadAndPlainEnd_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
247 | 410_PF_SS_eElbow90DegAdaptor_WithMaleThread_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
248 | 410_PF_SS_eElbow90DegTapConnector_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
249 | 410_PF_SS_eElbow90Deg_FemaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
250 | 410_PF_SS_eElbowTapConector90Degree_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
251 | 410_PF_SS_eElbow_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
252 | 410_PF_SS_eLongBend_1Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
253 | 410_PF_SS_ePTrap_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
254 | 410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
255 | 410_PF_SS_mCornerElbow90Deg_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
256 | 410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | [7 empty] | SUB | REV | FIN
257 | 410_PF_SS_Rapid_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
258 | 410_PF_SS_rConcentricIncreaserCoupling_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
259 | 410_PF_SS_rConnectorExternalThreadSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
260 | 410_PF_SS_rConnectorInternal_ThreadSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
261 | 410_PF_SS_rConnectorWithSocketAndFlange.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
262 | 410_PF_SS_rConnector_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
263 | 410_PF_SS_rConnector_SocketAndThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
264 | 410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
265 | 410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
266 | 410_PF_SS_rReducerWithPlainEnd_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
267 | 410_PF_SS_rTransition_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
268 | 410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
269 | 410_PF_SS_TPiece_Mapress_Equal.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
270 | 410_PF_SS_tReducingDoubleBranch45_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
271 | 410_PF_SS_tReducingSingleBranch45.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
272 | 410_PF_SS_tReducingSingleBranch_87.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
273 | 410_PF_SS_tSingleBranch45_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
274 | 410_PF_SS_tSweptBranch87Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
275 | 410_PF_SS_tTeePiece_FemaleThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
276 | 410_PF_SS_tTeePiece_MaleThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
277 | 410_PF_SS_tTeePiece_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
278 | 410_PF_SS_T_Piece_Reducer_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
279 | 410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
280 | 410_PF_SS_uAdaptorUnion_MaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
281 | 410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
282 | 410_PF_SS_uAdaptor_WithFemaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
283 | 410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
284 | 410_PF_SS_uAdaptor_WithMaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
285 | 410_PF_SS_uAdaptor_WithMaleThreadAndPlainEnd_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
286 | 410_PF_SS_uAxialExpansion_PressingSockets.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
287 | 410_PF_SS_uBulkhead_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
288 | 410_PF_SS_uConnectionWithPlainEnd_Flanged_PN10PN16.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | [8 empty] | SUB | REV | FIN
289 | 410_PF_SS_uConnectionWithPlainEnd_Mapress&PressingSocket_PN10PN16.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
290 | 410_PF_SS_uConnectorwithFlangeandSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
291 | 410_PF_SS_uConnector_SocketAndThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
292 | 410_PF_SS_uCoupling_ThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
293 | 410_PF_SS_uExpansionSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
294 | 410_PF_SS_uPeakPressure_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
295 | 410_PF_SS_uRatStop_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
296 | 410_PF_SS_uRepairCoupling_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
297 | 410_PF_SS_uSocketClamp_Special.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
298 | 410_PF_SS_uSocketClamp_Twopiece.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
299 | 410_PF_SS_uStraightCoupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
300 | 410_PF_SS_uUnion_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
301 | 410_PF_SS_wCleaningPipes.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
302 | 410_PF_SS_xCornerBranch87Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
303 | 410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
304 | 410_PF_SS_xDoubleBranch87_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
305 | 410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
306 | 410_PF_ST_SanpressDoubleWallPane_Threaded_DN15.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
307 | 410_PF_UPVC_cCap_FemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
308 | 410_PF_UPVC_cCap_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
309 | 410_PF_UPVC_eBend90Deg_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
310 | 410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
311 | 410_PF_UPVC_eElbow90Deg_FemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
312 | 410_PF_UPVC_eElbow_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
313 | 410_PF_UPVC_eReducerElbow_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
314 | 410_PF_UPVC_eShortBend90Deg_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
315 | 410_PF_UPVC_rBushReducing_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
316 | 410_PF_UPVC_rLongBushReducing_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
317 | 410_PF_UPVC_rShortBushReducing_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
318 | 410_PF_UPVC_tLateralTee90Deg_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
319 | 410_PF_UPVC_tTee90Deg_FemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
320 | 410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 10 | [9 empty] | SUB | REV | FIN
321 | 410_PF_UPVC_tTee_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
322 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
323 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
324 | 410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
325 | 410_PF_UPVC_uCoupling_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
326 | 410_PF_UPVC_uInspectionPort_Glue.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
327 | 410_PF_UPVC_USiphon_Horizontal.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
328 | 410_PF_UPVC_xCross_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
329 | 410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
330 | 410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
331 | 410_PX_BasementFloorDrain_Vertical_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
332 | 410_PX_BoxGutters_Horizontal_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
333 | 410_PX_BoxGutters_Vertical_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
334 | 410_PX_DoppelPumpStationPowerlift_ACO.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
335 | 410_PX_DrainageChannel_B125.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
336 | 410_PX_DuofixElementForSinkAGB.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
337 | 410_PX_DuofixElementForWallHungWC.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
338 | 410_PX_DuofixElementForWallHungWC_BarrierFree.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
339 | 410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
340 | 410_PX_DuofixElementForWashbasin.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
341 | 410_PX_DuofixElementForWashBasin_BarrierFree.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
342 | 410_PX_DuofixElementInsetWashbasin_PillarTap.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
343 | 410_PX_DuofixForShower&Bathtub.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
344 | 410_PX_DuofixForShower&Bathtub_WallFittingAP.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
345 | 410_PX_DuofixForUrinal.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
346 | 410_PX_DuofixForUrinal_Universal.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
347 | 410_PX_DuofixSigmaToilet12cm_BarrierFree.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
348 | 410_PX_DuofixTraverseForStandaloneFaucetKitchenSink.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
349 | 410_PX_FaucetWithFlexibleHose.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
350 | 410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
351 | 410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
352 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 11 | [10 empty] | SUB | REV | FIN
353 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
354 | 410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
355 | 410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
356 | 410_PX_FloorDrain_Horizontal_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
357 | 410_PX_FloorDrain_Horizontal_Coupling_Plastic.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
358 | 410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
359 | 410_PX_FloorDrain_VerticalFinor2PartL15_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
360 | 410_PX_FloorDrain_Vertical_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
361 | 410_PX_FloorDrain_Vertical_Coupling_Plastic.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
362 | 410_PX_FloorDrain_Vertical_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
363 | 410_PX_GardenWater_Kemper.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
364 | 410_PX_GreaseDisposalPoint.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
365 | 410_PX_GullyGrating.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
366 | 410_PX_HorizontalFloorDrain.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
367 | 410_PX_InspectionShaft_OnePipe_Nosystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
368 | 410_PX_InspectionShaft_TwoPipe_Nosystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
369 | 410_PX_KitchenTap.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
370 | 410_PX_ManholeAdjustingUnits_Round_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
371 | 410_PX_ManholeBase_CastIn.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
372 | 410_PX_ManholeChamberUnits_Round_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
373 | 410_PX_ManholeCoverSlabs_Eccentrical_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
374 | 410_PX_ManholeReducingSlabs_Eccentrical_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
375 | 410_PX_ManholeTaper_EccentricalCones_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
376 | 410_PX_Manhole_Round.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
377 | 410_PX_ReusedRainWaterTank.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
378 | 410_PX_RoadGully.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
379 | 410_PX_SumpPit_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
380 | 410_PX_TapWithMaleHose_Threaded_DN15.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
381 | 410_PX_WaterTap.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
382 | 410_SE_Conlit150U_NoSystem.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
383 | 410_SE_ConlitFireProtectionSleeve_NoSystem.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
384 | 410_SE_CoverBox.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 12 | [11 empty] | SUB | REV | FIN
385 | 410_NF_GS_rConcentric_NoSocket_GMX.rfa | 410_NF | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
386 | 410_PA_Adapter&ExpansionPiece_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
387 | 410_PA_AirReleaseValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
388 | 410_PA_AngleSafetyValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
389 | 410_PA_AngleSeatPistonValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
390 | 410_PA_AngleSeatPistonValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
391 | 410_PA_AngleValve_Threaded_WithRegulatingFunction.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
392 | 410_PA_AutomaticBackwashFilter_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
393 | 410_PA_AutomaticCirculationRegulatingValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
394 | 410_PA_AutomaticHygieneFlushingStationHS10_Geberit.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
395 | 410_PA_BackflowPreventerValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
396 | 410_PA_BackflowPreventer_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
397 | 410_PA_BallValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
398 | 410_PA_BallValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
399 | 410_PA_CoarseTrap.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
400 | 410_PA_CombinationAngleValve_Standard.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
401 | 410_PA_DiaphragmValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
402 | 410_PA_DoubleInstallationRackWatermeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
403 | 410_PA_DrainValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
404 | 410_PA_FillSetStandardValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
405 | 410_PA_FillsoftHousing_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
406 | 410_PA_Filter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
407 | 410_PA_FittingSpacerForWaterMeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
408 | 410_PA_FlexibleConnection_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
409 | 410_PA_FloatingValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
410 | 410_PA_FlowSplitterBox_Floor_Threaded_KHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
411 | 410_PA_FlowSplitterSet_Threaded_KHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
412 | 410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
413 | 410_PA_FlowSplitterUnit_Threaded_DynamicKHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
414 | 410_PA_FlowTemperatureMeterValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
415 | 410_PA_FlushMountedStopValve_Mapress_UpPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
416 | 410_PA_FlushMoutedStopValve_Threaded_UpPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 13 | [12 empty] | SUB | REV | FIN
417 | 410_PA_FunnelSiphon_Horizontal.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
418 | 410_PA_GateValveSealingDirectionWithDrain_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
419 | 410_PA_GateValveWithDrain_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
420 | 410_PA_GateValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
421 | 410_PA_GateValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
422 | 410_PA_GlobeValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
423 | 410_PA_GlobeValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
424 | 410_PA_KHSFlushPoint_Threaded_230V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
425 | 410_PA_KHSFlushPoint_Threaded_24V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
426 | 410_PA_KHSFlushPoint_Threaded_ControlPlus230V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
427 | 410_PA_KHSFlushPoint_Threaded_ControlPlus24V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
428 | 410_PA_KugelSyphon_Standard.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
429 | 410_PA_MotorButterflyValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
430 | 410_PA_NozzleCheckValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
431 | 410_PA_OutletValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
432 | 410_PA_OutletValve_Threaded_WithHoseScrewConnection.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
433 | 410_PA_PoolMainDrain_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
434 | 410_PA_PoolReturnJet_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
435 | 410_PA_PoolSkimmer_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
436 | 410_PA_PPR_BallVale_SocketFusion.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
437 | 410_PA_PPR_StopVale_SocketFusion.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
438 | 410_PA_PressureGauge.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
439 | 410_PA_PressureGauge_withSiphon.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
440 | 410_PA_PressureReducingValveFilterCombination_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
441 | 410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
442 | 410_PA_PressureReducingValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
443 | 410_PA_PressureReducingValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
444 | 410_PA_PressureRegulator.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
445 | 410_PA_SamplingValveForWashBasinAngleValve_Standard_SS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
446 | 410_PA_SamplingValve_Standard_Gunmetal.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
447 | 410_PA_SamplingValve_Standard_SS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
448 | 410_PA_ShutoffValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 14 | [13 empty] | SUB | REV | FIN
449 | 410_PA_ShutoffValve_Flanged_DrainValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
450 | 410_PA_ShutoffValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
451 | 410_PA_ShutoffValve_Withdrainplug.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
452 | 410_PA_SingleInstallationRackWatermeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
453 | 410_PA_SolenoidControlValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
454 | 410_PA_SS_ShutoffValve_Mapress_WithDrainValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
455 | 410_PA_StainlessSteel_ShutoffValve_MapressGeberit.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
456 | 410_PA_StraightSafetyValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
457 | 410_PA_ST_StaticBalancingValve_Threaded_MultiFixPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
458 | 410_PA_ST_StaticBalancingValve_UnionThreaded_MultiFixPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
459 | 410_PA_SwingcheckValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
460 | 410_PA_SwingcheckValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
461 | 410_PA_SystemSeparator_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
462 | 410_PA_SystemSeparator_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
463 | 410_PA_TemperatureMeasuringValve_Threaded_KHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
464 | 410_PA_THandleBallValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
465 | 410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
466 | 410_PA_ThreePiecesBallValve_Welded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
467 | 410_PA_ThreeWayMotorisedControlValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
468 | 410_PA_ThreeWayMotorisedControlValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
469 | 410_PA_Two-WayDiaphragmValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
470 | 410_PA_TwoWayDiaphragmValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
471 | 410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
472 | 410_PA_UpETATHERMThermostaticBalancingValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
473 | 410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
474 | 410_PA_UPVSenkrecht.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
475 | 410_PA_UP_ConcealedShutoffValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
476 | 410_PA_VAVFullFlowShutOffValve_FemaleThreaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
477 | 410_PA_VentCowl.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
478 | 410_PA_WaferButterflyValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
479 | 410_PA_WaterHammerArrestor_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
480 | 410_PA_WaterMeterUNI.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 15 | [14 empty] | SUB | REV | FIN
481 | 410_PA_WaterMeter_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
482 | 410_PA_WaterMeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
483 | 410_PA_YStrainer_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
484 | 410_PA_YStrainer_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
485 | 410_PA_ZBCapRoof.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
486 | 410_CS_eRadiusReturnBends_Welded.rfa | 410_CS | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
487 | 410_CS_tTee_Welded.rfa | 410_CS | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
488 | 410_ME_CentrifugalPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
489 | 410_ME_CompactPressureBoostingSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
490 | 410_ME_CompactPressureBoostingSystem_1MVISE.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
491 | 410_ME_CompactWaterHeater_WallMounted.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
492 | 410_ME_Desoftening.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
493 | 410_ME_DoppelHebeanlageSchmutzwasser.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
494 | 410_ME_DoublePressureBoosterSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
495 | 410_ME_DrainLiftL_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
496 | 410_ME_DrainLiftM_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
497 | 410_ME_DrainLiftS_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
498 | 410_ME_DrainLiftXL_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
499 | 410_ME_DualTank_WaterSofteners.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
500 | 410_ME_DuplexSofteningUnit_RondomatDuo.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
501 | 410_ME_EKleindurchlauferhitzerCEX.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
502 | 410_ME_EKleindurchlauferhitzer_MCX.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
503 | 410_ME_ElectricInstantaneousHeater_DLE.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
504 | 410_ME_ExpansionVessel.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
505 | 410_ME_ExpansionVessel_Reflex.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
506 | 410_ME_FettabscheiderNG2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
507 | 410_ME_FreshWaterStation.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
508 | 410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
509 | 410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
510 | 410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
511 | 410_ME_GreaseSeparatorFreeStandingInstallationNS10.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
512 | 410_ME_GreaseSeparator_FloorStand.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | [15 empty] | SUB | REV | FIN
513 | 410_ME_HighPerformanceIndustrialMixers.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
514 | 410_ME_HotWaterStorageTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
515 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
516 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
517 | 410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
518 | 410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
519 | 410_ME_IBCTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
520 | 410_ME_iboxUniversalForShower_WallRecessed.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
521 | 410_ME_InstantaneousWaterHeater_Shower.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
522 | 410_ME_InstantaneousWaterHeater_SinkAGB.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
523 | 410_ME_InstantaneousWaterHeater_TeaKitchen.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
524 | 410_ME_InstantaneousWaterHeater_WashBasin.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
525 | 410_ME_KHSHygieneFlushBoxLITE_FlowSensorDoublePortwithThreaded.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
526 | 410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
527 | 410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
528 | 410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
529 | 410_ME_KHSHygieneFlushBoxPUREwithFlowSensorSinglePort_Threaded.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
530 | 410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
531 | 410_ME_KHSMiniControlSystemSLAVE_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
532 | 410_ME_KHSMiniControlSystem_WallSurface_Master.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
533 | 410_ME_KHSTimer_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
534 | 410_ME_MiniTresorCabinet_InWall.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
535 | 410_ME_MiniTresorCabinet_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
536 | 410_ME_MixingTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
537 | 410_ME_PHController.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
538 | 410_ME_PlasticInnerTankSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
539 | 410_ME_PoolHeatPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
540 | 410_ME_PoolSandFilter_FloorStand_Round.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
541 | 410_ME_PressureBoosterPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
542 | 410_ME_PressurisationUnit_FixedSpeedUnits2Pump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
543 | 410_ME_PressurisationUnit_FixedSpeedUnits3Pump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
544 | 410_ME_PressurisationUnit_VariableSpeedUnits3Pump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 17 | [16 empty] | SUB | REV | FIN
545 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith1PumP.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
546 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
547 | 410_ME_Probenahmetopf.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
548 | 410_ME_PumpGlandlessCirculator_StarZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
549 | 410_ME_PumpGlandlessCirculator_StarZD.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
550 | 410_ME_PumpGlandlessCirculator_TopZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
551 | 410_ME_PureWaterTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
552 | 410_ME_ReverseOsmosisSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
553 | 410_ME_SeparationStation.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
554 | 410_ME_ServiceStorageTank_Round.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
555 | 410_ME_Sicherheitstrennstation.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
556 | 410_ME_SinglePressureBoosterSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
557 | 410_ME_StratosMAXOZPump_Vertical.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
558 | 410_ME_StratosPICOZPump_Vertical.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
559 | 410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
560 | 410_ME_SubmergedPump_Horizontal_SatSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
561 | 410_ME_SubmergedPump_SitaSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
562 | 410_ME_SubmergedPump_Vertical_SATSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
563 | 410_ME_SubmergedPump_Vertical_SATVSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
564 | 410_ME_TresorCabinet_InWall.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
565 | 410_ME_TresorCabinet_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
566 | 410_ME_TripleSofteningSystem_DeltaP.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
567 | 410_ME_TWPressureBoosterSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
568 | 410_ME_VerticaltubeHeatexchanger.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [17 empty] | SUB | REV | FIN
569 | 410_ME_WasteWaterLiftingStationPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 18 | [18 empty] | SUB | REV | FIN
570 | 410_ME_WastewaterLiftingStation_DouPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
571 | 410_ME_WasteWaterLiftingStation_KesselPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
572 | 410_ME_WastewaterLiftingStation_MuliPES&Mono.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
573 | 410_ME_WastewaterLiftingStation_MuliProPEKDuo.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
574 | 410_ME_WastewaterLiftingStation_MuliProPEKParallel.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
575 | 410_ME_WastewaterLiftingStation_MuliProPENXLDuo.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
576 | 410_ME_WastewaterLiftingStation_MuliStarDDP.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
577 | 410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
578 | 410_ME_WastewaterLiftingStation_Sinkamat-HW.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
579 | 410_ME_WasteWaterLiftingStation_VerticalPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
580 | 410_ME_WasteWaterLift_Floor_C3.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
581 | 410_ME_WasteWaterLift_Floor_CWC3.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
582 | 410_ME_WasteWaterLift_Floor_D2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
583 | 410_ME_WasteWaterLift_Floor_WC1.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
584 | 410_ME_WasteWaterLift_Floor_WC3.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
585 | 410_ME_WaterDispenser_FloorStand.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
586 | 410_ME_WaterFilterTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
587 | 410_ME_WaterFilterVertical.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
588 | 410_ME_WaterHardnessMeter.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
589 | 410_ME_WaterHeaterWithTap_WallMounted.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
590 | 410_ME_WaterHeater_WallMounted.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
591 | 410_ME_WaterSofteningTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 19 | [18 empty] | SUB | REV | FIN
| Create the Revit templates for each LPH SAN |  | Revit Template |  | MEP | DIG
| LPH3 | SAN | Revit Template |  | MEP | DIG | [20 empty] | SUB | REV | FIN
| LPH5 | SAN | Revit Template |  | MEP | DIG | [20 empty] | SUB | REV | FIN
| LPH8 | SAN | Revit Template |  | MEP | DIG | [20 empty] | SUB | REV | FIN
| TGA_OUtput Checklists |  | Checklists |  | MEP | DIG
| LPH3 | SAN | Checklists |  | MEP | DIG | [5 empty] | SUB | REV | FIN
| LPH5 | SAN | Checklists |  | MEP | DIG | [7 empty] | SUB | REV | FIN
| LPH8 | SAN | Checklists |  | MEP | DIG | [9 empty] | SUB | REV | FIN
| Sample Model + Out Put Data | SAN |  |  | MEP | DIG | [19 empty] | SUB | REV | FIN
| Export layouts to Revizto & set up 3D Review SAN | SAN |  |  | MEP | DIG | [20 empty] | SUB | REV | FIN
| Lesson Learned | SAN |  |  | MEP | DIG | [20 empty] | SUB | REV | FIN
Legend:
| Initial Submission | Review Feedback | Final Submission
| MEP | DIG | MEP
| ✔ | ✔✔ | ✔✔✔

## Roll Down List (hidden)
Member
c.le
hoa.le
k.mai
y.nguyen
n.vo
dhn.nguyen
t.luu
tt.bui