## TIDP 430
PROJECT: DCMvn Annotation
DOCUMENT: DCMvn_RLT_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP) | [5 empty] | CW: 05 | CW: 06 | CW: 07 | CW: 08 | CW: 09 | CW: 10 | CW: 11 | CW: 12 | CW: 13 | CW: 14 | CW: 15 | CW: 16 | CW: 17 | CW: 18 | CW: 19 | CW: 20 | CW: 21 | CW: 22 | CW: 23 | CW: 24 | CW: 25 | CW: 26 | CW: 27 | CW: 28 | CW: 29 | CW: 30 | CW: 31 | CW: 32 | CW: 33 | CW: 34 | CW: 35 | CW: 36 | CW: 37 | CW: 38 | CW: 39 | CW: 40 | CW: 41 | CW: 42
NO: | NAME | DESCRIPTION | FILE TYPE | CREATED BY: | AUTHORISED BY: | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16
A | Framework deliverable
A1 | Define the "Graphical Annotation Framework"
|  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 2026-01-30: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
|  | Fill the content for RLT disciplines | .xlsx | MEP | DIG | 2026-01-30: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
|  | Confirm and sign the document | .pdf | MEP | DIG | 2026-01-30: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
A2 | Define the "Data Requirement Framework
|  | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 2026-01-30: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
|  | Fill the content for RLT disciplines | .xlsx | MEP | DIG | 2026-01-30: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
|  | Confirm and sign the document | .pdf | MEP | DIG | 2026-01-30: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
A3 | Define the process to revise the RFA library
|  | Confirm and sign the process document | .pdf |  |  | 2026-02-06: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
|  | Workshop the process with delivery team | .pptx |  |  | 2026-02-06: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
A4 | Define the desired outcome_RLT
B | Revise the RFA library | 280
B1 | DF_Duct Fitting | 18
1 | 430_DF_GS_sUbergangsstutzen_Flanged | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
2 | 430_DF_GS_cBoden_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
3 | 430_DF_GS_cCapEnd_Spigot_Round.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
4 | 430_DF_GS_eBogen_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
5 | 430_DF_GS_eEckbogen_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
6 | 430_DF_GS_eRoundElbow_Spigot.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
7 | 430_DF_GS_eTransitionElbow_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
8 | 430_DF_GS_rEtage_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
9 | 430_DF_GS_rReducer_Spigot_Round.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
10 | 430_DF_GS_rUbergangRechteckRund_Flanged_SlipJoint.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
11 | 430_DF_GS_rUbergang_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
12 | 430_DF_GS_sRoundTaps_Spigot.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
13 | 430_DF_GS_tTee_Spigot_Round.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
14 | 430_DF_GS_tTStuck_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
15 | 430_DF_GS_uCoupling_Spigot_Round.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
16 | 430_DF_GS_uUnion_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
17 | 430_DF_GS_wHosenStuck_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
18 | 430_DF_GS_xKreuzstuck_Flanged.rfa | Duct Fitting Revit Family | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
B2 | DA_Duct Accessory | 63
1 | 430_DA_AirtightLouverDamper.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
2 | 430_DA_CircularSilencers_CA_050.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
3 | 430_DA_CircularSilencers_CA_100.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
4 | 430_DA_CircularSilencers_CB.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
5 | 430_DA_CircularSilencers_CS.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
6 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowEN.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
7 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowENEx.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
8 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRN.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
9 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRNEx.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
10 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFL.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
11 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFC | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
12 | 430_DA_PressureOverflowElements.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
13 | 430_DA_FireDampersForCeiling_KU_K30.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
14 | 430_DA_FireDampers_CommercialKitchens_KA_EU.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
15 | 430_DA_FireDampers_FireProtectionValve_FV_EU.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
16 | 430_DA_FireInsulationSheets_Fitting_Promat_L90.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
17 | 430_DA_FireInsulationSheets_Promat_L90.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
18 | 430_DA_FireProtectionDamper_Round_FLIVE.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
19 | 430_DA_FlexibleConnection_Rectangular | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-26: CFM
20 | 430_DA_FlexibleConnection_Round | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
21 | 430_DA_FlowAdjustmentDampers.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
22 | 430_DA_IntumescentDamper_OverflowGrill_NoSystem.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
23 | 430_DA_MultileafDamperRec_LowLeakage.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
24 | 430_DA_NonReturnValves.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
25 | 430_DA_PressureReliefDamper_Rectangular_Standard_NoSystem.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
26 | 430_DA_RecFireDampers_FKEU.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
27 | 430_DA_RoundFireDampers_FKREU.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
28 | 430_DA_RoundFireDampers_FKRS_EU.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
29 | 430_DA_SchakoConstantVolumeFlowControl_Round_ConstantFlowVLV.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
30 | 430_DA_SchakoSilencer_Round_RS.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
31 | 430_DA_ShutOffDevices_AK.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
32 | 430_DA_ShutOffDevices_AKEx.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
33 | 430_DA_ShutOffDevices_AKK.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
34 | 430_DA_SilencersVAV_Rectangular_TS.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
35 | 430_DA_SilencersVAV_Rectangular_TX.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
36 | 430_DA_Silencer_Rectangular_Standard.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
37 | 430_DA_Silencer_Round_Standard.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
38 | 430_DA_SmokeControlDamper_EKEU.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
39 | 430_DA_SmokeControlDamper_EKJZ.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-26: REV; 2026-07-03: CFM
40 | 430_DA_SmokeDetectorinDucts_RMO3D.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
41 | 430_DA_SmokeDetectorinDucts_RMOVSD.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
42 | 430_DA_SmokeProtectionDamper_JZRS.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
43 | 430_DA_TunnelDampers_JF.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
44 | 430_DA_VariableAirVolume_Rectangular_MQTH.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
45 | 430_DA_VariableAirVolume_Round_MQTH.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
46 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTASilenzio.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
47 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVA.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
48 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVJ.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
49 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVM.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
50 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVT.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
51 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVZ.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
52 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTZSilenzio.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
53 | 430_DA_VariableVolumeFlowControl_Round_VarycontrolTVLK.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
54 | 430_DA_VariableVolumeFlowControl_Round_VaryControlTVREX.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
55 | 430_DA_VariableVolumeFlowControl_VaryControl _Round_LVC.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
56 | 430_DA_VariableVolumeFlowControl_VaryControl_Round_TVR.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
57 | 430_DA_VariableVolumeFlowControl_Varycontrol_Round_TVRK.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
58 | 430_DA_VolumeFlowRateMeasuringUnits_VME.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
59 | 430_DA_VolumeFlowRateMeasuringUnits_VMLK.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
60 | 430_DA_VolumeFlowRateMeasuringUnits_VMR.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
61 | 430_DA_RecFireDamperMechanism_FK2EU.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
62 | 430_DA_VolumeFlowRateMeasuringUnits_VMRK.rfa | Duct Accessories Revit Family | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-26: AUD; 2026-07-03: REV; 2026-07-10: CFM
B3 | AT_Air Terminal | 90
1 | 430_AT_AirDiffuser_Standard.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
2 | 430_AT_CircularDiscValves_LVS_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
3 | 430_AT_CircularDiscValves_ZLVS_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
4 | 430_AT_CrossflowCFE_TPP_NoSystem.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
5 | 430_AT_DeflectorHood_Roof_Rectangular_Exhaust | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
6 | 430_AT_DeflectorHood_Roof_Rectangular_FreshAirIntake.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
7 | 430_AT_DeflectorHood_Roof_Round_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
8 | 430_AT_DeflectorHood_Roof_Round_FreshAirIntake.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
9 | 430_AT_Diffusers_Floor_FBK_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
10 | 430_AT_Diffusers_Floor_FBK_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
11 | 430_AT_Diffusers_Wall_CHM_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
12 | 430_AT_Diffusers_Wall_CHS_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
13 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
14 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
15 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
16 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
17 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
18 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
19 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
20 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
21 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
22 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
23 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
24 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
25 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
26 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
27 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
28 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
29 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
30 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
31 | 430_AT_DiscValvesSTVA_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
32 | 430_AT_DiscValvesSTVZ_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
33 | 430_AT_DisplacementFlowDiffusers_Wall_QLF_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
34 | 430_AT_DisplacementFlowDiffusers_Wall_QLV_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
35 | 430_AT_DoubleSlot_CeilingHorizontal_1ConnectionSymmetrical_Withbox.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
36 | 430_AT_EggCrateAirGrill_HorizontalCeiling_Rectangular_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
37 | 430_AT_ExternalRainProtectionGrill_Wall_Round.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
38 | 430_AT_Grilles_Wall_Rectangular_TRS_FreshAirIntake.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
39 | 430_AT_Grilles_Wall_Rectangular_TRS_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
40 | 430_AT_Grilles_Wall_Rectangular_TRS_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
41 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdividedExhaust | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
42 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdivided_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
43 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
44 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
45 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
46 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
47 | 430_AT_InspectionOpenings_RecDuctHorizontal_Rectangular.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
48 | 430_AT_InspectionOpenings_RoundDuctHorizontal_Oval.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
49 | 430_AT_JetDiffuser_Round_Standard.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
50 | 430_AT_LamellarHood_Roof_Rectangular_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
51 | 430_AT_LamellarHood_Roof_Rectangular_FreshAirIntake.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
52 | 430_AT_LourveCover_Roof.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
53 | 430_AT_Louvre_Standard.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
54 | 430_AT_NozzlesElectricActuator_DUK_E_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
55 | 430_AT_NozzlesElectricActuator_DUK_E_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
56 | 430_AT_Nozzles_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
57 | 430_AT_Nozzles_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
58 | 430_AT_Nozzles_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
59 | 430_AT_Nozzle_Standard.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
60 | 430_AT_RoofHood.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
61 | 430_AT_RoundLouver_Standard.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
62 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
63 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
64 | 430_AT_SchakoDisplacementDiffusers_Wall_WQA_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
65 | 430_AT_SlotDiffuserDSXXXLP2A_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
66 | 430_AT_SlotDiffuserDSXXXLP2A_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
67 | 430_AT_SmokeExtractionAndVentilationHood_Roof_Rectangular_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
68 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
69 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
70 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
71 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
72 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
73 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
74 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
75 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
76 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
77 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
78 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
79 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
80 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
81 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
82 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
83 | 430_AT_SwirlDiffuser_VerticalCeiling_Rectangular_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
84 | 430_AT_TextileDiffuser_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
85 | 430_AT_VentilationGrilles_DoorWall_AGS_Exhaust.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
86 | 430_AT_VentilationGrilles_DoorWall_AGS_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
87 | 430_AT_VentilationGrilles_Rectangular_Standard.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
88 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Return.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
89 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Supply.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
90 | 430_AT_VentilationGrilles_RoundDuct_Standard.rfa | Air Terminal Revit Family | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
B4 | ME_Mechanical Equipment | 109
1 | 430_ME_AHUProcess.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
2 | 430_ME_AHU_BSF_Standard.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
3 | 430_ME_AIR1XC3200L.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
4 | 430_ME_AirCompressors_Standard.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
5 | 430_ME_AirHandingUnit_RectangularLeftConnection_CeilingStand.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
6 | 430_ME_AirHandingUnit_RectangularRightConnection_CeilingStand.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
7 | 430_ME_AirHandingUnit_RoundConnection_CeilingStand | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
8 | 430_ME_AirHandlingUnits_1Layer.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
9 | 430_ME_AirHandlingUnits_2Layer.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
10 | 430_ME_AirHandlingUnits_CF.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
11 | 430_ME_AirHandlingUnits_PHE.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
12 | 430_ME_AirHandlingUnit_1LayerFlachSeries_CeilingStand.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
13 | 430_ME_AirHandlingUnit_2LayerBowl_RoofStand.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
14 | 430_ME_AirHandlingUnit_2LayerCompactSeries_FloorStand.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
15 | 430_ME_AirHandlingUnit_2LayerForKitchen_FloorStand.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
16 | 430_ME_AirHandlingUnit_FloorStand.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
17 | 430_ME_AirHandlingUnit_Geniox29H.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
18 | 430_ME_AxialWindowFan_Rectangular.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
19 | 430_ME_CentrifugalDuctMountedFan.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
20 | 430_ME_ChemicalMachine.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
21 | 430_ME_CrossFlowFans_NoSystem.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
22 | 430_ME_DiesselTank_Becomix.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
23 | 430_ME_Ductfans_Round_DF.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
24 | 430_ME_Ductfans_WallMounted_Round.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
25 | 430_ME_ExpansionTank_BottomConnection.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
26 | 430_ME_FansForAggressiveAir.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
27 | 430_ME_Fan_Axial.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
28 | 430_ME_Fan_Roof_Exhaust.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
29 | 430_ME_Fan_Roof_SmokeExtraction_NoSystem.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
30 | 430_ME_Fan_WallMounted.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
31 | 430_ME_FilterFanCoilUnit.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
32 | 430_ME_FlushMountedFan_BackConnection_SilentECO.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
33 | 430_ME_FlushMountedFan_TopConnection_SilentECO.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
34 | 430_ME_GloveBox.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
35 | 430_ME_HeatExchangersAndAirHeaters_EL.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
36 | 430_ME_HeatExchangersAndAirHeaters_WL.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
37 | 430_ME_HeatExchangersAndAirHeaters_WT.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
38 | 430_ME_HeatExchangers_KTH_NoSystem.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
39 | 430_ME_HeatReclaimVentilator_VAMFC.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
40 | 430_ME_HeatRecoveryWheelPrimaryAirUnits_Standard.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
41 | 430_ME_AirHandlingUnit_Single_Fortluft.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
42 | 430_ME_AirHandlingUnit_Floor_Single_Aubenluft.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
43 | 430_ME_IndoorUnitsThermoVentI.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
44 | 430_ME_InlineCentrifugalFan_FRD.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
45 | 430_ME_JetFanCarPark_FloorSurface_NoSystem.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
46 | 430_ME_KitchenExtractorHood.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
47 | 430_ME_KitchenHoodMonoblock_Standard.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
48 | 430_ME_MixingTank_Becomix.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
49 | 430_ME_AirHandlingUnit_Single_Abluft.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
50 | 430_ME_AirHandlingUnit_Single_Zuluft.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
51 | 430_ME_RoofFanBendDHE_Supply.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
52 | 430_ME_RoofFanDV_Return.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
53 | 430_ME_RoofTopUnits_ThermoVentD.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
54 | 430_ME_RoofVentilationFans_DAX.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
55 | 430_ME_RoofVentilationFans_DAX_NoSystem.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
56 | 430_ME_RoofVentilationFans_DRVFH.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
57 | 430_ME_RoofVentilationFans_DRV_DRH.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
58 | 430_ME_RoofVentilationFans_DRV_EC.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
59 | 430_ME_Schleusenventilatoren.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
60 | 430_ME_SmokeExhaustAxialFans_BVAXO_F300.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
61 | 430_ME_SmokeExhaustAxialFans_BVAXO_F400.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
62 | 430_ME_SmokeExhaustCentrifugalFans_BVRA.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
63 | 430_ME_SmokeExhaustCentrifugalFans_BVREH.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
64 | 430_ME_SmokeExhaustCentrifugalFans_BVW-B.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
65 | 430_ME_SmokeExhaustFan_WallMounted_BVW_A.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
66 | 430_ME_SmokeExhaustJetFans_NoSystem.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
67 | 430_ME_SmokeExhaustPlugFans_BRERV.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
68 | 430_ME_StartingSolution.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
69 | 430_ME_VacuumPump.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
70 | 430_ME_VentilationAxialFans_AXN691256.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
71 | 430_ME_VentilationAxialFans_AXO.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
72 | 430_ME_VentilationAxialFans_AXO1050.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
73 | 430_ME_VentilationAxialFans_AXO927.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
74 | 430_ME_VentilationAxialFans_BVAXN_1256.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
75 | 430_ME_VentilationAxialFans_GLDF.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
76 | 430_ME_VentilationAxialFans_ZAXN691256.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
77 | 430_ME_VentilationCentrifugalFans_KFB.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
78 | 430_ME_VentilationCentrifugalFans_REH.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
79 | 430_ME_VentilationCentrifugalFans_RZH.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
80 | 430_ME_VentilationJetFans_GAXO_NoSystem.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
81 | 430_ME_VentilationPlugFans_ERV.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
82 | 430_ME_Ventilator_VAM.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
83 | 430_ME_WallMountedVentilator.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
84 | 430_ME_WallSmokeExhaustFans.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
85 | 430_ME_WindDrivenRoofVentilator_Standard.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
86 | 430_ME_FanCoilUnit_WithPlenumBox_ThreeConnector_Standard.rfa | RLT Equipment Revit Family | .rfa | MEP | DIG | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
C | Create the Revit templates for each LPH
C1 | RLT_Revit Template
1 | Revit Template for LPH3 | Revit Template | .rte | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
2 | Revit Template for LPH5 | Revit Template | .rte | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
3 | Revit Template for LPH8 | Revit Template | .rte | MEP | DIG | 2026-09-18: TRM; 2026-09-25: AUD; 2026-10-02: REV; 2026-10-09: CFM
C2 | RLT_Output Checklists
LPH3 Check list
1 | LPH3_Check list_RLT 01 | Checklist_Layout Plan. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
2 | LPH3_Check list_RLT 02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
3 | LPH3_Check list_RLT 03 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
LPH5 Check list
1 | LPH5_Check list_RLT 01 | Checklist_Layout Plan. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
2 | LPH5_Check list_RLT 02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
3 | LPH5_Check list_RLT 03 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
LPH8 Check list
1 | LPH8_Check list_RLT 01 | Checklist_Layout Plan. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
2 | LPH8_Check list_RLT 02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
3 | LPH8_Check list_RLT 03 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
D | Sample Model + Output Data
1 | Delivery Sample layout for LPH3 | Execute a sample layout | .pdf | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
2 | Delivery Sample layout for LPH5 | Execute a sample layout | .pdf | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
3 | Delivery Sample layout for LPH8 | Execute a sample layout | .pdf | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
4 | Delivery Schematic Drawing Sample for LPH3 | Execute a sample layout | .pdf | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
5 | Delivery Schematic Drawing Sample for LPH5 | Execute a sample layout | .pdf | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
6 | Delivery Schematic Drawing Sample for LPH8 | Execute a sample layout | .pdf | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
E | Export layouts to Revizto & set up 3D Review
1 | Export layouts to Revizto & set up 3D Review RLT_LPH3 | Overlay layout to Revizto | Revizto | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
2 | Export layouts to Revizto & set up 3D Review RLT_LPH5 | Overlay layout to Revizto | Revizto | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
3 | Export layouts to Revizto & set up 3D Review RLT_LPH8 | Overlay layout to Revizto | Revizto | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
F | Lesson Learned
1 |  | What went well. What didn’t go well What we learned, Action items / Improvements | .pdf | MEP | MEP | 2026-09-25: TRM; 2026-10-02: AUD; 2026-10-09: REV; 2026-10-16: CFM
Legend:
TRM | Transmittal / Submitted | MEP
AUD | Audit/Review | DIG
REV | Revision Required / Revised | MEP
CFM | Confimmation/Confirmed & Stored | DIG/MEP
Note on A237: Hanh Thi Bich Pham: Hanh's team support_SOW

## TIDP Detail (hidden)
PROJECT: DCMvn Annotation
DOCUMENT: DCMvn_SAN&SPR_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP)
NO: | NAME | DESCRIPTION: |  | FILE TYPE: | PRIORITY | CREATED BY: | AUDIT BY: | 2026-01-30 | 2026-02-27 | 2026-03-31 | 2026-04-29 | 2026-05-29 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-30 | 2026-11-30 | 2026-12-31 | 2027-01-29
1 | 410_CS_eRadiusReturnBends_Welded.rfa | Sanitary Revit Family | CS | .rfa | 1 | MEP | DIG | bar: 2026-02-27
2 | 410_CS_tTee_Welded.rfa | Sanitary Revit Family | CS | .rfa | 1 | MEP | DIG | bar: 2026-04-29
3 | 410_ME_CentrifugalPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG | bar: 2026-01-30
4 | 410_ME_CompactPressureBoostingSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
5 | 410_ME_CompactPressureBoostingSystem_1MVISE.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
6 | 410_ME_CompactWaterHeater_WallMounted.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
7 | 410_ME_Desoftening.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
8 | 410_ME_DoppelHebeanlageSchmutzwasser.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
9 | 410_ME_DoublePressureBoosterSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
10 | 410_ME_DrainLiftL_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
11 | 410_ME_DrainLiftM_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
12 | 410_ME_DrainLiftS_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
13 | 410_ME_DrainLiftXL_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
14 | 410_ME_DualTank_WaterSofteners.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
15 | 410_ME_DuplexSofteningUnit_RondomatDuo.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
16 | 410_ME_EKleindurchlauferhitzerCEX.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
17 | 410_ME_EKleindurchlauferhitzer_MCX.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
18 | 410_ME_ElectricInstantaneousHeater_DLE.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
19 | 410_ME_ExpansionVessel.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
20 | 410_ME_ExpansionVessel_Reflex.rfa | Sanitary Revit Family | ME | .rfa | 2 | MEP | DIG
21 | 410_ME_FettabscheiderNG2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
22 | 410_ME_FreshWaterStation.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
23 | 410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
24 | 410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
25 | 410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
26 | 410_ME_GreaseSeparatorFreeStandingInstallationNS10.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
27 | 410_ME_GreaseSeparator_FloorStand.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
28 | 410_ME_HighPerformanceIndustrialMixers.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
29 | 410_ME_HotWaterStorageTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
30 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
31 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
32 | 410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
33 | 410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
34 | 410_ME_IBCTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
35 | 410_ME_iboxUniversalForShower_WallRecessed.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
36 | 410_ME_InstantaneousWaterHeater_Shower.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
37 | 410_ME_InstantaneousWaterHeater_SinkAGB.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
38 | 410_ME_InstantaneousWaterHeater_TeaKitchen.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
39 | 410_ME_InstantaneousWaterHeater_WashBasin.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
40 | 410_ME_KHSHygieneFlushBoxLITE_FlowSensorDoublePortwithThreaded.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
41 | 410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
42 | 410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
43 | 410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
44 | 410_ME_KHSHygieneFlushBoxPUREwithFlowSensorSinglePort_Threaded.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
45 | 410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
46 | 410_ME_KHSMiniControlSystemSLAVE_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
47 | 410_ME_KHSMiniControlSystem_WallSurface_Master.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
48 | 410_ME_KHSTimer_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
49 | 410_ME_MiniTresorCabinet_InWall.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
50 | 410_ME_MiniTresorCabinet_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
51 | 410_ME_MixingTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
52 | 410_ME_PHController.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
53 | 410_ME_PlasticInnerTankSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
54 | 410_ME_PoolHeatPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
55 | 410_ME_PoolSandFilter_FloorStand_Round.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
56 | 410_ME_PressureBoosterPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
57 | 410_ME_PressurisationUnit_FixedSpeedUnits2Pump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
58 | 410_ME_PressurisationUnit_FixedSpeedUnits3Pump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
59 | 410_ME_PressurisationUnit_VariableSpeedUnits3Pump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
60 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith1PumP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
61 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
62 | 410_ME_Probenahmetopf.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
63 | 410_ME_PumpGlandlessCirculator_StarZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
64 | 410_ME_PumpGlandlessCirculator_StarZD.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
65 | 410_ME_PumpGlandlessCirculator_TopZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
66 | 410_ME_PureWaterTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
67 | 410_ME_ReverseOsmosisSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
68 | 410_ME_SeparationStation.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
69 | 410_ME_ServiceStorageTank_Round.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
70 | 410_ME_Sicherheitstrennstation.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
71 | 410_ME_SinglePressureBoosterSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
72 | 410_ME_StratosMAXOZPump_Vertical.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
73 | 410_ME_StratosPICOZPump_Vertical.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
74 | 410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
75 | 410_ME_SubmergedPump_Horizontal_SatSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
76 | 410_ME_SubmergedPump_SitaSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
77 | 410_ME_SubmergedPump_Vertical_SATSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
78 | 410_ME_SubmergedPump_Vertical_SATVSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
79 | 410_ME_TresorCabinet_InWall.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
80 | 410_ME_TresorCabinet_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
81 | 410_ME_TripleSofteningSystem_DeltaP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
82 | 410_ME_TWPressureBoosterSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
83 | 410_ME_VerticaltubeHeatexchanger.rfa | Sanitary Revit Family | ME | .rfa | 2 | MEP | DIG
84 | 410_ME_WasteWaterLiftingStationPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
85 | 410_ME_WastewaterLiftingStation_DouPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
86 | 410_ME_WasteWaterLiftingStation_KesselPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
87 | 410_ME_WastewaterLiftingStation_MuliPES&Mono.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
88 | 410_ME_WastewaterLiftingStation_MuliProPEKDuo.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
89 | 410_ME_WastewaterLiftingStation_MuliProPEKParallel.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
90 | 410_ME_WastewaterLiftingStation_MuliProPENXLDuo.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
91 | 410_ME_WastewaterLiftingStation_MuliStarDDP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
92 | 410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
93 | 410_ME_WastewaterLiftingStation_Sinkamat-HW.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
94 | 410_ME_WasteWaterLiftingStation_VerticalPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
95 | 410_ME_WasteWaterLift_Floor_C3.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
96 | 410_ME_WasteWaterLift_Floor_CWC3.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
97 | 410_ME_WasteWaterLift_Floor_D2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
98 | 410_ME_WasteWaterLift_Floor_WC1.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
99 | 410_ME_WasteWaterLift_Floor_WC3.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
100 | 410_ME_WaterDispenser_FloorStand.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
101 | 410_ME_WaterFilterTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
102 | 410_ME_WaterFilterVertical.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
103 | 410_ME_WaterHardnessMeter.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
104 | 410_ME_WaterHeaterWithTap_WallMounted.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
105 | 410_ME_WaterHeater_WallMounted.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
106 | 410_ME_WaterSofteningTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
107 | 410_NF_GS_rConcentric_NoSocket_GMX.rfa | Sanitary Revit Family | NF | .rfa | 1 | MEP | DIG
108 | 410_PA_Adapter&ExpansionPiece_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
109 | 410_PA_AirReleaseValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
110 | 410_PA_AngleSafetyValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
111 | 410_PA_AngleSeatPistonValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
112 | 410_PA_AngleSeatPistonValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
113 | 410_PA_AngleValve_Threaded_WithRegulatingFunction.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
114 | 410_PA_AutomaticBackwashFilter_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
115 | 410_PA_AutomaticCirculationRegulatingValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
116 | 410_PA_AutomaticHygieneFlushingStationHS10_Geberit.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
117 | 410_PA_BackflowPreventerValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
118 | 410_PA_BackflowPreventer_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
119 | 410_PA_BallValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
120 | 410_PA_BallValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
121 | 410_PA_CoarseTrap.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
122 | 410_PA_CombinationAngleValve_Standard.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
123 | 410_PA_DiaphragmValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
124 | 410_PA_DoubleInstallationRackWatermeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
125 | 410_PA_DrainValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
126 | 410_PA_FillSetStandardValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
127 | 410_PA_FillsoftHousing_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
128 | 410_PA_Filter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
129 | 410_PA_FittingSpacerForWaterMeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
130 | 410_PA_FlexibleConnection_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
131 | 410_PA_FloatingValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
132 | 410_PA_FlowSplitterBox_Floor_Threaded_KHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
133 | 410_PA_FlowSplitterSet_Threaded_KHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
134 | 410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
135 | 410_PA_FlowSplitterUnit_Threaded_DynamicKHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
136 | 410_PA_FlowTemperatureMeterValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
137 | 410_PA_FlushMountedStopValve_Mapress_UpPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
138 | 410_PA_FlushMoutedStopValve_Threaded_UpPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
139 | 410_PA_FunnelSiphon_Horizontal.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
140 | 410_PA_GateValveSealingDirectionWithDrain_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
141 | 410_PA_GateValveWithDrain_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
142 | 410_PA_GateValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
143 | 410_PA_GateValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
144 | 410_PA_GlobeValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
145 | 410_PA_GlobeValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
146 | 410_PA_KHSFlushPoint_Threaded_230V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
147 | 410_PA_KHSFlushPoint_Threaded_24V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
148 | 410_PA_KHSFlushPoint_Threaded_ControlPlus230V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
149 | 410_PA_KHSFlushPoint_Threaded_ControlPlus24V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
150 | 410_PA_KugelSyphon_Standard.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
151 | 410_PA_MotorButterflyValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
152 | 410_PA_NozzleCheckValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
153 | 410_PA_OutletValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
154 | 410_PA_OutletValve_Threaded_WithHoseScrewConnection.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
155 | 410_PA_PoolMainDrain_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
156 | 410_PA_PoolReturnJet_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
157 | 410_PA_PoolSkimmer_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
158 | 410_PA_PPR_BallVale_SocketFusion.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
159 | 410_PA_PPR_StopVale_SocketFusion.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
160 | 410_PA_PressureGauge.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
161 | 410_PA_PressureGauge_withSiphon.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
162 | 410_PA_PressureReducingValveFilterCombination_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
163 | 410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
164 | 410_PA_PressureReducingValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
165 | 410_PA_PressureReducingValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
166 | 410_PA_PressureRegulator.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
167 | 410_PA_SamplingValveForWashBasinAngleValve_Standard_SS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
168 | 410_PA_SamplingValve_Standard_Gunmetal.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
169 | 410_PA_SamplingValve_Standard_SS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
170 | 410_PA_ShutoffValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
171 | 410_PA_ShutoffValve_Flanged_DrainValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
172 | 410_PA_ShutoffValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
173 | 410_PA_ShutoffValve_Withdrainplug.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
174 | 410_PA_SingleInstallationRackWatermeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
175 | 410_PA_SolenoidControlValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
176 | 410_PA_SS_ShutoffValve_Mapress_WithDrainValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
177 | 410_PA_StainlessSteel_ShutoffValve_MapressGeberit.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
178 | 410_PA_StraightSafetyValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
179 | 410_PA_ST_StaticBalancingValve_Threaded_MultiFixPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
180 | 410_PA_ST_StaticBalancingValve_UnionThreaded_MultiFixPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
181 | 410_PA_SwingcheckValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
182 | 410_PA_SwingcheckValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
183 | 410_PA_SystemSeparator_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
184 | 410_PA_SystemSeparator_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
185 | 410_PA_TemperatureMeasuringValve_Threaded_KHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
186 | 410_PA_THandleBallValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
187 | 410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
188 | 410_PA_ThreePiecesBallValve_Welded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
189 | 410_PA_ThreeWayMotorisedControlValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
190 | 410_PA_ThreeWayMotorisedControlValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
191 | 410_PA_Two-WayDiaphragmValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
192 | 410_PA_TwoWayDiaphragmValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
193 | 410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
194 | 410_PA_UpETATHERMThermostaticBalancingValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
195 | 410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
196 | 410_PA_UPVSenkrecht.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
197 | 410_PA_UP_ConcealedShutoffValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
198 | 410_PA_VAVFullFlowShutOffValve_FemaleThreaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
199 | 410_PA_VentCowl.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
200 | 410_PA_WaferButterflyValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
201 | 410_PA_WaterHammerArrestor_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
202 | 410_PA_WaterMeterUNI.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
203 | 410_PA_WaterMeter_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
204 | 410_PA_WaterMeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
205 | 410_PA_YStrainer_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
206 | 410_PA_YStrainer_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
207 | 410_PA_ZBCapRoof.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
208 | 410_PF_CastIron_Branch68Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
209 | 410_PF_CastIron_CleaningPipeWithRectangularCover_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
210 | 410_PF_CastIron_CleaningPipeWithRoundCover_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
211 | 410_PF_CastIron_CombinationBranch_88Degree_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
212 | 410_PF_CastIron_DownPipeBracket_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
213 | 410_PF_CastIron_EccentricReducer_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
214 | 410_PF_CastIron_Plug_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
215 | 410_PF_CastIron_RainwaterSiphon_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
216 | 410_PF_CastIron_SMLRainwaterSiphonVertical_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
217 | 410_PF_cHDPE_BlindFlange_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
218 | 410_PF_CI_AngleDoubleBranch88Degree_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
219 | 410_PF_CI_Bearing.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
220 | 410_PF_CI_Branch45Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
221 | 410_PF_CI_Branch45Deg_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
222 | 410_PF_CI_cPushinPlug_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
223 | 410_PF_CI_DoubleBranch_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
224 | 410_PF_CI_eAccessBendLong_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
225 | 410_PF_CI_eAccessBendShort_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
226 | 410_PF_CI_eBend15Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
227 | 410_PF_CI_eBend30Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
228 | 410_PF_CI_eBend68Degree_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
229 | 410_PF_CI_eBend88Degree_SpigotAndClamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
230 | 410_PF_CI_eBend88Deg_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
231 | 410_PF_CI_eBendWC_Clamp_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
232 | 410_PF_CI_eBend_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
233 | 410_PF_CI_eBend_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
234 | 410_PF_CI_eBend_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
235 | 410_PF_CI_eConectionBend_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
236 | 410_PF_CI_eDoubleBend45Deg_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
237 | 410_PF_CI_eDoubleBend88Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
238 | 410_PF_CI_eDoubleBend88Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
239 | 410_PF_CI_eOffsetBend130_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
240 | 410_PF_CI_eOffsetBend200_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
241 | 410_PF_CI_eOffsetBend65_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
242 | 410_PF_CI_ePlainTrap_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
243 | 410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
244 | 410_PF_CI_eRestBend88_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
245 | 410_PF_CI_eVentilationBend88Axial_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
246 | 410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
247 | 410_PF_CI_GutterAngleUniversal.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
248 | 410_PF_CI_GutterCap_ExternalStopEnd.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
249 | 410_PF_CI_GutterCap_InternalStopEnd.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
250 | 410_PF_CI_GutterElbow_ExternalDropEndOutlet.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
251 | 410_PF_CI_GutterElbow_InternalDropEndOutlet.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
252 | 410_PF_CI_GutterHalfRound.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
253 | 410_PF_CI_GutterTee_RunningOutlet.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
254 | 410_PF_CI_GutterUnionConnector.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
255 | 410_PF_CI_mShortPipeRectangularAccessDoor_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
256 | 410_PF_CI_mVerticalTrap_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
257 | 410_PF_CI_rEccentricReducer_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
258 | 410_PF_CI_rEccentricReducer_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
259 | 410_PF_CI_rReducingEccentric_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
260 | 410_PF_CI_tBranch45_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
261 | 410_PF_CI_tBranch70_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
262 | 410_PF_CI_tBranch88Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
263 | 410_PF_CI_tBranch88Deg_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
264 | 410_PF_CI_tBranch88Long_Spigot_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
265 | 410_PF_CI_tBranch88_Spigot_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
266 | 410_PF_CI_tCombinationBranch90_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
267 | 410_PF_CI_tCornerBranch88_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
268 | 410_PF_CI_tSweptEntryBranch88_Spigot_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
269 | 410_PF_CI_uShortPipeRoundAccessDoor_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
270 | 410_PF_CI_uTrapHorizontal_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
271 | 410_PF_CI_xDoubleBranch45_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
272 | 410_PF_CI_xDoubleBranch70Deg_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
273 | 410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
274 | 410_PF_CS_cEndCaps_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
275 | 410_PF_CS_eLongRadiusElbows_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
276 | 410_PF_CS_eLongRadiusReturnBends_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
277 | 410_PF_CS_eRadiusElbows_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
278 | 410_PF_CS_fPlaneFlange_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
279 | 410_PF_CS_rConcentricReducers_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
280 | 410_PF_CS_rConnector_MapressAndFemaleThread.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
281 | 410_PF_CS_uConnector_MapressAndFemaleThread.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
282 | 410_PF_DI_cBellmouth_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
283 | 410_PF_DI_cBlind_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
284 | 410_PF_DI_cCap_KType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
285 | 410_PF_DI_cPlug_TType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
286 | 410_PF_DI_eBend_Flange.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
287 | 410_PF_DI_eBend_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
288 | 410_PF_DI_eDuckfoodBend90Deg_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
289 | 410_PF_DI_fFlange_RFType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
290 | 410_PF_DI_rFlangedCover.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
291 | 410_PF_DI_rFlangeSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
292 | 410_PF_DI_rFlangeSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
293 | 410_PF_DI_rTapper_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
294 | 410_PF_DI_rTapper_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
295 | 410_PF_DI_tLevelInvertTee_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
296 | 410_PF_DI_tTeeSocketWithFlangedBranch.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
297 | 410_PF_DI_tTeeSocketWithLevelInvertFlangedBranch.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
298 | 410_PF_DI_tTee_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
299 | 410_PF_DI_tTee_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
300 | 410_PF_DI_uAdaptorRestrained_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
301 | 410_PF_DI_uFlangeAdaptor.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
302 | 410_PF_DI_uUnionFlange_RFType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
303 | 410_PF_DI_uUnionSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
304 | 410_PF_DuctileIron_DoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
305 | 410_PF_EPDM_mKonfixConnector_PushOnJoint.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
306 | 410_PF_eSweptBendLong_Medium_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
307 | 410_PF_fHDPE_LooseFlange.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
308 | 410_PF_FireCollar_FloorMounted.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
309 | 410_PF_FireCollar_WallMounted.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
310 | 410_PF_GS_cFrogFlap_Socket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
311 | 410_PF_GS_cSealingPlugsWithVentilationSlots.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
312 | 410_PF_GS_eAngleBend_1PushShortSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
313 | 410_PF_GS_eAngleBend_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
314 | 410_PF_GS_eBasinConnector_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
315 | 410_PF_GS_eBendWithCalm_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
316 | 410_PF_GS_eBend_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
317 | 410_PF_GS_eBend_NoSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
318 | 410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
319 | 410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
320 | 410_PF_GS_eReductionAngleBend_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
321 | 410_PF_GS_GutterRound_SocketAndStandard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
322 | 410_PF_GS_mOptimisationPart_1PushSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
323 | 410_PF_GS_mSBendTrap_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
324 | 410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
325 | 410_PF_GS_rAdapterConcentric_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
326 | 410_PF_GS_rAdapterEccentric_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
327 | 410_PF_GS_rConcentricOptimiser_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
328 | 410_PF_GS_rTransitiontoCastIron_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
329 | 410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
330 | 410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
331 | 410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
332 | 410_PF_GS_tTeeBranches_2PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
333 | 410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
334 | 410_PF_GS_uBends_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
335 | 410_PF_GS_uGutterPipes_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
336 | 410_PF_GS_uLongCleaningOpening_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
337 | 410_PF_GS_uLongCleaningOpening_NoSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
338 | 410_PF_GS_uLongUnion_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
339 | 410_PF_GS_uSpigottoPlastic_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
340 | 410_PF_GS_uTransitionSMLtoGMX_1PushSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
341 | 410_PF_GS_uTranstiontoCastIron_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
342 | 410_PF_GS_uUnion_2PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
343 | 410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
344 | 410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
345 | 410_PF_HDPE_cProtectionCap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
346 | 410_PF_HDPE_cProtectionCapForPipeEnd.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
347 | 410_PF_HDPE_cThreadedConnectorWithScrewCap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
348 | 410_PF_HDPE_eBend90Deg_Reducer_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
349 | 410_PF_HDPE_eBend_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
350 | 410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
351 | 410_PF_HDPE_eConnectionBend88Deg_WithLateralSupplementary_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
352 | 410_PF_HDPE_eConnectionBend90DegForSleeve.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
353 | 410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
354 | 410_PF_HDPE_eConnectionBend90Deg_RightOffset_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
355 | 410_PF_HDPE_eScrewCap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
356 | 410_PF_HDPE_eSegmentBend_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
357 | 410_PF_HDPE_mDoubleConnectionBend90Deg_ForSleeve.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
358 | 410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
359 | 410_PF_HDPE_mDoubleConnectionBend90Deg_VerticalForWallHungWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
360 | 410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
361 | 410_PF_HDPE_mRunningTrap_Standard.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
362 | 410_PF_HDPE_mSoventFitting_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
363 | 410_PF_HDPE_mSTrap_Standard.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
364 | 410_PF_HDPE_mUniversalTrap_WithFlangeBushing.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
365 | 410_PF_HDPE_mWasteManifold.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
366 | 410_PF_HDPE_rAdaptorSocket_DN90xDN100.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
367 | 410_PF_HDPE_rCompressionJoint.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
368 | 410_PF_HDPE_rReducer_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
369 | 410_PF_HDPE_rRingSealSocket_ReducedWithLipSeal.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
370 | 410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
371 | 410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
372 | 410_PF_HDPE_tLateralTee_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
373 | 410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
374 | 410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
375 | 410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
376 | 410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
377 | 410_PF_HDPE_uAdapterUnion_FemaleThread.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
378 | 410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
379 | 410_PF_HDPE_uAdapterUnion_MaleThread.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
380 | 410_PF_HDPE_uClampingConnector.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
381 | 410_PF_HDPE_uExpansionSocket.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
382 | 410_PF_HDPE_uFlangeAdapter.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
383 | 410_PF_HDPE_uFlangeBushing.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
384 | 410_PF_HDPE_uFlangeSet.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
385 | 410_PF_HDPE_uStraightAdapterToCastIronPipe.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
386 | 410_PF_HDPE_uStraightAdapterToPVCPipe.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
387 | 410_PF_HDPE_uStraightAdapterWithCompressionJoint_Glueing.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
388 | 410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
389 | 410_PF_HDPE_uStraightConnectorWithRingSealSocket_WC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
390 | 410_PF_HDPE_uStraightConnector_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
391 | 410_PF_HDPE_uThreadedConnectorWithCompressionJoint.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
392 | 410_PF_HDPE_uUnionConnection_WeldingJoints.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
393 | 410_PF_HDPE_xDoubleBrandFitting45Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
394 | 410_PF_mGalvanized_PTrap_GMX.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
395 | 410_PF_mHDPE_PTrap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
396 | 410_PF_PE_eBendForWandWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
397 | 410_PF_PPR_cEndCap_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
398 | 410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
399 | 410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
400 | 410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
401 | 410_PF_PPR_eElbow_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
402 | 410_PF_PPR_rCoupling_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
403 | 410_PF_PPR_rCoupling_MaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
404 | 410_PF_PPR_rElbow90DegMaleThread_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
405 | 410_PF_PPR_rReducing_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
406 | 410_PF_PPR_tTee_FemaleThreadedAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
407 | 410_PF_PPR_tTee_MaleThreadedAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
408 | 410_PF_PPR_tTee_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
409 | 410_PF_PPR_uCoupling_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
410 | 410_PF_PPR_uCoupling_MaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
411 | 410_PF_PPR_uUnion_BushSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
412 | 410_PF_PPR_uUnion_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
413 | 410_PF_PPSilent_DuctBranch_SocketAndSpigot_SweptEntry88DegLeft.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
414 | 410_PF_PPSilent_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
415 | 410_PF_PPSilent_tDoubleConnectionBend90Deg_Extended.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
416 | 410_PF_PP_AccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
417 | 410_PF_PP_Adaptor_SleeveToCastIronAndSilent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
418 | 410_PF_PP_Bend_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
419 | 410_PF_PP_Branch_SocketSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
420 | 410_PF_PP_CapEnd_Socket_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
421 | 410_PF_PP_CombinedCornerBranch_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
422 | 410_PF_PP_DoubleBranchFitting88Deg_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
423 | 410_PF_PP_DoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
424 | 410_PF_PP_mOdorTrapForSinkHorizontal_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
425 | 410_PF_PP_mOdorTrapForSinkVertical_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
426 | 410_PF_PP_mOdorTrapForSink_VerticalandHorizontal_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
427 | 410_PF_PP_ParallelBrand45Deg_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
428 | 410_PF_PP_ReducerEccentric_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
429 | 410_PF_PP_SlipCoupling_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
430 | 410_PF_SilentPro_cCapEnd_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
431 | 410_PF_SilentPro_eElbow_SocketAndSpigot.rfa.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
432 | 410_PF_SilentPro_mCombinedCornerBranch_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
433 | 410_PF_SilentPro_mCornerBranch88Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
434 | 410_PF_SilentPro_rReducerEccentric_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
435 | 410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
436 | 410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
437 | 410_PF_SilentPro_tTeeBranch_SocketSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
438 | 410_PF_SilentPro_uAccessPipe90Deg_WithRoundServiceOpening&Silent_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
439 | 410_PF_SilentPro_uSlipCoupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
440 | 410_PF_SilentPro_wParallelBrand45Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
441 | 410_PF_SilentPro_xCrossDoubleBranchFitting88Deg_SweptEntry_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
442 | 410_PF_SS _Union_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
443 | 410_PF_SS_cCap_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
444 | 410_PF_SS_cDrainplugWithScrewedPlug.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
445 | 410_PF_SS_cSocketPlug.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
446 | 410_PF_SS_cSocketPlugWithClamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
447 | 410_PF_SS_cVentCowl_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
448 | 410_PF_SS_eBend45Degrees_SocketAndStandard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
449 | 410_PF_SS_eBend87_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
450 | 410_PF_SS_eBendWith250mmOblong_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
451 | 410_PF_SS_eBend_15_1Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
452 | 410_PF_SS_eBend_30_1Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
453 | 410_PF_SS_eElbow90DegAdaptor_FemaleThreadAndPlainEnd_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
454 | 410_PF_SS_eElbow90DegAdaptor_WithMaleThread_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
455 | 410_PF_SS_eElbow90DegTapConnector_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
456 | 410_PF_SS_eElbow90Deg_FemaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
457 | 410_PF_SS_eElbowTapConector90Degree_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
458 | 410_PF_SS_eElbow_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
459 | 410_PF_SS_eLongBend_1Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
460 | 410_PF_SS_ePTrap_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
461 | 410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
462 | 410_PF_SS_mCornerElbow90Deg_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
463 | 410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
464 | 410_PF_SS_Rapid_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
465 | 410_PF_SS_rConcentricIncreaserCoupling_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
466 | 410_PF_SS_rConnectorExternalThreadSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
467 | 410_PF_SS_rConnectorInternal_ThreadSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
468 | 410_PF_SS_rConnectorWithSocketAndFlange.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
469 | 410_PF_SS_rConnector_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
470 | 410_PF_SS_rConnector_SocketAndThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
471 | 410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
472 | 410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
473 | 410_PF_SS_rReducerWithPlainEnd_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
474 | 410_PF_SS_rTransition_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
475 | 410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
476 | 410_PF_SS_TPiece_Mapress_Equal.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
477 | 410_PF_SS_tReducingDoubleBranch45_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
478 | 410_PF_SS_tReducingSingleBranch45.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
479 | 410_PF_SS_tReducingSingleBranch_87.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
480 | 410_PF_SS_tSingleBranch45_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
481 | 410_PF_SS_tSweptBranch87Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
482 | 410_PF_SS_tTeePiece_FemaleThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
483 | 410_PF_SS_tTeePiece_MaleThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
484 | 410_PF_SS_tTeePiece_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
485 | 410_PF_SS_T_Piece_Reducer_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
486 | 410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
487 | 410_PF_SS_uAdaptorUnion_MaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
488 | 410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
489 | 410_PF_SS_uAdaptor_WithFemaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
490 | 410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
491 | 410_PF_SS_uAdaptor_WithMaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
492 | 410_PF_SS_uAdaptor_WithMaleThreadAndPlainEnd_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
493 | 410_PF_SS_uAxialExpansion_PressingSockets.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
494 | 410_PF_SS_uBulkhead_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
495 | 410_PF_SS_uConnectionWithPlainEnd_Flanged_PN10PN16.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
496 | 410_PF_SS_uConnectionWithPlainEnd_Mapress&PressingSocket_PN10PN16.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
497 | 410_PF_SS_uConnectorwithFlangeandSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
498 | 410_PF_SS_uConnector_SocketAndThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
499 | 410_PF_SS_uCoupling_ThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
500 | 410_PF_SS_uExpansionSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
501 | 410_PF_SS_uPeakPressure_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
502 | 410_PF_SS_uRatStop_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
503 | 410_PF_SS_uRepairCoupling_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
504 | 410_PF_SS_uSocketClamp_Special.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
505 | 410_PF_SS_uSocketClamp_Twopiece.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
506 | 410_PF_SS_uStraightCoupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
507 | 410_PF_SS_uUnion_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
508 | 410_PF_SS_wCleaningPipes.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
509 | 410_PF_SS_xCornerBranch87Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
510 | 410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
511 | 410_PF_SS_xDoubleBranch87_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
512 | 410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
513 | 410_PF_ST_SanpressDoubleWallPane_Threaded_DN15.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
514 | 410_PF_UPVC_cCap_FemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
515 | 410_PF_UPVC_cCap_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
516 | 410_PF_UPVC_eBend90Deg_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
517 | 410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
518 | 410_PF_UPVC_eElbow90Deg_FemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
519 | 410_PF_UPVC_eElbow_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
520 | 410_PF_UPVC_eReducerElbow_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
521 | 410_PF_UPVC_eShortBend90Deg_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
522 | 410_PF_UPVC_rBushReducing_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
523 | 410_PF_UPVC_rLongBushReducing_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
524 | 410_PF_UPVC_rShortBushReducing_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
525 | 410_PF_UPVC_tLateralTee90Deg_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
526 | 410_PF_UPVC_tTee90Deg_FemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
527 | 410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
528 | 410_PF_UPVC_tTee_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
529 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
530 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
531 | 410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
532 | 410_PF_UPVC_uCoupling_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
533 | 410_PF_UPVC_uInspectionPort_Glue.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
534 | 410_PF_UPVC_USiphon_Horizontal.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
535 | 410_PF_UPVC_xCross_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
536 | 410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
537 | 410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
538 | 410_PX_BasementFloorDrain_Vertical_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
539 | 410_PX_BoxGutters_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
540 | 410_PX_BoxGutters_Vertical_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
541 | 410_PX_DoppelPumpStationPowerlift_ACO.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
542 | 410_PX_DrainageChannel_B125.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
543 | 410_PX_DuofixElementForSinkAGB.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
544 | 410_PX_DuofixElementForWallHungWC.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
545 | 410_PX_DuofixElementForWallHungWC_BarrierFree.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
546 | 410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
547 | 410_PX_DuofixElementForWashbasin.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
548 | 410_PX_DuofixElementForWashBasin_BarrierFree.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
549 | 410_PX_DuofixElementInsetWashbasin_PillarTap.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
550 | 410_PX_DuofixForShower&Bathtub.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
551 | 410_PX_DuofixForShower&Bathtub_WallFittingAP.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
552 | 410_PX_DuofixForUrinal.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
553 | 410_PX_DuofixForUrinal_Universal.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
554 | 410_PX_DuofixSigmaToilet12cm_BarrierFree.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
555 | 410_PX_DuofixTraverseForStandaloneFaucetKitchenSink.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
556 | 410_PX_FaucetWithFlexibleHose.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
557 | 410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
558 | 410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
559 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
560 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
561 | 410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
562 | 410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
563 | 410_PX_FloorDrain_Horizontal_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
564 | 410_PX_FloorDrain_Horizontal_Coupling_Plastic.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
565 | 410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
566 | 410_PX_FloorDrain_VerticalFinor2PartL15_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
567 | 410_PX_FloorDrain_Vertical_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
568 | 410_PX_FloorDrain_Vertical_Coupling_Plastic.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
569 | 410_PX_FloorDrain_Vertical_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
570 | 410_PX_GardenWater_Kemper.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
571 | 410_PX_GreaseDisposalPoint.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
572 | 410_PX_GullyGrating.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
573 | 410_PX_HorizontalFloorDrain.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
574 | 410_PX_InspectionShaft_OnePipe_Nosystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
575 | 410_PX_InspectionShaft_TwoPipe_Nosystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
576 | 410_PX_KitchenTap.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
577 | 410_PX_ManholeAdjustingUnits_Round_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
578 | 410_PX_ManholeBase_CastIn.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
579 | 410_PX_ManholeChamberUnits_Round_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
580 | 410_PX_ManholeCoverSlabs_Eccentrical_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
581 | 410_PX_ManholeReducingSlabs_Eccentrical_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
582 | 410_PX_ManholeTaper_EccentricalCones_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
583 | 410_PX_Manhole_Round.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
584 | 410_PX_ReusedRainWaterTank.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
585 | 410_PX_RoadGully.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
586 | 410_PX_SumpPit_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
587 | 410_PX_TapWithMaleHose_Threaded_DN15.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
588 | 410_PX_WaterTap.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
589 | 410_SE_Conlit150U_NoSystem.rfa | Sanitary Revit Family | SE | .rfa | 1 | MEP | DIG
590 | 410_SE_ConlitFireProtectionSleeve_NoSystem.rfa | Sanitary Revit Family | SE | .rfa | 1 | MEP | DIG
591 | 410_SE_CoverBox.rfa | Sanitary Revit Family | SE | .rfa | 1 | MEP | DIG
592 | 474_ME_AirSamplingPump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
593 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC12kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
594 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC1kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
595 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC3kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
596 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC6kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
597 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC14kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
598 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC4d5kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
599 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC8kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
600 | 474_ME_Cabinet_ExtinguishingWaterSupply.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
601 | 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
602 | 474_ME_Cabinet_FlushMountedWall.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
603 | 474_ME_Compressor.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
604 | 474_ME_ControlBox_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
605 | 474_ME_CylinderTank_FM200.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
606 | 474_ME_CylinderWithCylinderValve_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
607 | 474_ME_DieselPump_FloorSurface_AURORA481.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
608 | 474_ME_EndSuctionFirePump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
609 | 474_ME_FE_AutomaticDryPowerCeiling_HFC17_NoSystem.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
610 | 474_ME_FireExtinguisherCarbonDioxide.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
611 | 474_ME_FireExtinguisherPortable_Foam.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
612 | 474_ME_FireExtinguisherPortable_Powder.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
613 | 474_ME_FireHoseReel_WallSurface.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
614 | 474_ME_FirePump_Horizontal_SplitCase.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
615 | 474_ME_FireValveBox.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
616 | 474_ME_FoamBladderTank_HorizontalType.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
617 | 474_ME_FoamBladderTank_VerticalType.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
618 | 474_ME_FoamPump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
619 | 474_ME_HorizontalPresssureTank.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
620 | 474_ME_JockeyPump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
621 | 474_ME_JunctionBox_VESDA.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
622 | 474_ME_MasterCylinderWithTopValveOfActuator_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
623 | 474_ME_NitrogenPilotCylinderWithTopValve.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
624 | 474_ME_ProtectiveCabinetWithVentilationValve.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
625 | 474_ME_ReceiverTank.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
626 | 474_ME_SlaveCylinderWithTopOfValve_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
627 | 474_ME_SolventTank.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
628 | 474_ME_VerticalFirePump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
629 | 474_PA_3WayBronzeGlobeValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
630 | 474_PA_AerationVentilationValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
631 | 474_PA_AirMaintenanceCompressorAssembly.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
632 | 474_PA_AirVentValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
633 | 474_PA_AlarmCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
634 | 474_PA_AlarmCheckValve_Dry.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
635 | 474_PA_AlarmCheckValve_European.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
636 | 474_PA_AlarmCheckValve_Preaction.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
637 | 474_PA_AlarmPressureSwitch.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
638 | 474_PA_AlarmTestModuleGrooveEnd.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
639 | 474_PA_AlarmTestModulePressureReliefValve_ThreadEnd.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
640 | 474_PA_AlarmTestModuleThreadEnd.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
641 | 474_PA_AngleHoseValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
642 | 474_PA_AutoConvertAssembly.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
643 | 474_PA_AutoDrainValve_FloatType_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
644 | 474_PA_AutomaticConcentrateControlValve_Foam.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
645 | 474_PA_BallValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
646 | 474_PA_BallValvesThreadandThread.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
647 | 474_PA_BallValves_GrooveAndGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
648 | 474_PA_BrassBodyBallValves_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
649 | 474_PA_ButterflyValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
650 | 474_PA_ButterflyValveSupervisedOpen.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
651 | 474_PA_CheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
652 | 474_PA_CheckValveAlternateWetDrySystem.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
653 | 474_PA_CS_BalancingValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
654 | 474_PA_CS_GateValveWithElectricActuator.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
655 | 474_PA_CS_YStrainer_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
656 | 474_PA_CurrentDetector.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
657 | 474_PA_CurrentDetector_ZoneCheck.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
658 | 474_PA_CylinderValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
659 | 474_PA_DelugeValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
660 | 474_PA_DiaphragmValves.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
661 | 474_PA_DischargeValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
662 | 474_PA_DoubleDoorCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
663 | 474_PA_DryAccelerator.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
664 | 474_PA_DryPilotActuator_.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
665 | 474_PA_DuplexPressureGauges.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
666 | 474_PA_FileLockBallValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
667 | 474_PA_FireHoseAngleValveWithCap.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
668 | 474_PA_FireLockAlarmCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
669 | 474_PA_FlexibleMetalHose.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
670 | 474_PA_FlowTestMeter_Flange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
671 | 474_PA_Flushing_Connection.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
672 | 474_PA_FM200_ActuatorBox.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
673 | 474_PA_FM200_DischagePressureSwitch.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
674 | 474_PA_FM200_SectorValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
675 | 474_PA_FM200_SectorValve_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
676 | 474_PA_FM200_SolenoidValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
677 | 474_PA_FoamLineProportioner.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
678 | 474_PA_Foam_AutomaticControlValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
679 | 474_PA_Foam_DuctileIron_DelugeValve_AngleStype.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
680 | 474_PA_Foam_InLineBalancedPressureProportioners.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
681 | 474_PA_FootValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
682 | 474_PA_GateValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
683 | 474_PA_HighPressureCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
684 | 474_PA_HighPressureRiserCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
685 | 474_PA_HydrantGateValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
686 | 474_PA_InlineCheckValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
687 | 474_PA_LevelControlValves_Flange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
688 | 474_PA_LevelControlValves_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
689 | 474_PA_MaintenanceUnit.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
690 | 474_PA_ManifoldCheckValve_FM200.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
691 | 474_PA_ManifoldCheckValve_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
692 | 474_PA_ManifoldCheckValve_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
693 | 474_PA_ManuallyActuatedBallValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
694 | 474_PA_ManualPneumaticActuator_FM200.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
695 | 474_PA_NRSOS&YGateValvesGrooveandFlange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
696 | 474_PA_NRSOS&YGateValvesGrooveandGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
697 | 474_PA_NRSOS&YGateValves_GrooveAndGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
698 | 474_PA_OS&YGateValves_GrooveAndFlange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
699 | 474_PA_OS&YGateValves_GrooveAndGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
700 | 474_PA_PressureGauge_AnalogueType.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
701 | 474_PA_PressureGauge_withBallValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
702 | 474_PA_PressureMeter.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
703 | 474_PA_PressureOperatedDirectionalValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
704 | 474_PA_PressureReducingControlValveThread.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
705 | 474_PA_PressureReducingControlValve_Groove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
706 | 474_PA_PressureReducingValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
707 | 474_PA_PressureReliefControlValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
708 | 474_PA_PressureReliefValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
709 | 474_PA_PressureSensor.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
710 | 474_PA_PressureSwitch_FM200.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
711 | 474_PA_RiserCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
712 | 474_PA_RubberExpansionJoint_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
713 | 474_PA_RubberExpansionJoint_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
714 | 474_PA_SafertyReliefValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
715 | 474_PA_SafetyValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
716 | 474_PA_SelectorValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
717 | 474_PA_ShutoffValve_Motorized.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
718 | 474_PA_SightGlasses.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
719 | 474_PA_SolenoidValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
720 | 474_PA_SS_CompoundPressureGauge.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
721 | 474_PA_StoneCatcher.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
722 | 474_PA_SwingCheckValve_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
723 | 474_PA_WaterflowSwitches.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
724 | 474_PA_WaterMeter.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
725 | 474_PA_ZoneControlRiserModule_Residential.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
726 | 474_PF_ CarbonSteel_LowProfileSprinklerTee_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
727 | 474_PF_CarbonSteel_AdapterNipple_Flanged.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
728 | 474_PF_CarbonSteel_LateralTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
729 | 474_PF_CarbonSteel_LateralThread_Standard.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
730 | 474_PF_CarbonSteel_OutletTeeReducing_Coupling.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
731 | 474_PF_CarbonSteel_OutletTeeReducing_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
732 | 474_PF_CarbonSteel_ReducingLateralTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
733 | 474_PF_CarbonSteel_TeeGroovedEnd_Standard.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
734 | 474_PF_CarbonSteel_TeeReducing_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
735 | 474_PF_CastIron_Cap_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
736 | 474_PF_Castiron_Cross_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
737 | 474_PF_CastIron_Elbow_Threaded_ShortBend.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
738 | 474_PF_Castiron_HexNipple.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
739 | 474_PF_CastIron_Reducer_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
740 | 474_PF_CastIron_SocketUnion_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
741 | 474_PF_CastIron_TeeReducing_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
742 | 474_PF_CastIron_Tee_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
743 | 474_PF_CastIron_Union_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
744 | 474_PF_CS_cCap_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
745 | 474_PF_CS_eElbowEndOfRun_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
746 | 474_PF_CS_eElbow_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
747 | 474_PF_CS_fConnection_Coupling_FireLockEZRigid.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
748 | 474_PF_CS_fConnection_Coupling_FireLockRigid.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
749 | 474_PF_CS_rConcentricReducer_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
750 | 474_PF_CS_rEccentricReducer_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
751 | 474_PF_CS_tOutletReducingCouplingTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
752 | 474_PF_CS_tSprinkerTeeCoupling_Grooved_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
753 | 474_PF_CS_tTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
754 | 474_PF_CS_uAdaptorNipple_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
755 | 474_PF_CS_wTrueWye_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
756 | 474_PF_CS_xCross_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
757 | 474_PF_DuctileIron_CapFemale_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
758 | 474_PF_DuctileIron_DrainElbow_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
759 | 474_PF_DuctileIron_SmallReducer_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
760 | 474_PF_GalvanizedSteel_NippleReducer_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
761 | 474_PF_SS_eUnionElbow_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
762 | 474_PF_SS_sHaftCoupling.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
763 | 474_PF_StainlessSteel_FlexibleCoupling_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
764 | 474_PROMAT_4Sided_Horizontal_CeilingMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
765 | 474_PROMAT_4Sided_Horizontal_Vertical_CeilingMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
766 | 474_PROMAT_4Sided_Vertical_CeilingMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
767 | 474_PROMAT_Horizontal_Vertical_WallMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
768 | 474_PROMAT_Horizontal_WallMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
769 | 474_PROMAT_Vertical_WallMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
770 | 474_SP_DischargeNozzle_CO2.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
771 | 474_SP_FM200_180RadialNozzle_2Port.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
772 | 474_SP_FM200_360RadialNozzle_1Port.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
773 | 474_SP_FM200_360RadialNozzle_4Port.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
774 | 474_SP_FM200_DischargeNozzle.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
775 | 474_SP_FoamNozzle_Pendent.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
776 | 474_SP_FoamNozzle_Upright.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
777 | 474_SP_GE_DoubleSprinkler.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
778 | 474_SP_GE_HorizontalSideWall.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
779 | 474_SP_GE_HVSprayNozzles.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
780 | 474_SP_GE_Pendent.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
781 | 474_SP_GE_PendentCover.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
782 | 474_SP_GE_SprayNozzles.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
783 | 474_SP_GE_Upright.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
784 | 474_SP_GE_UprightCover.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
785 | 474_SP_GE_WindowOpenNozzle.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
786 | SAN_GraphicalAnnotationFramework.pdf | Graphical Annotation Framework - SAN | SAN | .pdf | 1 | MEP | DIG | bar: 2026-01-30
787 | SPR_GraphicalAnnotationFramework.pdf | Graphical Annotation Framework - SPR | SPR | .pdf | 1 | MEP | DIG | bar: 2026-01-30
788 | SAN_DataRequirementFramework.xlsx | Data Requirement Framework - SAN | SAN | .xlsx | 1 | MEP | DIG | bar: 2026-01-30
789 | SPR_DataRequirementFramework.xlsx | Data Requirement Framework - SPR | SPR | .xlsx | 1 | MEP | DIG | bar: 2026-01-30
790 | RFA_RevisionProcess.pdf | Process to revise RFA library (SAN & SPR) |  | .pdf | 1 | MEP | DIG | bar: 2026-01-30
791 | SAN_RFA_Library_Update.zip | Updated SAN family library package | SAN | .zip | 1 | MEP | DIG
792 | SPR_RFA_Library_Update.zip | Updated SPR family library package | SPR | .zip | 1 | MEP | DIG
793 | SAN_LPH_ViewTemplates.rte | View templates for LPH (SAN) | SAN | .rte | 1 | MEP | DIG
794 | SPR_LPH_ViewTemplates.rte | View templates for LPH (SPR) | SPR | .rte | 1 | MEP | DIG
795 | AuditPublishSupportSolution.py | Digital solution to control use / publish / audit |  |  | 1 | MEP | DIG
796 | Revizto_3DReview_SAN_SPR.pdf | Revizto export + 3D review setup report SAN |  | .pdf | 2 | MEP | DIG
|  | Revizto export + 3D review setup report SPR |  | .pdf | 1 | MEP | DIG
797 | SharedLibrary_PublishLog_SAN_SPR.xlsx | Publish log and audit trail for shared library |  | .xlsx | 3 | MEP | DIG