## TIDP 410_Rev 04
PROJECT: DCMvn Annotation
DOCUMENT: DCMvn_SAN_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP)
NO: | NAME | Category | DESCRIPTION | FILE TYPE | CREATED BY | AUTHORISED BY | Batch | 2026-01-30 | 2026-02-27 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30
A | Framework deliverables |  |  |  | MEP | DIG |  |  |  | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
1 | Define the "Graphical Annotation Framework" SAN
|  |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 0 | 2026-01-30: TRM
|  |  | Fill the content for SAN discipline | .xlsx | MEP | DIG | 0 | 2026-01-30: TRM
|  |  | Confirm and sign the document | .pdf | MEP | DIG | 0
2 | Define the "Data Requirement Framework" SAN
|  |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 0 | 2026-01-30: TRM
|  |  | Fill the content for SAN discipline | .xlsx | MEP | DIG | 0 | 2026-02-27: TRM
|  |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | 2026-05-22: TRM
3 | Define the process to revise the RFA library
|  |  | Confirm and sign the process document | .pdf | MEP | DIG | 0 | 2026-05-22: TRM
|  |  | Workshop the process with delivery team | .pptx | DIG | DIG | 0 | 2026-02-27: TRM
B | Revise the RFA library for SAN system |  |  |  | MEP | DIG
| SAN Discipline |  | 591 Families need to be revise
B.1 | PF_Pipe Fitting |  | 330 | .rfa | MEP | DIG
1 | 410_PF_CI_tBranch68Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
2 | 410_PF_CI_uCleaningPipeWithRoundCover_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
3 | 410_PF_CI_uCleaningPipeWithRectangularcover_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
4 | 410_PF_CI_xCombinationBranch88Degree_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
5 | 410_PF_CI_uDownPipeBracket_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
6 | 410_PF_CI_rEccentricReducer_WithoutCoupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
7 | 410_PF_CI_cPlug_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
8 | 410_PF_CI_eRainwaterSiphon_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
9 | 410_PF_CI_uSMLRainwaterSiphonVertical_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
10 | 410_PF_cHDPE_BlindFlange_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
11 | 410_PF_CI_fAngleDoubleBranch88Degree_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
12 | 410_PF_CI_uBearing.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
13 | 410_PF_CI_tBranch45Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
14 | 410_PF_CI_tBranch45Deg_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
15 | 410_PF_CI_cPushinPlug_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
16 | 410_PF_CI_xDoubleBranch_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
17 | 410_PF_CI_eAccessBendLong_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
18 | 410_PF_CI_eAccessBendShort_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
19 | 410_PF_CI_eBend15Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
20 | 410_PF_CI_eBend30Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
21 | 410_PF_CI_eBend68Degree_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
22 | 410_PF_CI_eBend88Degree_SpigotAndClamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
23 | 410_PF_CI_eBend88Deg_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
24 | 410_PF_CI_eBendWC_Clamp_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22: TRM; 2026-05-29: AUD; 2026-06-05: REV; 2026-06-12: CFM
25 | 410_PF_CI_eBend_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
26 | 410_PF_CI_eBend_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
27 | 410_PF_CI_eBend_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
28 | 410_PF_CI_eConectionBend_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
29 | 410_PF_CI_eDoubleBend45Deg_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
30 | 410_PF_CI_xDoubleBend88Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
31 | 410_PF_CI_eDoubleBend88Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
32 | 410_PF_CI_eOffsetBend130_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
33 | 410_PF_CI_eOffsetBend200_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
34 | 410_PF_CI_eOffsetBend65_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
35 | 410_PF_CI_ePlainTrap_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
36 | 410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
37 | 410_PF_CI_eRestBend88_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
38 | 410_PF_CI_eVentilationBend88Axial_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
39 | 410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
40 | 410_PF_CI_eGutterAngleUniversal.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
41 | 410_PF_CI_cGutterCap_ExternalStopEnd.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
42 | 410_PF_CI_cGutterCap_InternalStopEnd.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
43 | 410_PF_CI_eGutterElbow_ExternalDropEndOutlet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
44 | 410_PF_CI_eGutterElbow_InternalDropEndOutlet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
45 | 410_PF_CI_mGutterHalfRound.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
46 | 410_PF_CI_tGutterTee_RunningOutlet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
47 | 410_PF_CI_uGutterUnionConnector.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
48 | 410_PF_CI_mShortPipeRectangularAccessDoor_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
49 | 410_PF_CI_mVerticalTrap_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
50 | 410_PF_CI_rEccentricReducer_WithoutCoupling | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
51 | 410_PF_CI_rEccentricReducer_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
52 | 410_PF_CI_rReducingEccentric_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
53 | 410_PF_CI_tBranch45_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
54 | 410_PF_CI_tBranch70_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
55 | 410_PF_CI_tBranch88Deg_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
56 | 410_PF_CI_tBranch88Deg_Coupling_HOST.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-12: REV; 2026-06-19: CFM
57 | 410_PF_CI_tBranch88Long_Spigot_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
58 | 410_PF_CI_tBranch88_Spigot_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
59 | 410_PF_CI_tCombinationBranch90_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
60 | 410_PF_CI_tCornerBranch88_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
61 | 410_PF_CI_tSweptEntryBranch88_Spigot_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
62 | 410_PF_CI_uShortPipeRoundAccessDoor_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
63 | 410_PF_CI_uTrapHorizontal_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
64 | 410_PF_CI_xDoubleBranch45_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
65 | 410_PF_CI_xDoubleBranch70Deg_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
66 | 410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
67 | 410_PF_CS_cEndCaps_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
68 | 410_PF_CS_eLongRadiusElbows_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
69 | 410_PF_CS_eLongRadiusReturnBends_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
70 | 410_PF_CS_eRadiusElbows_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
71 | 410_PF_CS_fPlaneFlange_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
72 | 410_PF_CS_rConcentricReducers_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
73 | 410_PF_CS_rConnector_MapressAndFemaleThread.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
74 | 410_PF_CS_uConnector_MapressAndFemaleThread.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
75 | 410_PF_DI_cBellmouth_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
76 | 410_PF_DI_cBlind_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
77 | 410_PF_DI_cCap_KType.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
78 | 410_PF_DI_cPlug_TType.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
79 | 410_PF_DI_eBend_Flange.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
80 | 410_PF_DI_eBend_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
81 | 410_PF_DI_eDuckfoodBend90Deg_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
82 | 410_PF_DI_fFlange_RFType.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
83 | 410_PF_DI_rFlangedCover.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
84 | 410_PF_DI_uConnector_FlangedAndSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
85 | 410_PF_DI_fFlange_Spigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
86 | 410_PF_DI_rTapper_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
87 | 410_PF_DI_rTapper_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
88 | 410_PF_DI_tLevelInvertTee_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
89 | 410_PF_DI_tTee_SocketAndFlangedBranch.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
90 | 410_PF_DI_tTeeSocketWithLevelInvertFlangedBranch.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
91 | 410_PF_DI_tTee_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
92 | 410_PF_DI_tTee_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
93 | 410_PF_DI_uAdaptorRestrained_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
94 | 410_PF_DI_uFlangeAdaptor.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
95 | 410_PF_DI_uUnion_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-19: REV; 2026-06-25: CFM
96 | 410_PF_DI_tDoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
98 | 410_PF_EPDM_mKonfixConnector_PushOnJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
99 | 410_PF_eSweptBendLong_Medium_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
100 | 410_PF_HDPE_fLooseFlange_Flanged.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
101 | 410_SE_FireCollar_Horizontal.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
102 | 410_SE_FireCollar_Vertical.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
103 | 410_PF_GS_cFrogFlap_Socket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
104 | 410_PF_GS_cSealingPlugsWithVentilationSlots_PushOnJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
105 | 410_PF_GS_eAngleBend_1PushShortSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
106 | 410_PF_GS_eAngleBend_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
107 | 410_PF_GS_eBasinConnector_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
108 | 410_PF_GS_eBendWithCalm_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
109 | 410_PF_GS_eBend_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
110 | 410_PF_GS_eBend_NoSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
111 | 410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
112 | 410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
113 | 410_PF_GS_eReductionAngleBend_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
114 | 410_PF_GS_uGutterRound_SocketAndStandard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
115 | 410_PF_GS_mOptimisationPart_1PushSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
116 | 410_PF_GS_mSBendTrap_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
117 | 410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
118 | 410_PF_GS_rAdapterConcentric_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
119 | 410_PF_GS_rAdapterEccentric_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
120 | 410_PF_GS_rConcentricOptimiser_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
121 | 410_PF_GS_rTransitiontoCastIron_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
122 | 410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
123 | 410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
124 | 410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
125 | 410_PF_GS_tTeeBranches_2PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
126 | 410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
127 | 410_PF_GS_uBends_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
128 | 410_PF_GS_uGutterPipes_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
129 | 410_PF_GS_uLongCleaningOpening_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
130 | 410_PF_GS_uLongCleaningOpening_NoSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
131 | 410_PF_GS_uLongUnion_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
132 | 410_PF_GS_uSpigottoPlastic_1PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
133 | 410_PF_GS_uTransitionSMLtoGMX_1PushSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
134 | 410_PF_GS_uTranstiontoCastIron_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
135 | 410_PF_GS_uUnion_2PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
136 | 410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12: TRM; 2026-06-19: AUD; 2026-06-25: REV; 2026-07-03: CFM
137 | 410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
138 | 410_PF_HDPE_cProtectionCap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
139 | 410_PF_HDPE_cProtectionCapForPipeEnd_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
140 | 410_PF_HDPE_cThreadedConnectorWithScrewCap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
141 | 410_PF_HDPE_eBend90Deg_Reducer_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
142 | 410_PF_HDPE_eBend_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
143 | 410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
144 | 410_PF_HDPE_eBend88DegWithLateralSupplementary_Standard_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
145 | 410_PF_HDPE_eConnectionBend90DegForSleeve_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
146 | 410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
147 | 410_PF_HDPE_eRightOffsetBend90Deg_Standard_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
148 | 410_PF_HDPE_eScrewCap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
149 | 410_PF_HDPE_eSegmentBend_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
150 | 410_PF_HDPE_tDoubleConnectionBend90Deg_ForSleeve.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
151 | 410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
152 | 410_PF_HDPE_tDoubleConnectionBend90Deg_SlipJoint_VerticalForWallHungWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
153 | 410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
154 | 410_PF_HDPE_mRunningTrap_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
155 | 410_PF_HDPE_mSoventFitting_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
156 | 410_PF_HDPE_mSTrap_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
157 | 410_PF_HDPE_mUniversalTrap_WithFlangeBushing.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
158 | 410_PF_HDPE_mWasteManifold.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
159 | 410_PF_HDPE_rAdaptorSocket_DN90xDN100.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
160 | 410_PF_HDPE_rCompressionJoint_MechanicalJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
161 | 410_PF_HDPE_rReducer_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
162 | 410_PF_HDPE_mReducedRingSealSocket_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
163 | 410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
164 | 410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
165 | 410_PF_HDPE_tLateralTee_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
166 | 410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
167 | 410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
168 | 410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
169 | 410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
170 | 410_PF_HDPE_uAdapterUnion_FemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
171 | 410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
172 | 410_PF_HDPE_rReducerAdaptor_MaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
173 | 410_PF_HDPE_uClampingConnector.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
174 | 410_PF_HDPE_uExpansion_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
175 | 410_PF_HDPE_uFlangeAdapter_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
176 | 410_PF_HDPE_uFlangeBushing_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
177 | 410_PF_HDPE_uFlangeSet.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
178 | 410_PF_HDPE_uStraightAdapterToCastIronPipe.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
179 | 410_PF_HDPE_uStraightAdapterHDPEToPVC_ButtFusionAndPushOnJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
180 | 410_PF_HDPE_uStraightAdapter_CompressionAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
181 | 410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
182 | 410_PF_HDPE_uStraightConnectorForWC_ButtFusionAndPushOnJoint.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
183 | 410_PF_HDPE_uStraightConnector_ForFloorStandingWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
184 | 410_PF_HDPE_uUnion_FemaleThreadAndCompression.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
185 | 410_PF_HDPE_uUnionConnection_WeldingJoints.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
186 | 410_PF_HDPE_xDoubleBrandFitting45Deg_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
187 | 410_PF_GA_mPTrapGMX_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
188 | 410_PF_HDPE_mPTrap.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
189 | 410_PF_PE_eBendForWandWC.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
190 | 410_PF_PPR_cEndCap_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
191 | 410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
192 | 410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
193 | 410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
194 | 410_PF_PPR_eElbow_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
195 | 410_PF_PPR_rCoupling_FemaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
196 | 410_PF_PPR_mCoupling_MaleThreadAndSocketFusion | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
197 | 410_PF_PPR_eElbow90Deg_MaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
198 | 410_PF_PPR_rReducing_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
199 | 410_PF_PPR_tTee_FemaleThreadedAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
200 | 410_PF_PPR_tTee_MaleThreadedAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
201 | 410_PF_PPR_tTee_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
202 | 410_PF_PPR_mCoupling_FemaleThreadAndSocketFusion | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
203 | 410_PF_PPR_uCoupling_MaleThreadAndSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
204 | 410_PF_PPR_uUnion_BushSocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
205 | 410_PF_PPR_uUnion_SocketFusion.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
206 | 410_PF_PPMD_xDuctBranchSweptEntry88DegLeft_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
207 | 410_PF_PPMD_tBranchSweptEntry88Deg_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
208 | 410_PF_PPMD_tDoubleConnectionBend90Deg_Extended_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
209 | 410_PF_PP_uAccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
210 | 410_PF_EPDM_mSleeveToCastIron_MechanicalJoint_Silent | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
211 | 410_PF_PPMD_eBend_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
212 | 410_PF_PP_tBranch_SocketSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
213 | 410_PF_PPMD_cEndCap_Socket_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
214 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
215 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
216 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
217 | 410_PF_PP_mOdorTrapForSinkHorizontal_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
218 | 410_PF_PP_mOdorTrapForSinkVertical_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
219 | 410_PF_PP_mOdorTrapForSinkVerticalAndHorizontal_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
220 | 410_PF_PPMD_wParallelBrand45Deg_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
221 | 410_PF_PPMD_rReducerEccentric_SocketAndSpigot_Silent.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
222 | 410_PF_PP_uSilentSlipCoupling_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
223 | 410_PF_SilentPro_cCapEnd_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
224 | 410_PF_PPMX_eElbow_SocketAndSpigot_SilentPro.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
225 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_SilentPro.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
226 | 410_PF_PPMD_mCornerBranch88Deg_SocketAndSpigot_SilentPro.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
227 | 410_PF_PPMX_rReducerEccentric_SocketAndSpigot_SilentPro.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
228 | 410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
229 | 410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
230 | 410_PF_SilentPro_tTeeBranch_SocketSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
231 | 410_PF_PPMD_uAccessPipe90DegWithRoundServiceOpening_SocketAndSpigot_SilentPro.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
232 | 410_PF_PPMX_uSlipCoupling_PushOnJoint_SilentPro.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
233 | 410_PF_PPMX_wParallelBrand45Deg_SocketAndSpigot_SilentPro.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
234 | 410_PF_SilentPro_xCrossDoubleBranchFitting88DegSweptEntry_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
235 | 410_PF_SS_uUnion_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
236 | 410_PF_SS_cCap_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
237 | 410_PF_SS_cDrainplugWithScrewedPlug.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
238 | 410_PF_SS_cSocketPlug.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
239 | 410_PF_SS_cSocketPlugWithClamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
240 | 410_PF_SS_cVentCowl_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
241 | 410_PF_SS_eBend45Degrees_SocketAndStandard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
242 | 410_PF_SS_eBend87_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
243 | 410_PF_SS_eBendWith250mmOblong_Clamp.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
244 | 410_PF_SS_eBend_15_1Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
245 | 410_PF_SS_eBend_30_1Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
246 | 410_PF_SS_eElbow90DegAdaptor_FemaleThreadedAndPlainEndAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
247 | 410_PF_SS_eElbow90DegAdaptor_MaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
248 | 410_PF_SS_eElbow90DegTapConnector_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
249 | 410_PF_SS_eElbow90Deg_FemaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
250 | 410_PF_SS_eElbowTapConector90Degree_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
251 | 410_PF_SS_eElbow_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
252 | 410_PF_SS_eLongBend_1Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
253 | 410_PF_SS_ePTrap_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
254 | 410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
255 | 410_PF_SS_mCornerElbow90Deg_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
256 | 410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-17: REV; 2026-07-24: CFM
257 | 410_PF_SS_uRapid_Coupling.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
258 | 410_PF_SS_rConcentricIncreaserCoupling_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
259 | 410_PF_SS_rConnectorExternalThreadSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
260 | 410_PF_SS_rConnectorInternal_ThreadSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
261 | 410_PF_SS_rConnectorWithSocketAndFlange.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
262 | 410_PF_SS_rConnector_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
263 | 410_PF_SS_rConnector_SocketAndThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
264 | 410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
265 | 410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
266 | 410_PF_SS_rReducerWithPlainEnd_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
267 | 410_PF_SS_rTransition_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
268 | 410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
269 | 410_PF_SS_tTPiece_Mapress_Equal | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
270 | 410_PF_SS_tReducingDoubleBranch45_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
271 | 410_PF_SS_tReducingSingleBranch45Degree_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
272 | 410_PF_SS_tReducingSingleBranch87Deg_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
273 | 410_PF_SS_tSingleBranch45_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
274 | 410_PF_SS_tSweptBranch87Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
275 | 410_PF_SS_tTeePiece_FemaleThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
276 | 410_PF_SS_tTeePiece_MaleThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
277 | 410_PF_SS_tTeePiece_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
278 | 410_PF_SS_tPieceReducer_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
279 | 410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
280 | 410_PF_SS_uAdaptorUnion_MaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
281 | 410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
282 | 410_PF_SS_uAdaptor_WithFemaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
283 | 410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
284 | 410_PF_SS_uAdaptor_WithMaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
285 | 410_PF_SS_uAdaptorWithPlainEnd_MaleThreadAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
286 | 410_PF_SS_uAxialExpansion_PressingSockets.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
287 | 410_PF_SS_uBulkhead_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
288 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndWelded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
289 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndMapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
290 | 410_PF_SS_uConnector_FlangedAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
291 | 410_PF_SS_uConnector_SocketAndThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
292 | 410_PF_SS_uCoupling_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
293 | 410_PF_SS_uExpansionSocket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
294 | 410_PF_SS_uPeakPressure_Standard.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
295 | 410_PF_SS_uRatStop_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
296 | 410_PF_SS_uRepairCoupling_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
297 | 410_PF_SS_uSocketClamp_Special.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
298 | 410_PF_SS_uSocketClamp_Twopiece.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
299 | 410_PF_SS_uStraightCoupling_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
300 | 410_PF_SS_uUnion_Mapress.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
301 | 410_PF_SS_wCleaningPipes.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
302 | 410_PF_SS_xCornerBranch87Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
303 | 410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
304 | 410_PF_SS_xDoubleBranch87_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
305 | 410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
306 | 410_PF_ST_SanpressDoubleWallPane_Threaded_DN15.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
307 | 410_PF_UPVC_cCap_FemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
308 | 410_PF_UPVC_cCap_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
309 | 410_PF_UPVC_eBend90Deg_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
310 | 410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
311 | 410_PF_UPVC_eElbow90Deg_FemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
312 | 410_PF_UPVC_eElbow_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
313 | 410_PF_UPVC_eReducerElbow_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
314 | 410_PF_UPVC_eShortBend90Deg_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
315 | 410_PF_UPVC_rBushReducing_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
316 | 410_PF_UPVC_rLongBushReducing_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
317 | 410_PF_UPVC_rShortBushReducing_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
318 | 410_PF_UPVC_tLateralTee90Deg_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
319 | 410_PF_UPVC_tTee90Deg_FemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
320 | 410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
321 | 410_PF_UPVC_tTee_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
322 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
323 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
324 | 410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
325 | 410_PF_UPVC_uCoupling_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
326 | 410_PF_UPVC_uInspectionPort_Glue.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
327 | 410_PF_UPVC_uSiphon_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
328 | 410_PF_UPVC_xCross_Socket.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
329 | 410_PF_CS_eRadiusReturnBends_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
330 | 410_PF_CS_tTee_Welded.rfa | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
B.2 | PA + NF |  | 101 | .rfa | MEP | DIG
1 | 410_NF_GS_rConcentric_NoSocket_GMX.rfa | 410_NF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
2 | 410_PA_Adapter&ExpansionPiece_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
3 | 410_PA_AirReleaseValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
4 | 410_PA_AngleSafetyValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
5 | 410_PA_AngleSeatPistonValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
6 | 410_PA_AngleSeatPistonValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
7 | 410_PA_AngleValve_Threaded_WithRegulatingFunction.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
8 | 410_PA_AutomaticBackwashFilter_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
9 | 410_PA_AutomaticCirculationRegulatingValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
10 | 410_PA_AutomaticHygieneFlushingStationHS10_Geberit.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
11 | 410_PA_BackflowPreventerValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
12 | 410_PA_BackflowPreventer_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
13 | 410_PA_BallValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
14 | 410_PA_BallValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
15 | 410_PA_CoarseTrap.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
16 | 410_PA_CombinationAngleValve_Standard.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
17 | 410_PA_DiaphragmValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
18 | 410_PA_DoubleInstallationRackWatermeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
19 | 410_PA_DrainValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
20 | 410_PA_FillSetStandardValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
21 | 410_PA_FillsoftHousing_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
22 | 410_PA_Filter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
23 | 410_PA_FittingSpacerForWaterMeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
24 | 410_PA_FlexibleConnection_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
25 | 410_PA_FloatingValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
26 | 410_PA_FlowSplitterBox_Floor_Threaded_KHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
27 | 410_PA_FlowSplitterSet_Threaded_KHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
28 | 410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
29 | 410_PA_FlowSplitterUnit_Threaded_DynamicKHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
30 | 410_PA_FlowTemperatureMeterValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
31 | 410_PA_FlushMountedStopValve_Mapress_UpPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
32 | 410_PA_FlushMoutedStopValve_Threaded_UpPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
33 | 410_PA_FunnelSiphon_Horizontal.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
34 | 410_PA_GateValveSealingDirectionWithDrain_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
35 | 410_PA_GateValveWithDrain_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
36 | 410_PA_GateValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
37 | 410_PA_GateValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
38 | 410_PA_GlobeValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
39 | 410_PA_GlobeValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
40 | 410_PA_KHSFlushPoint_Threaded_230V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
41 | 410_PA_KHSFlushPoint_Threaded_24V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
42 | 410_PA_KHSFlushPoint_Threaded_ControlPlus230V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
43 | 410_PA_KHSFlushPoint_Threaded_ControlPlus24V.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
44 | 410_PA_KugelSiphon_Standard.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
45 | 410_PA_MotorButterflyValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
46 | 410_PA_NozzleCheckValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
47 | 410_PA_OutletValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
48 | 410_PA_OutletValve_Threaded_WithHoseScrewConnection.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-07: REV; 2026-08-14: CFM
49 | 410_PA_PoolMainDrain_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
50 | 410_PA_PoolReturnJet_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
51 | 410_PA_PoolSkimmer_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
52 | 410_PA_BallValve_SocketFusion.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
53 | 410_PA_StopValve_SocketFusion.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
54 | 410_PA_PressureGauge.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
55 | 410_PA_PressureGauge_WithSiphon.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
56 | 410_PA_PressureReducingValveFilterCombination_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
57 | 410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
58 | 410_PA_PressureReducingValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
59 | 410_PA_PressureReducingValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
60 | 410_PA_PressureRegulator_Thread.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
61 | 410_PA_SamplingValveForWashBasinAngleValve_Standard_SS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
62 | 410_PA_SamplingValve_Standard_Gunmetal.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
63 | 410_PA_SamplingValve_Standard_SS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
64 | 410_PA_ShutoffValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
65 | 410_PA_ShutoffValve_Flanged_DrainValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
66 | 410_PA_ShutoffValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
67 | 410_PA_ShutoffValve_WithDrainPlug_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
68 | 410_PA_SingleInstallationRackWatermeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
69 | 410_PA_SolenoidControlValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
70 | 410_PA_ShutoffValve_Mapress_WithDrainValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
71 | 410_PA_ShutoffValve_MapressGeberit.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
72 | 410_PA_StraightSafetyValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
73 | 410_PA_StaticBalancingValve_Threaded_MultiFixPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
74 | 410_PA_StaticBalancingValve_UnionThreaded_MultiFixPlus.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
75 | 410_PA_SwingcheckValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
76 | 410_PA_SwingcheckValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
77 | 410_PA_SystemSeparator_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
78 | 410_PA_SystemSeparator_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
79 | 410_PA_TemperatureMeasuringValve_Threaded_KHS.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
80 | 410_PA_THandleBallValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
81 | 410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
82 | 410_PA_ThreePiecesBallValve_Welded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
83 | 410_PA_ThreeWayMotorisedControlValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
84 | 410_PA_ThreeWayMotorisedControlValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
85 | 410_PA_TwoWayDiaphragmValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
86 | 410_PA_TwoWayDiaphragmValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
87 | 410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
88 | 410_PA_UpETATHERMThermostaticBalancingValve_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
89 | 410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
90 | 410_PA_UPVSenkrecht.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
91 | 410_PA_UPConcealedShutoffValve.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
92 | 410_PA_VAVFullFlowShutOffValve_FemaleThreaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
93 | 410_PA_VentCowl.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
94 | 410_PA_WaferButterflyValve_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
95 | 410_PA_WaterHammerArrestor_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
96 | 410_PA_WaterMeterUNI.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
97 | 410_PA_WaterMeter_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
98 | 410_PA_WaterMeter_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
99 | 410_PA_YStrainer_Flanged.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
100 | 410_PA_YStrainer_Threaded.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
101 | 410_PA_ZBCapRoof_Standard.rfa | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
B.3 | PX_Plumbing Fixure |  | 53 | .rfa | MEP | DIG
1 | 410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
2 | 410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
3 | 410_PX_BasementFloorDrain_Vertical_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
4 | 410_PX_StainlessSteelBoxGutters_Horizontal_Coupling.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
5 | 410_PX_BoxGutters_Vertical_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
6 | 410_PX_DoppelPumpStationPowerlift_ACO.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
7 | 410_PX_DrainageChannel_B125.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
8 | 410_PX_DuofixElementForSinkAGB.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
9 | 410_PX_DuofixElementForWallHungWC.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
10 | 410_PX_DuofixElementForWallHungWC_BarrierFree.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
11 | 410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
12 | 410_PX_DuofixElementForWashbasin.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
13 | 410_PX_DuofixElementForWashBasin_BarrierFree.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
14 | 410_PX_DuofixElementInsetWashbasin_PillarTap.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
15 | 410_PX_DuofixForShower&Bathtub.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
16 | 410_PX_DuofixForShower&Bathtub_WallFittingAP.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
17 | 410_PX_DuofixForUrinal.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
18 | 410_PX_DuofixForUrinal_Universal.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
19 | 410_PX_DuofixSigmaToilet12cm_BarrierFree.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
20 | 410_PX_DuofixTraverseForStandaloneFaucetKitchenSink.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
21 | 410_PX_FaucetWithFlexibleHose.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
22 | 410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
23 | 410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
24 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
25 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
26 | 410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
27 | 410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
28 | 410_PX_FloorDrain_Horizontal_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
29 | 410_PX_FloorDrain_Horizontal_Coupling_Plastic.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
30 | 410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
31 | 410_PX_FloorDrain_VerticalFinor2PartL15_Coupling_CastIron.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
32 | 410_PX_CastIronFloorDrain_Vertical_Coupling.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
33 | 410_PX_FloorDrain_Vertical_Coupling_Plastic.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
34 | 410_PX_FloorDrain_Vertical_Coupling_StainlessSteel.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
35 | 410_PX_GardenWater_Kemper.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
36 | 410_PX_GreaseDisposalPoint.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
37 | 410_PX_GullyGrating.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
38 | 410_PX_HorizontalFloorDrain.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
39 | 410_PX_InspectionShaft_OnePipe_Nosystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
40 | 410_PX_InspectionShaft_TwoPipe_Nosystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
41 | 410_PX_KitchenTap.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
42 | 410_PX_ManholeAdjustingUnits_Round_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
43 | 410_PX_ManholeBase_CastIn.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
44 | 410_PX_ManholeChamberUnits_Round_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
45 | 410_PX_ManholeCoverSlabs_Eccentrical_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
46 | 410_PX_ManholeReducingSlabs_Eccentrical_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
47 | 410_PX_ManholeTaper_EccentricalCones_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
48 | 410_PX_Manhole_Round.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
49 | 410_PX_ReusedRainWaterTank.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
50 | 410_PX_RoadGully.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
51 | 410_PX_SumpPit_NoSystem.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
52 | 410_PX_TapWithMaleHose_Threaded_DN15.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
53 | 410_PX_WaterTap.rfa | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
B.4 | SE |  | 3 | .rfa | MEP | DIG
1 | 410_SE_Conlit150U_NoSystem.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
2 | 410_SE_ConlitFireProtectionSleeve_NoSystem.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
3 | 410_SE_CoverBox.rfa | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
B.5 | ME |  | 104 | .rfa | MEP | DIG
1 | 410_ME_CentrifugalPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
2 | 410_ME_CompactPressureBoostingSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
3 | 410_ME_CompactPressureBoostingSystem_1MVISE.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
4 | 410_ME_CompactWaterHeater_WallMounted.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
5 | 410_ME_Desoftening.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
6 | 410_ME_DoppelHebeanlageSchmutzwasser.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
7 | 410_ME_DoublePressureBoosterSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
8 | 410_ME_DrainLiftL_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
9 | 410_ME_DrainLiftM_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
10 | 410_ME_DrainLiftS_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14: TRM; 2026-08-21: AUD; 2026-08-28: REV; 2026-09-04: CFM
11 | 410_ME_DrainLiftXL_Floor.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
12 | 410_ME_DualTank_WaterSofteners.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
13 | 410_ME_DuplexSofteningUnit_RondomatDuo.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
14 | 410_ME_EKleindurchlauferhitzerCEX.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
15 | 410_ME_EKleindurchlauferhitzer_MCX.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
16 | 410_ME_ElectricInstantaneousHeater_DLE.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
17 | 410_ME_ExpansionVessel.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
18 | 410_ME_ExpansionVessel_Reflex.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
19 | 410_ME_FettabscheiderNG2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
20 | 410_ME_FreshWaterStation.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
21 | 410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
22 | 410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
23 | 410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
24 | 410_ME_GreaseSeparatorFreeStandingInstallationNS10.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
25 | 410_ME_GreaseSeparator_FloorStand.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
26 | 410_ME_HighPerformanceIndustrialMixers.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
27 | 410_ME_HotWaterStorageTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
28 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
29 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
30 | 410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
31 | 410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
32 | 410_ME_IBCTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
33 | 410_ME_iboxUniversalForShower_WallRecessed.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
34 | 410_ME_InstantaneousWaterHeater_Shower.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
35 | 410_ME_InstantaneousWaterHeater_SinkAGB.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
36 | 410_ME_InstantaneousWaterHeater_TeaKitchen.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
37 | 410_ME_InstantaneousWaterHeater_WashBasin.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
38 | 410_ME_KHSHygieneFlushBoxLITE_FlowSensorDoublePortwithThreaded.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
39 | 410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
40 | 410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
41 | 410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
42 | 410_ME_KHSHygieneFlushBoxPUREwithFlowSensorSinglePort_Threaded.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21: TRM; 2026-08-28: AUD; 2026-09-04: REV; 2026-09-11: CFM
43 | 410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
44 | 410_ME_KHSMiniControlSystemSLAVE_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
45 | 410_ME_KHSMiniControlSystem_WallSurface_Master.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
46 | 410_ME_KHSTimer_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
47 | 410_ME_MiniTresorCabinet_InWall.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
48 | 410_ME_MiniTresorCabinet_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
49 | 410_ME_MixingTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
50 | 410_ME_PHController.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
51 | 410_ME_PlasticInnerTankSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
52 | 410_ME_PoolHeatPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
53 | 410_ME_PoolSandFilter_FloorStand_Round.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
54 | 410_ME_PressureBoosterPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
55 | 410_ME_PressurisationUnit_FixedSpeedUnits2Pump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
56 | 410_ME_PressurisationUnit_FixedSpeedUnits3Pump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
57 | 410_ME_PressurisationUnit_VariableSpeedUnits3Pump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
58 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith1Pump | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
59 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
60 | 410_ME_Probenahmetopf.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
61 | 410_ME_PumpGlandlessCirculator_StarZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
62 | 410_ME_PumpGlandlessCirculator_StarZD.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
63 | 410_ME_PumpGlandlessCirculator_TopZ.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
64 | 410_ME_PureWaterTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
65 | 410_ME_ReverseOsmosisSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
66 | 410_ME_SeparationStation.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
67 | 410_ME_ServiceStorageTank_Round.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
68 | 410_ME_Sicherheitstrennstation.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
69 | 410_ME_SinglePressureBoosterSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
70 | 410_ME_StratosMAXOZPump_Vertical.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
71 | 410_ME_StratosPICOZPump_Vertical.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
72 | 410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
73 | 410_ME_SubmergedPump_Horizontal_SatSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
74 | 410_ME_SubmergedPump_SitaSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28: TRM; 2026-09-04: AUD; 2026-09-11: REV; 2026-09-18: CFM
75 | 410_ME_SubmergedPump_Vertical_SATSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
76 | 410_ME_SubmergedPump_Vertical_SATVSeries.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
77 | 410_ME_TresorCabinet_InWall.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
78 | 410_ME_TresorCabinet_WallSurface.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
79 | 410_ME_TripleSofteningSystem_DeltaP.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
80 | 410_ME_TWPressureBoosterSystem.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
81 | 410_ME_VerticaltubeHeatexchanger.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
82 | 410_ME_WasteWaterLiftingStationPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
83 | 410_ME_WastewaterLiftingStation_DouPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
84 | 410_ME_WasteWaterLiftingStation_KesselPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
85 | 410_ME_WastewaterLiftingStation_MuliPES&Mono.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
86 | 410_ME_WastewaterLiftingStation_MuliProPEKDuo.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
87 | 410_ME_WastewaterLiftingStation_MuliProPEKParallel.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
88 | 410_ME_WastewaterLiftingStation_MuliProPENXLDuo.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
89 | 410_ME_WastewaterLiftingStation_MuliStarDDP.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
90 | 410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
91 | 410_ME_WastewaterLiftingStation_Sinkamat-HW.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
92 | 410_ME_WasteWaterLiftingStation_VerticalPump.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
93 | 410_ME_WasteWaterLift_Floor_C3.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
94 | 410_ME_WasteWaterLift_Floor_CWC3.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
95 | 410_ME_WasteWaterLift_Floor_D2.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
96 | 410_ME_WasteWaterLift_Floor_WC1.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
97 | 410_ME_WasteWaterLift_Floor_WC3.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
98 | 410_ME_WaterDispenser_FloorStand.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
99 | 410_ME_WaterFilterTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
100 | 410_ME_WaterFilterVertical.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
101 | 410_ME_WaterHardnessMeter.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
102 | 410_ME_WaterHeaterWithTap_WallMounted.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
103 | 410_ME_WaterHeater_WallMounted.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
104 | 410_ME_WaterSofteningTank.rfa | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
C | Create the Revit templates for each LPH SAN |  |  |  | MEP | DIG
TGA_Revit Template
1 | LPH3 |  | Revit Template | .rte | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
2 | LPH5 |  | Revit Template | .rte | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
3 | LPH8 |  | Revit Template | .rte | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
D | TGA_OUtput Checklists
1 | LPH3 Check list for SAN discipline |  |  | .xlsx | MEP | DIG
2 | LPH3_Check list_SAN 01 |  | Define Checklist_layout Plan. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
3 | LPH3_Check list_SAN 02 |  | Define Checklist_Isometric Drawing. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
4 | LPH3_Check list_SAN 03 |  | Define Checklist_Schematic Diagram. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
5 | LPH5 Check list for SAN discipline |  |  | .xlsx | MEP | DIG
6 | LPH5_Check list_SAN 01 |  | Define Checklist_layout Plan. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
8 | LPH5_Check list_SAN 02 |  | Define Checklist_Isometric Drawing. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
9 | LPH5_Check list_SAN 03 |  | Define Checklist_Schematic Diagram. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
10 | LPH8 Check list for SAN discipline |  |  | .xlsx | MEP | DIG
11 | LPH8_Check list_SAN 01 |  | Define Checklist_layout Plan. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
13 | LPH8_Check list_SAN 02 |  | Define Checklist_Isometric Drawing. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
14 | LPH8_Check list_SAN 03 |  | Define Checklist_Schematic Diagram. |  | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
E | Sample Model + Out Put Data |  |  |  | MEP | DIG
Sample Model + Out Put Data For SAN
1 | Delivery layout Sample for SAN LPH3 |  | Execute a sample layout for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
2 | Delivery layout Sample for SAN LPH5 |  | Execute a sample layout for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
3 | Delivery layout Sample for SAN LPH8 |  | Execute a sample layout for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
4 | Delivery Schematic Drawing Sample for SAN LPH3 |  | Execute a sample schematic for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
5 | Delivery Schematic Drawing Sample for SAN LPH5 |  | Execute a sample schematic for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
6 | Delivery Isometric Drawing Sample for SAN LPH3 |  | Execute a sample Isometric for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
7 | Delivery Isometric Drawing Sample for SAN LPH5 |  | Execute a sample Isometric for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
F | Export layouts to Revizto & set up 3D Review SAN |  |  |  | MEP | DIG
1 | Export layouts to Revizto & set up 3D Review SAN _LPH3 |  |  | .pdf | MEP | DIG |  | 2026-09-18: TRM; 2026-09-25: REV; 2026-09-30: CFM
2 | Export layouts to Revizto & set up 3D Review SAN _LPH5 |  |  | .pdf | MEP | DIG |  | 2026-09-18: TRM; 2026-09-25: REV; 2026-09-30: CFM
3 | Export layouts to Revizto & set up 3D Review SAN _LPH8 |  |  | .pdf | MEP | DIG |  | 2026-09-18: TRM; 2026-09-25: REV; 2026-09-30: CFM
G | Lesson Learned |  |  |  | MEP | DIG
| Lesson Learned SAN |  | What went well. What didn’t go well What we learned, Action items / Improvements | .pdf | MEP | DIG |  | 2026-09-25: TRM; 2026-09-30: CFM
Legend:
TRM | Transmittal / Submitted | MEP
AUD | Audit/Review | DIG
REV | Revision Required / Revised | MEP
CFM | Confimmation/Confirmed & Stored | DIG/MEP