## TIDP 473 & 474
PROJECT: DCMvn Annotation
DOCUMENT: DCMvn_SPR & MED_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP)
NO: | STATUS | DESCRIPTION: | FILE TYPE: | CREATED BY: | AUTHORISED BY: | 2026-01-30 | 2026-02-27 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30
1 | Define the "Graphical Annotation Framework" | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 2026-02-27: TRM
|  | Fill the content for SPR disciplines | .xlsx | MEP | DIG | 2026-02-27: TRM
|  | Confirm and sign the document | .pdf | MEP | DIG | 2026-02-27: TRM
2 | Define the "Data Requirement Framework" | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 2026-05-29: TRM; 2026-06-25: TRM; 2026-07-31: TRM
|  | Fill the content for SPR disciplines | .xlsx | MEP | DIG | 2026-05-29: TRM; 2026-06-25: TRM; 2026-07-31: TRM
|  | Confirm and sign the document | .pdf | MEP | DIG | 2026-05-29: TRM; 2026-06-25: TRM; 2026-07-31: TRM
3 | Define the process to revise the RFA library | Confirm and sign the process document | .pdf | MEP | DIG | 2026-05-29: TRM; 2026-06-25: TRM; 2026-07-31: TRM
|  | Workshop the process with delivery team | .pptx | DIG | DIG | 2026-02-27: TRM
4 | Revit Template for SPR in LPH3 |  | .rte | MEP/DIG | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
5 | Revit Template for SPR in LPH5 |  | .rte | MEP/DIG | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
6 | Revit Template for SPR in LPH8 |  | .rte | MEP/DIG | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
7 | Revit Template for MED in LPH3 |  |  |  |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
8 | Revit Template for MED in LPH5 |  |  |  |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
9 | Revit Template for MED in LPH8 |  |  |  |  | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
10 | LPH3_Check list_SPR 01 | Checklist_layout Plan. | .xlsx | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
11 | LPH3_Check list_SPR 02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
12 | LPH3_Check list_SPR 03 | Checklist_Isometric Drawing. | .xlsx | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
13 | LPH3_Check list_SPR 04 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-03: REV; 2026-07-10: CFM
14 | LPH5_Check list_SPR01 | Checklist_layout Plan. | .xlsx | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
15 | LPH5_Check list_SPR02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
16 | LPH5_Check list_SPR03 | Checklist_Isometric Drawing. | .xlsx | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
17 | LPH5_Check list_SPR04 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-24: REV; 2026-07-31: CFM
18 | LPH8_Check list_SPR01 | Checklist_layout Plan. | .xlsx | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
19 | LPH8_Check list_SPR02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
20 | LPH8_Check list_SPR03 | Checklist_Isometric Drawing. | .xlsx | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
21 | LPH8_Check list_SPR04 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-14: REV; 2026-08-21: CFM
22 | LPH3_Check list_MED_01 | Checklist_layout Plan. | .xlsx | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
23 | LPH3_Check list_MED_02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
24 | LPH3_Check list_MED_03 | Checklist_Isometric Drawing. | .xlsx | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
25 | LPH3_Check list_MED_04 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-10: REV; 2026-07-17: CFM
26 | LPH5_Check list_MED_01 | Checklist_layout Plan. | .xlsx | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
27 | LPH5_Check list_MED_02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
28 | LPH5_Check list_MED_03 | Checklist_Isometric Drawing. | .xlsx | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
29 | LPH5_Check list_MED_04 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-07-31: REV; 2026-08-07: CFM
30 | LPH8_Check list_MED_01 | Checklist_layout Plan. | .xlsx | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
31 | LPH8_Check list_MED_02 | Checklist_Section. | .xlsx | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
32 | LPH8_Check list_MED_03 | Checklist_Isometric Drawing. | .xlsx | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
33 | LPH8_Check list_MED_04 | Checklist_Schematic Diagram. | .xlsx | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-21: REV; 2026-08-28: CFM
34 | Delivery layout Sample for SPR LPH3 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
35 | Delivery layout Sample for SPR LPH5 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
36 | Delivery layout Sample for SPR LPH8 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
37 | Delivery Schematic Drawing Sample for SPR LPH3 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
38 | Delivery Schematic Drawing Sample for SPR LPH5 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
39 | Delivery Schematic Drawing Sample for SPR LPH8 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
40 | Delivery Isometric Drawing Sample for SPR LPH3 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
41 | Delivery Isometric Drawing Sample for SPR LPH5 |  | .pdf | MEP | DIG | 2026-09-04: TRM; 2026-09-11: AUD; 2026-09-18: REV; 2026-09-25: CFM
42 | Delivery layout Sample for MED LPH3 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
43 | Delivery layout Sample for MED LPH5 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
44 | Delivery layout Sample for MED LPH8 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
45 | Delivery Schematic Drawing Sample for MED LPH3 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
46 | Delivery Schematic Drawing Sample for MED LPH5 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
47 | Delivery Schematic Drawing Sample for MED LPH8 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
48 | Delivery Isometric Drawing Sample for MED LPH3 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
49 | Delivery Isometric Drawing Sample for MED LPH5 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
50 | Export layouts to Revizto & set up 3D Review_LPH3 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
51 | Export layouts to Revizto & set up 3D Review_LPH5 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
52 | Export layouts to Revizto & set up 3D Review_LPH8 |  | .pdf | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
53 | Lesson Learns | What went well. | .doc | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
|  | What didn’t go well | .doc | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
|  | What we learned | .doc | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
|  | Action items / Improvements | .doc | MEP | DIG | 2026-09-11: TRM; 2026-09-18: AUD; 2026-09-25: REV; 2026-09-30: CFM
54 |  | 474_SP_GE_WindowOpenNozzle | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
55 |  | 474_ME_AirSamplingPump | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
56 |  | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC1kg | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
57 |  | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC3kg | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
58 |  | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC6kg | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
59 |  | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC12kg | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
60 |  | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC4d5kg | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
61 |  | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC8kg | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
62 |  | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC14kg | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
63 |  | 474_ME_Cabinet_ExtinguishingWaterSupply | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
64 |  | 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
65 |  | 474_ME_Cabinet_FlushMountedWall | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
66 |  | 474_ME_Compressor | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
67 |  | 474_ME_ControlBox_CO2 | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
68 |  | 474_ME_CylinderTank_FM200 | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
69 |  | 474_ME_CylinderWithCylinderValve_CO2 | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
70 |  | 474_PA_AirMaintenanceCompressorAssembly | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
71 |  | 474_ME_EndSuctionFirePump | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
72 |  | 474_ME_FE_AutomaticDryPowerCeiling_HFC17_NoSystem | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
73 |  | 474_ME_FireExtinguisherCarbonDioxide | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
74 |  | 474_ME_FireExtinguisherPortable_Foam | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
75 |  | 474_ME_FireExtinguisherPortable_Powder | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
76 |  | 474_ME_FireHoseReel_WallSurface | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
77 |  | 474_ME_FirePump_Horizontal_SplitCase | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
78 |  | 474_ME_FireValveBox | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
79 |  | 474_ME_FoamBladderTank_HorizontalType | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
80 |  | 474_ME_FoamBladderTank_VerticalType | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
81 |  | 474_ME_FoamPump | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
82 |  | 474_ME_HorizontalPresssureTank | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
83 |  | 474_ME_JockeyPump | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
84 |  | 474_ME_JunctionBox_VESDA | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
85 |  | 474_ME_MasterCylinderWithTopValveOfActuator_CO2 | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
86 |  | 474_ME_NitrogenPilotCylinderWithTopValve | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
87 |  | 474_PA_AlarmCheckValve | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
88 |  | 474_PA_AlarmPressureSwitch | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
89 |  | 474_ME_SlaveCylinderWithTopOfValve_CO2 | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
90 |  | 474_ME_SolventTank | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
91 |  | 474_ME_VerticalFirePump | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
92 |  | 474_PA_3WayBronzeGlobeValve | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
93 |  | 474_PA_AerationVentilationValve | .rfa | MEP | DIG | 2026-05-29: TRM; 2026-06-05: AUD; 2026-06-19: REV; 2026-06-25: CFM
94 |  | 474_PF_CS_tLowProfileSprinklerTee_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
95 |  | 474_PF_CS_uAdapterNipple_Flanged | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
96 |  | 474_PF_CS_tLateralTee_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
97 |  | 474_PF_CS_tLateralThread_Standard | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
98 |  | 474_PF_CS_tOutletTeeReducing_Coupling | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
99 |  | 474_PF_CS_tOutletReducingTee_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
100 |  | 474_PF_CS_tReducingLateralTee_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
101 |  | 474_PF_CS_tGroovedEndTee_Standard | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
102 |  | 474_PF_CS_tReducingTee_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
103 |  | 474_PF_CI_cCap_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
104 |  | 474_PF_CI_xCross_Thread | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
105 |  | 474_PF_CI_eShortBend_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
106 |  | 474_PF_CI_uHexNipple | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
107 |  | 474_PF_CI_rReducer_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
108 |  | 474_PF_CI_xSocketUnion_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
109 |  | 474_PF_CI_tEqualTee_Thread | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
110 |  | 474_PF_CI_tTeeReducing_Thread | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
111 |  | 474_PF_CI_uUnion_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
112 |  | 474_PF_CS_cCap_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
113 |  | 474_PF_CS_eElbow_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
114 |  | 474_PF_CS_eElbowEndOfRun_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
115 |  | 474_PF_CS_fConnection_Coupling_FireLockEZRigid | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
116 |  | 474_PF_CS_fConnection_Coupling_FireLockRigid | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
117 |  | 474_PF_CS_rConcentricReducer_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
118 |  | 474_PF_CS_rEccentricReducer_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
119 |  | 474_PF_CS_tOutletReducingCouplingTee_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
120 |  | 474_PF_CS_tSprinkerTeeCoupling_Grooved_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
121 |  | 474_PF_CS_tTee_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
122 |  | 474_PF_CS_uAdaptorNipple_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
123 |  | 474_PF_CS_wTrueWye_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
124 |  | 474_PF_CS_xCross_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
125 |  | 474_PF_DuctileIron_CapFemale_Thread | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
126 |  | 474_PF_DuctileIron_DrainElbow_Grooved | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
127 |  | 474_PF_DuctileIron_SmallReducer_Thread | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
128 |  | 474_PF_GalvanizedSteel_NippleReducer_Threaded | .rfa | MEP | DIG | 2026-06-05: TRM; 2026-06-12: AUD; 2026-06-25: REV; 2026-07-03: CFM
129 |  | 474_PF_SS_eUnionElbow_Threaded | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
130 |  | 474_PF_SS_sHaftCoupling | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
131 |  | 474_PF_StainlessSteel_FlexibleCoupling_Grooved | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
132 |  | 474_ME_DieselPump_FloorSurface_AURORA481 | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
133 |  | 474_PA_AirVentValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
134 |  | 474_ME_ProtectiveCabinetWithVentilationValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
135 |  | 474_PA_AlarmCheckValve_Dry | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
136 |  | 474_PA_AlarmCheckValve_European | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
137 |  | 474_PA_AlarmCheckValve_Preaction | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
138 |  | 474_ME_ReceiverTank | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
139 |  | 474_PA_AlarmTestModuleGrooveEnd | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
140 |  | 474_PA_AlarmTestModulePressureReliefValve_ThreadEnd | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
141 |  | 474_PA_AlarmTestModuleThreadEnd | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
142 |  | 474_PA_AngleHoseValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
143 |  | 474_PA_AutoConvertAssembly | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
144 |  | 474_PA_AutoDrainValve_FloatType_Threaded | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
145 |  | 474_PA_AutomaticConcentrateControlValve_Foam | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
146 |  | 474_PA_BallValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
147 |  | 474_PA_BallValves_GrooveAndGroove | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
148 |  | 474_PA_BallValvesThreadandThread | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
149 |  | 474_PA_BrassBodyBallValves_Threaded | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
150 |  | 474_PA_ButterflyValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
151 |  | 474_PA_ButterflyValveSupervisedOpen | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
152 |  | 474_PA_CheckValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
153 |  | 474_PA_CheckValveAlternateWetDrySystem | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
154 |  | 474_PA_CS_BalancingValve_Flanged | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
155 |  | 474_PA_GateValveWithElectricActuator | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
156 |  | 474_PA_CS_YStrainer_Grooved | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
157 |  | 474_PA_WaterFlowDetector | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
158 |  | 474_PA_WaterFlowDetector_ZoneCheck | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
159 |  | 474_PA_CylinderValve_CO2 | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
160 |  | 474_PA_DelugeValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
161 |  | 474_PA_DiaphragmValves | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
162 |  | 474_PA_DischargeValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
163 |  | 474_PA_DoubleDoorCheckValve | .rfa | MEP | DIG | 2026-06-12: TRM; 2026-06-19: AUD; 2026-07-03: REV; 2026-07-10: CFM
164 |  | 474_PA_DryAccelerator | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
165 |  | 474_PA_DryPilotActuator | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
166 |  | 474_PA_DuplexPressureGauges | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
167 |  | 474_PA_PressureReducingControlValve_Groove | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
168 |  | 474_PA_PressureReducingControlValveThread | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
169 |  | 474_PA_PressureReducingValve_Flanged | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
170 |  | 474_PA_PressureReliefControlValve | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
171 |  | 474_PA_PressureReliefValve | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
172 |  | 474_PA_PressureSensor | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
173 |  | 474_PA_PressureSwitch_FM200 | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
174 |  | 474_PA_RiserCheckValve | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
175 |  | 474_PA_RubberExpansionJoint_Flanged | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
176 |  | 474_PA_RubberExpansionJoint_Threaded | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
177 |  | 474_PA_SafertyReliefValve_CO2 | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
178 |  | 474_PA_SafetyValve | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
179 |  | 474_PA_SelectorValve_CO2 | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
180 |  | 474_PA_ShutoffValve_Motorized | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
181 |  | 474_PA_SightGlasses | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
182 |  | 474_PA_SolenoidValve | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
183 |  | 474_PA_SS_CompoundPressureGauge | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
184 |  | 474_PA_StoneCatcher | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
185 |  | 474_PA_SwingCheckValve_Grooved | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
186 |  | 474_PA_WaterflowSwitches | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
187 |  | 474_PA_WaterMeter | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
188 |  | 474_PA_ZoneControlRiserModule_Residential | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
189 |  | 474_PA_FireLockBallValve | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
190 |  | 474_PA_FireHoseAngleValveWithCap | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
191 |  | 474_PA_FireLockAlarmCheckValve | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
192 |  | 474_PA_FlexibleMetalHose | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
193 |  | 474_PA_FlowTestMeter_Flange | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
194 |  | 474_PA_Flushing_Connection | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
195 |  | 474_PA_FM200_ActuatorBox | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
196 |  | 474_PA_FM200_DischagePressureSwitch | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
197 |  | 474_PA_FM200_SectorValve_Flanged | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
198 |  | 474_PA_FM200_SectorValve_Threaded | .rfa | MEP | DIG | 2026-06-19: TRM; 2026-06-25: AUD; 2026-07-10: REV; 2026-07-17: CFM
199 |  | 474_PA_FM200_SolenoidValve | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
200 |  | 474_PA_Foam_AutomaticControlValve_Flanged | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
201 |  | 474_PA_Foam_DuctileIron_DelugeValve_AngleStype | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
202 |  | 474_PA_Foam_InLineBalancedPressureProportioners | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
203 |  | 474_PA_FoamLineProportioner | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
204 |  | 474_PA_FootValve | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
205 |  | 474_PA_GateValve | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
206 |  | 474_PA_HighPressureCheckValve | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
207 |  | 474_PA_HighPressureRiserCheckValve | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
208 |  | 474_PA_HydrantGateValve | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
209 |  | 474_PA_InlineCheckValve_CO2 | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
210 |  | 474_PA_LevelControlValves_Flange | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
211 |  | 474_PA_LevelControlValves_Grooved | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
212 |  | 474_PA_MaintenanceUnit | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
213 |  | 474_PA_ManifoldCheckValve_FM200 | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
214 |  | 474_PA_ManifoldCheckValve_Grooved | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
215 |  | 474_PA_ManifoldCheckValve_Threaded | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
216 |  | 474_PA_ManuallyActuatedBallValve_CO2 | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
217 |  | 474_PA_ManualPneumaticActuator_FM200 | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
218 |  | 474_PA_NRSOS&YGateValves_GrooveAndGroove | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
219 |  | 474_PA_NRSOS&YGateValves_GrooveandFlange | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
220 |  | 474_PA_OS&YGateValves_GrooveAndFlange | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
221 |  | 474_PA_OS&YGateValves_GrooveAndGroove | .rfa | MEP | DIG | 2026-06-25: TRM; 2026-07-03: AUD; 2026-07-17: REV; 2026-07-24: CFM
222 |  | 474_PA_PressureGauge_AnalogueType | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
223 |  | 474_PA_PressureGauge_withBallValve | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
224 |  | 474_PA_PressureMeter | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
225 |  | 474_PA_PressureOperatedDirectionalValve_CO2 | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
226 |  | 474_PROMAT_4Sided_Horizontal_CeilingMount | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
227 |  | 474_PROMAT_4Sided_Horizontal_Vertical_CeilingMount | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
228 |  | 474_PROMAT_4Sided_Vertical_CeilingMount | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
229 |  | 474_PROMAT_Horizontal_Vertical_WallMount | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
230 |  | 474_PROMAT_Horizontal_WallMount | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
231 |  | 474_PROMAT_Vertical_WallMount | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
232 |  | 474_SP_DischargeNozzle_CO2 | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
233 |  | 474_SP_FM200_180RadialNozzle_2Port | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
234 |  | 474_SP_FM200_360RadialNozzle_1Port | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
235 |  | 474_SP_FM200_360RadialNozzle_4Port | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
236 |  | 474_SP_FM200_DischargeNozzle | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
237 |  | 474_SP_FoamNozzle_Pendent | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
238 |  | 474_SP_FoamNozzle_Upright | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
239 |  | 474_SP_GE_DoubleSprinkler | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
240 |  | 474_SP_GE_HorizontalSideWall | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
241 |  | 474_SP_GE_HVSprayNozzles | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
242 |  | 474_SP_GE_Pendent | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
243 |  | 474_SP_GE_PendentCover | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
244 |  | 474_SP_GE_SprayNozzles | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
245 |  | 474_SP_GE_Upright | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
246 |  | 474_SP_GE_UprightCover | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
247 | Revise Family | 473_PF_CO_rReducer_FemaleSoldered | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
248 |  | 473_PF_CO_rReducerMF_Soldered | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
249 |  | 473_PF_CO_tEqualTee_FemaleSoldered | .rfa | MEP | DIG | 2026-07-03: TRM; 2026-07-10: AUD; 2026-07-24: REV; 2026-07-31: CFM
250 |  | 473_PF_CO_tTee_Reducing_FemaleSoldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
251 |  | 473_PF_CO_uCoupling_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
252 |  | 473_PF_CO_uOffsetFF_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
253 |  | 473_PF_SS_tTee_Welded | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
254 |  | 473_PF_SS_uClampConnector | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
255 |  | 473_PF_SS_uClampConnectorWithWeldedConnection | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
256 |  | 473_PF_CO_cEndCap_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
257 |  | 473_PF_CO_eElbow_Reduce_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
258 |  | 473_PF_CO_eElbow45_FemaleAndFemaleSoldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
259 |  | 473_PF_CO_eElbow45_MaleAndFemaleSoldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
260 |  | 473_PF_CO_eElbow180_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
261 |  | 473_PF_CO_eElbowLongRadiusFF_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
262 |  | 473_PF_CO_eElbowShortRadiusMF_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
263 |  | 473_PF_CO_eLongRadius_MFSoldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
264 |  | 473_PF_CO_eLongRadius_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
265 |  | 473_PF_CO_eOffset_M_F_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
266 |  | 473_PF_CO_eShortRadiusFF_Soldered | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
267 |  | 473_EF_BathroomCallUnit_PullCord | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
268 |  | 473_EF_BathroomCallUnit_PushButton | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
269 |  | 473_EF_BiomedicalCallPlugandSocket | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
270 |  | 473_EF_CallDisplayUnit | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
271 |  | 473_EF_CallTranferUnitForCorridors | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
272 |  | 473_EF_DoorUnit | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
273 |  | 473_EF_ElectronicBuzzer_WallSurface | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
274 |  | 473_EF_RemoteControlModules | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
275 |  | 473_EF_SocketForCordedPushButton_WallSurface | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
276 |  | 473_EF_SocketforHandPushButton | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
277 |  | 473_EF_TableControlUnit | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
278 |  | 473_PA_3WayMotorControlValve_Threaded | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
279 |  | 473_PA_AGSSOutletType1L | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
280 |  | 473_PA_AirHeader_8Connection | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
281 |  | 473_PA_AirHeader_10Connection | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
282 |  | 473_PA_AirHeader_12Connection | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
283 |  | 473_PA_AirHeader_14Connection | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
284 |  | 473_PA_AirHeader_16Connection | .rfa | MEP | DIG | 2026-07-10: TRM; 2026-07-17: AUD; 2026-07-31: REV; 2026-08-07: CFM
285 |  | 473_PA_AirHeader_18Connection | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
286 |  | 473_PA_AirPressureRegulator_Mapress | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
287 |  | 473_PA_AirRegulatorValve_Threaded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
288 |  | 473_PA_AirVentingFilters_Standard | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
289 |  | 473_PA_AutoDrainValve_FloatType_Threaded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
290 |  | 473_PA_AutomaticMechanicalCondensateDrain | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
291 |  | 473_PA_BallValve_Threaded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
292 |  | 473_PA_BR_3WayMotorControlValve_Threaded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
293 |  | 473_PA_BR_3WayValveDN15toDN50_Threaded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
294 |  | 473_PA_BR_AirReliefValve_Threaded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
295 |  | 473_PA_Brass_CheckValve_Threaded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
296 |  | 473_PA_ClampedStraightSightGlass | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
297 |  | 473_PA_CompressedAirFilters_DDp | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
298 |  | 473_PA_CompressedAirFilters_QDT | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
299 |  | 473_PA_CondensateDistributor2Branch_WOSCD | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
300 |  | 473_PA_CondensateDistributor4Branch_WOSCD | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
301 |  | 473_PA_CondensateDistributor8Branch_WOSCD | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
302 |  | 473_PA_CondensateDistributor12Branch_WOSCD | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
303 |  | 473_PA_CS_PressureReducingValve_Flanged | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
304 |  | 473_PA_CycloneSeparator_Standard | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
305 |  | 473_PA_ElectronicCondensateDrain | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
306 |  | 473_PA_ElectronicMotorizedValve | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
307 |  | 473_PA_Filters_Flanged | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
308 |  | 473_PA_Filters_Welded | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
309 |  | 473_PA_GasN2_Outlet | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
310 |  | 473_PA_GasO2Outlet | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
311 |  | 473_PA_LineBallValve_LV10_V | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
312 |  | 473_PA_LineBallValve_LV10VF | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
313 |  | 473_PA_LockableLineBallValve_LVL10 | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
314 |  | 473_PA_LockableLineBallValve_LVL20 | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
315 |  | 473_PA_LockableLineBallValve_NIST | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
316 |  | 473_PA_MembraneAirDryers | .rfa | MEP | DIG | 2026-07-17: TRM; 2026-07-24: AUD; 2026-08-07: REV; 2026-08-14: CFM
317 |  | 473_PA_MotorizedPneumaticDiaphragmValve_Welded | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
318 |  | 473_PA_N2OOutlet | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
319 |  | 473_PA_NRVValve | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
320 |  | 473_PA_PlasticBox_Air | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
321 |  | 473_PA_PneumaticButterflyValve_Welded | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
322 |  | 473_PA_PneumaticDiaphragmValveWithAlarm | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
323 |  | 473_PA_PneumaticManualDiaphragmValve | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
324 |  | 473_PA_PressureGauge_ElectricalContactCodeA | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
325 |  | 473_PA_RectangularPressureRegulator | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
326 |  | 473_PA_SafetyValve | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
327 |  | 473_PA_ShutOffValveBox_MultiConnection | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
328 |  | 473_PA_SingleZone_ValveBox | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
329 |  | 473_PA_SS_AirHeader_4Connection | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
330 |  | 473_PA_SS_AirHeader_6Connection | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
331 |  | 473_PA_SS_CouplingsFemale_Threaded | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
332 |  | 473_PA_SS_HighPressureProcessFilters_Welded | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
333 |  | 473_PA_SS_PressureGauge_AnalogueType | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
334 |  | 473_PA_SS_PressureReducingValve_Flanged | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
335 |  | 473_PA_SS_WeldedCondensateSeparators | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
336 |  | 473_PA_StainlessSteel1WayValve | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
337 |  | 473_PA_StainlessSteelFlexibleConnection | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
338 |  | 473_PA_SterileFilters_SFSeries_Flanged | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
339 |  | 473_PA_VAC_Outlet | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
340 |  | 473_PA_WaterOilSeparators_WOS | .rfa | MEP | DIG | 2026-07-24: TRM; 2026-07-31: AUD; 2026-08-14: REV; 2026-08-21: CFM
341 |  | 473_PA_WaterOilSeparators_WOSm | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
342 |  | 473_ME_ActivatedCarbonTower | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
343 |  | 473_ME_AirDryer | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
344 |  | 473_ME_AirDryer_Vertical | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
345 |  | 473_ME_AirPurifiers | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
346 |  | 473_ME_AirReceiverTank | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
347 |  | 473_ME_AreaAlarmPanel | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
348 |  | 473_ME_AutomatedH2O2AirlockAccessible | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
349 |  | 473_ME_BHU_DK2014 | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
350 |  | 473_ME_BHU_DK2014M | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
351 |  | 473_ME_BHU_HY2017 | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
352 |  | 473_ME_BHU_HY2017D | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
353 |  | 473_ME_BHU_HY2017DS | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
354 |  | 473_ME_BHU_SC2015 | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
355 |  | 473_ME_BHU_Vertical | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
356 |  | 473_ME_BottleFillingPlant | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
357 |  | 473_ME_CompactH2O2DecontaminationAirlock | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
358 |  | 473_ME_CylinderTank_NoSystem | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
359 |  | 473_ME_DesiccantAdsorptionCompressedAirDryers | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
360 |  | 473_ME_DryVacuumPump | .rfa | MEP | DIG | 2026-07-31: TRM; 2026-08-07: AUD; 2026-08-21: REV; 2026-08-28: CFM
361 |  | 473_ME_ExternalHeatRecoveryUnits | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
362 |  | 473_ME_HeatlessRegenerationAdsorptionDryers | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
363 |  | 473_ME_HeatlessRegenerationAdsorptionDryers_ActivatedCarbonTower | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
364 |  | 473_ME_HeatRegenerationAdsorptionDryers | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
365 |  | 473_ME_ICU_Eurocare | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
366 |  | 473_ME_ICU_EurocareD | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
367 |  | 473_ME_ICU_SMICare | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
368 |  | 473_ME_ICU_SMICAREDS | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
369 |  | 473_ME_IntensiveCareUnits_WallMounted_SMICAREDS | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
370 |  | 473_ME_IntensiveCareUnits_WallMounted_SMICareHD | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
371 |  | 473_ME_MedicalAirCompressors_FloorMounted | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
372 |  | 473_ME_MedicalAirCompressors_TankMounted | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
373 |  | 473_ME_NitrogenGenerators | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
374 |  | 473_ME_OxygenGenerators | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
375 |  | 473_ME_RefrigerationAirDryer_Flanged | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
376 |  | 473_ME_RefrigerationAirDryer_Threaded | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
377 |  | 473_ME_VacuumPump | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
378 |  | 473_ME_ZoneWallUnit_CZ200 | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
379 |  | 473_ME_ZoneWallUnit_HST100 | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
380 |  | 473_ME_ZoneWallUnit_HST200 | .rfa | MEP | DIG | 2026-08-07: TRM; 2026-08-14: AUD; 2026-08-28: REV; 2026-09-04: CFM
Legend:
TRM | Transmittal / Submitted | MEP
AUD | Audit/Review | DIG
REV | Revision Required / Revised | MEP
CFM | Confimmation/Confirmed & Stored | DIG/MEP

## TIDP Detail (hidden)
PROJECT: DCMvn Annotation
DOCUMENT: DCMvn_SAN&SPR_TIDP
TASK INFORMATION DELIVERY PLAN (TIDP)
NO: | NAME | DESCRIPTION: |  | FILE TYPE: | PRIORITY | CREATED BY: | AUDIT BY: | 2026-01-30 | 2026-02-27 | 2026-03-31 | 2026-04-29 | 2026-05-29 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-30 | 2026-11-30 | 2026-12-31 | 2027-01-29
1 | 410_CS_eRadiusReturnBends_Welded.rfa | Sanitary Revit Family | CS | .rfa | 1 | MEP | DIG | bar: 2026-02-27
2 | 410_CS_tTee_Welded.rfa | Sanitary Revit Family | CS | .rfa | 1 | MEP | DIG | bar: 2026-04-29
3 | 410_ME_CentrifugalPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG | bar: 2026-01-30
4 | 410_ME_CompactPressureBoostingSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
5 | 410_ME_CompactPressureBoostingSystem_1MVISE.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
6 | 410_ME_CompactWaterHeater_WallMounted.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
7 | 410_ME_Desoftening.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
8 | 410_ME_DoppelHebeanlageSchmutzwasser.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
9 | 410_ME_DoublePressureBoosterSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
10 | 410_ME_DrainLiftL_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
11 | 410_ME_DrainLiftM_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
12 | 410_ME_DrainLiftS_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
13 | 410_ME_DrainLiftXL_Floor.rfa | Sanitary Revit Family | ME | .rfa | 3 | MEP | DIG
14 | 410_ME_DualTank_WaterSofteners.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
15 | 410_ME_DuplexSofteningUnit_RondomatDuo.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
16 | 410_ME_EKleindurchlauferhitzerCEX.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
17 | 410_ME_EKleindurchlauferhitzer_MCX.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
18 | 410_ME_ElectricInstantaneousHeater_DLE.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
19 | 410_ME_ExpansionVessel.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
20 | 410_ME_ExpansionVessel_Reflex.rfa | Sanitary Revit Family | ME | .rfa | 2 | MEP | DIG
21 | 410_ME_FettabscheiderNG2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
22 | 410_ME_FreshWaterStation.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
23 | 410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
24 | 410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
25 | 410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
26 | 410_ME_GreaseSeparatorFreeStandingInstallationNS10.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
27 | 410_ME_GreaseSeparator_FloorStand.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
28 | 410_ME_HighPerformanceIndustrialMixers.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
29 | 410_ME_HotWaterStorageTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
30 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
31 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
32 | 410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
33 | 410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
34 | 410_ME_IBCTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
35 | 410_ME_iboxUniversalForShower_WallRecessed.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
36 | 410_ME_InstantaneousWaterHeater_Shower.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
37 | 410_ME_InstantaneousWaterHeater_SinkAGB.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
38 | 410_ME_InstantaneousWaterHeater_TeaKitchen.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
39 | 410_ME_InstantaneousWaterHeater_WashBasin.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
40 | 410_ME_KHSHygieneFlushBoxLITE_FlowSensorDoublePortwithThreaded.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
41 | 410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
42 | 410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
43 | 410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
44 | 410_ME_KHSHygieneFlushBoxPUREwithFlowSensorSinglePort_Threaded.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
45 | 410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
46 | 410_ME_KHSMiniControlSystemSLAVE_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
47 | 410_ME_KHSMiniControlSystem_WallSurface_Master.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
48 | 410_ME_KHSTimer_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
49 | 410_ME_MiniTresorCabinet_InWall.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
50 | 410_ME_MiniTresorCabinet_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
51 | 410_ME_MixingTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
52 | 410_ME_PHController.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
53 | 410_ME_PlasticInnerTankSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
54 | 410_ME_PoolHeatPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
55 | 410_ME_PoolSandFilter_FloorStand_Round.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
56 | 410_ME_PressureBoosterPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
57 | 410_ME_PressurisationUnit_FixedSpeedUnits2Pump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
58 | 410_ME_PressurisationUnit_FixedSpeedUnits3Pump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
59 | 410_ME_PressurisationUnit_VariableSpeedUnits3Pump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
60 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith1PumP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
61 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
62 | 410_ME_Probenahmetopf.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
63 | 410_ME_PumpGlandlessCirculator_StarZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
64 | 410_ME_PumpGlandlessCirculator_StarZD.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
65 | 410_ME_PumpGlandlessCirculator_TopZ.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
66 | 410_ME_PureWaterTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
67 | 410_ME_ReverseOsmosisSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
68 | 410_ME_SeparationStation.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
69 | 410_ME_ServiceStorageTank_Round.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
70 | 410_ME_Sicherheitstrennstation.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
71 | 410_ME_SinglePressureBoosterSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
72 | 410_ME_StratosMAXOZPump_Vertical.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
73 | 410_ME_StratosPICOZPump_Vertical.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
74 | 410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
75 | 410_ME_SubmergedPump_Horizontal_SatSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
76 | 410_ME_SubmergedPump_SitaSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
77 | 410_ME_SubmergedPump_Vertical_SATSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
78 | 410_ME_SubmergedPump_Vertical_SATVSeries.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
79 | 410_ME_TresorCabinet_InWall.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
80 | 410_ME_TresorCabinet_WallSurface.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
81 | 410_ME_TripleSofteningSystem_DeltaP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
82 | 410_ME_TWPressureBoosterSystem.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
83 | 410_ME_VerticaltubeHeatexchanger.rfa | Sanitary Revit Family | ME | .rfa | 2 | MEP | DIG
84 | 410_ME_WasteWaterLiftingStationPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
85 | 410_ME_WastewaterLiftingStation_DouPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
86 | 410_ME_WasteWaterLiftingStation_KesselPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
87 | 410_ME_WastewaterLiftingStation_MuliPES&Mono.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
88 | 410_ME_WastewaterLiftingStation_MuliProPEKDuo.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
89 | 410_ME_WastewaterLiftingStation_MuliProPEKParallel.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
90 | 410_ME_WastewaterLiftingStation_MuliProPENXLDuo.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
91 | 410_ME_WastewaterLiftingStation_MuliStarDDP.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
92 | 410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
93 | 410_ME_WastewaterLiftingStation_Sinkamat-HW.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
94 | 410_ME_WasteWaterLiftingStation_VerticalPump.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
95 | 410_ME_WasteWaterLift_Floor_C3.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
96 | 410_ME_WasteWaterLift_Floor_CWC3.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
97 | 410_ME_WasteWaterLift_Floor_D2.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
98 | 410_ME_WasteWaterLift_Floor_WC1.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
99 | 410_ME_WasteWaterLift_Floor_WC3.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
100 | 410_ME_WaterDispenser_FloorStand.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
101 | 410_ME_WaterFilterTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
102 | 410_ME_WaterFilterVertical.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
103 | 410_ME_WaterHardnessMeter.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
104 | 410_ME_WaterHeaterWithTap_WallMounted.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
105 | 410_ME_WaterHeater_WallMounted.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
106 | 410_ME_WaterSofteningTank.rfa | Sanitary Revit Family | ME | .rfa | 1 | MEP | DIG
107 | 410_NF_GS_rConcentric_NoSocket_GMX.rfa | Sanitary Revit Family | NF | .rfa | 1 | MEP | DIG
108 | 410_PA_Adapter&ExpansionPiece_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
109 | 410_PA_AirReleaseValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
110 | 410_PA_AngleSafetyValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
111 | 410_PA_AngleSeatPistonValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
112 | 410_PA_AngleSeatPistonValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
113 | 410_PA_AngleValve_Threaded_WithRegulatingFunction.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
114 | 410_PA_AutomaticBackwashFilter_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
115 | 410_PA_AutomaticCirculationRegulatingValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
116 | 410_PA_AutomaticHygieneFlushingStationHS10_Geberit.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
117 | 410_PA_BackflowPreventerValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
118 | 410_PA_BackflowPreventer_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
119 | 410_PA_BallValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
120 | 410_PA_BallValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
121 | 410_PA_CoarseTrap.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
122 | 410_PA_CombinationAngleValve_Standard.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
123 | 410_PA_DiaphragmValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
124 | 410_PA_DoubleInstallationRackWatermeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
125 | 410_PA_DrainValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
126 | 410_PA_FillSetStandardValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
127 | 410_PA_FillsoftHousing_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
128 | 410_PA_Filter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
129 | 410_PA_FittingSpacerForWaterMeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
130 | 410_PA_FlexibleConnection_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
131 | 410_PA_FloatingValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
132 | 410_PA_FlowSplitterBox_Floor_Threaded_KHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
133 | 410_PA_FlowSplitterSet_Threaded_KHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
134 | 410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
135 | 410_PA_FlowSplitterUnit_Threaded_DynamicKHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
136 | 410_PA_FlowTemperatureMeterValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
137 | 410_PA_FlushMountedStopValve_Mapress_UpPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
138 | 410_PA_FlushMoutedStopValve_Threaded_UpPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
139 | 410_PA_FunnelSiphon_Horizontal.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
140 | 410_PA_GateValveSealingDirectionWithDrain_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
141 | 410_PA_GateValveWithDrain_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
142 | 410_PA_GateValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
143 | 410_PA_GateValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
144 | 410_PA_GlobeValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
145 | 410_PA_GlobeValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
146 | 410_PA_KHSFlushPoint_Threaded_230V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
147 | 410_PA_KHSFlushPoint_Threaded_24V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
148 | 410_PA_KHSFlushPoint_Threaded_ControlPlus230V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
149 | 410_PA_KHSFlushPoint_Threaded_ControlPlus24V.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
150 | 410_PA_KugelSyphon_Standard.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
151 | 410_PA_MotorButterflyValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
152 | 410_PA_NozzleCheckValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
153 | 410_PA_OutletValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
154 | 410_PA_OutletValve_Threaded_WithHoseScrewConnection.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
155 | 410_PA_PoolMainDrain_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
156 | 410_PA_PoolReturnJet_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
157 | 410_PA_PoolSkimmer_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
158 | 410_PA_PPR_BallVale_SocketFusion.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
159 | 410_PA_PPR_StopVale_SocketFusion.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
160 | 410_PA_PressureGauge.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
161 | 410_PA_PressureGauge_withSiphon.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
162 | 410_PA_PressureReducingValveFilterCombination_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
163 | 410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
164 | 410_PA_PressureReducingValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
165 | 410_PA_PressureReducingValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
166 | 410_PA_PressureRegulator.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
167 | 410_PA_SamplingValveForWashBasinAngleValve_Standard_SS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
168 | 410_PA_SamplingValve_Standard_Gunmetal.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
169 | 410_PA_SamplingValve_Standard_SS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
170 | 410_PA_ShutoffValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
171 | 410_PA_ShutoffValve_Flanged_DrainValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
172 | 410_PA_ShutoffValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
173 | 410_PA_ShutoffValve_Withdrainplug.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
174 | 410_PA_SingleInstallationRackWatermeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
175 | 410_PA_SolenoidControlValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
176 | 410_PA_SS_ShutoffValve_Mapress_WithDrainValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
177 | 410_PA_StainlessSteel_ShutoffValve_MapressGeberit.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
178 | 410_PA_StraightSafetyValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
179 | 410_PA_ST_StaticBalancingValve_Threaded_MultiFixPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
180 | 410_PA_ST_StaticBalancingValve_UnionThreaded_MultiFixPlus.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
181 | 410_PA_SwingcheckValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
182 | 410_PA_SwingcheckValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
183 | 410_PA_SystemSeparator_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
184 | 410_PA_SystemSeparator_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
185 | 410_PA_TemperatureMeasuringValve_Threaded_KHS.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
186 | 410_PA_THandleBallValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
187 | 410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
188 | 410_PA_ThreePiecesBallValve_Welded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
189 | 410_PA_ThreeWayMotorisedControlValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
190 | 410_PA_ThreeWayMotorisedControlValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
191 | 410_PA_Two-WayDiaphragmValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
192 | 410_PA_TwoWayDiaphragmValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
193 | 410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
194 | 410_PA_UpETATHERMThermostaticBalancingValve_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
195 | 410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
196 | 410_PA_UPVSenkrecht.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
197 | 410_PA_UP_ConcealedShutoffValve.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
198 | 410_PA_VAVFullFlowShutOffValve_FemaleThreaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
199 | 410_PA_VentCowl.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
200 | 410_PA_WaferButterflyValve_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
201 | 410_PA_WaterHammerArrestor_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
202 | 410_PA_WaterMeterUNI.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
203 | 410_PA_WaterMeter_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
204 | 410_PA_WaterMeter_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
205 | 410_PA_YStrainer_Flanged.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
206 | 410_PA_YStrainer_Threaded.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
207 | 410_PA_ZBCapRoof.rfa | Sanitary Revit Family | PA | .rfa | 1 | MEP | DIG
208 | 410_PF_CastIron_Branch68Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
209 | 410_PF_CastIron_CleaningPipeWithRectangularCover_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
210 | 410_PF_CastIron_CleaningPipeWithRoundCover_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
211 | 410_PF_CastIron_CombinationBranch_88Degree_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
212 | 410_PF_CastIron_DownPipeBracket_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
213 | 410_PF_CastIron_EccentricReducer_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
214 | 410_PF_CastIron_Plug_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
215 | 410_PF_CastIron_RainwaterSiphon_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
216 | 410_PF_CastIron_SMLRainwaterSiphonVertical_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
217 | 410_PF_cHDPE_BlindFlange_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
218 | 410_PF_CI_AngleDoubleBranch88Degree_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
219 | 410_PF_CI_Bearing.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
220 | 410_PF_CI_Branch45Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
221 | 410_PF_CI_Branch45Deg_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
222 | 410_PF_CI_cPushinPlug_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
223 | 410_PF_CI_DoubleBranch_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
224 | 410_PF_CI_eAccessBendLong_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
225 | 410_PF_CI_eAccessBendShort_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
226 | 410_PF_CI_eBend15Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
227 | 410_PF_CI_eBend30Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
228 | 410_PF_CI_eBend68Degree_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
229 | 410_PF_CI_eBend88Degree_SpigotAndClamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
230 | 410_PF_CI_eBend88Deg_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
231 | 410_PF_CI_eBendWC_Clamp_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
232 | 410_PF_CI_eBend_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
233 | 410_PF_CI_eBend_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
234 | 410_PF_CI_eBend_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
235 | 410_PF_CI_eConectionBend_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
236 | 410_PF_CI_eDoubleBend45Deg_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
237 | 410_PF_CI_eDoubleBend88Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
238 | 410_PF_CI_eDoubleBend88Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
239 | 410_PF_CI_eOffsetBend130_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
240 | 410_PF_CI_eOffsetBend200_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
241 | 410_PF_CI_eOffsetBend65_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
242 | 410_PF_CI_ePlainTrap_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
243 | 410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
244 | 410_PF_CI_eRestBend88_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
245 | 410_PF_CI_eVentilationBend88Axial_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
246 | 410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
247 | 410_PF_CI_GutterAngleUniversal.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
248 | 410_PF_CI_GutterCap_ExternalStopEnd.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
249 | 410_PF_CI_GutterCap_InternalStopEnd.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
250 | 410_PF_CI_GutterElbow_ExternalDropEndOutlet.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
251 | 410_PF_CI_GutterElbow_InternalDropEndOutlet.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
252 | 410_PF_CI_GutterHalfRound.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
253 | 410_PF_CI_GutterTee_RunningOutlet.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
254 | 410_PF_CI_GutterUnionConnector.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
255 | 410_PF_CI_mShortPipeRectangularAccessDoor_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
256 | 410_PF_CI_mVerticalTrap_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
257 | 410_PF_CI_rEccentricReducer_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
258 | 410_PF_CI_rEccentricReducer_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
259 | 410_PF_CI_rReducingEccentric_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
260 | 410_PF_CI_tBranch45_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
261 | 410_PF_CI_tBranch70_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
262 | 410_PF_CI_tBranch88Deg_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
263 | 410_PF_CI_tBranch88Deg_Coupling_HOST.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
264 | 410_PF_CI_tBranch88Long_Spigot_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
265 | 410_PF_CI_tBranch88_Spigot_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
266 | 410_PF_CI_tCombinationBranch90_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
267 | 410_PF_CI_tCornerBranch88_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
268 | 410_PF_CI_tSweptEntryBranch88_Spigot_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
269 | 410_PF_CI_uShortPipeRoundAccessDoor_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
270 | 410_PF_CI_uTrapHorizontal_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
271 | 410_PF_CI_xDoubleBranch45_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
272 | 410_PF_CI_xDoubleBranch70Deg_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
273 | 410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
274 | 410_PF_CS_cEndCaps_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
275 | 410_PF_CS_eLongRadiusElbows_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
276 | 410_PF_CS_eLongRadiusReturnBends_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
277 | 410_PF_CS_eRadiusElbows_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
278 | 410_PF_CS_fPlaneFlange_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
279 | 410_PF_CS_rConcentricReducers_Welded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
280 | 410_PF_CS_rConnector_MapressAndFemaleThread.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
281 | 410_PF_CS_uConnector_MapressAndFemaleThread.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
282 | 410_PF_DI_cBellmouth_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
283 | 410_PF_DI_cBlind_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
284 | 410_PF_DI_cCap_KType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
285 | 410_PF_DI_cPlug_TType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
286 | 410_PF_DI_eBend_Flange.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
287 | 410_PF_DI_eBend_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
288 | 410_PF_DI_eDuckfoodBend90Deg_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
289 | 410_PF_DI_fFlange_RFType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
290 | 410_PF_DI_rFlangedCover.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
291 | 410_PF_DI_rFlangeSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
292 | 410_PF_DI_rFlangeSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
293 | 410_PF_DI_rTapper_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
294 | 410_PF_DI_rTapper_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
295 | 410_PF_DI_tLevelInvertTee_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
296 | 410_PF_DI_tTeeSocketWithFlangedBranch.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
297 | 410_PF_DI_tTeeSocketWithLevelInvertFlangedBranch.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
298 | 410_PF_DI_tTee_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
299 | 410_PF_DI_tTee_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
300 | 410_PF_DI_uAdaptorRestrained_Flanged.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
301 | 410_PF_DI_uFlangeAdaptor.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
302 | 410_PF_DI_uUnionFlange_RFType.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
303 | 410_PF_DI_uUnionSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
304 | 410_PF_DuctileIron_DoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
305 | 410_PF_EPDM_mKonfixConnector_PushOnJoint.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
306 | 410_PF_eSweptBendLong_Medium_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
307 | 410_PF_fHDPE_LooseFlange.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
308 | 410_PF_FireCollar_FloorMounted.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
309 | 410_PF_FireCollar_WallMounted.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
310 | 410_PF_GS_cFrogFlap_Socket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
311 | 410_PF_GS_cSealingPlugsWithVentilationSlots.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
312 | 410_PF_GS_eAngleBend_1PushShortSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
313 | 410_PF_GS_eAngleBend_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
314 | 410_PF_GS_eBasinConnector_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
315 | 410_PF_GS_eBendWithCalm_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
316 | 410_PF_GS_eBend_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
317 | 410_PF_GS_eBend_NoSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
318 | 410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
319 | 410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
320 | 410_PF_GS_eReductionAngleBend_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
321 | 410_PF_GS_GutterRound_SocketAndStandard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
322 | 410_PF_GS_mOptimisationPart_1PushSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
323 | 410_PF_GS_mSBendTrap_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
324 | 410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
325 | 410_PF_GS_rAdapterConcentric_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
326 | 410_PF_GS_rAdapterEccentric_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
327 | 410_PF_GS_rConcentricOptimiser_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
328 | 410_PF_GS_rTransitiontoCastIron_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
329 | 410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
330 | 410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
331 | 410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
332 | 410_PF_GS_tTeeBranches_2PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
333 | 410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
334 | 410_PF_GS_uBends_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
335 | 410_PF_GS_uGutterPipes_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
336 | 410_PF_GS_uLongCleaningOpening_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
337 | 410_PF_GS_uLongCleaningOpening_NoSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
338 | 410_PF_GS_uLongUnion_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
339 | 410_PF_GS_uSpigottoPlastic_1PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
340 | 410_PF_GS_uTransitionSMLtoGMX_1PushSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
341 | 410_PF_GS_uTranstiontoCastIron_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
342 | 410_PF_GS_uUnion_2PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
343 | 410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
344 | 410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
345 | 410_PF_HDPE_cProtectionCap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
346 | 410_PF_HDPE_cProtectionCapForPipeEnd.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
347 | 410_PF_HDPE_cThreadedConnectorWithScrewCap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
348 | 410_PF_HDPE_eBend90Deg_Reducer_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
349 | 410_PF_HDPE_eBend_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
350 | 410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
351 | 410_PF_HDPE_eConnectionBend88Deg_WithLateralSupplementary_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
352 | 410_PF_HDPE_eConnectionBend90DegForSleeve.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
353 | 410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
354 | 410_PF_HDPE_eConnectionBend90Deg_RightOffset_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
355 | 410_PF_HDPE_eScrewCap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
356 | 410_PF_HDPE_eSegmentBend_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
357 | 410_PF_HDPE_mDoubleConnectionBend90Deg_ForSleeve.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
358 | 410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
359 | 410_PF_HDPE_mDoubleConnectionBend90Deg_VerticalForWallHungWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
360 | 410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
361 | 410_PF_HDPE_mRunningTrap_Standard.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
362 | 410_PF_HDPE_mSoventFitting_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
363 | 410_PF_HDPE_mSTrap_Standard.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
364 | 410_PF_HDPE_mUniversalTrap_WithFlangeBushing.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
365 | 410_PF_HDPE_mWasteManifold.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
366 | 410_PF_HDPE_rAdaptorSocket_DN90xDN100.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
367 | 410_PF_HDPE_rCompressionJoint.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
368 | 410_PF_HDPE_rReducer_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
369 | 410_PF_HDPE_rRingSealSocket_ReducedWithLipSeal.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
370 | 410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
371 | 410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
372 | 410_PF_HDPE_tLateralTee_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
373 | 410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
374 | 410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
375 | 410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
376 | 410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
377 | 410_PF_HDPE_uAdapterUnion_FemaleThread.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
378 | 410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
379 | 410_PF_HDPE_uAdapterUnion_MaleThread.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
380 | 410_PF_HDPE_uClampingConnector.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
381 | 410_PF_HDPE_uExpansionSocket.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
382 | 410_PF_HDPE_uFlangeAdapter.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
383 | 410_PF_HDPE_uFlangeBushing.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
384 | 410_PF_HDPE_uFlangeSet.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
385 | 410_PF_HDPE_uStraightAdapterToCastIronPipe.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
386 | 410_PF_HDPE_uStraightAdapterToPVCPipe.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
387 | 410_PF_HDPE_uStraightAdapterWithCompressionJoint_Glueing.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
388 | 410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
389 | 410_PF_HDPE_uStraightConnectorWithRingSealSocket_WC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
390 | 410_PF_HDPE_uStraightConnector_ForFloorStandingWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
391 | 410_PF_HDPE_uThreadedConnectorWithCompressionJoint.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
392 | 410_PF_HDPE_uUnionConnection_WeldingJoints.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
393 | 410_PF_HDPE_xDoubleBrandFitting45Deg_Welded.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
394 | 410_PF_mGalvanized_PTrap_GMX.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
395 | 410_PF_mHDPE_PTrap.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
396 | 410_PF_PE_eBendForWandWC.rfa | Sanitary Revit Family | PF | .rfa | 2 | MEP | DIG
397 | 410_PF_PPR_cEndCap_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
398 | 410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
399 | 410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
400 | 410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
401 | 410_PF_PPR_eElbow_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
402 | 410_PF_PPR_rCoupling_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
403 | 410_PF_PPR_rCoupling_MaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
404 | 410_PF_PPR_rElbow90DegMaleThread_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
405 | 410_PF_PPR_rReducing_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
406 | 410_PF_PPR_tTee_FemaleThreadedAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
407 | 410_PF_PPR_tTee_MaleThreadedAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
408 | 410_PF_PPR_tTee_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
409 | 410_PF_PPR_uCoupling_FemaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
410 | 410_PF_PPR_uCoupling_MaleThreadAndSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
411 | 410_PF_PPR_uUnion_BushSocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
412 | 410_PF_PPR_uUnion_SocketFusion.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
413 | 410_PF_PPSilent_DuctBranch_SocketAndSpigot_SweptEntry88DegLeft.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
414 | 410_PF_PPSilent_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
415 | 410_PF_PPSilent_tDoubleConnectionBend90Deg_Extended.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
416 | 410_PF_PP_AccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
417 | 410_PF_PP_Adaptor_SleeveToCastIronAndSilent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
418 | 410_PF_PP_Bend_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
419 | 410_PF_PP_Branch_SocketSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
420 | 410_PF_PP_CapEnd_Socket_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
421 | 410_PF_PP_CombinedCornerBranch_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
422 | 410_PF_PP_DoubleBranchFitting88Deg_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
423 | 410_PF_PP_DoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
424 | 410_PF_PP_mOdorTrapForSinkHorizontal_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
425 | 410_PF_PP_mOdorTrapForSinkVertical_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
426 | 410_PF_PP_mOdorTrapForSink_VerticalandHorizontal_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
427 | 410_PF_PP_ParallelBrand45Deg_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
428 | 410_PF_PP_ReducerEccentric_SocketAndSpigot_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
429 | 410_PF_PP_SlipCoupling_Silent.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
430 | 410_PF_SilentPro_cCapEnd_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
431 | 410_PF_SilentPro_eElbow_SocketAndSpigot.rfa.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
432 | 410_PF_SilentPro_mCombinedCornerBranch_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
433 | 410_PF_SilentPro_mCornerBranch88Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
434 | 410_PF_SilentPro_rReducerEccentric_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
435 | 410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
436 | 410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
437 | 410_PF_SilentPro_tTeeBranch_SocketSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
438 | 410_PF_SilentPro_uAccessPipe90Deg_WithRoundServiceOpening&Silent_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
439 | 410_PF_SilentPro_uSlipCoupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
440 | 410_PF_SilentPro_wParallelBrand45Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
441 | 410_PF_SilentPro_xCrossDoubleBranchFitting88Deg_SweptEntry_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
442 | 410_PF_SS _Union_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
443 | 410_PF_SS_cCap_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
444 | 410_PF_SS_cDrainplugWithScrewedPlug.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
445 | 410_PF_SS_cSocketPlug.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
446 | 410_PF_SS_cSocketPlugWithClamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
447 | 410_PF_SS_cVentCowl_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
448 | 410_PF_SS_eBend45Degrees_SocketAndStandard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
449 | 410_PF_SS_eBend87_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
450 | 410_PF_SS_eBendWith250mmOblong_Clamp.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
451 | 410_PF_SS_eBend_15_1Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
452 | 410_PF_SS_eBend_30_1Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
453 | 410_PF_SS_eElbow90DegAdaptor_FemaleThreadAndPlainEnd_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
454 | 410_PF_SS_eElbow90DegAdaptor_WithMaleThread_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
455 | 410_PF_SS_eElbow90DegTapConnector_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
456 | 410_PF_SS_eElbow90Deg_FemaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
457 | 410_PF_SS_eElbowTapConector90Degree_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
458 | 410_PF_SS_eElbow_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
459 | 410_PF_SS_eLongBend_1Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
460 | 410_PF_SS_ePTrap_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
461 | 410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
462 | 410_PF_SS_mCornerElbow90Deg_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
463 | 410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
464 | 410_PF_SS_Rapid_Coupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
465 | 410_PF_SS_rConcentricIncreaserCoupling_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
466 | 410_PF_SS_rConnectorExternalThreadSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
467 | 410_PF_SS_rConnectorInternal_ThreadSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
468 | 410_PF_SS_rConnectorWithSocketAndFlange.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
469 | 410_PF_SS_rConnector_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
470 | 410_PF_SS_rConnector_SocketAndThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
471 | 410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
472 | 410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
473 | 410_PF_SS_rReducerWithPlainEnd_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
474 | 410_PF_SS_rTransition_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
475 | 410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
476 | 410_PF_SS_TPiece_Mapress_Equal.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
477 | 410_PF_SS_tReducingDoubleBranch45_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
478 | 410_PF_SS_tReducingSingleBranch45.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
479 | 410_PF_SS_tReducingSingleBranch_87.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
480 | 410_PF_SS_tSingleBranch45_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
481 | 410_PF_SS_tSweptBranch87Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
482 | 410_PF_SS_tTeePiece_FemaleThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
483 | 410_PF_SS_tTeePiece_MaleThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
484 | 410_PF_SS_tTeePiece_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
485 | 410_PF_SS_T_Piece_Reducer_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
486 | 410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
487 | 410_PF_SS_uAdaptorUnion_MaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
488 | 410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
489 | 410_PF_SS_uAdaptor_WithFemaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
490 | 410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
491 | 410_PF_SS_uAdaptor_WithMaleThreadAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
492 | 410_PF_SS_uAdaptor_WithMaleThreadAndPlainEnd_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
493 | 410_PF_SS_uAxialExpansion_PressingSockets.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
494 | 410_PF_SS_uBulkhead_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
495 | 410_PF_SS_uConnectionWithPlainEnd_Flanged_PN10PN16.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
496 | 410_PF_SS_uConnectionWithPlainEnd_Mapress&PressingSocket_PN10PN16.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
497 | 410_PF_SS_uConnectorwithFlangeandSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
498 | 410_PF_SS_uConnector_SocketAndThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
499 | 410_PF_SS_uCoupling_ThreadedAndMapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
500 | 410_PF_SS_uExpansionSocket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
501 | 410_PF_SS_uPeakPressure_Standard.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
502 | 410_PF_SS_uRatStop_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
503 | 410_PF_SS_uRepairCoupling_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
504 | 410_PF_SS_uSocketClamp_Special.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
505 | 410_PF_SS_uSocketClamp_Twopiece.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
506 | 410_PF_SS_uStraightCoupling.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
507 | 410_PF_SS_uUnion_Mapress.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
508 | 410_PF_SS_wCleaningPipes.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
509 | 410_PF_SS_xCornerBranch87Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
510 | 410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
511 | 410_PF_SS_xDoubleBranch87_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
512 | 410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
513 | 410_PF_ST_SanpressDoubleWallPane_Threaded_DN15.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
514 | 410_PF_UPVC_cCap_FemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
515 | 410_PF_UPVC_cCap_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
516 | 410_PF_UPVC_eBend90Deg_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
517 | 410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
518 | 410_PF_UPVC_eElbow90Deg_FemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
519 | 410_PF_UPVC_eElbow_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
520 | 410_PF_UPVC_eReducerElbow_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
521 | 410_PF_UPVC_eShortBend90Deg_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
522 | 410_PF_UPVC_rBushReducing_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
523 | 410_PF_UPVC_rLongBushReducing_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
524 | 410_PF_UPVC_rShortBushReducing_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
525 | 410_PF_UPVC_tLateralTee90Deg_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
526 | 410_PF_UPVC_tTee90Deg_FemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
527 | 410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
528 | 410_PF_UPVC_tTee_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
529 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
530 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
531 | 410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
532 | 410_PF_UPVC_uCoupling_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
533 | 410_PF_UPVC_uInspectionPort_Glue.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
534 | 410_PF_UPVC_USiphon_Horizontal.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
535 | 410_PF_UPVC_xCross_Socket.rfa | Sanitary Revit Family | PF | .rfa | 1 | MEP | DIG
536 | 410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
537 | 410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
538 | 410_PX_BasementFloorDrain_Vertical_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
539 | 410_PX_BoxGutters_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
540 | 410_PX_BoxGutters_Vertical_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
541 | 410_PX_DoppelPumpStationPowerlift_ACO.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
542 | 410_PX_DrainageChannel_B125.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
543 | 410_PX_DuofixElementForSinkAGB.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
544 | 410_PX_DuofixElementForWallHungWC.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
545 | 410_PX_DuofixElementForWallHungWC_BarrierFree.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
546 | 410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
547 | 410_PX_DuofixElementForWashbasin.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
548 | 410_PX_DuofixElementForWashBasin_BarrierFree.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
549 | 410_PX_DuofixElementInsetWashbasin_PillarTap.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
550 | 410_PX_DuofixForShower&Bathtub.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
551 | 410_PX_DuofixForShower&Bathtub_WallFittingAP.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
552 | 410_PX_DuofixForUrinal.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
553 | 410_PX_DuofixForUrinal_Universal.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
554 | 410_PX_DuofixSigmaToilet12cm_BarrierFree.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
555 | 410_PX_DuofixTraverseForStandaloneFaucetKitchenSink.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
556 | 410_PX_FaucetWithFlexibleHose.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
557 | 410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
558 | 410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
559 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
560 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
561 | 410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
562 | 410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
563 | 410_PX_FloorDrain_Horizontal_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
564 | 410_PX_FloorDrain_Horizontal_Coupling_Plastic.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
565 | 410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
566 | 410_PX_FloorDrain_VerticalFinor2PartL15_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
567 | 410_PX_FloorDrain_Vertical_Coupling_CastIron.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
568 | 410_PX_FloorDrain_Vertical_Coupling_Plastic.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
569 | 410_PX_FloorDrain_Vertical_Coupling_StainlessSteel.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
570 | 410_PX_GardenWater_Kemper.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
571 | 410_PX_GreaseDisposalPoint.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
572 | 410_PX_GullyGrating.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
573 | 410_PX_HorizontalFloorDrain.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
574 | 410_PX_InspectionShaft_OnePipe_Nosystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
575 | 410_PX_InspectionShaft_TwoPipe_Nosystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
576 | 410_PX_KitchenTap.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
577 | 410_PX_ManholeAdjustingUnits_Round_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
578 | 410_PX_ManholeBase_CastIn.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
579 | 410_PX_ManholeChamberUnits_Round_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
580 | 410_PX_ManholeCoverSlabs_Eccentrical_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
581 | 410_PX_ManholeReducingSlabs_Eccentrical_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
582 | 410_PX_ManholeTaper_EccentricalCones_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
583 | 410_PX_Manhole_Round.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
584 | 410_PX_ReusedRainWaterTank.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
585 | 410_PX_RoadGully.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
586 | 410_PX_SumpPit_NoSystem.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
587 | 410_PX_TapWithMaleHose_Threaded_DN15.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
588 | 410_PX_WaterTap.rfa | Sanitary Revit Family | PX | .rfa | 1 | MEP | DIG
589 | 410_SE_Conlit150U_NoSystem.rfa | Sanitary Revit Family | SE | .rfa | 1 | MEP | DIG
590 | 410_SE_ConlitFireProtectionSleeve_NoSystem.rfa | Sanitary Revit Family | SE | .rfa | 1 | MEP | DIG
591 | 410_SE_CoverBox.rfa | Sanitary Revit Family | SE | .rfa | 1 | MEP | DIG
592 | 474_ME_AirSamplingPump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
593 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC12kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
594 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC1kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
595 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC3kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
596 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC6kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
597 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC14kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
598 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC4d5kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
599 | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC8kg.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
600 | 474_ME_Cabinet_ExtinguishingWaterSupply.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
601 | 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
602 | 474_ME_Cabinet_FlushMountedWall.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
603 | 474_ME_Compressor.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
604 | 474_ME_ControlBox_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
605 | 474_ME_CylinderTank_FM200.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
606 | 474_ME_CylinderWithCylinderValve_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
607 | 474_ME_DieselPump_FloorSurface_AURORA481.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
608 | 474_ME_EndSuctionFirePump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
609 | 474_ME_FE_AutomaticDryPowerCeiling_HFC17_NoSystem.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
610 | 474_ME_FireExtinguisherCarbonDioxide.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
611 | 474_ME_FireExtinguisherPortable_Foam.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
612 | 474_ME_FireExtinguisherPortable_Powder.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
613 | 474_ME_FireHoseReel_WallSurface.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
614 | 474_ME_FirePump_Horizontal_SplitCase.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
615 | 474_ME_FireValveBox.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
616 | 474_ME_FoamBladderTank_HorizontalType.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
617 | 474_ME_FoamBladderTank_VerticalType.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
618 | 474_ME_FoamPump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
619 | 474_ME_HorizontalPresssureTank.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
620 | 474_ME_JockeyPump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
621 | 474_ME_JunctionBox_VESDA.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
622 | 474_ME_MasterCylinderWithTopValveOfActuator_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
623 | 474_ME_NitrogenPilotCylinderWithTopValve.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
624 | 474_ME_ProtectiveCabinetWithVentilationValve.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
625 | 474_ME_ReceiverTank.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
626 | 474_ME_SlaveCylinderWithTopOfValve_CO2.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
627 | 474_ME_SolventTank.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
628 | 474_ME_VerticalFirePump.rfa | Fire Protection Revit Family | ME | .rfa | 1 | MEP | DIG
629 | 474_PA_3WayBronzeGlobeValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
630 | 474_PA_AerationVentilationValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
631 | 474_PA_AirMaintenanceCompressorAssembly.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
632 | 474_PA_AirVentValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
633 | 474_PA_AlarmCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
634 | 474_PA_AlarmCheckValve_Dry.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
635 | 474_PA_AlarmCheckValve_European.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
636 | 474_PA_AlarmCheckValve_Preaction.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
637 | 474_PA_AlarmPressureSwitch.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
638 | 474_PA_AlarmTestModuleGrooveEnd.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
639 | 474_PA_AlarmTestModulePressureReliefValve_ThreadEnd.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
640 | 474_PA_AlarmTestModuleThreadEnd.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
641 | 474_PA_AngleHoseValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
642 | 474_PA_AutoConvertAssembly.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
643 | 474_PA_AutoDrainValve_FloatType_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
644 | 474_PA_AutomaticConcentrateControlValve_Foam.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
645 | 474_PA_BallValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
646 | 474_PA_BallValvesThreadandThread.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
647 | 474_PA_BallValves_GrooveAndGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
648 | 474_PA_BrassBodyBallValves_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
649 | 474_PA_ButterflyValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
650 | 474_PA_ButterflyValveSupervisedOpen.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
651 | 474_PA_CheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
652 | 474_PA_CheckValveAlternateWetDrySystem.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
653 | 474_PA_CS_BalancingValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
654 | 474_PA_CS_GateValveWithElectricActuator.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
655 | 474_PA_CS_YStrainer_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
656 | 474_PA_CurrentDetector.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
657 | 474_PA_CurrentDetector_ZoneCheck.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
658 | 474_PA_CylinderValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
659 | 474_PA_DelugeValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
660 | 474_PA_DiaphragmValves.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
661 | 474_PA_DischargeValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
662 | 474_PA_DoubleDoorCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
663 | 474_PA_DryAccelerator.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
664 | 474_PA_DryPilotActuator_.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
665 | 474_PA_DuplexPressureGauges.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
666 | 474_PA_FileLockBallValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
667 | 474_PA_FireHoseAngleValveWithCap.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
668 | 474_PA_FireLockAlarmCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
669 | 474_PA_FlexibleMetalHose.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
670 | 474_PA_FlowTestMeter_Flange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
671 | 474_PA_Flushing_Connection.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
672 | 474_PA_FM200_ActuatorBox.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
673 | 474_PA_FM200_DischagePressureSwitch.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
674 | 474_PA_FM200_SectorValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
675 | 474_PA_FM200_SectorValve_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
676 | 474_PA_FM200_SolenoidValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
677 | 474_PA_FoamLineProportioner.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
678 | 474_PA_Foam_AutomaticControlValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
679 | 474_PA_Foam_DuctileIron_DelugeValve_AngleStype.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
680 | 474_PA_Foam_InLineBalancedPressureProportioners.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
681 | 474_PA_FootValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
682 | 474_PA_GateValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
683 | 474_PA_HighPressureCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
684 | 474_PA_HighPressureRiserCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
685 | 474_PA_HydrantGateValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
686 | 474_PA_InlineCheckValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
687 | 474_PA_LevelControlValves_Flange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
688 | 474_PA_LevelControlValves_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
689 | 474_PA_MaintenanceUnit.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
690 | 474_PA_ManifoldCheckValve_FM200.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
691 | 474_PA_ManifoldCheckValve_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
692 | 474_PA_ManifoldCheckValve_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
693 | 474_PA_ManuallyActuatedBallValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
694 | 474_PA_ManualPneumaticActuator_FM200.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
695 | 474_PA_NRSOS&YGateValvesGrooveandFlange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
696 | 474_PA_NRSOS&YGateValvesGrooveandGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
697 | 474_PA_NRSOS&YGateValves_GrooveAndGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
698 | 474_PA_OS&YGateValves_GrooveAndFlange.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
699 | 474_PA_OS&YGateValves_GrooveAndGroove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
700 | 474_PA_PressureGauge_AnalogueType.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
701 | 474_PA_PressureGauge_withBallValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
702 | 474_PA_PressureMeter.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
703 | 474_PA_PressureOperatedDirectionalValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
704 | 474_PA_PressureReducingControlValveThread.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
705 | 474_PA_PressureReducingControlValve_Groove.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
706 | 474_PA_PressureReducingValve_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
707 | 474_PA_PressureReliefControlValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
708 | 474_PA_PressureReliefValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
709 | 474_PA_PressureSensor.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
710 | 474_PA_PressureSwitch_FM200.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
711 | 474_PA_RiserCheckValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
712 | 474_PA_RubberExpansionJoint_Flanged.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
713 | 474_PA_RubberExpansionJoint_Threaded.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
714 | 474_PA_SafertyReliefValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
715 | 474_PA_SafetyValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
716 | 474_PA_SelectorValve_CO2.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
717 | 474_PA_ShutoffValve_Motorized.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
718 | 474_PA_SightGlasses.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
719 | 474_PA_SolenoidValve.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
720 | 474_PA_SS_CompoundPressureGauge.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
721 | 474_PA_StoneCatcher.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
722 | 474_PA_SwingCheckValve_Grooved.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
723 | 474_PA_WaterflowSwitches.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
724 | 474_PA_WaterMeter.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
725 | 474_PA_ZoneControlRiserModule_Residential.rfa | Fire Protection Revit Family | PA | .rfa | 1 | MEP | DIG
726 | 474_PF_ CarbonSteel_LowProfileSprinklerTee_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
727 | 474_PF_CarbonSteel_AdapterNipple_Flanged.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
728 | 474_PF_CarbonSteel_LateralTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
729 | 474_PF_CarbonSteel_LateralThread_Standard.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
730 | 474_PF_CarbonSteel_OutletTeeReducing_Coupling.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
731 | 474_PF_CarbonSteel_OutletTeeReducing_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
732 | 474_PF_CarbonSteel_ReducingLateralTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
733 | 474_PF_CarbonSteel_TeeGroovedEnd_Standard.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
734 | 474_PF_CarbonSteel_TeeReducing_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
735 | 474_PF_CastIron_Cap_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
736 | 474_PF_Castiron_Cross_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
737 | 474_PF_CastIron_Elbow_Threaded_ShortBend.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
738 | 474_PF_Castiron_HexNipple.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
739 | 474_PF_CastIron_Reducer_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
740 | 474_PF_CastIron_SocketUnion_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
741 | 474_PF_CastIron_TeeReducing_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
742 | 474_PF_CastIron_Tee_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
743 | 474_PF_CastIron_Union_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
744 | 474_PF_CS_cCap_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
745 | 474_PF_CS_eElbowEndOfRun_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
746 | 474_PF_CS_eElbow_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
747 | 474_PF_CS_fConnection_Coupling_FireLockEZRigid.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
748 | 474_PF_CS_fConnection_Coupling_FireLockRigid.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
749 | 474_PF_CS_rConcentricReducer_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
750 | 474_PF_CS_rEccentricReducer_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
751 | 474_PF_CS_tOutletReducingCouplingTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
752 | 474_PF_CS_tSprinkerTeeCoupling_Grooved_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
753 | 474_PF_CS_tTee_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
754 | 474_PF_CS_uAdaptorNipple_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
755 | 474_PF_CS_wTrueWye_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
756 | 474_PF_CS_xCross_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
757 | 474_PF_DuctileIron_CapFemale_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
758 | 474_PF_DuctileIron_DrainElbow_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
759 | 474_PF_DuctileIron_SmallReducer_Thread.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
760 | 474_PF_GalvanizedSteel_NippleReducer_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
761 | 474_PF_SS_eUnionElbow_Threaded.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
762 | 474_PF_SS_sHaftCoupling.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
763 | 474_PF_StainlessSteel_FlexibleCoupling_Grooved.rfa | Fire Protection Revit Family | PF | .rfa | 1 | MEP | DIG
764 | 474_PROMAT_4Sided_Horizontal_CeilingMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
765 | 474_PROMAT_4Sided_Horizontal_Vertical_CeilingMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
766 | 474_PROMAT_4Sided_Vertical_CeilingMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
767 | 474_PROMAT_Horizontal_Vertical_WallMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
768 | 474_PROMAT_Horizontal_WallMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
769 | 474_PROMAT_Vertical_WallMount.rfa | Fire Protection Revit Family | PROMAT | .rfa | 1 | MEP | DIG
770 | 474_SP_DischargeNozzle_CO2.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
771 | 474_SP_FM200_180RadialNozzle_2Port.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
772 | 474_SP_FM200_360RadialNozzle_1Port.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
773 | 474_SP_FM200_360RadialNozzle_4Port.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
774 | 474_SP_FM200_DischargeNozzle.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
775 | 474_SP_FoamNozzle_Pendent.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
776 | 474_SP_FoamNozzle_Upright.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
777 | 474_SP_GE_DoubleSprinkler.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
778 | 474_SP_GE_HorizontalSideWall.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
779 | 474_SP_GE_HVSprayNozzles.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
780 | 474_SP_GE_Pendent.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
781 | 474_SP_GE_PendentCover.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
782 | 474_SP_GE_SprayNozzles.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
783 | 474_SP_GE_Upright.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
784 | 474_SP_GE_UprightCover.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
785 | 474_SP_GE_WindowOpenNozzle.rfa | Fire Protection Revit Family | SP | .rfa | 1 | MEP | DIG
786 | SAN_GraphicalAnnotationFramework.pdf | Graphical Annotation Framework - SAN | SAN | .pdf | 1 | MEP | DIG | bar: 2026-01-30
787 | SPR_GraphicalAnnotationFramework.pdf | Graphical Annotation Framework - SPR | SPR | .pdf | 1 | MEP | DIG | bar: 2026-01-30
788 | SAN_DataRequirementFramework.xlsx | Data Requirement Framework - SAN | SAN | .xlsx | 1 | MEP | DIG | bar: 2026-01-30
789 | SPR_DataRequirementFramework.xlsx | Data Requirement Framework - SPR | SPR | .xlsx | 1 | MEP | DIG | bar: 2026-01-30
790 | RFA_RevisionProcess.pdf | Process to revise RFA library (SAN & SPR) |  | .pdf | 1 | MEP | DIG | bar: 2026-01-30
791 | SAN_RFA_Library_Update.zip | Updated SAN family library package | SAN | .zip | 1 | MEP | DIG
792 | SPR_RFA_Library_Update.zip | Updated SPR family library package | SPR | .zip | 1 | MEP | DIG
793 | SAN_LPH_ViewTemplates.rte | View templates for LPH (SAN) | SAN | .rte | 1 | MEP | DIG
794 | SPR_LPH_ViewTemplates.rte | View templates for LPH (SPR) | SPR | .rte | 1 | MEP | DIG
795 | AuditPublishSupportSolution.py | Digital solution to control use / publish / audit |  |  | 1 | MEP | DIG
796 | Revizto_3DReview_SAN_SPR.pdf | Revizto export + 3D review setup report SAN |  | .pdf | 2 | MEP | DIG
|  | Revizto export + 3D review setup report SPR |  | .pdf | 1 | MEP | DIG
797 | SharedLibrary_PublishLog_SAN_SPR.xlsx | Publish log and audit trail for shared library |  | .xlsx | 3 | MEP | DIG