## TIDP_Consolidation
Package | NO | Work Item | Parent Work Item | Category | Description | File Type | Created By | Authorised By | Batch | TRM | AUD | REV | CFM | Is Family | Source File | Source Sheet | Source Row
SPR_MED | 1 | Define the "Graphical Annotation Framework" |  |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG |  | 2026-02-27 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 5
SPR_MED | 1 |  | Define the "Graphical Annotation Framework" |  | Fill the content for SPR disciplines | .xlsx | MEP | DIG |  | 2026-02-27 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 6
SPR_MED | 1 |  | Define the "Graphical Annotation Framework" |  | Confirm and sign the document | .pdf | MEP | DIG |  | 2026-02-27 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 7
SPR_MED | 2 | Define the "Data Requirement Framework" |  |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG |  | 2026-05-29 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 8
SPR_MED | 2 |  | Define the "Data Requirement Framework" |  | Fill the content for SPR disciplines | .xlsx | MEP | DIG |  | 2026-05-29 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 9
SPR_MED | 2 |  | Define the "Data Requirement Framework" |  | Confirm and sign the document | .pdf | MEP | DIG |  | 2026-05-29 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 10
SPR_MED | 3 | Define the process to revise the RFA library |  |  | Confirm and sign the process document | .pdf | MEP | DIG |  | 2026-05-29 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 11
SPR_MED | 3 |  | Define the process to revise the RFA library |  | Workshop the process with delivery team | .pptx | DIG | DIG |  | 2026-02-27 |  |  |  |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 12
SPR_MED | 4 | Revit Template for SPR in LPH3 |  |  |  | .rte | MEP/DIG | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 13
SPR_MED | 5 | Revit Template for SPR in LPH5 |  |  |  | .rte | MEP/DIG | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 14
SPR_MED | 6 | Revit Template for SPR in LPH8 |  |  |  | .rte | MEP/DIG | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 15
SPR_MED | 7 | Revit Template for MED in LPH3 | [7 empty] | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 16
SPR_MED | 8 | Revit Template for MED in LPH5 | [7 empty] | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 17
SPR_MED | 9 | Revit Template for MED in LPH8 | [7 empty] | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 18
SPR_MED | 10 | LPH3_Check list_SPR 01 |  |  | Checklist_layout Plan. | .xlsx | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 19
SPR_MED | 11 | LPH3_Check list_SPR 02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 20
SPR_MED | 12 | LPH3_Check list_SPR 03 |  |  | Checklist_Isometric Drawing. | .xlsx | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 21
SPR_MED | 13 | LPH3_Check list_SPR 04 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 22
SPR_MED | 14 | LPH5_Check list_SPR01 |  |  | Checklist_layout Plan. | .xlsx | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 23
SPR_MED | 15 | LPH5_Check list_SPR02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 24
SPR_MED | 16 | LPH5_Check list_SPR03 |  |  | Checklist_Isometric Drawing. | .xlsx | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 25
SPR_MED | 17 | LPH5_Check list_SPR04 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 26
SPR_MED | 18 | LPH8_Check list_SPR01 |  |  | Checklist_layout Plan. | .xlsx | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 27
SPR_MED | 19 | LPH8_Check list_SPR02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 28
SPR_MED | 20 | LPH8_Check list_SPR03 |  |  | Checklist_Isometric Drawing. | .xlsx | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 29
SPR_MED | 21 | LPH8_Check list_SPR04 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 30
SPR_MED | 22 | LPH3_Check list_MED_01 |  |  | Checklist_layout Plan. | .xlsx | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 31
SPR_MED | 23 | LPH3_Check list_MED_02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 32
SPR_MED | 24 | LPH3_Check list_MED_03 |  |  | Checklist_Isometric Drawing. | .xlsx | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 33
SPR_MED | 25 | LPH3_Check list_MED_04 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 34
SPR_MED | 26 | LPH5_Check list_MED_01 |  |  | Checklist_layout Plan. | .xlsx | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 35
SPR_MED | 27 | LPH5_Check list_MED_02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 36
SPR_MED | 28 | LPH5_Check list_MED_03 |  |  | Checklist_Isometric Drawing. | .xlsx | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 37
SPR_MED | 29 | LPH5_Check list_MED_04 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 38
SPR_MED | 30 | LPH8_Check list_MED_01 |  |  | Checklist_layout Plan. | .xlsx | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 39
SPR_MED | 31 | LPH8_Check list_MED_02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 40
SPR_MED | 32 | LPH8_Check list_MED_03 |  |  | Checklist_Isometric Drawing. | .xlsx | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 41
SPR_MED | 33 | LPH8_Check list_MED_04 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 42
SPR_MED | 34 | Delivery layout Sample for SPR LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 43
SPR_MED | 35 | Delivery layout Sample for SPR LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 44
SPR_MED | 36 | Delivery layout Sample for SPR LPH8 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 45
SPR_MED | 37 | Delivery Schematic Drawing Sample for SPR LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 46
SPR_MED | 38 | Delivery Schematic Drawing Sample for SPR LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 47
SPR_MED | 39 | Delivery Schematic Drawing Sample for SPR LPH8 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 48
SPR_MED | 40 | Delivery Isometric Drawing Sample for SPR LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 49
SPR_MED | 41 | Delivery Isometric Drawing Sample for SPR LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 50
SPR_MED | 42 | Delivery layout Sample for MED LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 51
SPR_MED | 43 | Delivery layout Sample for MED LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 52
SPR_MED | 44 | Delivery layout Sample for MED LPH8 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 53
SPR_MED | 45 | Delivery Schematic Drawing Sample for MED LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 54
SPR_MED | 46 | Delivery Schematic Drawing Sample for MED LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 55
SPR_MED | 47 | Delivery Schematic Drawing Sample for MED LPH8 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 56
SPR_MED | 48 | Delivery Isometric Drawing Sample for MED LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 57
SPR_MED | 49 | Delivery Isometric Drawing Sample for MED LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 58
SPR_MED | 50 | Export layouts to Revizto & set up 3D Review_LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 59
SPR_MED | 51 | Export layouts to Revizto & set up 3D Review_LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 60
SPR_MED | 52 | Export layouts to Revizto & set up 3D Review_LPH8 |  |  |  | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 61
SPR_MED | 53 | Lesson Learns |  |  | What went well. | .doc | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 62
SPR_MED | 53 |  | Lesson Learns |  | What didn’t go well | .doc | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 63
SPR_MED | 53 |  | Lesson Learns |  | What we learned | .doc | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 64
SPR_MED | 53 |  | Lesson Learns |  | Action items / Improvements | .doc | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 65
SPR_MED | 54 |  |  | 474_SP | 474_SP_GE_WindowOpenNozzle | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 66
SPR_MED | 55 |  |  | 474_ME | 474_ME_AirSamplingPump | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 67
SPR_MED | 56 |  |  | 474_ME | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC1kg | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 68
SPR_MED | 57 |  |  | 474_ME | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC3kg | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 69
SPR_MED | 58 |  |  | 474_ME | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC6kg | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 70
SPR_MED | 59 |  |  | 474_ME | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC12kg | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 71
SPR_MED | 60 |  |  | 474_ME | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC4d5kg | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 72
SPR_MED | 61 |  |  | 474_ME | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC8kg | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 73
SPR_MED | 62 |  |  | 474_ME | 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC14kg | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 74
SPR_MED | 63 |  |  | 474_ME | 474_ME_Cabinet_ExtinguishingWaterSupply | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 75
SPR_MED | 64 |  |  | 474_ME | 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 76
SPR_MED | 65 |  |  | 474_ME | 474_ME_Cabinet_FlushMountedWall | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 77
SPR_MED | 66 |  |  | 474_ME | 474_ME_Compressor | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 78
SPR_MED | 67 |  |  | 474_ME | 474_ME_ControlBox_CO2 | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 79
SPR_MED | 68 |  |  | 474_ME | 474_ME_CylinderTank_FM200 | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 80
SPR_MED | 69 |  |  | 474_ME | 474_ME_CylinderWithCylinderValve_CO2 | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 81
SPR_MED | 70 |  |  | 474_PA | 474_PA_AirMaintenanceCompressorAssembly | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 82
SPR_MED | 71 |  |  | 474_ME | 474_ME_EndSuctionFirePump | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 83
SPR_MED | 72 |  |  | 474_ME | 474_ME_FE_AutomaticDryPowerCeiling_HFC17_NoSystem | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 84
SPR_MED | 73 |  |  | 474_ME | 474_ME_FireExtinguisherCarbonDioxide | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 85
SPR_MED | 74 |  |  | 474_ME | 474_ME_FireExtinguisherPortable_Foam | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 86
SPR_MED | 75 |  |  | 474_ME | 474_ME_FireExtinguisherPortable_Powder | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 87
SPR_MED | 76 |  |  | 474_ME | 474_ME_FireHoseReel_WallSurface | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 88
SPR_MED | 77 |  |  | 474_ME | 474_ME_FirePump_Horizontal_SplitCase | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 89
SPR_MED | 78 |  |  | 474_ME | 474_ME_FireValveBox | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 90
SPR_MED | 79 |  |  | 474_ME | 474_ME_FoamBladderTank_HorizontalType | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 91
SPR_MED | 80 |  |  | 474_ME | 474_ME_FoamBladderTank_VerticalType | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 92
SPR_MED | 81 |  |  | 474_ME | 474_ME_FoamPump | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 93
SPR_MED | 82 |  |  | 474_ME | 474_ME_HorizontalPresssureTank | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 94
SPR_MED | 83 |  |  | 474_ME | 474_ME_JockeyPump | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 95
SPR_MED | 84 |  |  | 474_ME | 474_ME_JunctionBox_VESDA | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 96
SPR_MED | 85 |  |  | 474_ME | 474_ME_MasterCylinderWithTopValveOfActuator_CO2 | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 97
SPR_MED | 86 |  |  | 474_ME | 474_ME_NitrogenPilotCylinderWithTopValve | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 98
SPR_MED | 87 |  |  | 474_PA | 474_PA_AlarmCheckValve | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 99
SPR_MED | 88 |  |  | 474_PA | 474_PA_AlarmPressureSwitch | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 100
SPR_MED | 89 |  |  | 474_ME | 474_ME_SlaveCylinderWithTopOfValve_CO2 | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 101
SPR_MED | 90 |  |  | 474_ME | 474_ME_SolventTank | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 102
SPR_MED | 91 |  |  | 474_ME | 474_ME_VerticalFirePump | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 103
SPR_MED | 92 |  |  | 474_PA | 474_PA_3WayBronzeGlobeValve | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 104
SPR_MED | 93 |  |  | 474_PA | 474_PA_AerationVentilationValve | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 105
SPR_MED | 94 |  |  | 474_PF | 474_PF_CS_tLowProfileSprinklerTee_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 106
SPR_MED | 95 |  |  | 474_PF | 474_PF_CS_uAdapterNipple_Flanged | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 107
SPR_MED | 96 |  |  | 474_PF | 474_PF_CS_tLateralTee_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 108
SPR_MED | 97 |  |  | 474_PF | 474_PF_CS_tLateralThread_Standard | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 109
SPR_MED | 98 |  |  | 474_PF | 474_PF_CS_tOutletTeeReducing_Coupling | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 110
SPR_MED | 99 |  |  | 474_PF | 474_PF_CS_tOutletReducingTee_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 111
SPR_MED | 100 |  |  | 474_PF | 474_PF_CS_tReducingLateralTee_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 112
SPR_MED | 101 |  |  | 474_PF | 474_PF_CS_tGroovedEndTee_Standard | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 113
SPR_MED | 102 |  |  | 474_PF | 474_PF_CS_tReducingTee_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 114
SPR_MED | 103 |  |  | 474_PF | 474_PF_CI_cCap_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 115
SPR_MED | 104 |  |  | 474_PF | 474_PF_CI_xCross_Thread | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 116
SPR_MED | 105 |  |  | 474_PF | 474_PF_CI_eShortBend_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 117
SPR_MED | 106 |  |  | 474_PF | 474_PF_CI_uHexNipple | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 118
SPR_MED | 107 |  |  | 474_PF | 474_PF_CI_rReducer_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 119
SPR_MED | 108 |  |  | 474_PF | 474_PF_CI_xSocketUnion_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 120
SPR_MED | 109 |  |  | 474_PF | 474_PF_CI_tEqualTee_Thread | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 121
SPR_MED | 110 |  |  | 474_PF | 474_PF_CI_tTeeReducing_Thread | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 122
SPR_MED | 111 |  |  | 474_PF | 474_PF_CI_uUnion_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 123
SPR_MED | 112 |  |  | 474_PF | 474_PF_CS_cCap_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 124
SPR_MED | 113 |  |  | 474_PF | 474_PF_CS_eElbow_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 125
SPR_MED | 114 |  |  | 474_PF | 474_PF_CS_eElbowEndOfRun_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 126
SPR_MED | 115 |  |  | 474_PF | 474_PF_CS_fConnection_Coupling_FireLockEZRigid | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 127
SPR_MED | 116 |  |  | 474_PF | 474_PF_CS_fConnection_Coupling_FireLockRigid | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 128
SPR_MED | 117 |  |  | 474_PF | 474_PF_CS_rConcentricReducer_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 129
SPR_MED | 118 |  |  | 474_PF | 474_PF_CS_rEccentricReducer_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 130
SPR_MED | 119 |  |  | 474_PF | 474_PF_CS_tOutletReducingCouplingTee_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 131
SPR_MED | 120 |  |  | 474_PF | 474_PF_CS_tSprinkerTeeCoupling_Grooved_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 132
SPR_MED | 121 |  |  | 474_PF | 474_PF_CS_tTee_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 133
SPR_MED | 122 |  |  | 474_PF | 474_PF_CS_uAdaptorNipple_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 134
SPR_MED | 123 |  |  | 474_PF | 474_PF_CS_wTrueWye_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 135
SPR_MED | 124 |  |  | 474_PF | 474_PF_CS_xCross_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 136
SPR_MED | 125 |  |  | 474_PF | 474_PF_DuctileIron_CapFemale_Thread | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 137
SPR_MED | 126 |  |  | 474_PF | 474_PF_DuctileIron_DrainElbow_Grooved | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 138
SPR_MED | 127 |  |  | 474_PF | 474_PF_DuctileIron_SmallReducer_Thread | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 139
SPR_MED | 128 |  |  | 474_PF | 474_PF_GalvanizedSteel_NippleReducer_Threaded | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 140
SPR_MED | 129 |  |  | 474_PF | 474_PF_SS_eUnionElbow_Threaded | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 141
SPR_MED | 130 |  |  | 474_PF | 474_PF_SS_sHaftCoupling | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 142
SPR_MED | 131 |  |  | 474_PF | 474_PF_StainlessSteel_FlexibleCoupling_Grooved | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 143
SPR_MED | 132 |  |  | 474_ME | 474_ME_DieselPump_FloorSurface_AURORA481 | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 144
SPR_MED | 133 |  |  | 474_PA | 474_PA_AirVentValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 145
SPR_MED | 134 |  |  | 474_ME | 474_ME_ProtectiveCabinetWithVentilationValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 146
SPR_MED | 135 |  |  | 474_PA | 474_PA_AlarmCheckValve_Dry | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 147
SPR_MED | 136 |  |  | 474_PA | 474_PA_AlarmCheckValve_European | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 148
SPR_MED | 137 |  |  | 474_PA | 474_PA_AlarmCheckValve_Preaction | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 149
SPR_MED | 138 |  |  | 474_ME | 474_ME_ReceiverTank | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 150
SPR_MED | 139 |  |  | 474_PA | 474_PA_AlarmTestModuleGrooveEnd | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 151
SPR_MED | 140 |  |  | 474_PA | 474_PA_AlarmTestModulePressureReliefValve_ThreadEnd | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 152
SPR_MED | 141 |  |  | 474_PA | 474_PA_AlarmTestModuleThreadEnd | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 153
SPR_MED | 142 |  |  | 474_PA | 474_PA_AngleHoseValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 154
SPR_MED | 143 |  |  | 474_PA | 474_PA_AutoConvertAssembly | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 155
SPR_MED | 144 |  |  | 474_PA | 474_PA_AutoDrainValve_FloatType_Threaded | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 156
SPR_MED | 145 |  |  | 474_PA | 474_PA_AutomaticConcentrateControlValve_Foam | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 157
SPR_MED | 146 |  |  | 474_PA | 474_PA_BallValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 158
SPR_MED | 147 |  |  | 474_PA | 474_PA_BallValves_GrooveAndGroove | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 159
SPR_MED | 148 |  |  | 474_PA | 474_PA_BallValvesThreadandThread | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 160
SPR_MED | 149 |  |  | 474_PA | 474_PA_BrassBodyBallValves_Threaded | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 161
SPR_MED | 150 |  |  | 474_PA | 474_PA_ButterflyValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 162
SPR_MED | 151 |  |  | 474_PA | 474_PA_ButterflyValveSupervisedOpen | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 163
SPR_MED | 152 |  |  | 474_PA | 474_PA_CheckValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 164
SPR_MED | 153 |  |  | 474_PA | 474_PA_CheckValveAlternateWetDrySystem | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 165
SPR_MED | 154 |  |  | 474_PA | 474_PA_CS_BalancingValve_Flanged | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 166
SPR_MED | 155 |  |  | 474_PA | 474_PA_GateValveWithElectricActuator | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 167
SPR_MED | 156 |  |  | 474_PA | 474_PA_CS_YStrainer_Grooved | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 168
SPR_MED | 157 |  |  | 474_PA | 474_PA_WaterFlowDetector | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 169
SPR_MED | 158 |  |  | 474_PA | 474_PA_WaterFlowDetector_ZoneCheck | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 170
SPR_MED | 159 |  |  | 474_PA | 474_PA_CylinderValve_CO2 | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 171
SPR_MED | 160 |  |  | 474_PA | 474_PA_DelugeValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 172
SPR_MED | 161 |  |  | 474_PA | 474_PA_DiaphragmValves | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 173
SPR_MED | 162 |  |  | 474_PA | 474_PA_DischargeValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 174
SPR_MED | 163 |  |  | 474_PA | 474_PA_DoubleDoorCheckValve | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 175
SPR_MED | 164 |  |  | 474_PA | 474_PA_DryAccelerator | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 176
SPR_MED | 165 |  |  | 474_PA | 474_PA_DryPilotActuator | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 177
SPR_MED | 166 |  |  | 474_PA | 474_PA_DuplexPressureGauges | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 178
SPR_MED | 167 |  |  | 474_PA | 474_PA_PressureReducingControlValve_Groove | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 179
SPR_MED | 168 |  |  | 474_PA | 474_PA_PressureReducingControlValveThread | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 180
SPR_MED | 169 |  |  | 474_PA | 474_PA_PressureReducingValve_Flanged | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 181
SPR_MED | 170 |  |  | 474_PA | 474_PA_PressureReliefControlValve | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 182
SPR_MED | 171 |  |  | 474_PA | 474_PA_PressureReliefValve | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 183
SPR_MED | 172 |  |  | 474_PA | 474_PA_PressureSensor | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 184
SPR_MED | 173 |  |  | 474_PA | 474_PA_PressureSwitch_FM200 | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 185
SPR_MED | 174 |  |  | 474_PA | 474_PA_RiserCheckValve | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 186
SPR_MED | 175 |  |  | 474_PA | 474_PA_RubberExpansionJoint_Flanged | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 187
SPR_MED | 176 |  |  | 474_PA | 474_PA_RubberExpansionJoint_Threaded | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 188
SPR_MED | 177 |  |  | 474_PA | 474_PA_SafertyReliefValve_CO2 | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 189
SPR_MED | 178 |  |  | 474_PA | 474_PA_SafetyValve | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 190
SPR_MED | 179 |  |  | 474_PA | 474_PA_SelectorValve_CO2 | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 191
SPR_MED | 180 |  |  | 474_PA | 474_PA_ShutoffValve_Motorized | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 192
SPR_MED | 181 |  |  | 474_PA | 474_PA_SightGlasses | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 193
SPR_MED | 182 |  |  | 474_PA | 474_PA_SolenoidValve | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 194
SPR_MED | 183 |  |  | 474_PA | 474_PA_SS_CompoundPressureGauge | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 195
SPR_MED | 184 |  |  | 474_PA | 474_PA_StoneCatcher | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 196
SPR_MED | 185 |  |  | 474_PA | 474_PA_SwingCheckValve_Grooved | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 197
SPR_MED | 186 |  |  | 474_PA | 474_PA_WaterflowSwitches | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 198
SPR_MED | 187 |  |  | 474_PA | 474_PA_WaterMeter | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 199
SPR_MED | 188 |  |  | 474_PA | 474_PA_ZoneControlRiserModule_Residential | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 200
SPR_MED | 189 |  |  | 474_PA | 474_PA_FireLockBallValve | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 201
SPR_MED | 190 |  |  | 474_PA | 474_PA_FireHoseAngleValveWithCap | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 202
SPR_MED | 191 |  |  | 474_PA | 474_PA_FireLockAlarmCheckValve | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 203
SPR_MED | 192 |  |  | 474_PA | 474_PA_FlexibleMetalHose | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 204
SPR_MED | 193 |  |  | 474_PA | 474_PA_FlowTestMeter_Flange | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 205
SPR_MED | 194 |  |  | 474_PA | 474_PA_Flushing_Connection | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 206
SPR_MED | 195 |  |  | 474_PA | 474_PA_FM200_ActuatorBox | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 207
SPR_MED | 196 |  |  | 474_PA | 474_PA_FM200_DischagePressureSwitch | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 208
SPR_MED | 197 |  |  | 474_PA | 474_PA_FM200_SectorValve_Flanged | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 209
SPR_MED | 198 |  |  | 474_PA | 474_PA_FM200_SectorValve_Threaded | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-25 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 210
SPR_MED | 199 |  |  | 474_PA | 474_PA_FM200_SolenoidValve | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 211
SPR_MED | 200 |  |  | 474_PA | 474_PA_Foam_AutomaticControlValve_Flanged | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 212
SPR_MED | 201 |  |  | 474_PA | 474_PA_Foam_DuctileIron_DelugeValve_AngleStype | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 213
SPR_MED | 202 |  |  | 474_PA | 474_PA_Foam_InLineBalancedPressureProportioners | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 214
SPR_MED | 203 |  |  | 474_PA | 474_PA_FoamLineProportioner | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 215
SPR_MED | 204 |  |  | 474_PA | 474_PA_FootValve | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 216
SPR_MED | 205 |  |  | 474_PA | 474_PA_GateValve | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 217
SPR_MED | 206 |  |  | 474_PA | 474_PA_HighPressureCheckValve | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 218
SPR_MED | 207 |  |  | 474_PA | 474_PA_HighPressureRiserCheckValve | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 219
SPR_MED | 208 |  |  | 474_PA | 474_PA_HydrantGateValve | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 220
SPR_MED | 209 |  |  | 474_PA | 474_PA_InlineCheckValve_CO2 | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 221
SPR_MED | 210 |  |  | 474_PA | 474_PA_LevelControlValves_Flange | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 222
SPR_MED | 211 |  |  | 474_PA | 474_PA_LevelControlValves_Grooved | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 223
SPR_MED | 212 |  |  | 474_PA | 474_PA_MaintenanceUnit | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 224
SPR_MED | 213 |  |  | 474_PA | 474_PA_ManifoldCheckValve_FM200 | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 225
SPR_MED | 214 |  |  | 474_PA | 474_PA_ManifoldCheckValve_Grooved | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 226
SPR_MED | 215 |  |  | 474_PA | 474_PA_ManifoldCheckValve_Threaded | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 227
SPR_MED | 216 |  |  | 474_PA | 474_PA_ManuallyActuatedBallValve_CO2 | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 228
SPR_MED | 217 |  |  | 474_PA | 474_PA_ManualPneumaticActuator_FM200 | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 229
SPR_MED | 218 |  |  | 474_PA | 474_PA_NRSOS&YGateValves_GrooveAndGroove | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 230
SPR_MED | 219 |  |  | 474_PA | 474_PA_NRSOS&YGateValves_GrooveandFlange | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 231
SPR_MED | 220 |  |  | 474_PA | 474_PA_OS&YGateValves_GrooveAndFlange | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 232
SPR_MED | 221 |  |  | 474_PA | 474_PA_OS&YGateValves_GrooveAndGroove | .rfa | MEP | DIG |  | 2026-06-25 | 2026-07-03 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 233
SPR_MED | 222 |  |  | 474_PA | 474_PA_PressureGauge_AnalogueType | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 234
SPR_MED | 223 |  |  | 474_PA | 474_PA_PressureGauge_withBallValve | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 235
SPR_MED | 224 |  |  | 474_PA | 474_PA_PressureMeter | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 236
SPR_MED | 225 |  |  | 474_PA | 474_PA_PressureOperatedDirectionalValve_CO2 | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 237
SPR_MED | 226 |  |  |  | 474_PROMAT_4Sided_Horizontal_CeilingMount | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 238
SPR_MED | 227 |  |  |  | 474_PROMAT_4Sided_Horizontal_Vertical_CeilingMount | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 239
SPR_MED | 228 |  |  |  | 474_PROMAT_4Sided_Vertical_CeilingMount | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 240
SPR_MED | 229 |  |  |  | 474_PROMAT_Horizontal_Vertical_WallMount | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 241
SPR_MED | 230 |  |  |  | 474_PROMAT_Horizontal_WallMount | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 242
SPR_MED | 231 |  |  |  | 474_PROMAT_Vertical_WallMount | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 243
SPR_MED | 232 |  |  | 474_SP | 474_SP_DischargeNozzle_CO2 | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 244
SPR_MED | 233 |  |  | 474_SP | 474_SP_FM200_180RadialNozzle_2Port | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 245
SPR_MED | 234 |  |  | 474_SP | 474_SP_FM200_360RadialNozzle_1Port | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 246
SPR_MED | 235 |  |  | 474_SP | 474_SP_FM200_360RadialNozzle_4Port | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 247
SPR_MED | 236 |  |  | 474_SP | 474_SP_FM200_DischargeNozzle | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 248
SPR_MED | 237 |  |  | 474_SP | 474_SP_FoamNozzle_Pendent | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 249
SPR_MED | 238 |  |  | 474_SP | 474_SP_FoamNozzle_Upright | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 250
SPR_MED | 239 |  |  | 474_SP | 474_SP_GE_DoubleSprinkler | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 251
SPR_MED | 240 |  |  | 474_SP | 474_SP_GE_HorizontalSideWall | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 252
SPR_MED | 241 |  |  | 474_SP | 474_SP_GE_HVSprayNozzles | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 253
SPR_MED | 242 |  |  | 474_SP | 474_SP_GE_Pendent | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 254
SPR_MED | 243 |  |  | 474_SP | 474_SP_GE_PendentCover | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 255
SPR_MED | 244 |  |  | 474_SP | 474_SP_GE_SprayNozzles | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 256
SPR_MED | 245 |  |  | 474_SP | 474_SP_GE_Upright | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 257
SPR_MED | 246 |  |  | 474_SP | 474_SP_GE_UprightCover | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 258
SPR_MED | 247 | Revise Family |  |  | 473_PF_CO_rReducer_FemaleSoldered | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 |  | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 259
SPR_MED | 248 |  |  | 473_PF | 473_PF_CO_rReducerMF_Soldered | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 260
SPR_MED | 249 |  |  | 473_PF | 473_PF_CO_tEqualTee_FemaleSoldered | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 261
SPR_MED | 250 |  |  | 473_PF | 473_PF_CO_tTee_Reducing_FemaleSoldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 262
SPR_MED | 251 |  |  | 473_PF | 473_PF_CO_uCoupling_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 263
SPR_MED | 252 |  |  | 473_PF | 473_PF_CO_uOffsetFF_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 264
SPR_MED | 253 |  |  | 473_PF | 473_PF_SS_tTee_Welded | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 265
SPR_MED | 254 |  |  | 473_PF | 473_PF_SS_uClampConnector | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 266
SPR_MED | 255 |  |  | 473_PF | 473_PF_SS_uClampConnectorWithWeldedConnection | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 267
SPR_MED | 256 |  |  | 473_PF | 473_PF_CO_cEndCap_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 268
SPR_MED | 257 |  |  | 473_PF | 473_PF_CO_eElbow_Reduce_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 269
SPR_MED | 258 |  |  | 473_PF | 473_PF_CO_eElbow45_FemaleAndFemaleSoldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 270
SPR_MED | 259 |  |  | 473_PF | 473_PF_CO_eElbow45_MaleAndFemaleSoldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 271
SPR_MED | 260 |  |  | 473_PF | 473_PF_CO_eElbow180_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 272
SPR_MED | 261 |  |  | 473_PF | 473_PF_CO_eElbowLongRadiusFF_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 273
SPR_MED | 262 |  |  | 473_PF | 473_PF_CO_eElbowShortRadiusMF_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 274
SPR_MED | 263 |  |  | 473_PF | 473_PF_CO_eLongRadius_MFSoldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 275
SPR_MED | 264 |  |  | 473_PF | 473_PF_CO_eLongRadius_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 276
SPR_MED | 265 |  |  | 473_PF | 473_PF_CO_eOffset_M_F_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 277
SPR_MED | 266 |  |  | 473_PF | 473_PF_CO_eShortRadiusFF_Soldered | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 278
SPR_MED | 267 |  |  | 473_EF | 473_EF_BathroomCallUnit_PullCord | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 279
SPR_MED | 268 |  |  | 473_EF | 473_EF_BathroomCallUnit_PushButton | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 280
SPR_MED | 269 |  |  | 473_EF | 473_EF_BiomedicalCallPlugandSocket | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 281
SPR_MED | 270 |  |  | 473_EF | 473_EF_CallDisplayUnit | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 282
SPR_MED | 271 |  |  | 473_EF | 473_EF_CallTranferUnitForCorridors | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 283
SPR_MED | 272 |  |  | 473_EF | 473_EF_DoorUnit | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 284
SPR_MED | 273 |  |  | 473_EF | 473_EF_ElectronicBuzzer_WallSurface | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 285
SPR_MED | 274 |  |  | 473_EF | 473_EF_RemoteControlModules | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 286
SPR_MED | 275 |  |  | 473_EF | 473_EF_SocketForCordedPushButton_WallSurface | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 287
SPR_MED | 276 |  |  | 473_EF | 473_EF_SocketforHandPushButton | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 288
SPR_MED | 277 |  |  | 473_EF | 473_EF_TableControlUnit | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 289
SPR_MED | 278 |  |  | 473_PA | 473_PA_3WayMotorControlValve_Threaded | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 290
SPR_MED | 279 |  |  | 473_PA | 473_PA_AGSSOutletType1L | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 291
SPR_MED | 280 |  |  | 473_PA | 473_PA_AirHeader_8Connection | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 292
SPR_MED | 281 |  |  | 473_PA | 473_PA_AirHeader_10Connection | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 293
SPR_MED | 282 |  |  | 473_PA | 473_PA_AirHeader_12Connection | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 294
SPR_MED | 283 |  |  | 473_PA | 473_PA_AirHeader_14Connection | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 295
SPR_MED | 284 |  |  | 473_PA | 473_PA_AirHeader_16Connection | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 296
SPR_MED | 285 |  |  | 473_PA | 473_PA_AirHeader_18Connection | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 297
SPR_MED | 286 |  |  | 473_PA | 473_PA_AirPressureRegulator_Mapress | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 298
SPR_MED | 287 |  |  | 473_PA | 473_PA_AirRegulatorValve_Threaded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 299
SPR_MED | 288 |  |  | 473_PA | 473_PA_AirVentingFilters_Standard | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 300
SPR_MED | 289 |  |  | 473_PA | 473_PA_AutoDrainValve_FloatType_Threaded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 301
SPR_MED | 290 |  |  | 473_PA | 473_PA_AutomaticMechanicalCondensateDrain | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 302
SPR_MED | 291 |  |  | 473_PA | 473_PA_BallValve_Threaded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 303
SPR_MED | 292 |  |  | 473_PA | 473_PA_BR_3WayMotorControlValve_Threaded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 304
SPR_MED | 293 |  |  | 473_PA | 473_PA_BR_3WayValveDN15toDN50_Threaded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 305
SPR_MED | 294 |  |  | 473_PA | 473_PA_BR_AirReliefValve_Threaded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 306
SPR_MED | 295 |  |  | 473_PA | 473_PA_Brass_CheckValve_Threaded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 307
SPR_MED | 296 |  |  | 473_PA | 473_PA_ClampedStraightSightGlass | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 308
SPR_MED | 297 |  |  | 473_PA | 473_PA_CompressedAirFilters_DDp | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 309
SPR_MED | 298 |  |  | 473_PA | 473_PA_CompressedAirFilters_QDT | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 310
SPR_MED | 299 |  |  | 473_PA | 473_PA_CondensateDistributor2Branch_WOSCD | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 311
SPR_MED | 300 |  |  | 473_PA | 473_PA_CondensateDistributor4Branch_WOSCD | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 312
SPR_MED | 301 |  |  | 473_PA | 473_PA_CondensateDistributor8Branch_WOSCD | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 313
SPR_MED | 302 |  |  | 473_PA | 473_PA_CondensateDistributor12Branch_WOSCD | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 314
SPR_MED | 303 |  |  | 473_PA | 473_PA_CS_PressureReducingValve_Flanged | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 315
SPR_MED | 304 |  |  | 473_PA | 473_PA_CycloneSeparator_Standard | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 316
SPR_MED | 305 |  |  | 473_PA | 473_PA_ElectronicCondensateDrain | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 317
SPR_MED | 306 |  |  | 473_PA | 473_PA_ElectronicMotorizedValve | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 318
SPR_MED | 307 |  |  | 473_PA | 473_PA_Filters_Flanged | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 319
SPR_MED | 308 |  |  | 473_PA | 473_PA_Filters_Welded | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 320
SPR_MED | 309 |  |  | 473_PA | 473_PA_GasN2_Outlet | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 321
SPR_MED | 310 |  |  | 473_PA | 473_PA_GasO2Outlet | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 322
SPR_MED | 311 |  |  | 473_PA | 473_PA_LineBallValve_LV10_V | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 323
SPR_MED | 312 |  |  | 473_PA | 473_PA_LineBallValve_LV10VF | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 324
SPR_MED | 313 |  |  | 473_PA | 473_PA_LockableLineBallValve_LVL10 | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 325
SPR_MED | 314 |  |  | 473_PA | 473_PA_LockableLineBallValve_LVL20 | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 326
SPR_MED | 315 |  |  | 473_PA | 473_PA_LockableLineBallValve_NIST | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 327
SPR_MED | 316 |  |  | 473_PA | 473_PA_MembraneAirDryers | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 328
SPR_MED | 317 |  |  | 473_PA | 473_PA_MotorizedPneumaticDiaphragmValve_Welded | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 329
SPR_MED | 318 |  |  | 473_PA | 473_PA_N2OOutlet | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 330
SPR_MED | 319 |  |  | 473_PA | 473_PA_NRVValve | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 331
SPR_MED | 320 |  |  | 473_PA | 473_PA_PlasticBox_Air | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 332
SPR_MED | 321 |  |  | 473_PA | 473_PA_PneumaticButterflyValve_Welded | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 333
SPR_MED | 322 |  |  | 473_PA | 473_PA_PneumaticDiaphragmValveWithAlarm | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 334
SPR_MED | 323 |  |  | 473_PA | 473_PA_PneumaticManualDiaphragmValve | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 335
SPR_MED | 324 |  |  | 473_PA | 473_PA_PressureGauge_ElectricalContactCodeA | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 336
SPR_MED | 325 |  |  | 473_PA | 473_PA_RectangularPressureRegulator | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 337
SPR_MED | 326 |  |  | 473_PA | 473_PA_SafetyValve | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 338
SPR_MED | 327 |  |  | 473_PA | 473_PA_ShutOffValveBox_MultiConnection | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 339
SPR_MED | 328 |  |  | 473_PA | 473_PA_SingleZone_ValveBox | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 340
SPR_MED | 329 |  |  | 473_PA | 473_PA_SS_AirHeader_4Connection | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 341
SPR_MED | 330 |  |  | 473_PA | 473_PA_SS_AirHeader_6Connection | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 342
SPR_MED | 331 |  |  | 473_PA | 473_PA_SS_CouplingsFemale_Threaded | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 343
SPR_MED | 332 |  |  | 473_PA | 473_PA_SS_HighPressureProcessFilters_Welded | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 344
SPR_MED | 333 |  |  | 473_PA | 473_PA_SS_PressureGauge_AnalogueType | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 345
SPR_MED | 334 |  |  | 473_PA | 473_PA_SS_PressureReducingValve_Flanged | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 346
SPR_MED | 335 |  |  | 473_PA | 473_PA_SS_WeldedCondensateSeparators | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 347
SPR_MED | 336 |  |  | 473_PA | 473_PA_StainlessSteel1WayValve | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 348
SPR_MED | 337 |  |  | 473_PA | 473_PA_StainlessSteelFlexibleConnection | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 349
SPR_MED | 338 |  |  | 473_PA | 473_PA_SterileFilters_SFSeries_Flanged | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 350
SPR_MED | 339 |  |  | 473_PA | 473_PA_VAC_Outlet | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 351
SPR_MED | 340 |  |  | 473_PA | 473_PA_WaterOilSeparators_WOS | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 352
SPR_MED | 341 |  |  | 473_PA | 473_PA_WaterOilSeparators_WOSm | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 353
SPR_MED | 342 |  |  | 473_ME | 473_ME_ActivatedCarbonTower | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 354
SPR_MED | 343 |  |  | 473_ME | 473_ME_AirDryer | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 355
SPR_MED | 344 |  |  | 473_ME | 473_ME_AirDryer_Vertical | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 356
SPR_MED | 345 |  |  | 473_ME | 473_ME_AirPurifiers | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 357
SPR_MED | 346 |  |  | 473_ME | 473_ME_AirReceiverTank | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 358
SPR_MED | 347 |  |  | 473_ME | 473_ME_AreaAlarmPanel | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 359
SPR_MED | 348 |  |  | 473_ME | 473_ME_AutomatedH2O2AirlockAccessible | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 360
SPR_MED | 349 |  |  | 473_ME | 473_ME_BHU_DK2014 | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 361
SPR_MED | 350 |  |  | 473_ME | 473_ME_BHU_DK2014M | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 362
SPR_MED | 351 |  |  | 473_ME | 473_ME_BHU_HY2017 | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 363
SPR_MED | 352 |  |  | 473_ME | 473_ME_BHU_HY2017D | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 364
SPR_MED | 353 |  |  | 473_ME | 473_ME_BHU_HY2017DS | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 365
SPR_MED | 354 |  |  | 473_ME | 473_ME_BHU_SC2015 | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 366
SPR_MED | 355 |  |  | 473_ME | 473_ME_BHU_Vertical | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 367
SPR_MED | 356 |  |  | 473_ME | 473_ME_BottleFillingPlant | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 368
SPR_MED | 357 |  |  | 473_ME | 473_ME_CompactH2O2DecontaminationAirlock | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 369
SPR_MED | 358 |  |  | 473_ME | 473_ME_CylinderTank_NoSystem | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 370
SPR_MED | 359 |  |  | 473_ME | 473_ME_DesiccantAdsorptionCompressedAirDryers | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 371
SPR_MED | 360 |  |  | 473_ME | 473_ME_DryVacuumPump | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 372
SPR_MED | 361 |  |  | 473_ME | 473_ME_ExternalHeatRecoveryUnits | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 373
SPR_MED | 362 |  |  | 473_ME | 473_ME_HeatlessRegenerationAdsorptionDryers | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 374
SPR_MED | 363 |  |  | 473_ME | 473_ME_HeatlessRegenerationAdsorptionDryers_ActivatedCarbonTower | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 375
SPR_MED | 364 |  |  | 473_ME | 473_ME_HeatRegenerationAdsorptionDryers | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 376
SPR_MED | 365 |  |  | 473_ME | 473_ME_ICU_Eurocare | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 377
SPR_MED | 366 |  |  | 473_ME | 473_ME_ICU_EurocareD | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 378
SPR_MED | 367 |  |  | 473_ME | 473_ME_ICU_SMICare | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 379
SPR_MED | 368 |  |  | 473_ME | 473_ME_ICU_SMICAREDS | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 380
SPR_MED | 369 |  |  | 473_ME | 473_ME_IntensiveCareUnits_WallMounted_SMICAREDS | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 381
SPR_MED | 370 |  |  | 473_ME | 473_ME_IntensiveCareUnits_WallMounted_SMICareHD | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 382
SPR_MED | 371 |  |  | 473_ME | 473_ME_MedicalAirCompressors_FloorMounted | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 383
SPR_MED | 372 |  |  | 473_ME | 473_ME_MedicalAirCompressors_TankMounted | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 384
SPR_MED | 373 |  |  | 473_ME | 473_ME_NitrogenGenerators | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 385
SPR_MED | 374 |  |  | 473_ME | 473_ME_OxygenGenerators | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 386
SPR_MED | 375 |  |  | 473_ME | 473_ME_RefrigerationAirDryer_Flanged | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 387
SPR_MED | 376 |  |  | 473_ME | 473_ME_RefrigerationAirDryer_Threaded | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 388
SPR_MED | 377 |  |  | 473_ME | 473_ME_VacuumPump | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 389
SPR_MED | 378 |  |  | 473_ME | 473_ME_ZoneWallUnit_CZ200 | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 390
SPR_MED | 379 |  |  | 473_ME | 473_ME_ZoneWallUnit_HST100 | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 391
SPR_MED | 380 |  |  | 473_ME | 473_ME_ZoneWallUnit_HST200 | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 392
SPR_MED | TRM | Transmittal / Submitted |  |  | MEP | [9 empty] | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 395
SPR_MED | AUD | Audit/Review |  |  | DIG | [9 empty] | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 396
SPR_MED | REV | Revision Required / Revised |  |  | MEP | [9 empty] | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 397
SPR_MED | CFM | Confimmation/Confirmed & Stored |  |  | DIG/MEP | [9 empty] | DCMvn_SPR MED_TIDP_REV04.xlsx | TIDP 473 & 474 | 398
SAN | A | Framework deliverables |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 5
SAN | 1 | Define the "Graphical Annotation Framework" SAN | [12 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 6
SAN | 1 |  | Define the "Graphical Annotation Framework" SAN |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 7
SAN | 1 |  | Define the "Graphical Annotation Framework" SAN |  | Fill the content for SAN discipline | .xlsx | MEP | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 8
SAN | 1 |  | Define the "Graphical Annotation Framework" SAN |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | [5 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 9
SAN | 2 | Define the "Data Requirement Framework" SAN | [12 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 10
SAN | 2 |  | Define the "Data Requirement Framework" SAN |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 11
SAN | 2 |  | Define the "Data Requirement Framework" SAN |  | Fill the content for SAN discipline | .xlsx | MEP | DIG | 0 | 2026-02-27 |  |  |  |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 12
SAN | 2 |  | Define the "Data Requirement Framework" SAN |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | 2026-05-22 |  |  |  |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 13
SAN | 3 | Define the process to revise the RFA library | [12 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 14
SAN | 3 |  | Define the process to revise the RFA library |  | Confirm and sign the process document | .pdf | MEP | DIG | 0 | 2026-05-22 |  |  |  |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 15
SAN | 3 |  | Define the process to revise the RFA library |  | Workshop the process with delivery team | .pptx | DIG | DIG | 0 | 2026-02-27 |  |  |  |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 16
SAN | B | Revise the RFA library for SAN system |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 17
SAN | B | SAN Discipline |  |  | 591 Families need to be revise | [9 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 18
SAN | B.1 | PF_Pipe Fitting |  |  | 330 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 19
SAN | 1 | 410_PF_CI_tBranch68Deg_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 20
SAN | 2 | 410_PF_CI_uCleaningPipeWithRoundCover_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 21
SAN | 3 | 410_PF_CI_uCleaningPipeWithRectangularcover_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 22
SAN | 4 | 410_PF_CI_xCombinationBranch88Degree_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 23
SAN | 5 | 410_PF_CI_uDownPipeBracket_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 24
SAN | 6 | 410_PF_CI_rEccentricReducer_WithoutCoupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 25
SAN | 7 | 410_PF_CI_cPlug_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 26
SAN | 8 | 410_PF_CI_eRainwaterSiphon_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 27
SAN | 9 | 410_PF_CI_uSMLRainwaterSiphonVertical_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 28
SAN | 10 | 410_PF_cHDPE_BlindFlange_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 29
SAN | 11 | 410_PF_CI_fAngleDoubleBranch88Degree_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 30
SAN | 12 | 410_PF_CI_uBearing.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 31
SAN | 13 | 410_PF_CI_tBranch45Deg_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 32
SAN | 14 | 410_PF_CI_tBranch45Deg_Coupling_HOST.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 33
SAN | 15 | 410_PF_CI_cPushinPlug_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 34
SAN | 16 | 410_PF_CI_xDoubleBranch_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 35
SAN | 17 | 410_PF_CI_eAccessBendLong_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 36
SAN | 18 | 410_PF_CI_eAccessBendShort_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 37
SAN | 19 | 410_PF_CI_eBend15Degrees_Standard_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 38
SAN | 20 | 410_PF_CI_eBend30Degrees_Standard_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 39
SAN | 21 | 410_PF_CI_eBend68Degree_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 40
SAN | 22 | 410_PF_CI_eBend88Degree_SpigotAndClamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 41
SAN | 23 | 410_PF_CI_eBend88Deg_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 42
SAN | 24 | 410_PF_CI_eBendWC_Clamp_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 1 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 43
SAN | 25 | 410_PF_CI_eBend_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 44
SAN | 26 | 410_PF_CI_eBend_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 45
SAN | 27 | 410_PF_CI_eBend_Coupling_HOST.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 46
SAN | 28 | 410_PF_CI_eConectionBend_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 47
SAN | 29 | 410_PF_CI_eDoubleBend45Deg_Coupling_HOST.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 48
SAN | 30 | 410_PF_CI_xDoubleBend88Degrees_Standard_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 49
SAN | 31 | 410_PF_CI_eDoubleBend88Deg_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 50
SAN | 32 | 410_PF_CI_eOffsetBend130_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 51
SAN | 33 | 410_PF_CI_eOffsetBend200_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 52
SAN | 34 | 410_PF_CI_eOffsetBend65_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 53
SAN | 35 | 410_PF_CI_ePlainTrap_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 54
SAN | 36 | 410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 55
SAN | 37 | 410_PF_CI_eRestBend88_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 56
SAN | 38 | 410_PF_CI_eVentilationBend88Axial_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 57
SAN | 39 | 410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 58
SAN | 40 | 410_PF_CI_eGutterAngleUniversal.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 59
SAN | 41 | 410_PF_CI_cGutterCap_ExternalStopEnd.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 60
SAN | 42 | 410_PF_CI_cGutterCap_InternalStopEnd.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 61
SAN | 43 | 410_PF_CI_eGutterElbow_ExternalDropEndOutlet.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 62
SAN | 44 | 410_PF_CI_eGutterElbow_InternalDropEndOutlet.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 63
SAN | 45 | 410_PF_CI_mGutterHalfRound.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 64
SAN | 46 | 410_PF_CI_tGutterTee_RunningOutlet.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 65
SAN | 47 | 410_PF_CI_uGutterUnionConnector.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 66
SAN | 48 | 410_PF_CI_mShortPipeRectangularAccessDoor_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 67
SAN | 49 | 410_PF_CI_mVerticalTrap_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 68
SAN | 50 | 410_PF_CI_rEccentricReducer_WithoutCoupling |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 69
SAN | 51 | 410_PF_CI_rEccentricReducer_Coupling_HOST.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 70
SAN | 52 | 410_PF_CI_rReducingEccentric_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 71
SAN | 53 | 410_PF_CI_tBranch45_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 72
SAN | 54 | 410_PF_CI_tBranch70_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 73
SAN | 55 | 410_PF_CI_tBranch88Deg_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 74
SAN | 56 | 410_PF_CI_tBranch88Deg_Coupling_HOST.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 2 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 75
SAN | 57 | 410_PF_CI_tBranch88Long_Spigot_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 76
SAN | 58 | 410_PF_CI_tBranch88_Spigot_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 77
SAN | 59 | 410_PF_CI_tCombinationBranch90_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 78
SAN | 60 | 410_PF_CI_tCornerBranch88_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 79
SAN | 61 | 410_PF_CI_tSweptEntryBranch88_Spigot_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 80
SAN | 62 | 410_PF_CI_uShortPipeRoundAccessDoor_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 81
SAN | 63 | 410_PF_CI_uTrapHorizontal_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 82
SAN | 64 | 410_PF_CI_xDoubleBranch45_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 83
SAN | 65 | 410_PF_CI_xDoubleBranch70Deg_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 84
SAN | 66 | 410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 85
SAN | 67 | 410_PF_CS_cEndCaps_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 86
SAN | 68 | 410_PF_CS_eLongRadiusElbows_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 87
SAN | 69 | 410_PF_CS_eLongRadiusReturnBends_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 88
SAN | 70 | 410_PF_CS_eRadiusElbows_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 89
SAN | 71 | 410_PF_CS_fPlaneFlange_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 90
SAN | 72 | 410_PF_CS_rConcentricReducers_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 91
SAN | 73 | 410_PF_CS_rConnector_MapressAndFemaleThread.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 92
SAN | 74 | 410_PF_CS_uConnector_MapressAndFemaleThread.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 93
SAN | 75 | 410_PF_DI_cBellmouth_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 94
SAN | 76 | 410_PF_DI_cBlind_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 95
SAN | 77 | 410_PF_DI_cCap_KType.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 96
SAN | 78 | 410_PF_DI_cPlug_TType.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 97
SAN | 79 | 410_PF_DI_eBend_Flange.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 98
SAN | 80 | 410_PF_DI_eBend_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 99
SAN | 81 | 410_PF_DI_eDuckfoodBend90Deg_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 100
SAN | 82 | 410_PF_DI_fFlange_RFType.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 101
SAN | 83 | 410_PF_DI_rFlangedCover.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 102
SAN | 84 | 410_PF_DI_uConnector_FlangedAndSocket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 103
SAN | 85 | 410_PF_DI_fFlange_Spigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 104
SAN | 86 | 410_PF_DI_rTapper_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 105
SAN | 87 | 410_PF_DI_rTapper_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 106
SAN | 88 | 410_PF_DI_tLevelInvertTee_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 107
SAN | 89 | 410_PF_DI_tTee_SocketAndFlangedBranch.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 108
SAN | 90 | 410_PF_DI_tTeeSocketWithLevelInvertFlangedBranch.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 109
SAN | 91 | 410_PF_DI_tTee_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 110
SAN | 92 | 410_PF_DI_tTee_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 111
SAN | 93 | 410_PF_DI_uAdaptorRestrained_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 112
SAN | 94 | 410_PF_DI_uFlangeAdaptor.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 113
SAN | 95 | 410_PF_DI_uUnion_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 3 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 114
SAN | 96 | 410_PF_DI_tDoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 115
SAN | 98 | 410_PF_EPDM_mKonfixConnector_PushOnJoint.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 116
SAN | 99 | 410_PF_eSweptBendLong_Medium_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 117
SAN | 100 | 410_PF_HDPE_fLooseFlange_Flanged.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 118
SAN | 101 | 410_SE_FireCollar_Horizontal.rfa |  | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 119
SAN | 102 | 410_SE_FireCollar_Vertical.rfa |  | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 120
SAN | 103 | 410_PF_GS_cFrogFlap_Socket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 121
SAN | 104 | 410_PF_GS_cSealingPlugsWithVentilationSlots_PushOnJoint.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 122
SAN | 105 | 410_PF_GS_eAngleBend_1PushShortSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 123
SAN | 106 | 410_PF_GS_eAngleBend_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 124
SAN | 107 | 410_PF_GS_eBasinConnector_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 125
SAN | 108 | 410_PF_GS_eBendWithCalm_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 126
SAN | 109 | 410_PF_GS_eBend_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 127
SAN | 110 | 410_PF_GS_eBend_NoSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 128
SAN | 111 | 410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 129
SAN | 112 | 410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 130
SAN | 113 | 410_PF_GS_eReductionAngleBend_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 131
SAN | 114 | 410_PF_GS_uGutterRound_SocketAndStandard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 132
SAN | 115 | 410_PF_GS_mOptimisationPart_1PushSocket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 133
SAN | 116 | 410_PF_GS_mSBendTrap_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 134
SAN | 117 | 410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 135
SAN | 118 | 410_PF_GS_rAdapterConcentric_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 136
SAN | 119 | 410_PF_GS_rAdapterEccentric_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 137
SAN | 120 | 410_PF_GS_rConcentricOptimiser_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 138
SAN | 121 | 410_PF_GS_rTransitiontoCastIron_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 139
SAN | 122 | 410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 140
SAN | 123 | 410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 141
SAN | 124 | 410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 142
SAN | 125 | 410_PF_GS_tTeeBranches_2PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 143
SAN | 126 | 410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 144
SAN | 127 | 410_PF_GS_uBends_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 145
SAN | 128 | 410_PF_GS_uGutterPipes_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 146
SAN | 129 | 410_PF_GS_uLongCleaningOpening_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 147
SAN | 130 | 410_PF_GS_uLongCleaningOpening_NoSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 148
SAN | 131 | 410_PF_GS_uLongUnion_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 149
SAN | 132 | 410_PF_GS_uSpigottoPlastic_1PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 150
SAN | 133 | 410_PF_GS_uTransitionSMLtoGMX_1PushSocket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 151
SAN | 134 | 410_PF_GS_uTranstiontoCastIron_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 152
SAN | 135 | 410_PF_GS_uUnion_2PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 153
SAN | 136 | 410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 4 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 154
SAN | 137 | 410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 155
SAN | 138 | 410_PF_HDPE_cProtectionCap.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 156
SAN | 139 | 410_PF_HDPE_cProtectionCapForPipeEnd_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 157
SAN | 140 | 410_PF_HDPE_cThreadedConnectorWithScrewCap.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 158
SAN | 141 | 410_PF_HDPE_eBend90Deg_Reducer_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 159
SAN | 142 | 410_PF_HDPE_eBend_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 160
SAN | 143 | 410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 161
SAN | 144 | 410_PF_HDPE_eBend88DegWithLateralSupplementary_Standard_ForFloorStandingWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 162
SAN | 145 | 410_PF_HDPE_eConnectionBend90DegForSleeve_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 163
SAN | 146 | 410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 164
SAN | 147 | 410_PF_HDPE_eRightOffsetBend90Deg_Standard_ForFloorStandingWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 165
SAN | 148 | 410_PF_HDPE_eScrewCap.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 166
SAN | 149 | 410_PF_HDPE_eSegmentBend_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 167
SAN | 150 | 410_PF_HDPE_tDoubleConnectionBend90Deg_ForSleeve.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 168
SAN | 151 | 410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 169
SAN | 152 | 410_PF_HDPE_tDoubleConnectionBend90Deg_SlipJoint_VerticalForWallHungWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 170
SAN | 153 | 410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 171
SAN | 154 | 410_PF_HDPE_mRunningTrap_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 172
SAN | 155 | 410_PF_HDPE_mSoventFitting_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 173
SAN | 156 | 410_PF_HDPE_mSTrap_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 174
SAN | 157 | 410_PF_HDPE_mUniversalTrap_WithFlangeBushing.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 175
SAN | 158 | 410_PF_HDPE_mWasteManifold.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 176
SAN | 159 | 410_PF_HDPE_rAdaptorSocket_DN90xDN100.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 177
SAN | 160 | 410_PF_HDPE_rCompressionJoint_MechanicalJoint.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 178
SAN | 161 | 410_PF_HDPE_rReducer_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 179
SAN | 162 | 410_PF_HDPE_mReducedRingSealSocket_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 180
SAN | 163 | 410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 181
SAN | 164 | 410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 182
SAN | 165 | 410_PF_HDPE_tLateralTee_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 183
SAN | 166 | 410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 184
SAN | 167 | 410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 185
SAN | 168 | 410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 186
SAN | 169 | 410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 187
SAN | 170 | 410_PF_HDPE_uAdapterUnion_FemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 188
SAN | 171 | 410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 189
SAN | 172 | 410_PF_HDPE_rReducerAdaptor_MaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 190
SAN | 173 | 410_PF_HDPE_uClampingConnector.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 191
SAN | 174 | 410_PF_HDPE_uExpansion_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 192
SAN | 175 | 410_PF_HDPE_uFlangeAdapter_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 193
SAN | 176 | 410_PF_HDPE_uFlangeBushing_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 5 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 194
SAN | 177 | 410_PF_HDPE_uFlangeSet.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 195
SAN | 178 | 410_PF_HDPE_uStraightAdapterToCastIronPipe.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 196
SAN | 179 | 410_PF_HDPE_uStraightAdapterHDPEToPVC_ButtFusionAndPushOnJoint.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 197
SAN | 180 | 410_PF_HDPE_uStraightAdapter_CompressionAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 198
SAN | 181 | 410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 199
SAN | 182 | 410_PF_HDPE_uStraightConnectorForWC_ButtFusionAndPushOnJoint.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 200
SAN | 183 | 410_PF_HDPE_uStraightConnector_ForFloorStandingWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 201
SAN | 184 | 410_PF_HDPE_uUnion_FemaleThreadAndCompression.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 202
SAN | 185 | 410_PF_HDPE_uUnionConnection_WeldingJoints.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 203
SAN | 186 | 410_PF_HDPE_xDoubleBrandFitting45Deg_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 204
SAN | 187 | 410_PF_GA_mPTrapGMX_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 205
SAN | 188 | 410_PF_HDPE_mPTrap.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 206
SAN | 189 | 410_PF_PE_eBendForWandWC.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 207
SAN | 190 | 410_PF_PPR_cEndCap_SocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 208
SAN | 191 | 410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 209
SAN | 192 | 410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 210
SAN | 193 | 410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 211
SAN | 194 | 410_PF_PPR_eElbow_SocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 212
SAN | 195 | 410_PF_PPR_rCoupling_FemaleThreadAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 213
SAN | 196 | 410_PF_PPR_mCoupling_MaleThreadAndSocketFusion |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 214
SAN | 197 | 410_PF_PPR_eElbow90Deg_MaleThreadAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 215
SAN | 198 | 410_PF_PPR_rReducing_SocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 216
SAN | 199 | 410_PF_PPR_tTee_FemaleThreadedAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 217
SAN | 200 | 410_PF_PPR_tTee_MaleThreadedAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 218
SAN | 201 | 410_PF_PPR_tTee_SocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 219
SAN | 202 | 410_PF_PPR_mCoupling_FemaleThreadAndSocketFusion |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 220
SAN | 203 | 410_PF_PPR_uCoupling_MaleThreadAndSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 221
SAN | 204 | 410_PF_PPR_uUnion_BushSocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 222
SAN | 205 | 410_PF_PPR_uUnion_SocketFusion.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 223
SAN | 206 | 410_PF_PPMD_xDuctBranchSweptEntry88DegLeft_SocketAndSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 224
SAN | 207 | 410_PF_PPMD_tBranchSweptEntry88Deg_SocketAndSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 225
SAN | 208 | 410_PF_PPMD_tDoubleConnectionBend90Deg_Extended_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 226
SAN | 209 | 410_PF_PP_uAccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 227
SAN | 210 | 410_PF_EPDM_mSleeveToCastIron_MechanicalJoint_Silent |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 228
SAN | 211 | 410_PF_PPMD_eBend_SocketAndSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 229
SAN | 212 | 410_PF_PP_tBranch_SocketSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 230
SAN | 213 | 410_PF_PPMD_cEndCap_Socket_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 231
SAN | 214 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 232
SAN | 215 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 233
SAN | 216 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 6 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 234
SAN | 217 | 410_PF_PP_mOdorTrapForSinkHorizontal_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 235
SAN | 218 | 410_PF_PP_mOdorTrapForSinkVertical_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 236
SAN | 219 | 410_PF_PP_mOdorTrapForSinkVerticalAndHorizontal_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 237
SAN | 220 | 410_PF_PPMD_wParallelBrand45Deg_SocketAndSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 238
SAN | 221 | 410_PF_PPMD_rReducerEccentric_SocketAndSpigot_Silent.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 239
SAN | 222 | 410_PF_PP_uSilentSlipCoupling_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 240
SAN | 223 | 410_PF_SilentPro_cCapEnd_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 241
SAN | 224 | 410_PF_PPMX_eElbow_SocketAndSpigot_SilentPro.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 242
SAN | 225 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_SilentPro.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 243
SAN | 226 | 410_PF_PPMD_mCornerBranch88Deg_SocketAndSpigot_SilentPro.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 244
SAN | 227 | 410_PF_PPMX_rReducerEccentric_SocketAndSpigot_SilentPro.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 245
SAN | 228 | 410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 246
SAN | 229 | 410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 247
SAN | 230 | 410_PF_SilentPro_tTeeBranch_SocketSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 248
SAN | 231 | 410_PF_PPMD_uAccessPipe90DegWithRoundServiceOpening_SocketAndSpigot_SilentPro.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 249
SAN | 232 | 410_PF_PPMX_uSlipCoupling_PushOnJoint_SilentPro.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 250
SAN | 233 | 410_PF_PPMX_wParallelBrand45Deg_SocketAndSpigot_SilentPro.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 251
SAN | 234 | 410_PF_SilentPro_xCrossDoubleBranchFitting88DegSweptEntry_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 252
SAN | 235 | 410_PF_SS_uUnion_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 253
SAN | 236 | 410_PF_SS_cCap_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 254
SAN | 237 | 410_PF_SS_cDrainplugWithScrewedPlug.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 255
SAN | 238 | 410_PF_SS_cSocketPlug.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 256
SAN | 239 | 410_PF_SS_cSocketPlugWithClamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 257
SAN | 240 | 410_PF_SS_cVentCowl_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 258
SAN | 241 | 410_PF_SS_eBend45Degrees_SocketAndStandard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 259
SAN | 242 | 410_PF_SS_eBend87_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 260
SAN | 243 | 410_PF_SS_eBendWith250mmOblong_Clamp.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 261
SAN | 244 | 410_PF_SS_eBend_15_1Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 262
SAN | 245 | 410_PF_SS_eBend_30_1Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 263
SAN | 246 | 410_PF_SS_eElbow90DegAdaptor_FemaleThreadedAndPlainEndAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 264
SAN | 247 | 410_PF_SS_eElbow90DegAdaptor_MaleThreadAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 265
SAN | 248 | 410_PF_SS_eElbow90DegTapConnector_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 266
SAN | 249 | 410_PF_SS_eElbow90Deg_FemaleThreadAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 267
SAN | 250 | 410_PF_SS_eElbowTapConector90Degree_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 268
SAN | 251 | 410_PF_SS_eElbow_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 269
SAN | 252 | 410_PF_SS_eLongBend_1Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 270
SAN | 253 | 410_PF_SS_ePTrap_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 271
SAN | 254 | 410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 272
SAN | 255 | 410_PF_SS_mCornerElbow90Deg_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 273
SAN | 256 | 410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 274
SAN | 257 | 410_PF_SS_uRapid_Coupling.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 275
SAN | 258 | 410_PF_SS_rConcentricIncreaserCoupling_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 276
SAN | 259 | 410_PF_SS_rConnectorExternalThreadSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 277
SAN | 260 | 410_PF_SS_rConnectorInternal_ThreadSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 278
SAN | 261 | 410_PF_SS_rConnectorWithSocketAndFlange.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 279
SAN | 262 | 410_PF_SS_rConnector_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 280
SAN | 263 | 410_PF_SS_rConnector_SocketAndThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 281
SAN | 264 | 410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 282
SAN | 265 | 410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 283
SAN | 266 | 410_PF_SS_rReducerWithPlainEnd_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 284
SAN | 267 | 410_PF_SS_rTransition_SocketAndFemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 285
SAN | 268 | 410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 286
SAN | 269 | 410_PF_SS_tTPiece_Mapress_Equal |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 287
SAN | 270 | 410_PF_SS_tReducingDoubleBranch45_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 288
SAN | 271 | 410_PF_SS_tReducingSingleBranch45Degree_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 289
SAN | 272 | 410_PF_SS_tReducingSingleBranch87Deg_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 290
SAN | 273 | 410_PF_SS_tSingleBranch45_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 291
SAN | 274 | 410_PF_SS_tSweptBranch87Deg_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 292
SAN | 275 | 410_PF_SS_tTeePiece_FemaleThreadedAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 293
SAN | 276 | 410_PF_SS_tTeePiece_MaleThreadedAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 294
SAN | 277 | 410_PF_SS_tTeePiece_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 295
SAN | 278 | 410_PF_SS_tPieceReducer_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 296
SAN | 279 | 410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 297
SAN | 280 | 410_PF_SS_uAdaptorUnion_MaleThreadAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 298
SAN | 281 | 410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 299
SAN | 282 | 410_PF_SS_uAdaptor_WithFemaleThreadAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 300
SAN | 283 | 410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 301
SAN | 284 | 410_PF_SS_uAdaptor_WithMaleThreadAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 302
SAN | 285 | 410_PF_SS_uAdaptorWithPlainEnd_MaleThreadAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 303
SAN | 286 | 410_PF_SS_uAxialExpansion_PressingSockets.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 304
SAN | 287 | 410_PF_SS_uBulkhead_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 305
SAN | 288 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndWelded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 306
SAN | 289 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndMapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 307
SAN | 290 | 410_PF_SS_uConnector_FlangedAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 308
SAN | 291 | 410_PF_SS_uConnector_SocketAndThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 309
SAN | 292 | 410_PF_SS_uCoupling_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 310
SAN | 293 | 410_PF_SS_uExpansionSocket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 311
SAN | 294 | 410_PF_SS_uPeakPressure_Standard.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 312
SAN | 295 | 410_PF_SS_uRatStop_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 313
SAN | 296 | 410_PF_SS_uRepairCoupling_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 314
SAN | 297 | 410_PF_SS_uSocketClamp_Special.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 315
SAN | 298 | 410_PF_SS_uSocketClamp_Twopiece.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 316
SAN | 299 | 410_PF_SS_uStraightCoupling_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 317
SAN | 300 | 410_PF_SS_uUnion_Mapress.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 318
SAN | 301 | 410_PF_SS_wCleaningPipes.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 319
SAN | 302 | 410_PF_SS_xCornerBranch87Deg_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 320
SAN | 303 | 410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 321
SAN | 304 | 410_PF_SS_xDoubleBranch87_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 322
SAN | 305 | 410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 323
SAN | 306 | 410_PF_ST_SanpressDoubleWallPane_Threaded_DN15.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 324
SAN | 307 | 410_PF_UPVC_cCap_FemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 325
SAN | 308 | 410_PF_UPVC_cCap_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 326
SAN | 309 | 410_PF_UPVC_eBend90Deg_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 327
SAN | 310 | 410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 328
SAN | 311 | 410_PF_UPVC_eElbow90Deg_FemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 329
SAN | 312 | 410_PF_UPVC_eElbow_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 330
SAN | 313 | 410_PF_UPVC_eReducerElbow_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 331
SAN | 314 | 410_PF_UPVC_eShortBend90Deg_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 332
SAN | 315 | 410_PF_UPVC_rBushReducing_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 333
SAN | 316 | 410_PF_UPVC_rLongBushReducing_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 334
SAN | 317 | 410_PF_UPVC_rShortBushReducing_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 335
SAN | 318 | 410_PF_UPVC_tLateralTee90Deg_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 336
SAN | 319 | 410_PF_UPVC_tTee90Deg_FemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 337
SAN | 320 | 410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 338
SAN | 321 | 410_PF_UPVC_tTee_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 339
SAN | 322 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 340
SAN | 323 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 341
SAN | 324 | 410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 342
SAN | 325 | 410_PF_UPVC_uCoupling_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 343
SAN | 326 | 410_PF_UPVC_uInspectionPort_Glue.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 344
SAN | 327 | 410_PF_UPVC_uSiphon_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 345
SAN | 328 | 410_PF_UPVC_xCross_Socket.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 346
SAN | 329 | 410_PF_CS_eRadiusReturnBends_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 347
SAN | 330 | 410_PF_CS_tTee_Welded.rfa |  | 410_PF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 348
SAN | B.2 | PA + NF |  |  | 101 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 349
SAN | 1 | 410_NF_GS_rConcentric_NoSocket_GMX.rfa |  | 410_NF | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 350
SAN | 2 | 410_PA_Adapter&ExpansionPiece_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 351
SAN | 3 | 410_PA_AirReleaseValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 352
SAN | 4 | 410_PA_AngleSafetyValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 353
SAN | 5 | 410_PA_AngleSeatPistonValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 354
SAN | 6 | 410_PA_AngleSeatPistonValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 355
SAN | 7 | 410_PA_AngleValve_Threaded_WithRegulatingFunction.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 356
SAN | 8 | 410_PA_AutomaticBackwashFilter_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 9 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 357
SAN | 9 | 410_PA_AutomaticCirculationRegulatingValve.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 358
SAN | 10 | 410_PA_AutomaticHygieneFlushingStationHS10_Geberit.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 359
SAN | 11 | 410_PA_BackflowPreventerValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 360
SAN | 12 | 410_PA_BackflowPreventer_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 361
SAN | 13 | 410_PA_BallValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 362
SAN | 14 | 410_PA_BallValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 363
SAN | 15 | 410_PA_CoarseTrap.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 364
SAN | 16 | 410_PA_CombinationAngleValve_Standard.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 365
SAN | 17 | 410_PA_DiaphragmValve.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 366
SAN | 18 | 410_PA_DoubleInstallationRackWatermeter_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 367
SAN | 19 | 410_PA_DrainValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 368
SAN | 20 | 410_PA_FillSetStandardValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 369
SAN | 21 | 410_PA_FillsoftHousing_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 370
SAN | 22 | 410_PA_Filter_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 371
SAN | 23 | 410_PA_FittingSpacerForWaterMeter_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 372
SAN | 24 | 410_PA_FlexibleConnection_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 373
SAN | 25 | 410_PA_FloatingValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 374
SAN | 26 | 410_PA_FlowSplitterBox_Floor_Threaded_KHS.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 375
SAN | 27 | 410_PA_FlowSplitterSet_Threaded_KHS.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 376
SAN | 28 | 410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 377
SAN | 29 | 410_PA_FlowSplitterUnit_Threaded_DynamicKHS.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 378
SAN | 30 | 410_PA_FlowTemperatureMeterValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 379
SAN | 31 | 410_PA_FlushMountedStopValve_Mapress_UpPlus.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 380
SAN | 32 | 410_PA_FlushMoutedStopValve_Threaded_UpPlus.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 381
SAN | 33 | 410_PA_FunnelSiphon_Horizontal.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 382
SAN | 34 | 410_PA_GateValveSealingDirectionWithDrain_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 383
SAN | 35 | 410_PA_GateValveWithDrain_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 384
SAN | 36 | 410_PA_GateValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 385
SAN | 37 | 410_PA_GateValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 386
SAN | 38 | 410_PA_GlobeValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 387
SAN | 39 | 410_PA_GlobeValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 388
SAN | 40 | 410_PA_KHSFlushPoint_Threaded_230V.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 389
SAN | 41 | 410_PA_KHSFlushPoint_Threaded_24V.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 390
SAN | 42 | 410_PA_KHSFlushPoint_Threaded_ControlPlus230V.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 391
SAN | 43 | 410_PA_KHSFlushPoint_Threaded_ControlPlus24V.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 392
SAN | 44 | 410_PA_KugelSiphon_Standard.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 393
SAN | 45 | 410_PA_MotorButterflyValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 394
SAN | 46 | 410_PA_NozzleCheckValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 395
SAN | 47 | 410_PA_OutletValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 396
SAN | 48 | 410_PA_OutletValve_Threaded_WithHoseScrewConnection.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 10 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 397
SAN | 49 | 410_PA_PoolMainDrain_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 398
SAN | 50 | 410_PA_PoolReturnJet_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 399
SAN | 51 | 410_PA_PoolSkimmer_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 400
SAN | 52 | 410_PA_BallValve_SocketFusion.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 401
SAN | 53 | 410_PA_StopValve_SocketFusion.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 402
SAN | 54 | 410_PA_PressureGauge.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 403
SAN | 55 | 410_PA_PressureGauge_WithSiphon.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 404
SAN | 56 | 410_PA_PressureReducingValveFilterCombination_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 405
SAN | 57 | 410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 406
SAN | 58 | 410_PA_PressureReducingValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 407
SAN | 59 | 410_PA_PressureReducingValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 408
SAN | 60 | 410_PA_PressureRegulator_Thread.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 409
SAN | 61 | 410_PA_SamplingValveForWashBasinAngleValve_Standard_SS.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 410
SAN | 62 | 410_PA_SamplingValve_Standard_Gunmetal.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 411
SAN | 63 | 410_PA_SamplingValve_Standard_SS.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 412
SAN | 64 | 410_PA_ShutoffValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 413
SAN | 65 | 410_PA_ShutoffValve_Flanged_DrainValve.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 414
SAN | 66 | 410_PA_ShutoffValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 415
SAN | 67 | 410_PA_ShutoffValve_WithDrainPlug_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 416
SAN | 68 | 410_PA_SingleInstallationRackWatermeter_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 417
SAN | 69 | 410_PA_SolenoidControlValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 418
SAN | 70 | 410_PA_ShutoffValve_Mapress_WithDrainValve.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 419
SAN | 71 | 410_PA_ShutoffValve_MapressGeberit.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 420
SAN | 72 | 410_PA_StraightSafetyValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 421
SAN | 73 | 410_PA_StaticBalancingValve_Threaded_MultiFixPlus.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 422
SAN | 74 | 410_PA_StaticBalancingValve_UnionThreaded_MultiFixPlus.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 423
SAN | 75 | 410_PA_SwingcheckValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 424
SAN | 76 | 410_PA_SwingcheckValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 425
SAN | 77 | 410_PA_SystemSeparator_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 426
SAN | 78 | 410_PA_SystemSeparator_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 427
SAN | 79 | 410_PA_TemperatureMeasuringValve_Threaded_KHS.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 428
SAN | 80 | 410_PA_THandleBallValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 429
SAN | 81 | 410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 430
SAN | 82 | 410_PA_ThreePiecesBallValve_Welded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 431
SAN | 83 | 410_PA_ThreeWayMotorisedControlValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 432
SAN | 84 | 410_PA_ThreeWayMotorisedControlValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 433
SAN | 85 | 410_PA_TwoWayDiaphragmValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 434
SAN | 86 | 410_PA_TwoWayDiaphragmValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 435
SAN | 87 | 410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 436
SAN | 88 | 410_PA_UpETATHERMThermostaticBalancingValve_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 11 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 437
SAN | 89 | 410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 438
SAN | 90 | 410_PA_UPVSenkrecht.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 439
SAN | 91 | 410_PA_UPConcealedShutoffValve.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 440
SAN | 92 | 410_PA_VAVFullFlowShutOffValve_FemaleThreaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 441
SAN | 93 | 410_PA_VentCowl.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 442
SAN | 94 | 410_PA_WaferButterflyValve_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 443
SAN | 95 | 410_PA_WaterHammerArrestor_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 444
SAN | 96 | 410_PA_WaterMeterUNI.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 445
SAN | 97 | 410_PA_WaterMeter_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 446
SAN | 98 | 410_PA_WaterMeter_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 447
SAN | 99 | 410_PA_YStrainer_Flanged.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 448
SAN | 100 | 410_PA_YStrainer_Threaded.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 449
SAN | 101 | 410_PA_ZBCapRoof_Standard.rfa |  | 410_PA | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 450
SAN | B.3 | PX_Plumbing Fixure |  |  | 53 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 451
SAN | 1 | 410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 452
SAN | 2 | 410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 453
SAN | 3 | 410_PX_BasementFloorDrain_Vertical_Coupling_CastIron.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 454
SAN | 4 | 410_PX_StainlessSteelBoxGutters_Horizontal_Coupling.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 455
SAN | 5 | 410_PX_BoxGutters_Vertical_Coupling_StainlessSteel.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 456
SAN | 6 | 410_PX_DoppelPumpStationPowerlift_ACO.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 457
SAN | 7 | 410_PX_DrainageChannel_B125.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 458
SAN | 8 | 410_PX_DuofixElementForSinkAGB.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 459
SAN | 9 | 410_PX_DuofixElementForWallHungWC.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 460
SAN | 10 | 410_PX_DuofixElementForWallHungWC_BarrierFree.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 461
SAN | 11 | 410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 462
SAN | 12 | 410_PX_DuofixElementForWashbasin.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 463
SAN | 13 | 410_PX_DuofixElementForWashBasin_BarrierFree.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 464
SAN | 14 | 410_PX_DuofixElementInsetWashbasin_PillarTap.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 465
SAN | 15 | 410_PX_DuofixForShower&Bathtub.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 466
SAN | 16 | 410_PX_DuofixForShower&Bathtub_WallFittingAP.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 467
SAN | 17 | 410_PX_DuofixForUrinal.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 468
SAN | 18 | 410_PX_DuofixForUrinal_Universal.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 469
SAN | 19 | 410_PX_DuofixSigmaToilet12cm_BarrierFree.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 470
SAN | 20 | 410_PX_DuofixTraverseForStandaloneFaucetKitchenSink.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 471
SAN | 21 | 410_PX_FaucetWithFlexibleHose.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 472
SAN | 22 | 410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 473
SAN | 23 | 410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 474
SAN | 24 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 475
SAN | 25 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 476
SAN | 26 | 410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 477
SAN | 27 | 410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 478
SAN | 28 | 410_PX_FloorDrain_Horizontal_Coupling_CastIron.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 479
SAN | 29 | 410_PX_FloorDrain_Horizontal_Coupling_Plastic.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 480
SAN | 30 | 410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 481
SAN | 31 | 410_PX_FloorDrain_VerticalFinor2PartL15_Coupling_CastIron.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 482
SAN | 32 | 410_PX_CastIronFloorDrain_Vertical_Coupling.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 483
SAN | 33 | 410_PX_FloorDrain_Vertical_Coupling_Plastic.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 484
SAN | 34 | 410_PX_FloorDrain_Vertical_Coupling_StainlessSteel.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 485
SAN | 35 | 410_PX_GardenWater_Kemper.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 486
SAN | 36 | 410_PX_GreaseDisposalPoint.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 487
SAN | 37 | 410_PX_GullyGrating.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 488
SAN | 38 | 410_PX_HorizontalFloorDrain.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 489
SAN | 39 | 410_PX_InspectionShaft_OnePipe_Nosystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 490
SAN | 40 | 410_PX_InspectionShaft_TwoPipe_Nosystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 12 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 491
SAN | 41 | 410_PX_KitchenTap.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 492
SAN | 42 | 410_PX_ManholeAdjustingUnits_Round_NoSystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 493
SAN | 43 | 410_PX_ManholeBase_CastIn.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 494
SAN | 44 | 410_PX_ManholeChamberUnits_Round_NoSystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 495
SAN | 45 | 410_PX_ManholeCoverSlabs_Eccentrical_NoSystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 496
SAN | 46 | 410_PX_ManholeReducingSlabs_Eccentrical_NoSystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 497
SAN | 47 | 410_PX_ManholeTaper_EccentricalCones_NoSystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 498
SAN | 48 | 410_PX_Manhole_Round.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 499
SAN | 49 | 410_PX_ReusedRainWaterTank.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 500
SAN | 50 | 410_PX_RoadGully.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 501
SAN | 51 | 410_PX_SumpPit_NoSystem.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 502
SAN | 52 | 410_PX_TapWithMaleHose_Threaded_DN15.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 503
SAN | 53 | 410_PX_WaterTap.rfa |  | 410_PX | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 504
SAN | B.4 | SE |  |  | 3 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 505
SAN | 1 | 410_SE_Conlit150U_NoSystem.rfa |  | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 506
SAN | 2 | 410_SE_ConlitFireProtectionSleeve_NoSystem.rfa |  | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 507
SAN | 3 | 410_SE_CoverBox.rfa |  | 410_SE | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 508
SAN | B.5 | ME |  |  | 104 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 509
SAN | 1 | 410_ME_CentrifugalPump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 510
SAN | 2 | 410_ME_CompactPressureBoostingSystem.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 511
SAN | 3 | 410_ME_CompactPressureBoostingSystem_1MVISE.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 512
SAN | 4 | 410_ME_CompactWaterHeater_WallMounted.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 513
SAN | 5 | 410_ME_Desoftening.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 514
SAN | 6 | 410_ME_DoppelHebeanlageSchmutzwasser.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 515
SAN | 7 | 410_ME_DoublePressureBoosterSystem.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 516
SAN | 8 | 410_ME_DrainLiftL_Floor.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 517
SAN | 9 | 410_ME_DrainLiftM_Floor.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 518
SAN | 10 | 410_ME_DrainLiftS_Floor.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 13 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 519
SAN | 11 | 410_ME_DrainLiftXL_Floor.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 520
SAN | 12 | 410_ME_DualTank_WaterSofteners.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 521
SAN | 13 | 410_ME_DuplexSofteningUnit_RondomatDuo.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 522
SAN | 14 | 410_ME_EKleindurchlauferhitzerCEX.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 523
SAN | 15 | 410_ME_EKleindurchlauferhitzer_MCX.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 524
SAN | 16 | 410_ME_ElectricInstantaneousHeater_DLE.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 525
SAN | 17 | 410_ME_ExpansionVessel.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 526
SAN | 18 | 410_ME_ExpansionVessel_Reflex.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 527
SAN | 19 | 410_ME_FettabscheiderNG2.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 528
SAN | 20 | 410_ME_FreshWaterStation.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 529
SAN | 21 | 410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 530
SAN | 22 | 410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 531
SAN | 23 | 410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 532
SAN | 24 | 410_ME_GreaseSeparatorFreeStandingInstallationNS10.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 533
SAN | 25 | 410_ME_GreaseSeparator_FloorStand.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 534
SAN | 26 | 410_ME_HighPerformanceIndustrialMixers.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 535
SAN | 27 | 410_ME_HotWaterStorageTank.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 536
SAN | 28 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 537
SAN | 29 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 538
SAN | 30 | 410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 539
SAN | 31 | 410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 540
SAN | 32 | 410_ME_IBCTank.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 541
SAN | 33 | 410_ME_iboxUniversalForShower_WallRecessed.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 542
SAN | 34 | 410_ME_InstantaneousWaterHeater_Shower.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 543
SAN | 35 | 410_ME_InstantaneousWaterHeater_SinkAGB.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 544
SAN | 36 | 410_ME_InstantaneousWaterHeater_TeaKitchen.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 545
SAN | 37 | 410_ME_InstantaneousWaterHeater_WashBasin.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 546
SAN | 38 | 410_ME_KHSHygieneFlushBoxLITE_FlowSensorDoublePortwithThreaded.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 547
SAN | 39 | 410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 548
SAN | 40 | 410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 549
SAN | 41 | 410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 550
SAN | 42 | 410_ME_KHSHygieneFlushBoxPUREwithFlowSensorSinglePort_Threaded.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 551
SAN | 43 | 410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 552
SAN | 44 | 410_ME_KHSMiniControlSystemSLAVE_WallSurface.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 553
SAN | 45 | 410_ME_KHSMiniControlSystem_WallSurface_Master.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 554
SAN | 46 | 410_ME_KHSTimer_WallSurface.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 555
SAN | 47 | 410_ME_MiniTresorCabinet_InWall.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 556
SAN | 48 | 410_ME_MiniTresorCabinet_WallSurface.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 557
SAN | 49 | 410_ME_MixingTank.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 558
SAN | 50 | 410_ME_PHController.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 559
SAN | 51 | 410_ME_PlasticInnerTankSeries.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 560
SAN | 52 | 410_ME_PoolHeatPump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 561
SAN | 53 | 410_ME_PoolSandFilter_FloorStand_Round.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 562
SAN | 54 | 410_ME_PressureBoosterPump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 563
SAN | 55 | 410_ME_PressurisationUnit_FixedSpeedUnits2Pump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 564
SAN | 56 | 410_ME_PressurisationUnit_FixedSpeedUnits3Pump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 565
SAN | 57 | 410_ME_PressurisationUnit_VariableSpeedUnits3Pump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 566
SAN | 58 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith1Pump |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 567
SAN | 59 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 568
SAN | 60 | 410_ME_Probenahmetopf.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 569
SAN | 61 | 410_ME_PumpGlandlessCirculator_StarZ.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 570
SAN | 62 | 410_ME_PumpGlandlessCirculator_StarZD.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 571
SAN | 63 | 410_ME_PumpGlandlessCirculator_TopZ.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 572
SAN | 64 | 410_ME_PureWaterTank.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 573
SAN | 65 | 410_ME_ReverseOsmosisSystem.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 574
SAN | 66 | 410_ME_SeparationStation.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 575
SAN | 67 | 410_ME_ServiceStorageTank_Round.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 576
SAN | 68 | 410_ME_Sicherheitstrennstation.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 577
SAN | 69 | 410_ME_SinglePressureBoosterSystem.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 578
SAN | 70 | 410_ME_StratosMAXOZPump_Vertical.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 579
SAN | 71 | 410_ME_StratosPICOZPump_Vertical.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 580
SAN | 72 | 410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 581
SAN | 73 | 410_ME_SubmergedPump_Horizontal_SatSeries.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 582
SAN | 74 | 410_ME_SubmergedPump_SitaSeries.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 15 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 583
SAN | 75 | 410_ME_SubmergedPump_Vertical_SATSeries.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 584
SAN | 76 | 410_ME_SubmergedPump_Vertical_SATVSeries.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 585
SAN | 77 | 410_ME_TresorCabinet_InWall.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 586
SAN | 78 | 410_ME_TresorCabinet_WallSurface.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 587
SAN | 79 | 410_ME_TripleSofteningSystem_DeltaP.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 588
SAN | 80 | 410_ME_TWPressureBoosterSystem.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 589
SAN | 81 | 410_ME_VerticaltubeHeatexchanger.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 590
SAN | 82 | 410_ME_WasteWaterLiftingStationPump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 591
SAN | 83 | 410_ME_WastewaterLiftingStation_DouPump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 592
SAN | 84 | 410_ME_WasteWaterLiftingStation_KesselPump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 593
SAN | 85 | 410_ME_WastewaterLiftingStation_MuliPES&Mono.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 594
SAN | 86 | 410_ME_WastewaterLiftingStation_MuliProPEKDuo.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 595
SAN | 87 | 410_ME_WastewaterLiftingStation_MuliProPEKParallel.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 596
SAN | 88 | 410_ME_WastewaterLiftingStation_MuliProPENXLDuo.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 597
SAN | 89 | 410_ME_WastewaterLiftingStation_MuliStarDDP.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 598
SAN | 90 | 410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 599
SAN | 91 | 410_ME_WastewaterLiftingStation_Sinkamat-HW.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 600
SAN | 92 | 410_ME_WasteWaterLiftingStation_VerticalPump.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 601
SAN | 93 | 410_ME_WasteWaterLift_Floor_C3.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 602
SAN | 94 | 410_ME_WasteWaterLift_Floor_CWC3.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 603
SAN | 95 | 410_ME_WasteWaterLift_Floor_D2.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 604
SAN | 96 | 410_ME_WasteWaterLift_Floor_WC1.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 605
SAN | 97 | 410_ME_WasteWaterLift_Floor_WC3.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 606
SAN | 98 | 410_ME_WaterDispenser_FloorStand.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 607
SAN | 99 | 410_ME_WaterFilterTank.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 608
SAN | 100 | 410_ME_WaterFilterVertical.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 609
SAN | 101 | 410_ME_WaterHardnessMeter.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 610
SAN | 102 | 410_ME_WaterHeaterWithTap_WallMounted.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 611
SAN | 103 | 410_ME_WaterHeater_WallMounted.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 612
SAN | 104 | 410_ME_WaterSofteningTank.rfa |  | 410_ME | Sanitary Revit Family | .rfa | MEP | DIG | 16 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | Yes | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 613
SAN | C | Create the Revit templates for each LPH SAN |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 614
SAN | C | TGA_Revit Template | [12 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 615
SAN | 1 | LPH3 |  |  | Revit Template | .rte | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 616
SAN | 2 | LPH5 |  |  | Revit Template | .rte | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 617
SAN | 3 | LPH8 |  |  | Revit Template | .rte | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 618
SAN | D | TGA_OUtput Checklists | [12 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 619
SAN | 1 | LPH3 Check list for SAN discipline |  |  |  | .xlsx | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 620
SAN | 2 | LPH3_Check list_SAN 01 |  |  | Define Checklist_layout Plan. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 621
SAN | 3 | LPH3_Check list_SAN 02 |  |  | Define Checklist_Isometric Drawing. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 622
SAN | 4 | LPH3_Check list_SAN 03 |  |  | Define Checklist_Schematic Diagram. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 623
SAN | 5 | LPH5 Check list for SAN discipline |  |  |  | .xlsx | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 624
SAN | 6 | LPH5_Check list_SAN 01 |  |  | Define Checklist_layout Plan. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 625
SAN | 8 | LPH5_Check list_SAN 02 |  |  | Define Checklist_Isometric Drawing. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 626
SAN | 9 | LPH5_Check list_SAN 03 |  |  | Define Checklist_Schematic Diagram. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 627
SAN | 10 | LPH8 Check list for SAN discipline |  |  |  | .xlsx | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 628
SAN | 11 | LPH8_Check list_SAN 01 |  |  | Define Checklist_layout Plan. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 629
SAN | 13 | LPH8_Check list_SAN 02 |  |  | Define Checklist_Isometric Drawing. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 630
SAN | 14 | LPH8_Check list_SAN 03 |  |  | Define Checklist_Schematic Diagram. |  | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 631
SAN | E | Sample Model + Out Put Data |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 632
SAN | E | Sample Model + Out Put Data For SAN | [12 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 633
SAN | 1 | Delivery layout Sample for SAN LPH3 |  |  | Execute a sample layout for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 634
SAN | 2 | Delivery layout Sample for SAN LPH5 |  |  | Execute a sample layout for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 635
SAN | 3 | Delivery layout Sample for SAN LPH8 |  |  | Execute a sample layout for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 636
SAN | 4 | Delivery Schematic Drawing Sample for SAN LPH3 |  |  | Execute a sample schematic for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 637
SAN | 5 | Delivery Schematic Drawing Sample for SAN LPH5 |  |  | Execute a sample schematic for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 638
SAN | 6 | Delivery Isometric Drawing Sample for SAN LPH3 |  |  | Execute a sample Isometric for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 639
SAN | 7 | Delivery Isometric Drawing Sample for SAN LPH5 |  |  | Execute a sample Isometric for the SAN discipline. | .pdf | MEP | DIG |  | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 640
SAN | F | Export layouts to Revizto & set up 3D Review SAN |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 641
SAN | 1 | Export layouts to Revizto & set up 3D Review SAN _LPH3 |  |  |  | .pdf | MEP | DIG |  | 2026-09-18 |  | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 642
SAN | 2 | Export layouts to Revizto & set up 3D Review SAN _LPH5 |  |  |  | .pdf | MEP | DIG |  | 2026-09-18 |  | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 643
SAN | 3 | Export layouts to Revizto & set up 3D Review SAN _LPH8 |  |  |  | .pdf | MEP | DIG |  | 2026-09-18 |  | 2026-09-25 | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 644
SAN | G | Lesson Learned |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 645
SAN | G | Lesson Learned SAN |  |  | What went well. What didn’t go well What we learned, Action items / Improvements | .pdf | MEP | DIG |  | 2026-09-25 |  |  | 2026-09-30 |  | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 646
SAN | TRM | Transmittal / Submitted |  | MEP | [10 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 649
SAN | AUD | Audit/Review |  | DIG | [10 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 650
SAN | REV | Revision Required / Revised |  | MEP | [10 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 651
SAN | CFM | Confimmation/Confirmed & Stored |  | DIG/MEP | [10 empty] | DCMvn_SAN_TIDP_Rev 05.xlsx | TIDP 410_Rev 04 | 652
ELT_MSR | A | Framework deliverables (apply to SAN ) |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 6
ELT_MSR | 1 | Define the "Graphical Annotation Framework" (ELT + MSR) | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 7
ELT_MSR | 1 |  | Define the "Graphical Annotation Framework" (ELT + MSR) |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 8
ELT_MSR | 1 |  | Define the "Graphical Annotation Framework" (ELT + MSR) |  | Fill the content for ELT and MSR disciplines | .xlsx | MEP | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 9
ELT_MSR | 1 |  | Define the "Graphical Annotation Framework" (ELT + MSR) |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 10
ELT_MSR | 2 | Define the "Data Requirement Framework" (ELT + MSR) | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 11
ELT_MSR | 2 |  | Define the "Data Requirement Framework" (ELT + MSR) |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 12
ELT_MSR | 2 |  | Define the "Data Requirement Framework" (ELT + MSR) |  | Fill the content for ELT and MSR disciplines | .xlsx | MEP | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 13
ELT_MSR | 2 |  | Define the "Data Requirement Framework" (ELT + MSR) |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 14
ELT_MSR | 3 | Define the process to revise the RFA library | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 15
ELT_MSR | 3 |  | Define the process to revise the RFA library |  | Confirm and sign the process document | .pdf | MEP | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 16
ELT_MSR | 3 |  | Define the process to revise the RFA library |  | Workshop the process with delivery team | .pptx | DIG | DIG | 0 | 2026-02-27 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 17
ELT_MSR | 4 | Define the desired outcome (ELT + MSR) | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 18
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH3 - ELT Cable trays | .pdf | MEP | MEP | 0 | 2026-05-08 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 19
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH3 - ELT Installations | .pdf | MEP | MEP | 0 | 2026-05-08 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 20
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH3 - ELT Lightning protection & Earthing system | .pdf | MEP | MEP | 0 | 2026-05-08 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 21
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample schematics as multiple scales for LPH3 - ELT | .pdf | MEP | MEP | 0 | 2026-05-08 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 22
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH5 - ELT Cable trays | .pdf | MEP | MEP | 0 | 2026-05-15 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 23
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH5 - ELT Installations | .pdf | MEP | MEP | 0 | 2026-05-15 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 24
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH5 - ELT Lightning protection & Earthing system | .pdf | MEP | MEP | 0 | 2026-05-15 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 25
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample schematics as multiple scales for LPH5 - ELT | .pdf | MEP | MEP | 0 | 2026-05-15 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 26
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH8 - ELT Cable trays | .pdf | MEP | MEP | 0 | 2026-05-22 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 27
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH8 - ELT Installations | .pdf | MEP | MEP | 0 | 2026-05-22 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 28
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH8 - ELT Lightning protection & Earthing system | .pdf | MEP | MEP | 0 | 2026-05-22 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 29
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample schematics as multiple scales for LPH8 - ELT | .pdf | MEP | MEP | 0 | 2026-05-22 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 30
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH3 - MSR | .pdf | MEP | MEP | 0 | 2026-05-29 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 31
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample schematics as multiple scales for LPH3 - MSR | .pdf | MEP | MEP | 0 | 2026-05-29 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 32
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH5 - MSR | .pdf | MEP | MEP | 0 | 2026-05-29 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 33
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample schematics as multiple scales for LPH5 - MSR | .pdf | MEP | MEP | 0 | 2026-05-29 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 34
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample layouts as multiple scales for LPH8 - MSR | .pdf | MEP | MEP | 0 | 2026-05-29 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 35
ELT_MSR | 4 |  | Define the desired outcome (ELT + MSR) |  | Produce the sample schematics as multiple scales for LPH8 - MSR | .pdf | MEP | MEP | 0 | 2026-05-29 |  |  |  |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 36
ELT_MSR | B | Revise the RFA library for ELT + MSR system |  | 413 |  |  | MEP | DIG | [6 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 37
ELT_MSR | B1 | ELT Discipline |  | 325 | 326 Families need to revise | [9 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 38
ELT_MSR | B.1.1 | EE_Electrical Equipment |  |  | 46 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 39
ELT_MSR | 1 | 440_EE_AutomaticTranferSwitchPanel.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 40
ELT_MSR | 2 | 440_EE_BatteryStorage.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 41
ELT_MSR | 3 | 442_EE_ChargeController.rfa |  | 442_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 42
ELT_MSR | 4 | 440_EE_CircuitBreakerEnclosure.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 43
ELT_MSR | 5 | 440_EE_DCtoAC_Inverter.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 44
ELT_MSR | 6 | 440_EE_DieselGenerator.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 45
ELT_MSR | 7 | 440_EE_DieselTankGenerator.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 46
ELT_MSR | 8 | 440_EE_DistributionBox_DALI.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 47
ELT_MSR | 9 | 440_EE_DryTransformer.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 48
ELT_MSR | 10 | 440_EE_ElectricalCabinet_Standard.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 49
ELT_MSR | 11 | 440_EE_FlatRoofSolar.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 50
ELT_MSR | 12 | 440_EE_FlatRoofSolarFrameWithRoot_NoSystem.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 51
ELT_MSR | 13 | 440_EE_FlatRoofSolarFrame_NoSystem.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 52
ELT_MSR | 14 | 440_EE_FlatRoofSolarModule.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 53
ELT_MSR | 15 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSEVU.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 54
ELT_MSR | 16 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSKälte.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 55
ELT_MSR | 17 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSNord.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 56
ELT_MSR | 18 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MsPvAnlage.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 57
ELT_MSR | 19 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSSüd.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 58
ELT_MSR | 20 | 440_EE_Generator_Standard.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 59
ELT_MSR | 21 | 440_EE_IndoorTransformer.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 60
ELT_MSR | 22 | 440_EE_kwhMeter_3Phases.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 61
ELT_MSR | 23 | 440_EE_LowVoltagePanel.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 1 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-25 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 62
ELT_MSR | 24 | 440_EE_LowVoltageSwitchboard_GHVNord_HOST.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 63
ELT_MSR | 25 | 440_EE_LowVoltageSwitchboard_GHVSüd_HOST.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 64
ELT_MSR | 26 | 440_EE_LowVoltageSwitchboard_NshvKälte_HOST.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 65
ELT_MSR | 27 | 440_EE_LowVoltageSwitchboard_NshvPV_HOST.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 66
ELT_MSR | 28 | 440_EE_MainDistributionBoard_WallMounted.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 67
ELT_MSR | 29 | 440_EE_MainSupply_GEVBnetwork.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 68
ELT_MSR | 30 | 440_EE_MainSupply_UPSmains.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 69
ELT_MSR | 31 | 440_EE_MainSwitchBoard.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 70
ELT_MSR | 32 | 440_EE_Manhole_Standard.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 71
ELT_MSR | 33 | 440_EE_MediumVoltageSwitchgear.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 72
ELT_MSR | 34 | 440_EE_MotorControlCenter_SwitchBoard.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 73
ELT_MSR | 35 | 440_EE_OilTransformer.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 74
ELT_MSR | 36 | 440_EE_OutdoorTransformer.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 75
ELT_MSR | 37 | 440_EE_PanelBoard.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 76
ELT_MSR | 38 | 440_EE_SilentDieselGenerator.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 77
ELT_MSR | 39 | 440_EE_SinglePhase_Panel.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 78
ELT_MSR | 40 | 440_EE_SpringVibration.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 79
ELT_MSR | 41 | 440_EE_SubmainSwitchBoard.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 80
ELT_MSR | 42 | 440_EE_SwitchCabinet_OutgoingPanel.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 81
ELT_MSR | 43 | 440_EE_SwitchCabinet_SupplyPanel.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 82
ELT_MSR | 44 | 440_EE_SynchronizationPanel.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 83
ELT_MSR | 45 | 440_EE_TransferDistributor.rfa |  | 440_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 84
ELT_MSR | 46 | 456_EE_BMABusCoupler.rfa |  | 456_EE | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 85
ELT_MSR | B.1.2 | EF_Electrical Fixtures |  |  | 88 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 86
ELT_MSR | 1 | 440_EF_360DegreeRadiusMotionDetector_CeilingMounted.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 87
ELT_MSR | 2 | 446_EF_AirTerminationRodsForMetalRoofs.rfa |  | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 88
ELT_MSR | 3 | 446_EF_AirTerminationRods_FloorStand.rfa |  | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 89
ELT_MSR | 4 | 440_EF_AL_SideFeedingUnitForTransformer_Busway.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 90
ELT_MSR | 5 | 440_EF_AL_TakeOffUnitWithFuseSwitch_Busway.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 91
ELT_MSR | 6 | 440_EF_AL_TopFeedingUnitForTransformer_Busway.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 92
ELT_MSR | 7 | 481_EF_OutdoorAirTemperatureSensor.rfa |  | 481_EF | Electrical Revit Family | .rfa | MEP | DIG | 2 | 2026-06-12 | 2026-06-19 | 2026-06-25 | 2026-07-03 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 93
ELT_MSR | 8 | 440_EF_CableConnection_PluginSystem.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 94
ELT_MSR | 9 | 440_EF_ConnectionBrackets.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 95
ELT_MSR | 10 | 440_EF_DALIPresenceDetectorCombineLightingSensor_CeilingSurface.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 96
ELT_MSR | 11 | 440_EF_DALIPresenceDetector_CeilingSurface.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 97
ELT_MSR | 12 | 440_EF_DataConnectionSocket_Audio_Out_HDMI.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 98
ELT_MSR | 13 | 440_EF_DataConnectionSocket_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 99
ELT_MSR | 14 | 457_EF_DataConnectionSocket_CeilingMounted_WaterProof.rfa |  | 457_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 100
ELT_MSR | 15 | 440_EF_DataConnectionSocket_Floor.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 101
ELT_MSR | 16 | 440_EF_DataConnectionSocket_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 102
ELT_MSR | 17 | 440_EF_DaylightSensor_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 103
ELT_MSR | 18 | 440_EF_DaylightSensor_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 104
ELT_MSR | 19 | 440_EF_DimmerSwitch_WallRecessed.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 105
ELT_MSR | 20 | 440_EF_DoorbellPushButton_WallMounted.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 106
ELT_MSR | 21 | 440_EF_DoubleSocketOutletHorizontal_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 107
ELT_MSR | 22 | 440_EF_DoubleSocketOutletUSBTypeAC_WallSurface.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 108
ELT_MSR | 23 | 440_EF_DoubleSocketOutletVertical_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 109
ELT_MSR | 24 | 440_EF_DoubleSocketOutletVertical_WallFlush.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 110
ELT_MSR | 25 | 440_EF_DoubleSocketOutlet_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 111
ELT_MSR | 26 | 440_EF_DoubleSocketOutlet_Floor.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 112
ELT_MSR | 27 | 440_EF_DoubleSocketOutlet_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 113
ELT_MSR | 28 | 446_EF_EarthingFixedPoint_WallSurface.rfa |  | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 114
ELT_MSR | 29 | 446_EF_Earthing_WallSurface.rfa |  | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 115
ELT_MSR | 30 | 440_EF_EarthPit.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 116
ELT_MSR | 31 | 440_EF_EarthRod.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 117
ELT_MSR | 32 | 446_EF_EarthTestBox.rfa |  | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 118
ELT_MSR | 33 | 440_EF_EmergencyStopPushButtons.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 119
ELT_MSR | 34 | 440_EF_EnergyBollard.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 120
ELT_MSR | 35 | 440_EF_Equipotentialbondingbar.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 121
ELT_MSR | 36 | 446_EF_EquipotentialBondingBusbars_WallMounted.rfa |  | 446_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 122
ELT_MSR | 37 | 440_EF_FixedConnection_1Pole.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 123
ELT_MSR | 38 | 440_EF_FixedConnection_400V.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 124
ELT_MSR | 39 | 444_EF_GooseneckBushing_NoSystem.rfa |  | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 125
ELT_MSR | 40 | 481_EF_Hygrostat.rfa |  | 481_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 126
ELT_MSR | 41 | 444_EF_InstallationTrunking.rfa |  | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 127
ELT_MSR | 42 | 440_EF_Isolator_3Phases.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 128
ELT_MSR | 43 | 440_EF_Isolator_SinglePhase.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 129
ELT_MSR | 44 | 440_EF_JunctionBox_Ceiling_3Pole.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 130
ELT_MSR | 45 | 440_EF_JunctionBox_Floor_3Pole.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 131
ELT_MSR | 46 | 440_EF_BasementVentilationControl.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 132
ELT_MSR | 47 | 440_EF_KeySwitch_WallRecessed.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 3 | 2026-06-19 | 2026-06-25 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 133
ELT_MSR | 48 | 440_EF_KNXPresenceDetection_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 134
ELT_MSR | 49 | 440_EF_KNX_PushButtonSensor_2gang.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 135
ELT_MSR | 50 | 440_EF_MainEquipotentialBondingBar.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 136
ELT_MSR | 51 | 440_EF_PanelBoard.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 137
ELT_MSR | 52 | 440_EF_PresenceDetector_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 138
ELT_MSR | 53 | 440_EF_PresenceDetector_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 139
ELT_MSR | 54 | 440_EF_PushButtonSensorKNX_4gang.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 140
ELT_MSR | 55 | 440_EF_Raumluftfühler.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 141
ELT_MSR | 56 | 440_EF_RoomSignallight.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 142
ELT_MSR | 57 | 440_EF_RotaryDimmer.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 143
ELT_MSR | 58 | 440_EF_ShaverSocketOutlet_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 144
ELT_MSR | 59 | 440_EF_SocketDistributionBox_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 145
ELT_MSR | 60 | 440_EF_SocketDistributionBox_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 146
ELT_MSR | 61 | 440_EF_SocketOutletCombination_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 147
ELT_MSR | 62 | 440_EF_SocketOutletRound_Floor.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 148
ELT_MSR | 63 | 440_EF_SocketOutlet_FloorRecessed_Round.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 149
ELT_MSR | 64 | 440_EF_SocketOutlet_Horizontal_4Gangs_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 150
ELT_MSR | 65 | 444_EF_SocketOutlet_Rec_Floor.rfa |  | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 151
ELT_MSR | 66 | 444_EF_USBSocketOutlet_WallFlush.rfa |  | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 152
ELT_MSR | 67 | 444_EF_SocketOutlet_VerticalWallSurface_4Gangs.rfa |  | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 153
ELT_MSR | 68 | 440_EF_SocketOutlet_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 154
ELT_MSR | 69 | 440_EF_SocketOutlet_WallMounted_WaterProof.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 155
ELT_MSR | 70 | 440_EF_SocketOutlet_Wall_3Phase.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 156
ELT_MSR | 71 | 440_EF_SocketOutlet_Wall_4Gangs.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 157
ELT_MSR | 72 | 440_EF_SocketOutlet_Wall_Combination.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 158
ELT_MSR | 73 | 440_EF_SwitchableSocketOutlet_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 159
ELT_MSR | 74 | 440_EF_SwitchableSocketOutlet_Floor.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 160
ELT_MSR | 75 | 444_EF_SwitchableSocketOutlet_WallSurface.rfa |  | 444_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 161
ELT_MSR | 76 | 440_EF_SwitchPushButton_FlushMounted.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 162
ELT_MSR | 77 | 440_EF_Switch_1Gang.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 163
ELT_MSR | 78 | 440_EF_Switch_2Gang.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 164
ELT_MSR | 79 | 440_EF_Switch_2Gang2Way.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 165
ELT_MSR | 80 | 440_EF_Switch_3Gang.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 166
ELT_MSR | 81 | 451_EF_TelephoneOutlet_Single.rfa |  | 451_EF | Electrical Revit Family | .rfa | MEP | DIG | 4 | 2026-06-25 | 2026-07-03 | 2026-07-10 | 2026-07-17 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 167
ELT_MSR | 82 | 440_EF_Thermosat.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 168
ELT_MSR | 83 | 440_EF_TouchPanelRoomOperating_WallMounted.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 169
ELT_MSR | 84 | 440_EF_TripleSocketOutlet_Ceiling.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 170
ELT_MSR | 85 | 440_EF_TripleSocketOutlet_Floor.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 171
ELT_MSR | 86 | 440_EF_TripleSocketOutlet_Wall.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 172
ELT_MSR | 87 | 440_EF_WindowMotor_WallMounted.rfa |  | 440_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 173
ELT_MSR | 88 | 457_EF_VideoModul.rfa |  | 457_EF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 174
ELT_MSR | B.1.3 | LF_Lighting Fixtures |  |  | 65 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 175
ELT_MSR | 1 | 445_LF_3FoldPendantLight_CeilingSuspended.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 176
ELT_MSR | 2 | 445_LF_BathroomLuminaire_WallMounted_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 177
ELT_MSR | 3 | 445_LF_CoreLineLEDLight_CeilingSuspended.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 178
ELT_MSR | 4 | 445_LF_CoreLineLEDLight_WallSurface.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 179
ELT_MSR | 5 | 445_LF_CorelineSlimDownlight_CeilingMounted.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 180
ELT_MSR | 6 | 445_LF_CorelineSlimDownlight_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 181
ELT_MSR | 7 | 445_LF_CorelineSpotlight_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 182
ELT_MSR | 8 | 445_LF_DownlightLEDrigid_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 183
ELT_MSR | 9 | 445_LF_DownlightLEDSwivelling_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 184
ELT_MSR | 10 | 445_LF_EscapeSign_CeilingMounted.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 185
ELT_MSR | 11 | 445_LF_EscapeSign_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 186
ELT_MSR | 12 | 445_LF_EscapeSign_WallMounted.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 187
ELT_MSR | 13 | 445_LF_ExitCube_Ceiling.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 188
ELT_MSR | 14 | 445_LF_FixedOpticSmallBodyIroundOutdoorlight_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 189
ELT_MSR | 15 | 445_LF_GreenSpaceAccentSpotlightRigid_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 190
ELT_MSR | 16 | 445_LF_LaserBladeLightXSWallWasher_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 191
ELT_MSR | 17 | 445_LF_LaserBladeLightXS_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 192
ELT_MSR | 18 | 445_LF_LeadSacidTwinHeadEmergencyLight_WallSurface.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 193
ELT_MSR | 19 | 445_LF_LEDAccentRigidlight_CeilingRecessed_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 194
ELT_MSR | 20 | 445_LF_LEDBAPPendantLightWithAdjustableRod_CeilingSuspended.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 195
ELT_MSR | 21 | 445_LF_LEDDeckeneinbauMontage_CeilingMounted_LG6E.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 196
ELT_MSR | 22 | 445_LF_LEDDoubleHeadEmergencyLight_WallSurface.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 197
ELT_MSR | 23 | 445_LF_LEDDownlightForWC_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 5 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 198
ELT_MSR | 24 | 445_LF_LEDDownlightSM_CeilingRecessed_Round.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 199
ELT_MSR | 25 | 445_LF_LEDHighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 200
ELT_MSR | 26 | 445_LF_LedinaireHighbayPendantLightWithAdjustableRod_CeilingSuspended.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 201
ELT_MSR | 27 | 445_LF_LedinaireSlimDownlight_CeilingSuspended.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 202
ELT_MSR | 28 | 445_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 203
ELT_MSR | 29 | 445_LF_LEDMasterEmergencyLightingLuminaire_WallMounted.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 204
ELT_MSR | 30 | 445_LF_LEDPanel_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 205
ELT_MSR | 31 | 445_LF_LEDPendantLightWithAdjustableRod_CeilingSuspended.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 206
ELT_MSR | 32 | 445_LF_LEDPendantRingLight.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 207
ELT_MSR | 33 | 445_LF_LEDSignalLightForWC_WallMounted.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 208
ELT_MSR | 34 | 445_LF_LEDSpotEmergencyLightingLuminaireInFireResistantCeiling_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 209
ELT_MSR | 35 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 210
ELT_MSR | 36 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square_SQ5D.rfa |  | 440_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 211
ELT_MSR | 37 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round.rfa |  | 440_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 212
ELT_MSR | 38 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round_SQ6.rfa |  | 440_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 213
ELT_MSR | 39 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Square_SQ5E.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 214
ELT_MSR | 40 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Round.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 215
ELT_MSR | 41 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Square.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 216
ELT_MSR | 42 | 445_LF_LEDSpotEmergencyLightingLuminaire_WallMounted_Square_SQ5A.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 217
ELT_MSR | 43 | 445_LF_LEDStairEmergencyLight_WallSurface.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 218
ELT_MSR | 44 | 445_LF_LEDStripLight_CeilingMounted_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 219
ELT_MSR | 45 | 445_LF_LEDStripLight_CeilingRecessed_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 220
ELT_MSR | 46 | 445_LF_LEDStripLight_WallSurface_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 221
ELT_MSR | 47 | 445_LF_LEDTwinHeadsFastChargingIP30EmergencyLight_WallSurface.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 222
ELT_MSR | 48 | 445_LF_LEDTwoHeadWaterProofIP65EmergencyLight_WallSurface.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 223
ELT_MSR | 49 | 445_LF_LEDUplight_FloorRecessed_Round.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 224
ELT_MSR | 50 | 445_LF_LED_HighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 225
ELT_MSR | 51 | 445_LF_LuxSpaceAccentPerformanceSpotlightSwiveling_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 6 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 226
ELT_MSR | 52 | 445_LF_LuxSpaceCompactAnbaudownlight_CeilingSuspended.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 227
ELT_MSR | 53 | 445_LF_LuxSpaceDownlight_CeilingRecessed_Square.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 228
ELT_MSR | 54 | 445_LF_MoistureProofLuminaire_CeilingSuspended_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 229
ELT_MSR | 55 | 445_LF_OpticalLight_CeilingRecessed_Round_Outdoor.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 230
ELT_MSR | 56 | 445_LF_TrackSpot-S_CeilingMounted.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 231
ELT_MSR | 57 | 445_LF_TruelineLinearLuminaire_CeilingRecessed.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 232
ELT_MSR | 58 | 445_LF_UVCAirDisinfectionLight_WallSurface.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 233
ELT_MSR | 59 | 445_LF_InteriorLuminaireBL_CeilingRecessed_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 234
ELT_MSR | 60 | 445_LF_InteriorLuminaireINDMP_CeilingRecessed_Round.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 235
ELT_MSR | 61 | 445_LF_LEDDownlightOP_CeilingRecessed_Round.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 236
ELT_MSR | 62 | 445_LF_LEDDownlightSFNB_CeilingRecessed_Round.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 237
ELT_MSR | 63 | 445_LF_LEDLuminaireMP_CeilingMounted_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 238
ELT_MSR | 64 | 445_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 239
ELT_MSR | 65 | 445_LF_MoistureProofLuminaire_WallSurface_Rectangular.rfa |  | 445_LF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 240
ELT_MSR | B.1.4 | FA_Fire Alarm Devices |  |  | 2 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 241
ELT_MSR | 1 | 456_FA_AspiratingSmokesSystem2Channel_WallMounted.rfa |  | 456_FA | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 242
ELT_MSR | 2 | 456_FA_SmokeSamplingHead_Ceiling.rfa |  | 456_FA | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 243
ELT_MSR | B.1.5 | LD_Lighting Devices |  |  | 2 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 244
ELT_MSR | 1 | 440_LD_DoubleSwitchSocket_WallMounted.rfa |  | 440_LD | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 245
ELT_MSR | 2 | 440_LD_SingleSwitchSocket_WallMounted.rfa |  | 440_LD | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 246
ELT_MSR | B.1.6 | DD_Data Devices |  |  | 1 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 247
ELT_MSR | 1 | 481_EE_SmartHomeAccessPoint_WLAN.rfa |  | 481_EE | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 248
ELT_MSR | B.1.7 | SD_Security Devices |  |  | 1 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 249
ELT_MSR | 1 | 457_SD_DomeCamera_Outdoor.rfa |  | 457_SD | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 250
ELT_MSR | B.1.8 | SE |  |  | 2 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 251
ELT_MSR | 1 | 440_SE_AccessPanel_Ceiling.rfa |  | 440_SE | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 252
ELT_MSR | 2 | 440_SE_Penetration_CuraFlex.rfa |  | 440_SE | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 253
ELT_MSR | B.1.9 | CD_Communication Devices |  |  | 1 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 254
ELT_MSR | 1 | 455_CD_IndoorAntenna_Ceiling.rfa |  | 455_CD | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 255
ELT_MSR | B.1.10 | NC |  |  | 1 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 256
ELT_MSR | 1 | 440_NC_EmergencyPullCordSwitch_Wall.rfa |  | 440_NC | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 257
ELT_MSR | B.1.11 | CF_Cable Tray Fittings |  |  | 66 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 258
ELT_MSR | 1 | 440_CF_AL_eHorizontalElbow_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 259
ELT_MSR | 2 | 440_CF_AL_eVerticalElbow90Deg_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 260
ELT_MSR | 3 | 440_CF_AL_eVerticalOffsetElbow90Deg_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 261
ELT_MSR | 4 | 440_CF_AL_mHorizontalOffsetZShade_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 262
ELT_MSR | 5 | 440_CF_AL_mVerticalOffsetZShade_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 263
ELT_MSR | 6 | 440_CF_AL_StraightLength_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 264
ELT_MSR | 7 | 440_CF_AL_tVerticalTee_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 265
ELT_MSR | 8 | 440_CF_AL_uEndFlange_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 266
ELT_MSR | 9 | 440_CF_wChannelHorizontalWye_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 267
ELT_MSR | 10 | 440_CF_CO_eDoubleLeftElbow_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 268
ELT_MSR | 11 | 440_CF_CO_eEdgewiseElbowWithAngle_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 269
ELT_MSR | 12 | 440_CF_CO_eEdgewiseElbow_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 270
ELT_MSR | 13 | 440_CF_CO_eEdgewiseOffet_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 271
ELT_MSR | 14 | 440_CF_CO_eFlatwiseOffsetElbow_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 272
ELT_MSR | 15 | 440_CF_CO_eFlatwise_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 273
ELT_MSR | 16 | 440_CF_CO_mChannelMultiPort_Standard_FeedUnitForDryTransformer.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 7 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 274
ELT_MSR | 17 | 440_CF_CO_uFlangedEnd_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 275
ELT_MSR | 18 | 440_CF_CS_eCavityFloorBoxWithHeatResistantRoundFormworkBodyElbow_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 276
ELT_MSR | 19 | 440_CF_CS_eCavityFloorBoxWithHeatResistantSquareFormworkBodyElbow_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 277
ELT_MSR | 20 | 440_CF_CS_eCavityFloorBoxWithRoundFormworkBodyElbow_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 278
ELT_MSR | 21 | 440_CF_CS_eCavityFloorBoxWithSquareFormworkBodyElbow_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 279
ELT_MSR | 22 | 440_CF_CS_eScreedCovered_Standard_ChannelThreePartVerticalBend.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 280
ELT_MSR | 23 | 440_CF_CS_eScreedCovered_Standard_ChannelTwoPartVerticalBend.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 281
ELT_MSR | 24 | 440_CF_CS_tCavityFloorBoxWithHeatResistantRoundFormworkBodyTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 282
ELT_MSR | 25 | 440_CF_CS_tCavityFloorBoxWithHeatResistantSquareFormworkBodyTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 283
ELT_MSR | 26 | 440_CF_CS_tCavityFloorBoxWithRoundFormworkBodyTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 284
ELT_MSR | 27 | 440_CF_CS_tCavityFloorBoxWithSquareFormworkBodyTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 285
ELT_MSR | 28 | 440_CF_CS_uCavityFloorBoxWithHeatResistantRoundFormworkBodyEnd_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 286
ELT_MSR | 29 | 440_CF_CS_uCavityFloorBoxWithHeatResistantSquareFormworkBodyEnd_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 287
ELT_MSR | 30 | 440_CF_CS_uCavityFloorBoxWithRoundFormworkBodyEnd_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 288
ELT_MSR | 31 | 440_CF_CS_uCavityFloorBoxWithSquareFormworkBodyEnd_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 289
ELT_MSR | 32 | 440_CF_CS_xCavityFloorBoxWithHeatResistantRoundFormworkBodyCross_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 290
ELT_MSR | 33 | 440_CF_CS_xCavityFloorBoxWithHeatResistantSquareFormworkBodyCross_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 291
ELT_MSR | 34 | 440_CF_CS_xCavityFloorBoxWithRoundFormworkBodyCross_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 292
ELT_MSR | 35 | 440_CF_CS_xCavityFloorBoxWithSquareFormworkBodyCross_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 293
ELT_MSR | 36 | 440_CF_ehFlatwiseElbowFlangeEnd_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 294
ELT_MSR | 37 | 440_CF_ehFlatwiseElbowWithAngle_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 295
ELT_MSR | 38 | 440_CF_mFlatwiseTee_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 296
ELT_MSR | 39 | 440_CF_mPhaseTransition_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 297
ELT_MSR | 40 | 440_CF_mPotentialEqualisationBusbar.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 298
ELT_MSR | 41 | 440_CF_mStraightLength_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 299
ELT_MSR | 42 | 440_CF_ST_ehChannelHorizontalBend_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 300
ELT_MSR | 43 | 440_CF_ST_xChannelHorizontalCross_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 301
ELT_MSR | 44 | 440_CF_ST_ehChannelHorizontalMiteredBend_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 302
ELT_MSR | 45 | 440_CF_ST_tChannelHorizontalTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 303
ELT_MSR | 46 | 440_CF_ST_rChannelTransition_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 304
ELT_MSR | 47 | 440_CF_ST_uChannelUnion_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 305
ELT_MSR | 48 | 440_CF_ST_xvChannelVerticalCross_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 306
ELT_MSR | 49 | 440_CF_ST_tvChannelVerticalDownTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 307
ELT_MSR | 50 | 440_CF_ST_eiChannelVerticalInsideBend_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 8 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 308
ELT_MSR | 51 | 440_CF_ST_eoChannelVerticalOutsideBend_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 309
ELT_MSR | 52 | 440_CF_ST_ehLadderHorizontalBend_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 310
ELT_MSR | 53 | 440_CF_ST_xLadderHorizontalCross_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 311
ELT_MSR | 54 | 440_CF_ST_tLadderHorizontalTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 312
ELT_MSR | 55 | 440_CF_ST_rLadderTransition_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 313
ELT_MSR | 56 | 440_CF_ST_uLadderUnion_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 314
ELT_MSR | 57 | 440_CF_ST_tvLadderUTypeVerticalTee_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 315
ELT_MSR | 58 | 440_CF_ST_xvLadderVerticalCross_Standard |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 316
ELT_MSR | 59 | 440_CF_ST_eiLadderVerticalInsideBend_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 317
ELT_MSR | 60 | 440_CF_ST_eoLadderVerticalOutsideBend_Standard.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 318
ELT_MSR | 61 | 440_CF_uCableTapBoxCenter_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 319
ELT_MSR | 62 | 440_CF_uCableTapBoxEnd_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 320
ELT_MSR | 63 | 440_CF_uEndClosure_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 321
ELT_MSR | 64 | 440_CF_uFlexibleLink_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 322
ELT_MSR | 65 | 440_CF_UnfusedReducer_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 323
ELT_MSR | 66 | 440_CF_uWallFloorFlange_Busway.rfa |  | 440_CF | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 324
ELT_MSR | B.1.12 | CI_Conduit Fittings |  |  | 50 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 325
ELT_MSR | 1 | 440_CI_CS_tClamps_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 326
ELT_MSR | 2 | 440_CI_CS_tExpansionPiecesRound_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 327
ELT_MSR | 3 | 440_CI_CS_xClamps_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 328
ELT_MSR | 4 | 440_CI_CS_xExpansionPiecesRound_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 329
ELT_MSR | 5 | 440_CI_PC_mJunctionBox_Standard_Weatherproof.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 330
ELT_MSR | 6 | 440_CI_PVC_e30DegreeElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 331
ELT_MSR | 7 | 440_CI_PVC_e45DegreeElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 332
ELT_MSR | 8 | 440_CI_PVC_e90DegreeElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 333
ELT_MSR | 9 | 440_CI_PVC_eAngledTwoWayBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 334
ELT_MSR | 10 | 440_CI_PVC_cMarkerforConnectionLugs.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 335
ELT_MSR | 11 | 440_CI_PVC_uConduitBodiesTypeC_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 336
ELT_MSR | 12 | 440_CI_PVC_cConduitBodiesTypeE_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 337
ELT_MSR | 13 | 440_CI_PVC_eConduitBodiesTypeLB_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 338
ELT_MSR | 14 | 440_CI_PVC_eConduitBodiesTypeLL_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 339
ELT_MSR | 15 | 440_CI_PVC_eConduitBodiesTypeLR_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 340
ELT_MSR | 16 | 440_CI_PVC_tConduitBodiesTypeT_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 341
ELT_MSR | 17 | 440_CI_PVC_ConduitSleeveCoupling_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 342
ELT_MSR | 18 | 440_CI_PVC_fCoupling_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 343
ELT_MSR | 19 | 440_CI_PVC_mHWayJuntionBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 9 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 344
ELT_MSR | 20 | 440_CI_PVC_eInspectionBend_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 345
ELT_MSR | 21 | 440_CI_PVC_e90DegreeInspectionElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 346
ELT_MSR | 22 | 440_CI_PVC_tInspectionTee_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 347
ELT_MSR | 23 | 440_CI_PVC_xIntersectionFourWayBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 348
ELT_MSR | 24 | 440_CI_PVC_uJunctionBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 349
ELT_MSR | 25 | 440_CI_PVC_mJunctionBox_Standard_ThreeWay.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 350
ELT_MSR | 26 | 440_CI_PVC_rReducer_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 351
ELT_MSR | 27 | 440_CI_PVC_tTeeThreeWayBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 352
ELT_MSR | 28 | 440_CI_PVC_cTerminalOneWayBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 353
ELT_MSR | 29 | 440_CI_PVC_uThroughTwoWayBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 354
ELT_MSR | 30 | 440_CI_PVC_mUWayBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 355
ELT_MSR | 31 | 440_CI_PVC_mYWayBox_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 356
ELT_MSR | 32 | 440_CI_SS_cDeviceBoxes_Threaded.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 357
ELT_MSR | 33 | 440_CI_SS_e45DegreeElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 358
ELT_MSR | 34 | 440_CI_SS_e45DegreeElbow_Threaded.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 359
ELT_MSR | 35 | 440_CI_SS_e90DegreeElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 360
ELT_MSR | 36 | 440_CI_SS_e90DegreeElbow_Threaded.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 361
ELT_MSR | 37 | 440_CI_SS_eConduitBodies_Threaded_TypeLB.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 362
ELT_MSR | 38 | 440_CI_SS_eConduitBodies_Threaded_TypeLR.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 363
ELT_MSR | 39 | 440_CI_SS_eConduitBodies_Threaded_TypeLU.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 364
ELT_MSR | 40 | 440_CI_SS_eConduitBodies_TypeLL_Threaded.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 365
ELT_MSR | 41 | 440_CI_SS_eFlatConductorsElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 366
ELT_MSR | 42 | 440_CI_SS_eInspectionElbow_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 367
ELT_MSR | 43 | 440_CI_SS_FlatStrip_Standard.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 368
ELT_MSR | 44 | 440_CI_SS_tConduitBodies_Threaded_TypeT.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 369
ELT_MSR | 45 | 440_CI_SS_tConduitBodies_Threaded_TypeTB.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 370
ELT_MSR | 46 | 440_CI_SS_uCFormConduitUnion_Threaded.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 371
ELT_MSR | 47 | 440_CI_SS_xConduitBodies_Threaded_TypeX.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 372
ELT_MSR | 48 | 440_CI_SS_xCrossConductorFlatToRound.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 373
ELT_MSR | 49 | 440_CI_SS_xFlatConductorCross.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 374
ELT_MSR | 50 | 440_CI_ST_mJunctionBox_Explosionproof.rfa |  | 440_CI | Electrical Revit Family | .rfa | MEP | DIG | 10 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 375
ELT_MSR | B2 | MSR Discipline |  | 88 | 89 Families need to revise | [9 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 376
ELT_MSR | B.2.1 | FA_Fire Alarm Devices |  |  | 37 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 377
ELT_MSR | 1 | 480_FA_AddressableManualPullStation.rfa |  | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 378
ELT_MSR | 2 | 456_FA_AddressableSensor.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 379
ELT_MSR | 3 | 480_FA_AnnunciatorPanel.rfa |  | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 380
ELT_MSR | 4 | 456_FA_AspiratingSmokeDetector_WallMounted.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 10 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 381
ELT_MSR | 5 | 456_FA_BeamSensor_WallSurface_Rectangular.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 382
ELT_MSR | 6 | 480_FA_Bell.rfa |  | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 383
ELT_MSR | 7 | 456_FA_CouplerUnit.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 384
ELT_MSR | 8 | 456_FA_DetectorWithHorn.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 385
ELT_MSR | 9 | 456_FA_Detector_CO1224A.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 386
ELT_MSR | 10 | 456_FA_Detector_CO1224TR.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 387
ELT_MSR | 11 | 456_FA_EmegencyDoorRelease_WallMounted.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 388
ELT_MSR | 12 | 456_FA_FireAlarmCenter.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 389
ELT_MSR | 13 | 456_FA_FireAlarmControlPanel.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 390
ELT_MSR | 14 | 456_FA_FireAlarmZoneModuleControl.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 391
ELT_MSR | 15 | 456_FA_FireBrigadeInformationCenter_WallMounted.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 392
ELT_MSR | 16 | 456_FA_FireDepartmentKeyDepot.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 393
ELT_MSR | 17 | 480_FA_FireDoorHolder.rfa |  | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 394
ELT_MSR | 18 | 456_FA_HeatSensor.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 395
ELT_MSR | 19 | 480_FA_LEDIndicator_WallMounted.rfa |  | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 396
ELT_MSR | 20 | 456_FA_LinearHeatDetector.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 397
ELT_MSR | 21 | 456_FA_MultiSensorDetector_Ceiling.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 398
ELT_MSR | 22 | 456_FA_O2TMultisensordetector.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 399
ELT_MSR | 23 | 456_FA_O2TMultisensordetector_BottomSlab.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 400
ELT_MSR | 24 | 456_FA_PhotoelectricSmokeDetector.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 401
ELT_MSR | 25 | 456_FA_PhotoThermalSensor_CeilingMouted_Round.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 402
ELT_MSR | 26 | 456_FA_PresenceDetector24m_Ceiling.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 403
ELT_MSR | 27 | 456_FA_PresenceDetectorHTS_Ceiling.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 404
ELT_MSR | 28 | 456_FA_PushButton_WallMounted_RWA.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 405
ELT_MSR | 29 | 480_FA_SmokeDectectorOpticalSignal_Ceiling.rfa |  | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 406
ELT_MSR | 30 | 456_FA_SmokeSensor_BottomSlab.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 407
ELT_MSR | 31 | 456_FA_SmokeSensor_Ceiling.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 408
ELT_MSR | 32 | 456_FA_SmokeSensor_RaiseFloor.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 409
ELT_MSR | 33 | 456_FA_ManualCallPoint_WallMounted_Square.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 410
ELT_MSR | 34 | 456_FA_ManualCallPoint_WallMounted_Square_Waterproof.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 411
ELT_MSR | 35 | 480_FA_TransferUnit.rfa |  | 480_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 412
ELT_MSR | 36 | 454_FA_VandalResistantLoudSpeaker.rfa |  | 454_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 413
ELT_MSR | 37 | 456_FA_WindandRainDetector_WallMounted_RWA.rfa |  | 456_FA | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 414
ELT_MSR | B.2.2 | EE_Electrical Equipment |  |  | 11 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 415
ELT_MSR | 1 | 482_EE_ControlDistribution_WallMounted.rfa |  | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 416
ELT_MSR | 2 | 456_EE_ConventionalControlPanel_WallSurface_Rectangular.rfa |  | 456_EE | MSR Revit Family | .rfa | MEP | DIG | 11 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 417
ELT_MSR | 3 | 457_EE_DataCabinet.rfa |  | 457_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 418
ELT_MSR | 4 | 457_EE_DataServerCabinet_FloorStand_Rectangular.rfa |  | 457_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 419
ELT_MSR | 5 | 482_EE_Distribution_FloorStanding_Indoor.rfa |  | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 420
ELT_MSR | 6 | 482_EE_Distribution_FloorStanding_Outdoor.rfa |  | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 421
ELT_MSR | 7 | 456_EE_PowerSupplyUnitAccessControl_WallMounted.rfa |  | 456_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 422
ELT_MSR | 8 | 454_EE_PublicAddressSystemPanel_FloorMounted.rfa |  | 454_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 423
ELT_MSR | 9 | 482_EE_RackCabinet_WallMounted.rfa |  | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 424
ELT_MSR | 10 | 482_EE_SwitchCabinet_FloorStand_Rectangular.rfa |  | 482_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 425
ELT_MSR | 11 | 480_EE_WallControlPanel_WallMounted.rfa |  | 480_EE | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 426
ELT_MSR | B.2.3 | EF_Electrical Fixtures |  |  | 8 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 427
ELT_MSR | 1 | 480_EF_IndividualRoomController.rfa |  | 480_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 428
ELT_MSR | 2 | 444_CI_ABS_mIndustrialBox.rfa |  | 444_CI | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 429
ELT_MSR | 3 | 446_EF_LightningCounterDevice.rfa |  | 446_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 430
ELT_MSR | 4 | 446_EF_LightningRod_NoSystem.rfa |  | 446_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 431
ELT_MSR | 5 | 443_EF_OvervoltageProtection_WallFlush.rfa |  | 443_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 432
ELT_MSR | 6 | 442_EF_SealedBatteries.rfa |  | 442_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 433
ELT_MSR | 7 | 452_EF_TouchButton_WallMounted.rfa |  | 452_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 434
ELT_MSR | 8 | 484_EF_Transferbox.rfa |  | 484_EF | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 435
ELT_MSR | B.2.4 | CD_Communication Devices |  |  | 10 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 436
ELT_MSR | 1 | 454_CD_CabinetLoudspeaker6W_WallMounted_Circular.rfa |  | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 437
ELT_MSR | 2 | 454_CD_CabinetLoudspeaker6W_WallMounted_Rectangular.rfa |  | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 438
ELT_MSR | 3 | 454_CD_CabinetLoudspeaker6W_WallMounted_Square.rfa |  | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 439
ELT_MSR | 4 | 452_CD_CallButtonPullCord.rfa |  | 452_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 440
ELT_MSR | 5 | 456_CD_DeskIntercomStation.rfa |  | 456_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 441
ELT_MSR | 6 | 454_CD_FireDepartmentContactPoint_WallMounted.rfa |  | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 442
ELT_MSR | 7 | 454_CD_HornLoudspeaker15W_WallMounted.rfa |  | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 443
ELT_MSR | 8 | 454_CD_Loudspeaker6W_CeilingRecessed.rfa |  | 454_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 444
ELT_MSR | 9 | 457_CD_Router_Indoor.rfa |  | 457_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 445
ELT_MSR | 10 | 456_CD_Siren.rfa |  | 456_CD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 446
ELT_MSR | B.2.5 | SD_Security Devices |  |  | 17 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 447
ELT_MSR | 1 | 456_SD_AnalogCamera.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 448
ELT_MSR | 2 | 456_SD_CameraHub_16Port.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 449
ELT_MSR | 3 | 456_SD_CameraHub_8Port.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 450
ELT_MSR | 4 | 456_SD_CardReader.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 451
ELT_MSR | 5 | 456_SD_DomeCamera_Indoor.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 452
ELT_MSR | 6 | 456_SD_DomeCamera_Outdoor.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 12 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 453
ELT_MSR | 7 | 456_SD_ElectricalLock_DoorMounted.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 454
ELT_MSR | 8 | 456_SD_FingerScan.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 455
ELT_MSR | 9 | 456_SD_FingerScanFace_WallMounted.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 456
ELT_MSR | 10 | 456_SD_FixCameraIP_Indoor.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 457
ELT_MSR | 11 | 456_SD_FixCameraIP_Outdoor.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 458
ELT_MSR | 12 | 456_SD_Monitor.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 459
ELT_MSR | 13 | 456_SD_PTZCamera_Indoor.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 460
ELT_MSR | 14 | 456_SD_PTZCamera_Outdoor.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 461
ELT_MSR | 15 | 456_SD_SecurityAlarmBell.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 462
ELT_MSR | 16 | 456_SD_ThermalCamera.rfa |  | 456_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 463
ELT_MSR | 17 | 442_SD_UPSBattery_FloorStand_Rectangular.rfa |  | 442_SD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 464
ELT_MSR | B.2.6 | DD_Data Devices |  |  | 5 | .rfa | MEP | DIG | [5 empty] | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 465
ELT_MSR | 1 | 481_DD_BACnetGateway.rfa |  | 481_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 466
ELT_MSR | 2 | 457_DD_LanAndTelOutlet_WallSurface.rfa |  | 457_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 467
ELT_MSR | 3 | 457_DD_LanOutlet_WallMounted_2Gangs.rfa |  | 457_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 468
ELT_MSR | 4 | 451_DD_TelOutlet_WallMounted_2Gangs.rfa |  | 451_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 469
ELT_MSR | 5 | 455_DD_TVOutlet_WallMounted_1Gang.rfa |  | 455_DD | MSR Revit Family | .rfa | MEP | DIG | 13 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | Yes | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 470
ELT_MSR | C | Create the Revit templates for each LPH (ELT + MSR) | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 471
ELT_MSR | 1 | Revit Template for ELT in LPH3 |  | ELT | Revit Template | .rte | MEP | DIG | 13 | 2026-09-25 |  |  | 2026-10-02 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 472
ELT_MSR | 2 | Revit Template for ELT in LPH5 |  | ELT | Revit Template | .rte | MEP | DIG | 13 | 2026-09-25 |  |  | 2026-10-02 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 473
ELT_MSR | 3 | Revit Template for ELT in LPH8 |  | ELT | Revit Template | .rte | MEP | DIG | 13 | 2026-09-25 |  |  | 2026-10-02 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 474
ELT_MSR | 4 | Revit Template for MSR in LPH3 |  | MSR | Revit Template | .rte | MEP | DIG | 13 | 2026-09-25 |  |  | 2026-10-02 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 475
ELT_MSR | 5 | Revit Template for MSR in LPH5 |  | MSR | Revit Template | .rte | MEP | DIG | 13 | 2026-09-25 |  |  | 2026-10-02 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 476
ELT_MSR | 6 | Revit Template for MSR in LPH8 |  | MSR | Revit Template | .rte | MEP | DIG | 13 | 2026-09-25 |  |  | 2026-10-02 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 477
ELT_MSR | D | Create the Output Checklists for each LPH (ELT + MSR) | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 478
ELT_MSR | D1 | LPH3 Check list for ELT discipline |  | ELT |  | .xlsx | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 479
ELT_MSR | D1 | LPH3_Check list_ELT 01 |  | ELT | Checklist_Layout Plan. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 480
ELT_MSR | D1 | LPH3_Check list_ELT 02 |  | ELT | Checklist_Section. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 481
ELT_MSR | D1 | LPH3_Check list_ELT 03 |  | ELT | Checklist_Schematic Diagram. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 482
ELT_MSR | D2 | LPH5 Check list for ELT discipline |  | ELT |  | .xlsx | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 483
ELT_MSR | D2 | LPH5_Check list_ELT 01 |  | ELT | Checklist_Layout Plan. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 484
ELT_MSR | D2 | LPH5_Check list_ELT 02 |  | ELT | Checklist_Section. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 485
ELT_MSR | D2 | LPH5_Check list_ELT 03 |  | ELT | Checklist_Schematic Diagram. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 486
ELT_MSR | D3 | LPH8 Check list for ELT discipline |  | ELT |  | .xlsx | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 487
ELT_MSR | D3 | LPH8_Check list_ELT 01 |  | ELT | Checklist_Layout Plan. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 488
ELT_MSR | D3 | LPH8_Check list_ELT 02 |  | ELT | Checklist_Section. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 489
ELT_MSR | D3 | LPH8_Check list_ELT 03 |  | ELT | Checklist_Schematic Diagram. |  | MEP | DIG | 14 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 490
ELT_MSR | D4 | LPH3 Check list for MSR discipline |  | MSR |  | .xlsx | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 491
ELT_MSR | D4 | LPH3_Check list_MSR 01 |  | MSR | Checklist_Layout Plan. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 492
ELT_MSR | D4 | LPH3_Check list_MSR 02 |  | MSR | Checklist_Section. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 493
ELT_MSR | D4 | LPH3_Check list_MSR 03 |  | MSR | Checklist_Schematic Diagram. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 494
ELT_MSR | D5 | LPH5 Check list for MSR discipline |  | MSR |  | .xlsx | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 495
ELT_MSR | D5 | LPH5_Check list_MSR 01 |  | MSR | Checklist_Layout Plan. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 496
ELT_MSR | D5 | LPH5_Check list_MSR 02 |  | MSR | Checklist_Section. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 497
ELT_MSR | D5 | LPH5_Check list_MSR 03 |  | MSR | Checklist_Schematic Diagram. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 498
ELT_MSR | D6 | LPH8 Check list for MSR discipline |  | MSR |  | .xlsx | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 499
ELT_MSR | D6 | LPH8_Check list_MSR 01 |  | MSR | Checklist_Layout Plan. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 500
ELT_MSR | D6 | LPH8_Check list_MSR 02 |  | MSR | Checklist_Section. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 501
ELT_MSR | D6 | LPH8_Check list_MSR 03 |  | MSR | Checklist_Schematic Diagram. |  | MEP | DIG | 15 | 2026-10-02 |  |  | 2026-10-09 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 502
ELT_MSR | E | Sample Model + Output Data | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 503
ELT_MSR | E1 | Sample Model + Output Data For ELT | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 504
ELT_MSR | 1 | Delivery 2nd Draft layout for ELT LPH3 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 505
ELT_MSR | 2 | Delivery 2nd Draft layout for ELT LPH5 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 506
ELT_MSR | 3 | Delivery 2nd Draft layout for ELT LPH8 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 507
ELT_MSR | 4 | Delivery 2nd Draft Schematic Drawing Sample for ELT LPH3 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 508
ELT_MSR | 5 | Delivery 2nd Draft Schematic Drawing Sample for ELT LPH5 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 509
ELT_MSR | 6 | Delivery 2nd Draft Schematic Drawing Sample for ELT LPH8 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 510
ELT_MSR | E2 | Sample Model + Output Data For MSR | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 511
ELT_MSR | 1 | Delivery 2nd Draft layout for MSR LPH3 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 512
ELT_MSR | 2 | Delivery 2nd Draft layout for MSR LPH5 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 513
ELT_MSR | 3 | Delivery 2nd Draft layout for MSR LPH8 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 514
ELT_MSR | 4 | Delivery 2nd Draft Schematic Drawing Sample for MSR LPH3 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 515
ELT_MSR | 5 | Delivery 2nd Draft Schematic Drawing Sample for MSR LPH5 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 516
ELT_MSR | 6 | Delivery 2nd Draft Schematic Drawing Sample for MSR LPH8 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 517
ELT_MSR | F | Export layouts to Revizto & set up 3D Overlay (ELT + MSR) | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 518
ELT_MSR | 1 | Export layouts to Revizto & set up 3D Overlay ELT _LPH3 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 519
ELT_MSR | 2 | Export layouts to Revizto & set up 3D Overlay ELT _LPH5 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 520
ELT_MSR | 3 | Export layouts to Revizto & set up 3D Overlay ELT _LPH8 |  | ELT |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 521
ELT_MSR | 4 | Export layouts to Revizto & set up 3D Overlay MSR _LPH3 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 522
ELT_MSR | 5 | Export layouts to Revizto & set up 3D Overlay MSR _LPH5 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 523
ELT_MSR | 6 | Export layouts to Revizto & set up 3D Overlay MSR _LPH8 |  | MSR |  | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 524
ELT_MSR | G | Lesson Learned | [12 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 525
ELT_MSR | 1 | Lesson Learned ELT |  | ELT | What went well. What need to be improved What we learned, Action items / Improvements | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 526
ELT_MSR | 2 | Lesson Learned MSR |  | MSR | What went well. What need to be improved What we learned, Action items / Improvements | .pdf | MEP | DIG | 16 | 2026-10-09 |  |  | 2026-10-16 |  | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 527
ELT_MSR | TRM | Transmistal |  | MEP | [10 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 530
ELT_MSR | AUD | Auditing |  | DIG | [10 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 531
ELT_MSR | REV | Revision |  | MEP | [10 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 532
ELT_MSR | CFM | Confimmation/Final Submision |  | DIG/MEP | [10 empty] | DCMvn_Annotation Project_ELT_MSR_TIDP_Rev02.xlsx | TIDP 440+480_Rev 02 | 533
RLT | A | Framework deliverable | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 5
RLT | A1 | Define the "Graphical Annotation Framework" | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 6
RLT | A1 |  | Define the "Graphical Annotation Framework" |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG |  | 2026-01-30 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 7
RLT | A1 |  | Define the "Graphical Annotation Framework" |  | Fill the content for RLT disciplines | .xlsx | MEP | DIG |  | 2026-01-30 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 8
RLT | A1 |  | Define the "Graphical Annotation Framework" |  | Confirm and sign the document | .pdf | MEP | DIG |  | 2026-01-30 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 9
RLT | A2 | Define the "Data Requirement Framework | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 10
RLT | A2 |  | Define the "Data Requirement Framework |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG |  | 2026-01-30 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 11
RLT | A2 |  | Define the "Data Requirement Framework |  | Fill the content for RLT disciplines | .xlsx | MEP | DIG |  | 2026-01-30 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 12
RLT | A2 |  | Define the "Data Requirement Framework |  | Confirm and sign the document | .pdf | MEP | DIG |  | 2026-01-30 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 13
RLT | A3 | Define the process to revise the RFA library | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 14
RLT | A3 |  | Define the process to revise the RFA library |  | Confirm and sign the process document | .pdf |  |  |  | 2026-02-06 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 15
RLT | A3 |  | Define the process to revise the RFA library |  | Workshop the process with delivery team | .pptx |  |  |  | 2026-02-06 | 2026-06-05 | 2026-06-12 | 2026-06-19 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 16
RLT | A4 | Define the desired outcome_RLT | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 17
RLT | B | Revise the RFA library |  |  | 280 | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 18
RLT | B1 | DF_Duct Fitting |  |  | 18 | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 19
RLT | 1 | 430_DF_GS_sUbergangsstutzen_Flanged |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 20
RLT | 2 | 430_DF_GS_cBoden_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 21
RLT | 3 | 430_DF_GS_cCapEnd_Spigot_Round.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 22
RLT | 4 | 430_DF_GS_eBogen_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 23
RLT | 5 | 430_DF_GS_eEckbogen_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 24
RLT | 6 | 430_DF_GS_eRoundElbow_Spigot.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 25
RLT | 7 | 430_DF_GS_eTransitionElbow_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 26
RLT | 8 | 430_DF_GS_rEtage_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 27
RLT | 9 | 430_DF_GS_rReducer_Spigot_Round.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 28
RLT | 10 | 430_DF_GS_rUbergangRechteckRund_Flanged_SlipJoint.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 29
RLT | 11 | 430_DF_GS_rUbergang_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 30
RLT | 12 | 430_DF_GS_sRoundTaps_Spigot.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 31
RLT | 13 | 430_DF_GS_tTee_Spigot_Round.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 32
RLT | 14 | 430_DF_GS_tTStuck_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 33
RLT | 15 | 430_DF_GS_uCoupling_Spigot_Round.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 34
RLT | 16 | 430_DF_GS_uUnion_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 35
RLT | 17 | 430_DF_GS_wHosenStuck_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 36
RLT | 18 | 430_DF_GS_xKreuzstuck_Flanged.rfa |  | 430_DF | Duct Fitting Revit Family | .rfa | MEP | DIG |  | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 37
RLT | B2 | DA_Duct Accessory |  |  | 63 | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 38
RLT | 1 | 430_DA_AirtightLouverDamper.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 39
RLT | 2 | 430_DA_CircularSilencers_CA_050.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 40
RLT | 3 | 430_DA_CircularSilencers_CA_100.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 41
RLT | 4 | 430_DA_CircularSilencers_CB.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 42
RLT | 5 | 430_DA_CircularSilencers_CS.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 43
RLT | 6 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowEN.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 44
RLT | 7 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowENEx.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 45
RLT | 8 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRN.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 46
RLT | 9 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRNEx.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 47
RLT | 10 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFL.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 48
RLT | 11 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFC |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 49
RLT | 12 | 430_DA_PressureOverflowElements.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 50
RLT | 13 | 430_DA_FireDampersForCeiling_KU_K30.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 51
RLT | 14 | 430_DA_FireDampers_CommercialKitchens_KA_EU.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 52
RLT | 15 | 430_DA_FireDampers_FireProtectionValve_FV_EU.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 53
RLT | 16 | 430_DA_FireInsulationSheets_Fitting_Promat_L90.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 54
RLT | 17 | 430_DA_FireInsulationSheets_Promat_L90.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 55
RLT | 18 | 430_DA_FireProtectionDamper_Round_FLIVE.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 56
RLT | 19 | 430_DA_FlexibleConnection_Rectangular |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 57
RLT | 20 | 430_DA_FlexibleConnection_Round |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 58
RLT | 21 | 430_DA_FlowAdjustmentDampers.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 59
RLT | 22 | 430_DA_IntumescentDamper_OverflowGrill_NoSystem.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 60
RLT | 23 | 430_DA_MultileafDamperRec_LowLeakage.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 61
RLT | 24 | 430_DA_NonReturnValves.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 62
RLT | 25 | 430_DA_PressureReliefDamper_Rectangular_Standard_NoSystem.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 63
RLT | 26 | 430_DA_RecFireDampers_FKEU.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 64
RLT | 27 | 430_DA_RoundFireDampers_FKREU.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 65
RLT | 28 | 430_DA_RoundFireDampers_FKRS_EU.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 66
RLT | 29 | 430_DA_SchakoConstantVolumeFlowControl_Round_ConstantFlowVLV.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 67
RLT | 30 | 430_DA_SchakoSilencer_Round_RS.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 68
RLT | 31 | 430_DA_ShutOffDevices_AK.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 69
RLT | 32 | 430_DA_ShutOffDevices_AKEx.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 70
RLT | 33 | 430_DA_ShutOffDevices_AKK.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 71
RLT | 34 | 430_DA_SilencersVAV_Rectangular_TS.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 72
RLT | 35 | 430_DA_SilencersVAV_Rectangular_TX.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 73
RLT | 36 | 430_DA_Silencer_Rectangular_Standard.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 74
RLT | 37 | 430_DA_Silencer_Round_Standard.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 75
RLT | 38 | 430_DA_SmokeControlDamper_EKEU.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 76
RLT | 39 | 430_DA_SmokeControlDamper_EKJZ.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 77
RLT | 40 | 430_DA_SmokeDetectorinDucts_RMO3D.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 78
RLT | 41 | 430_DA_SmokeDetectorinDucts_RMOVSD.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 79
RLT | 42 | 430_DA_SmokeProtectionDamper_JZRS.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 80
RLT | 43 | 430_DA_TunnelDampers_JF.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 81
RLT | 44 | 430_DA_VariableAirVolume_Rectangular_MQTH.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 82
RLT | 45 | 430_DA_VariableAirVolume_Round_MQTH.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 83
RLT | 46 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTASilenzio.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 84
RLT | 47 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVA.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 85
RLT | 48 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVJ.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 86
RLT | 49 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVM.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 87
RLT | 50 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVT.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 88
RLT | 51 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVZ.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 89
RLT | 52 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTZSilenzio.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 90
RLT | 53 | 430_DA_VariableVolumeFlowControl_Round_VarycontrolTVLK.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 91
RLT | 54 | 430_DA_VariableVolumeFlowControl_Round_VaryControlTVREX.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 92
RLT | 55 | 430_DA_VariableVolumeFlowControl_VaryControl _Round_LVC.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 93
RLT | 56 | 430_DA_VariableVolumeFlowControl_VaryControl_Round_TVR.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 94
RLT | 57 | 430_DA_VariableVolumeFlowControl_Varycontrol_Round_TVRK.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 95
RLT | 58 | 430_DA_VolumeFlowRateMeasuringUnits_VME.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 96
RLT | 59 | 430_DA_VolumeFlowRateMeasuringUnits_VMLK.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 97
RLT | 60 | 430_DA_VolumeFlowRateMeasuringUnits_VMR.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 98
RLT | 61 | 430_DA_RecFireDamperMechanism_FK2EU.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 99
RLT | 62 | 430_DA_VolumeFlowRateMeasuringUnits_VMRK.rfa |  | 430_DA | Duct Accessories Revit Family | .rfa | MEP | DIG |  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 100
RLT | B3 | AT_Air Terminal |  |  | 90 | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 101
RLT | 1 | 430_AT_AirDiffuser_Standard.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 102
RLT | 2 | 430_AT_CircularDiscValves_LVS_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 103
RLT | 3 | 430_AT_CircularDiscValves_ZLVS_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 104
RLT | 4 | 430_AT_CrossflowCFE_TPP_NoSystem.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 105
RLT | 5 | 430_AT_DeflectorHood_Roof_Rectangular_Exhaust |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 106
RLT | 6 | 430_AT_DeflectorHood_Roof_Rectangular_FreshAirIntake.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 107
RLT | 7 | 430_AT_DeflectorHood_Roof_Round_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 108
RLT | 8 | 430_AT_DeflectorHood_Roof_Round_FreshAirIntake.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 109
RLT | 9 | 430_AT_Diffusers_Floor_FBK_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 110
RLT | 10 | 430_AT_Diffusers_Floor_FBK_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 111
RLT | 11 | 430_AT_Diffusers_Wall_CHM_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 112
RLT | 12 | 430_AT_Diffusers_Wall_CHS_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 113
RLT | 13 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 114
RLT | 14 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 115
RLT | 15 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 116
RLT | 16 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 117
RLT | 17 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 118
RLT | 18 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 119
RLT | 19 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 120
RLT | 20 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 121
RLT | 21 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 122
RLT | 22 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 123
RLT | 23 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 124
RLT | 24 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 125
RLT | 25 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 126
RLT | 26 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 127
RLT | 27 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 128
RLT | 28 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 129
RLT | 29 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 130
RLT | 30 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 131
RLT | 31 | 430_AT_DiscValvesSTVA_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 132
RLT | 32 | 430_AT_DiscValvesSTVZ_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 133
RLT | 33 | 430_AT_DisplacementFlowDiffusers_Wall_QLF_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 134
RLT | 34 | 430_AT_DisplacementFlowDiffusers_Wall_QLV_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 135
RLT | 35 | 430_AT_DoubleSlot_CeilingHorizontal_1ConnectionSymmetrical_Withbox.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 136
RLT | 36 | 430_AT_EggCrateAirGrill_HorizontalCeiling_Rectangular_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 137
RLT | 37 | 430_AT_ExternalRainProtectionGrill_Wall_Round.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 138
RLT | 38 | 430_AT_Grilles_Wall_Rectangular_TRS_FreshAirIntake.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 139
RLT | 39 | 430_AT_Grilles_Wall_Rectangular_TRS_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 140
RLT | 40 | 430_AT_Grilles_Wall_Rectangular_TRS_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 141
RLT | 41 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdividedExhaust |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 142
RLT | 42 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdivided_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 143
RLT | 43 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 144
RLT | 44 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 145
RLT | 45 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 146
RLT | 46 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 147
RLT | 47 | 430_AT_InspectionOpenings_RecDuctHorizontal_Rectangular.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 148
RLT | 48 | 430_AT_InspectionOpenings_RoundDuctHorizontal_Oval.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 149
RLT | 49 | 430_AT_JetDiffuser_Round_Standard.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 150
RLT | 50 | 430_AT_LamellarHood_Roof_Rectangular_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 151
RLT | 51 | 430_AT_LamellarHood_Roof_Rectangular_FreshAirIntake.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 152
RLT | 52 | 430_AT_LourveCover_Roof.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 153
RLT | 53 | 430_AT_Louvre_Standard.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 154
RLT | 54 | 430_AT_NozzlesElectricActuator_DUK_E_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 155
RLT | 55 | 430_AT_NozzlesElectricActuator_DUK_E_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 156
RLT | 56 | 430_AT_Nozzles_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 157
RLT | 57 | 430_AT_Nozzles_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 158
RLT | 58 | 430_AT_Nozzles_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 159
RLT | 59 | 430_AT_Nozzle_Standard.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 160
RLT | 60 | 430_AT_RoofHood.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 161
RLT | 61 | 430_AT_RoundLouver_Standard.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 162
RLT | 62 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 163
RLT | 63 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 164
RLT | 64 | 430_AT_SchakoDisplacementDiffusers_Wall_WQA_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 165
RLT | 65 | 430_AT_SlotDiffuserDSXXXLP2A_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 166
RLT | 66 | 430_AT_SlotDiffuserDSXXXLP2A_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 167
RLT | 67 | 430_AT_SmokeExtractionAndVentilationHood_Roof_Rectangular_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 168
RLT | 68 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 169
RLT | 69 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 170
RLT | 70 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 171
RLT | 71 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 172
RLT | 72 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 173
RLT | 73 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 174
RLT | 74 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 175
RLT | 75 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 176
RLT | 76 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 177
RLT | 77 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 178
RLT | 78 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 179
RLT | 79 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 180
RLT | 80 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 181
RLT | 81 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 182
RLT | 82 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 183
RLT | 83 | 430_AT_SwirlDiffuser_VerticalCeiling_Rectangular_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 184
RLT | 84 | 430_AT_TextileDiffuser_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 185
RLT | 85 | 430_AT_VentilationGrilles_DoorWall_AGS_Exhaust.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 186
RLT | 86 | 430_AT_VentilationGrilles_DoorWall_AGS_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 187
RLT | 87 | 430_AT_VentilationGrilles_Rectangular_Standard.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 188
RLT | 88 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Return.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 189
RLT | 89 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Supply.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 190
RLT | 90 | 430_AT_VentilationGrilles_RoundDuct_Standard.rfa |  | 430_AT | Air Terminal Revit Family | .rfa | MEP | DIG |  | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 191
RLT | B4 | ME_Mechanical Equipment |  |  | 109 | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 192
RLT | 1 | 430_ME_AHUProcess.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 193
RLT | 2 | 430_ME_AHU_BSF_Standard.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 194
RLT | 3 | 430_ME_AIR1XC3200L.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 195
RLT | 4 | 430_ME_AirCompressors_Standard.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 196
RLT | 5 | 430_ME_AirHandingUnit_RectangularLeftConnection_CeilingStand.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 197
RLT | 6 | 430_ME_AirHandingUnit_RectangularRightConnection_CeilingStand.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 198
RLT | 7 | 430_ME_AirHandingUnit_RoundConnection_CeilingStand |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 199
RLT | 8 | 430_ME_AirHandlingUnits_1Layer.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 200
RLT | 9 | 430_ME_AirHandlingUnits_2Layer.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 201
RLT | 10 | 430_ME_AirHandlingUnits_CF.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 202
RLT | 11 | 430_ME_AirHandlingUnits_PHE.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 203
RLT | 12 | 430_ME_AirHandlingUnit_1LayerFlachSeries_CeilingStand.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 204
RLT | 13 | 430_ME_AirHandlingUnit_2LayerBowl_RoofStand.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 205
RLT | 14 | 430_ME_AirHandlingUnit_2LayerCompactSeries_FloorStand.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 206
RLT | 15 | 430_ME_AirHandlingUnit_2LayerForKitchen_FloorStand.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 207
RLT | 16 | 430_ME_AirHandlingUnit_FloorStand.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 208
RLT | 17 | 430_ME_AirHandlingUnit_Geniox29H.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 209
RLT | 18 | 430_ME_AxialWindowFan_Rectangular.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 210
RLT | 19 | 430_ME_CentrifugalDuctMountedFan.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 211
RLT | 20 | 430_ME_ChemicalMachine.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 212
RLT | 21 | 430_ME_CrossFlowFans_NoSystem.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 213
RLT | 22 | 430_ME_DiesselTank_Becomix.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 214
RLT | 23 | 430_ME_Ductfans_Round_DF.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 215
RLT | 24 | 430_ME_Ductfans_WallMounted_Round.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 216
RLT | 25 | 430_ME_ExpansionTank_BottomConnection.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 217
RLT | 26 | 430_ME_FansForAggressiveAir.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 218
RLT | 27 | 430_ME_Fan_Axial.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 219
RLT | 28 | 430_ME_Fan_Roof_Exhaust.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 220
RLT | 29 | 430_ME_Fan_Roof_SmokeExtraction_NoSystem.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 221
RLT | 30 | 430_ME_Fan_WallMounted.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 222
RLT | 31 | 430_ME_FilterFanCoilUnit.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 223
RLT | 32 | 430_ME_FlushMountedFan_BackConnection_SilentECO.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 224
RLT | 33 | 430_ME_FlushMountedFan_TopConnection_SilentECO.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 225
RLT | 34 | 430_ME_GloveBox.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 226
RLT | 35 | 430_ME_HeatExchangersAndAirHeaters_EL.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 227
RLT | 36 | 430_ME_HeatExchangersAndAirHeaters_WL.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 228
RLT | 37 | 430_ME_HeatExchangersAndAirHeaters_WT.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 229
RLT | 38 | 430_ME_HeatExchangers_KTH_NoSystem.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 230
RLT | 39 | 430_ME_HeatReclaimVentilator_VAMFC.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 231
RLT | 40 | 430_ME_HeatRecoveryWheelPrimaryAirUnits_Standard.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 232
RLT | 41 | 430_ME_AirHandlingUnit_Single_Fortluft.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 233
RLT | 42 | 430_ME_AirHandlingUnit_Floor_Single_Aubenluft.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 234
RLT | 43 | 430_ME_IndoorUnitsThermoVentI.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 235
RLT | 44 | 430_ME_InlineCentrifugalFan_FRD.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 236
RLT | 45 | 430_ME_JetFanCarPark_FloorSurface_NoSystem.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 237
RLT | 46 | 430_ME_KitchenExtractorHood.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 238
RLT | 47 | 430_ME_KitchenHoodMonoblock_Standard.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 239
RLT | 48 | 430_ME_MixingTank_Becomix.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 240
RLT | 49 | 430_ME_AirHandlingUnit_Single_Abluft.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 241
RLT | 50 | 430_ME_AirHandlingUnit_Single_Zuluft.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 242
RLT | 51 | 430_ME_RoofFanBendDHE_Supply.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 243
RLT | 52 | 430_ME_RoofFanDV_Return.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 244
RLT | 53 | 430_ME_RoofTopUnits_ThermoVentD.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 245
RLT | 54 | 430_ME_RoofVentilationFans_DAX.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 246
RLT | 55 | 430_ME_RoofVentilationFans_DAX_NoSystem.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 247
RLT | 56 | 430_ME_RoofVentilationFans_DRVFH.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 248
RLT | 57 | 430_ME_RoofVentilationFans_DRV_DRH.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 249
RLT | 58 | 430_ME_RoofVentilationFans_DRV_EC.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 250
RLT | 59 | 430_ME_Schleusenventilatoren.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 251
RLT | 60 | 430_ME_SmokeExhaustAxialFans_BVAXO_F300.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 252
RLT | 61 | 430_ME_SmokeExhaustAxialFans_BVAXO_F400.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 253
RLT | 62 | 430_ME_SmokeExhaustCentrifugalFans_BVRA.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 254
RLT | 63 | 430_ME_SmokeExhaustCentrifugalFans_BVREH.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 255
RLT | 64 | 430_ME_SmokeExhaustCentrifugalFans_BVW-B.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 256
RLT | 65 | 430_ME_SmokeExhaustFan_WallMounted_BVW_A.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 257
RLT | 66 | 430_ME_SmokeExhaustJetFans_NoSystem.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 258
RLT | 67 | 430_ME_SmokeExhaustPlugFans_BRERV.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 259
RLT | 68 | 430_ME_StartingSolution.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 260
RLT | 69 | 430_ME_VacuumPump.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 261
RLT | 70 | 430_ME_VentilationAxialFans_AXN691256.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 262
RLT | 71 | 430_ME_VentilationAxialFans_AXO.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 263
RLT | 72 | 430_ME_VentilationAxialFans_AXO1050.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 264
RLT | 73 | 430_ME_VentilationAxialFans_AXO927.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 265
RLT | 74 | 430_ME_VentilationAxialFans_BVAXN_1256.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 266
RLT | 75 | 430_ME_VentilationAxialFans_GLDF.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 267
RLT | 76 | 430_ME_VentilationAxialFans_ZAXN691256.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 268
RLT | 77 | 430_ME_VentilationCentrifugalFans_KFB.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 269
RLT | 78 | 430_ME_VentilationCentrifugalFans_REH.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 270
RLT | 79 | 430_ME_VentilationCentrifugalFans_RZH.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 271
RLT | 80 | 430_ME_VentilationJetFans_GAXO_NoSystem.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 272
RLT | 81 | 430_ME_VentilationPlugFans_ERV.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 273
RLT | 82 | 430_ME_Ventilator_VAM.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 274
RLT | 83 | 430_ME_WallMountedVentilator.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 275
RLT | 84 | 430_ME_WallSmokeExhaustFans.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 276
RLT | 85 | 430_ME_WindDrivenRoofVentilator_Standard.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 277
RLT | 86 | 430_ME_FanCoilUnit_WithPlenumBox_ThreeConnector_Standard.rfa |  | 430_ME | RLT Equipment Revit Family | .rfa | MEP | DIG |  | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | Yes | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 278
RLT | C | Create the Revit templates for each LPH | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 279
RLT | C1 | RLT_Revit Template | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 280
RLT | 1 | Revit Template for LPH3 |  |  | Revit Template | .rte | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 281
RLT | 2 | Revit Template for LPH5 |  |  | Revit Template | .rte | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 282
RLT | 3 | Revit Template for LPH8 |  |  | Revit Template | .rte | MEP | DIG |  | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 283
RLT | C2 | RLT_Output Checklists | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 284
RLT | C2 | LPH3 Check list | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 285
RLT | 1 | LPH3_Check list_RLT 01 |  |  | Checklist_Layout Plan. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 286
RLT | 2 | LPH3_Check list_RLT 02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 287
RLT | 3 | LPH3_Check list_RLT 03 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 288
RLT | 3 | LPH5 Check list | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 289
RLT | 1 | LPH5_Check list_RLT 01 |  |  | Checklist_Layout Plan. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 290
RLT | 2 | LPH5_Check list_RLT 02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 291
RLT | 3 | LPH5_Check list_RLT 03 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 292
RLT | 3 | LPH8 Check list | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 293
RLT | 1 | LPH8_Check list_RLT 01 |  |  | Checklist_Layout Plan. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 294
RLT | 2 | LPH8_Check list_RLT 02 |  |  | Checklist_Section. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 295
RLT | 3 | LPH8_Check list_RLT 03 |  |  | Checklist_Schematic Diagram. | .xlsx | MEP | DIG |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 296
RLT | D | Sample Model + Output Data | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 297
RLT | 1 | Delivery Sample layout for LPH3 |  |  | Execute a sample layout | .pdf | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 298
RLT | 2 | Delivery Sample layout for LPH5 |  |  | Execute a sample layout | .pdf | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 299
RLT | 3 | Delivery Sample layout for LPH8 |  |  | Execute a sample layout | .pdf | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 300
RLT | 4 | Delivery Schematic Drawing Sample for LPH3 |  |  | Execute a sample layout | .pdf | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 301
RLT | 5 | Delivery Schematic Drawing Sample for LPH5 |  |  | Execute a sample layout | .pdf | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 302
RLT | 6 | Delivery Schematic Drawing Sample for LPH8 |  |  | Execute a sample layout | .pdf | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 303
RLT | E | Export layouts to Revizto & set up 3D Review | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 304
RLT | 1 | Export layouts to Revizto & set up 3D Review RLT_LPH3 |  |  | Overlay layout to Revizto | Revizto | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 305
RLT | 2 | Export layouts to Revizto & set up 3D Review RLT_LPH5 |  |  | Overlay layout to Revizto | Revizto | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 306
RLT | 3 | Export layouts to Revizto & set up 3D Review RLT_LPH8 |  |  | Overlay layout to Revizto | Revizto | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 307
RLT | F | Lesson Learned | [12 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 308
RLT | 1 |  |  |  | What went well. What didn’t go well What we learned, Action items / Improvements | .pdf | MEP | MEP |  | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 |  | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 309
RLT | TRM | Transmittal / Submitted |  |  | MEP | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 312
RLT | AUD | Audit/Review |  |  | DIG | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 313
RLT | REV | Revision Required / Revised |  |  | MEP | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 314
RLT | CFM | Confimmation/Confirmed & Stored |  |  | DIG/MEP | [9 empty] | DCMvn_RLT_TIDP_Rev05.xlsx | TIDP 430 | 315
HKG | A | Framework deliverables (apply to HKG ) |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 5
HKG | 1 | DeREVe the "Graphical Annotation Framework" HKG | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 6
HKG | 1 |  | DeREVe the "Graphical Annotation Framework" HKG |  | Set up the table frame (annotation rules structure) | .xlsx | DIG | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 7
HKG | 1 |  | DeREVe the "Graphical Annotation Framework" HKG |  | Fill the content for HKG disciplines | .xlsx | MEP | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 8
HKG | 1 |  | DeREVe the "Graphical Annotation Framework" HKG |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | [5 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 9
HKG | 2 | DeREVe the "Data Requirement Framework" HKG | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 10
HKG | 2 |  | DeREVe the "Data Requirement Framework" HKG |  | Set up the table frame (data requirements) | .xlsx | DIG | DIG | 0 | 2026-01-30 |  |  |  |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 11
HKG | 2 |  | DeREVe the "Data Requirement Framework" HKG |  | Fill the content for HKG discipline | .xlsx | MEP | DIG | 0 | 2026-02-27 |  |  |  |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 12
HKG | 2 |  | DeREVe the "Data Requirement Framework" HKG |  | Confirm and sign the document | .pdf | MEP | DIG | 0 | 2026-05-22 |  |  |  |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 13
HKG | 3 | DeREVe the process to revise the RFA library | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 14
HKG | 3 |  | DeREVe the process to revise the RFA library |  | Confirm and sign the process document | .pdf | MEP | DIG | 0 | 2026-05-22 |  |  |  |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 15
HKG | 3 |  | DeREVe the process to revise the RFA library |  | Workshop the process with delivery team | .pptx | DIG | DIG | 0 | 2026-02-27 |  |  |  |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 16
HKG | B | Revise the RFA library for HKG system |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 17
HKG | B | HZG Discipline | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 18
HKG | 1 | 420_PF_Brass_ThreeWayEqualTee_Compression |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 19
HKG | 2 | 420_PF_Copper_Elbow |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 20
HKG | 3 | 420_PF_CO_cCap_Soldered |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 21
HKG | 4 | 420_PF_CO_eElbow_Soldered |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 22
HKG | 5 | 420_PF_CO_rReducer_Soldered |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 23
HKG | 6 | 420_PF_CO_tTee_Soldered |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 24
HKG | 7 | 420_PF_CO_uUnion_Soldered |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 25
HKG | 8 | 420_PF_CO_xCross_Soldered |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 26
HKG | 9 | 420_PF_CS_cCap_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 27
HKG | 10 | 420_PF_CS_eElbow_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 28
HKG | 11 | 420_PF_CS_fConnectionFlanged_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 29
HKG | 12 | 420_PF_CS_rReducer_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 30
HKG | 13 | 420_PF_CS_sTap_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 31
HKG | 14 | 420_PF_CS_tTee_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 32
HKG | 15 | 420_PF_CS_uUnion_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 33
HKG | 16 | 420_PF_CS_xCross_Welded |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 34
HKG | 17 | 420_PF_MapressCarbonSteel_Cap_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 35
HKG | 18 | 420_PF_MapressCarbonSteel_Cross_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 36
HKG | 19 | 420_PF_MapressCarbonSteel_Elbow_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 37
HKG | 20 | 420_PF_MapressCarbonSteel_FlangeAdaptor_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 38
HKG | 21 | 420_PF_MapressCarbonSteel_SocketAdaptor_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 39
HKG | 22 | 420_PF_MapressCarbonSteel_SocketFlangeAdaptor_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 40
HKG | 23 | 420_PF_MapressCarbonSteel_Tee_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 41
HKG | 24 | 420_PF_MapressCarbonSteel_Transition_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 42
HKG | 25 | 420_PF_MapressCarbonSteel_Union_SlipJoin |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 43
HKG | 26 | 420_PF_PE_eElbow |  | 420_PF | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 44
HKG | 27 | 420_PA_6WayValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 45
HKG | 28 | 420_PA_AirReleaseValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 46
HKG | 29 | 420_PA_AirReleaseValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 47
HKG | 30 | 420_PA_AirValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 48
HKG | 31 | 420_PA_BalancingValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 49
HKG | 32 | 420_PA_BalancingValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 50
HKG | 33 | 420_PA_BalancingValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 51
HKG | 34 | 420_PA_BalancingValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 52
HKG | 35 | 420_PA_BallValve3Way_LPort |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 53
HKG | 36 | 420_PA_BallValve3Way_TPort |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 54
HKG | 37 | 420_PA_BallValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 55
HKG | 38 | 420_PA_BallValve_Flanged_LeverStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 56
HKG | 39 | 420_PA_BallValve_Flanged_WheelStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 57
HKG | 40 | 420_PA_BallValve_FullBore |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 58
HKG | 41 | 420_PA_BallValve_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 59
HKG | 42 | 420_PA_BallValve_Thread_LeverStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 60
HKG | 43 | 420_PA_BallValve_Thread_WheelStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 61
HKG | 44 | 420_PA_BasketStrainerValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 62
HKG | 45 | 420_PA_BasketStrainerValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 63
HKG | 46 | 420_PA_ButterflyValveHandwheel_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 64
HKG | 47 | 420_PA_ButterflyvalveMotor_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 65
HKG | 48 | 420_PA_ButterflyValve_Flanged_GearStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 66
HKG | 49 | 420_PA_ButterflyValve_Flanged_Handle |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 67
HKG | 50 | 420_PA_ButterflyValve_Flanged_LeverStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 68
HKG | 51 | 420_PA_ButterflyValve_Thread_GearStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 69
HKG | 52 | 420_PA_ButterflyValve_Thread_LeverStandard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 70
HKG | 53 | 420_PA_CapValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 71
HKG | 54 | 420_PA_CheckValveWithThermometer_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 72
HKG | 55 | 420_PA_DifferentialPressureControlValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 73
HKG | 56 | 420_PA_DifferentialPressureGauge_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 74
HKG | 57 | 420_PA_DifferentialPressureSensor |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 75
HKG | 58 | 420_PA_DifferentialPressureSensor_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 76
HKG | 59 | 420_PA_DiscCheckValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 77
HKG | 60 | 420_PA_DrainValve_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 78
HKG | 61 | 420_PA_DrainValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 79
HKG | 62 | 420_PA_ExpansionJoint_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 80
HKG | 63 | 420_PA_ExpansionJoint_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 81
HKG | 64 | 420_PA_ExpansionJoint_Weld |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 82
HKG | 65 | 420_PA_FillAndDrainBallValve_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 83
HKG | 66 | 420_PA_FilterValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 84
HKG | 67 | 420_PA_FilterValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 85
HKG | 68 | 420_PA_FlexibleConnection_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 86
HKG | 69 | 420_PA_FlexibleConnection_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 87
HKG | 70 | 420_PA_FlowSensor |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 88
HKG | 71 | 420_PA_FlowSensor_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 89
HKG | 72 | 420_PA_FlowSensor_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 90
HKG | 73 | 420_PA_GateValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 91
HKG | 74 | 420_PA_GateValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 92
HKG | 75 | 420_PA_GateValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 93
HKG | 76 | 420_PA_GateValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 94
HKG | 77 | 420_PA_GlobeValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 95
HKG | 78 | 420_PA_GlobeValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 96
HKG | 79 | 420_PA_GlobeValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 97
HKG | 80 | 420_PA_GlobeValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 98
HKG | 81 | 420_PA_HeatingBallValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 99
HKG | 82 | 420_PA_HeatMeter_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 100
HKG | 83 | 420_PA_HeatMeter_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 101
HKG | 84 | 420_PA_HeatMeter_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 102
HKG | 85 | 420_PA_LiftCheckValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 103
HKG | 86 | 420_PA_LiftCheckValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 104
HKG | 87 | 420_PA_ManifoldConnection_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 105
HKG | 88 | 420_PA_MotorizedBallValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 106
HKG | 89 | 420_PA_MotorizedBallValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 107
HKG | 90 | 420_PA_MotorizedButterflyValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 108
HKG | 91 | 420_PA_MotorizedGateValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 109
HKG | 92 | 420_PA_MotorizedGateValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 110
HKG | 93 | 420_PA_MotorizedGlobeValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 111
HKG | 94 | 420_PA_MotorizedGlobeValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 112
HKG | 95 | 420_PA_MotorizedThreeWayValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 113
HKG | 96 | 420_PA_MotorizedThreeWayvalve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 114
HKG | 97 | 420_PA_NonReturnFlap_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 115
HKG | 98 | 420_PA_PICCV2WayValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 116
HKG | 99 | 420_PA_PICCV3WayValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 117
HKG | 100 | 420_PA_PICVValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 1 | 2026-06-08 | 2026-06-12 | 2026-06-18 | 2026-06-24 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 118
HKG | 101 | 420_PA_PIQCV6WayValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 119
HKG | 102 | 420_PA_PIQCVValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 120
HKG | 103 | 420_PA_PneumaticControlValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 121
HKG | 104 | 420_PA_PneumaticGlobeControlValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 122
HKG | 105 | 420_PA_PneumaticGlobeControlValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 123
HKG | 106 | 420_PA_PressureGauge |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 124
HKG | 107 | 420_PA_PressureGauge_2Connection |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 125
HKG | 108 | 420_PA_PressureGauge_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 126
HKG | 109 | 420_PA_PressureIndependentControlValveCompact_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 127
HKG | 110 | 420_PA_PressureIndependentControlValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 128
HKG | 111 | 420_PA_PressureIndependentControlValve_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 129
HKG | 112 | 420_PA_PressureReducingValveWithGauge_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 130
HKG | 113 | 420_PA_PressureSensor |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 131
HKG | 114 | 420_PA_PressureSensor_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 132
HKG | 115 | 420_PA_RadiatorLockshield_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 133
HKG | 116 | 420_PA_RadiatorShutOffValveAngle_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 134
HKG | 117 | 420_PA_RadiatorShutOffValveStraight_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 135
HKG | 118 | 420_PA_RadiatorThermostatic2PointAngleValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 136
HKG | 119 | 420_PA_RadiatorThermostaticAngleValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 137
HKG | 120 | 420_PA_RadiatorThermostaticStraightValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 138
HKG | 121 | 420_PA_RegulatingValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 139
HKG | 122 | 420_PA_RegulatingValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 140
HKG | 123 | 420_PA_RegulatingValve_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 141
HKG | 124 | 420_PA_RegulatingValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 142
HKG | 125 | 420_PA_SafetyReliefValveConer_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 143
HKG | 126 | 420_PA_SafetyReliefValveCorner_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 144
HKG | 127 | 420_PA_SafetyReliefValveStraight_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 145
HKG | 128 | 420_PA_SafetyValveCorner_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 146
HKG | 129 | 420_PA_SafetyValveCorner_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 147
HKG | 130 | 420_PA_ShutOffValveWithSafetyFunction_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 148
HKG | 131 | 420_PA_ShutoffValve_Motorized |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 149
HKG | 132 | 420_PA_SixWayMotorisedControlValve_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 150
HKG | 133 | 420_PA_SmartForEnergyManagement_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 151
HKG | 134 | 420_PA_SmartForEnergyManagement_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 152
HKG | 135 | 420_PA_SpringCheckValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 153
HKG | 136 | 420_PA_SwingcheckValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 154
HKG | 137 | 420_PA_SwingCheckValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 155
HKG | 138 | 420_PA_SwingcheckValve_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 156
HKG | 139 | 420_PA_SwingCheckValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 157
HKG | 140 | 420_PA_TemperatureGauge_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 158
HKG | 141 | 420_PA_TemperatureRegulatorValve_SelfOperated |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 159
HKG | 142 | 420_PA_TemperatureSensor |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 160
HKG | 143 | 420_PA_TemperatureSensor_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 161
HKG | 144 | 420_PA_Thermometer |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 162
HKG | 145 | 420_PA_Thermometergauge |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 163
HKG | 146 | 420_PA_ThreeWayMotorisedControlValve_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 164
HKG | 147 | 420_PA_ThreeWayMotorisedControlValve_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 165
HKG | 148 | 420_PA_ThreeWayvalve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 166
HKG | 149 | 420_PA_ThreeWayvalve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 167
HKG | 150 | 420_PA_WaferCheckValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 168
HKG | 151 | 420_PA_WaterMeter_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 169
HKG | 152 | 420_PA_WaterMeter_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 170
HKG | 153 | 420_PA_WaterMeter_Threaded |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 171
HKG | 154 | 420_PA_WaterMeter_Threaded_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 172
HKG | 155 | 420_PA_YStrainerValve_Flanged_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 173
HKG | 156 | 420_PA_YStrainerValve_Thread_Standard |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 174
HKG | 157 | 420_PA_YStrainer_Flanged |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 175
HKG | 158 | 420_PA_YStrainer_Thread |  | 420_PA | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 176
HKG | 159 | 420_HeatExchangerTank_VerticalPump |  | 420_He | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 177
HKG | 160 | 420_ME_AirCoolHeatPump_MonoBlock |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 178
HKG | 161 | 420_ME_AirCurtain_StandingType |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 179
HKG | 162 | 420_ME_AirCurtain_WallMounted |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 180
HKG | 163 | 420_ME_AirCurtain_WallMounted_Standard |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 181
HKG | 164 | 420_ME_AirHeater_Top |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 182
HKG | 165 | 420_ME_AirSoureHeatPump |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 183
HKG | 166 | 420_ME_BufferHeatingTank |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 184
HKG | 167 | 420_ME_BufferTank_Custom |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 185
HKG | 168 | 420_ME_BufferTank_Standard |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 186
HKG | 169 | 420_ME_BufferTank_StorathermHeat&WithInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 187
HKG | 170 | 420_ME_BufferTank_StorathermHeat1Coil&WithInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 188
HKG | 171 | 420_ME_BufferTank_StorathermHeat1Coil&WithoutInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 189
HKG | 172 | 420_ME_BufferTank_StorathermHeat2Coil&WithInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 190
HKG | 173 | 420_ME_BufferTank_StorathermHeatCombi1Coil&WithInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 191
HKG | 174 | 420_ME_BufferTank_StorathermHeatCombi2Coil&WithInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 192
HKG | 175 | 420_ME_BufferTank_StorathermHeatFlange&WithInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 193
HKG | 176 | 420_ME_BufferTank_StorathermHeatFlange&WithoutInsulation |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 194
HKG | 177 | 420_ME_CeilingPanel_Standard |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 195
HKG | 178 | 420_ME_CentrifugalPumpWithElectricMotor_Horizontal |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 196
HKG | 179 | 420_ME_ColdWaterTank |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 197
HKG | 180 | 420_ME_CompressedAirTank |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 198
HKG | 181 | 420_ME_ControlValveGroup |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 199
HKG | 182 | 420_ME_Convector_FloorSurface |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 200
HKG | 183 | 420_ME_EnergyDistributor_6Pairs |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 201
HKG | 184 | 420_ME_EnergyDistributor_8Pairs |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 202
HKG | 185 | 420_ME_ExpansionTank_FloorStand |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 203
HKG | 186 | 420_ME_ExpansionTank_Standard |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 204
HKG | 187 | 420_ME_FacadeHeating_Standard |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 205
HKG | 188 | 420_ME_Fancoilunit_UnderfloorTrench_KathermNK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 206
HKG | 189 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQE_NoSystem |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 207
HKG | 190 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 208
HKG | 191 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQKnano |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 209
HKG | 192 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_1Connector |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 210
HKG | 193 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_2Connector |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 211
HKG | 194 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_3Connector |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 212
HKG | 195 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_4Connector |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 213
HKG | 196 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_5Connector |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 214
HKG | 197 | 420_ME_FWTransfer |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 215
HKG | 198 | 420_ME_HeatExchangerFreeCooling_Flange |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 216
HKG | 199 | 420_ME_HeatingCoolingSails_Ceiling |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 217
HKG | 200 | 420_ME_HeatPump_PackageDrooftop_48And50UA&UH |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 2 | 2026-06-18 | 2026-06-24 | 2026-06-30 | 2026-07-06 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 218
HKG | 201 | 420_ME_HeatTransferStation_Custom |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 219
HKG | 202 | 420_ME_HomeStation_DHK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 220
HKG | 203 | 420_ME_HomeStation_GHK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 221
HKG | 204 | 420_ME_HomeStation_GHKFBH |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 222
HKG | 205 | 420_ME_HotWaterBoiler |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 223
HKG | 206 | 420_ME_HotWaterStorageTank_Standard |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 224
HKG | 207 | 420_ME_HotWaterStorageTank_StorathermAqua |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 225
HKG | 208 | 420_ME_HotWaterStorageTank_StorathermAquaCompact&Electricheater |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 226
HKG | 209 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil&Electricheater |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 227
HKG | 210 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 228
HKG | 211 | 420_ME_HotWaterStorageTank_StorathermAquaCompactHorizontal |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 229
HKG | 212 | 420_ME_HotWaterStorageTank_StorathermAquaCompactWallHung |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 230
HKG | 213 | 420_ME_HotWaterStorageTank_StorathermAquaEEC |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 231
HKG | 214 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump1Coil |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 232
HKG | 215 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump2Coil |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 233
HKG | 216 | 420_ME_HotWaterStorageTank_StorathermAquaInox |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 234
HKG | 217 | 420_ME_HotWaterStorageTank_StorathermAquaLoad1Flange |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 235
HKG | 218 | 420_ME_HotWaterStorageTank_StorathermAquaLoad2Flange |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 236
HKG | 219 | 420_ME_HotWaterStorageTank_StorathermAquaLoad3Flange |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 237
HKG | 220 | 420_ME_HotWaterStorageTank_StorathermAquaLoad4Flange |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 238
HKG | 221 | 420_ME_HotWaterStorageTank_StorathermAquaSolar |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 239
HKG | 222 | 420_ME_HotWaterStorageTank_StorathermAquaSolarEEC |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 240
HKG | 223 | 420_ME_HotWaterTank |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 241
HKG | 224 | 420_ME_HydraulicSeparator_Flanged |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 242
HKG | 225 | 420_ME_HydraulicSeparator_Threaded |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 243
HKG | 226 | 420_ME_KTS_ThermoBox |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 244
HKG | 227 | 420_ME_LargeBecomixVessel_Vertical |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 245
HKG | 228 | 420_ME_Manifold12Connection_Custom |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 246
HKG | 229 | 420_ME_ManifoldCabinet_UP110 |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 247
HKG | 230 | 420_ME_MixedBecomixVessel_Vertical |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 248
HKG | 231 | 420_ME_MultiOutdoorUnit_SingleFan |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 249
HKG | 232 | 420_ME_PlateHeatExchanger |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 250
HKG | 233 | 420_ME_Pump_WaterJetPump_3Way_Flanged |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 251
HKG | 234 | 420_ME_Pump_WaterJetPump_3Way_Threaded |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 252
HKG | 235 | 420_ME_QuantumW500_DoubleCapacitor |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 253
HKG | 236 | 420_ME_RadiatorBathroom_WallMounted_Basic |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 254
HKG | 237 | 420_ME_RadiatorBathroom_WallMounted_BasicR |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 255
HKG | 238 | 420_ME_RadiatorBathroom_WallMounted_Casteo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 256
HKG | 239 | 420_ME_RadiatorBathroom_WallMounted_Credohalf |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 257
HKG | 240 | 420_ME_RadiatorBathroom_WallMounted_Credohalfflat |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 258
HKG | 241 | 420_ME_RadiatorBathroom_WallMounted_Credohalfround |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 259
HKG | 242 | 420_ME_RadiatorBathroom_WallMounted_Credoplus |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 260
HKG | 243 | 420_ME_RadiatorBathroom_WallMounted_DecorArteLine |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 261
HKG | 244 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePlan |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 262
HKG | 245 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureHorizontal |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 263
HKG | 246 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureVertical |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 264
HKG | 247 | 420_ME_RadiatorBathroom_WallMounted_Diveo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 265
HKG | 248 | 420_ME_RadiatorBathroom_WallMounted_Duett |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 266
HKG | 249 | 420_ME_RadiatorBathroom_WallMounted_Elveo_NoSystem |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 267
HKG | 250 | 420_ME_RadiatorBathroom_WallMounted_Fineo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 268
HKG | 251 | 420_ME_RadiatorBathroom_WallMounted_Geneocircle |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 269
HKG | 252 | 420_ME_RadiatorBathroom_WallMounted_Geneoquadris |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 270
HKG | 253 | 420_ME_RadiatorBathroom_WallMounted_Icaro |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 271
HKG | 254 | 420_ME_RadiatorBathroom_WallMounted_Ideos |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 272
HKG | 255 | 420_ME_RadiatorBathroom_WallMounted_Ineo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 273
HKG | 256 | 420_ME_RadiatorBathroom_WallMounted_Leveo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 274
HKG | 257 | 420_ME_RadiatorBathroom_WallMounted_Pateo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 275
HKG | 258 | 420_ME_RadiatorBathroom_WallMounted_Pio1layer |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 276
HKG | 259 | 420_ME_RadiatorBathroom_WallMounted_Pio2layer |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 277
HKG | 260 | 420_ME_RadiatorBathroom_WallMounted_PioPlus |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 278
HKG | 261 | 420_ME_RadiatorBathroom_WallMounted_Rubeo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 279
HKG | 262 | 420_ME_RadiatorBathroom_WallMounted_Signo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 280
HKG | 263 | 420_ME_RadiatorBathroom_WallMounted_Tabeo |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 281
HKG | 264 | 420_ME_RadiatorBathroom_WallMounted_TabeoV |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 282
HKG | 265 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanHorizontal_NoSystem |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 283
HKG | 266 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanVertical_NoSystem |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 284
HKG | 267 | 420_ME_RadiatorElectricPanel_WallMounted_xThermProfileHorizontal_NoSystem |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 285
HKG | 268 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 286
HKG | 269 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKHygiene |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 287
HKG | 270 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKReplacement |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 288
HKG | 271 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 289
HKG | 272 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVHygiene |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 290
HKG | 273 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlus |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 291
HKG | 274 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlusHygiene |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 292
HKG | 275 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 293
HKG | 276 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKHygiene |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 294
HKG | 277 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKReplacement |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 295
HKG | 278 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileV |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 296
HKG | 279 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVHygiene |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 297
HKG | 280 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlus |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 298
HKG | 281 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlusHygiene |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 299
HKG | 282 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoPlan |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 300
HKG | 283 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoProfile |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 301
HKG | 284 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 302
HKG | 285 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanV |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 303
HKG | 286 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanVPlus |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 304
HKG | 287 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileK |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 305
HKG | 288 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileV |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 306
HKG | 289 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileVPlus |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 307
HKG | 290 | 420_ME_RadiatorHeatingWall_WallMounted_Horizontal |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 308
HKG | 291 | 420_ME_RadiatorHeatingWall_WallMounted_ValveHorizontal |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 309
HKG | 292 | 420_ME_RadiatorHeatingWall_WallMounted_ValveVertical |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 310
HKG | 293 | 420_ME_RadiatorHeatingWall_WallMounted_Vertical |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 311
HKG | 294 | 420_ME_Radiator_WallMounted_Standard |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 312
HKG | 295 | 420_ME_RectangularTubeManifold_8Connection |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 313
HKG | 296 | 420_ME_SinglePassTubeHeatExchanger_Horizontal |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 314
HKG | 297 | 420_ME_WaterHeater_Vertical |  | 420_ME | Heating Revit Family | .rfa | MEP | DIG | 3 | 2026-06-30 | 2026-07-06 | 2026-07-10 | 2026-07-16 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 315
HKG | 297 | KLT | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 316
HKG | 1 | 434_PF_CO_30Cross_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 317
HKG | 2 | 434_PF_CO_AdaptorMultiPort_MapressAndNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 318
HKG | 3 | 434_PF_CO_AdaptorUnion_FemaleThreadAndMeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 319
HKG | 4 | 434_PF_CO_AdaptorUnion_MapressAndFlangeGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 320
HKG | 5 | 434_PF_CO_AdaptorUnion_PlainEndAndFlange |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 321
HKG | 6 | 434_PF_CO_Bend_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 322
HKG | 7 | 434_PF_CO_Bend_MapressFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 323
HKG | 8 | 434_PF_CO_Bend_MapressGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 324
HKG | 9 | 434_PF_CO_BridgeBendMultiPort_MapressGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 325
HKG | 10 | 434_PF_CO_Cap_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 326
HKG | 11 | 434_PF_CO_Cap_MapressFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 327
HKG | 12 | 434_PF_CO_Cap_MapressGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 328
HKG | 13 | 434_PF_CO_e90Elbow_ThreadAndMeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 329
HKG | 14 | 434_PF_CO_eAdaptorBend_MapressAndFemaleThread_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 330
HKG | 15 | 434_PF_CO_eAdaptorBend_MapressAndMeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 331
HKG | 16 | 434_PF_CO_eAdaptorBend_MapressAndThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 332
HKG | 17 | 434_PF_CO_eAdaptorBend_MapressAndThreadFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 333
HKG | 18 | 434_PF_CO_eAdaptorBend_MapressAndThreadGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 334
HKG | 19 | 434_PF_CO_eDouble90ElbowMultiPort_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 335
HKG | 20 | 434_PF_CO_eElbow90Deg_MaleThread_MeplaFixAndPremounted |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 336
HKG | 21 | 434_PF_CO_eElbowDouble90Deg_MaleThread_MeplaFixAndPremounted |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 337
HKG | 22 | 434_PF_CO_fFlange_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 338
HKG | 23 | 434_PF_CO_mBridgeBend_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 339
HKG | 24 | 434_PF_CO_mDouble90Elbow_Mapress_PreMounted |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 340
HKG | 25 | 434_PF_CO_mElbowOffset_MapressAndFemaleThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 341
HKG | 26 | 434_PF_CO_mElbow_MapressAndFemaleThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 342
HKG | 27 | 434_PF_CO_mTeeCrossing_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 343
HKG | 28 | 434_PF_CO_mTeeInletReturnUnion_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 344
HKG | 29 | 434_PF_CO_mTeeInletReturn_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 345
HKG | 30 | 434_PF_CO_mTeeReturn_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 346
HKG | 31 | 434_PF_CO_ReducerAdaptor_PlainEndAndClampingRing |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 347
HKG | 32 | 434_PF_CO_rReducerAdaptor_MaleThread_MeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 348
HKG | 33 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThreadFKMBlue_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 349
HKG | 34 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThread_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 350
HKG | 35 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThreadFKMBlue_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 351
HKG | 36 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThread_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 352
HKG | 37 | 434_PF_CO_rReducerAdaptor_MapressAndThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 353
HKG | 38 | 434_PF_CO_rReducerAdaptor_MapressAndThreadFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 354
HKG | 39 | 434_PF_CO_rReducerAdaptor_MapressAndThreadGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 355
HKG | 40 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 356
HKG | 41 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFixAdaptor |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 357
HKG | 42 | 434_PF_CO_rReducerAdaptor_PlainEndAndThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 358
HKG | 43 | 434_PF_CO_rReducerAdaptor_PlainEndAndThreadGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 359
HKG | 44 | 434_PF_CO_rReducerAdaptor_PlainEnd_WithMeplaFixAdaptor |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 360
HKG | 45 | 434_PF_CO_Tee_Mapress&FemaleThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 361
HKG | 46 | 434_PF_CO_Tee_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 362
HKG | 47 | 434_PF_CO_Tee_MapressFKMBlue&FemaleThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 363
HKG | 48 | 434_PF_CO_Tee_MapressFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 364
HKG | 49 | 434_PF_CO_Tee_MapressGas&FemaleThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 365
HKG | 50 | 434_PF_CO_Tee_MapressGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 366
HKG | 51 | 434_PF_CO_Transition_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 367
HKG | 52 | 434_PF_CO_Transition_MapressFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 368
HKG | 53 | 434_PF_CO_Transition_MapressGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 369
HKG | 54 | 434_PF_CO_uAdaptorUnion_MaleThreadAndMeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 370
HKG | 55 | 434_PF_CO_uAdaptorUnion_MaleThread_MeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 371
HKG | 56 | 434_PF_CO_uAdaptorUnion_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 372
HKG | 57 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThreadFKMBlue_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 373
HKG | 58 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThread_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 374
HKG | 59 | 434_PF_CO_uAdaptorUnion_MapressAndMaleThreadFKMBlue_WithNut |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 375
HKG | 60 | 434_PF_CO_uAdaptorUnion_MapressAndNutGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 376
HKG | 61 | 434_PF_CO_uAdaptorUnion_MapressAndThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 377
HKG | 62 | 434_PF_CO_uAdaptorUnion_MapressAndThreadFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 378
HKG | 63 | 434_PF_CO_uAdaptorUnion_MapressAndThreadGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 379
HKG | 64 | 434_PF_CO_uAdaptorUnion_PlainEndAndClampingRing |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 380
HKG | 65 | 434_PF_CO_uAdaptorUnion_PlainEndAndThread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 381
HKG | 66 | 434_PF_CO_uAdaptorUnion_PlainEndAndThreadGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 382
HKG | 67 | 434_PF_CO_uAdaptorUnion_PlainEnd_WithMeplaFix |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 383
HKG | 68 | 434_PF_CO_Union_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 384
HKG | 69 | 434_PF_CO_Union_MapressFKMBlue |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 385
HKG | 70 | 434_PF_CO_Union_MapressGas |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 386
HKG | 71 | 434_PF_CO_uTap_Thread |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 387
HKG | 72 | 434_PF_CO_xOffsetCross_Mapress |  | 434_PF | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 388
HKG | 73 | 434_PA_BranchProviderBox_BPMKS2Port |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 389
HKG | 74 | 434_PA_BranchProviderBox_BPMKS3Port |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 390
HKG | 75 | 434_PA_MultiConnectionPipingKit1_BHFPGas |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 391
HKG | 76 | 434_PA_MultiConnectionPipingKit1_BHFPLiquid |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 392
HKG | 77 | 434_PA_MultiConnectionPipingKit2_BHFPGas |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 393
HKG | 78 | 434_PA_MultiConnectionPipingKit2_BHFPLiquid |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 394
HKG | 79 | 434_PA_RefnetHeader_KHRPGas4Branches |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 395
HKG | 80 | 434_PA_RefnetHeader_KHRPGas8Branches |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 396
HKG | 81 | 434_PA_RefnetHeader_KHRPHP&LPGas |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 397
HKG | 82 | 434_PA_RefnetHeader_KHRPLiquid4Branches |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 398
HKG | 83 | 434_PA_RefnetHeader_KHRPLiquid8Branches |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 399
HKG | 84 | 434_PA_RefnetJoint_KHRPDischarge |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 400
HKG | 85 | 434_PA_RefnetJoint_KHRPGas |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 401
HKG | 86 | 434_PA_RefnetJoint_KHRPLiquid |  | 434_PA | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 402
HKG | 87 | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 403
HKG | 88 | 434_ME_AirCooledChillers_30AWH |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 404
HKG | 89 | 434_ME_AirCooledCondensingUnits_38RBS_2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 405
HKG | 90 | 434_ME_AirCooledCondensingUnits_38RBS_4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 406
HKG | 91 | 434_ME_AirCooledCondensingUnits_38RBS_LeftConnector |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 407
HKG | 92 | 434_ME_AirCooledLiquidChillers_30RB |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 408
HKG | 93 | 434_ME_AirCooledLiquidChillers_30RBS |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 409
HKG | 94 | 434_ME_AirCooledLiquidChillers_30XA |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 410
HKG | 95 | 434_ME_AirCooledLiquidChillers_30XAS |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 411
HKG | 96 | 434_ME_AirCooledLiquidChillers_30XAV |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 412
HKG | 97 | 434_ME_AirCooledLiquidChillers_HeatReclaimUnit30XAS |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 413
HKG | 98 | 434_ME_AirCooledScrollChillers_30RBP |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 414
HKG | 99 | 434_ME_CirculatorPump_CronoTwinDL |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 415
HKG | 100 | 434_ME_ConvectionElementsCeillings_CeilingMounted_KN |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 4 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-07-28 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 416
HKG | 101 | 434_ME_Convector_UnderFloorTrench_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 417
HKG | 102 | 434_ME_CyclonicVacuumDegasser_VentoVEC |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 418
HKG | 103 | 434_ME_CyclonicVacuumDegasser_VentoVIEC |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 419
HKG | 104 | 434_ME_DegassingSystem |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 420
HKG | 105 | 434_ME_Ductableaircooledliquidchillers_30RBSY_LeftConnection |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 421
HKG | 106 | 434_ME_DuctableAirCooledLiquidChillers_30RBY |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 422
HKG | 107 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 423
HKG | 108 | 434_ME_EndSuctionPump_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 424
HKG | 109 | 434_ME_ExpansionVessel_IntermediateDD |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 425
HKG | 110 | 434_ME_ExpansionVessel_IntermediateDG |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 426
HKG | 111 | 434_ME_ExpansionVessel_IntermediateDU |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 427
HKG | 112 | 434_ME_ExpansionVessel_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 428
HKG | 113 | 434_ME_ExpansionVessel_StaticoSD |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 429
HKG | 114 | 434_ME_ExpansionVessel_StaticoSG |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 430
HKG | 115 | 434_ME_ExpansionVessel_StaticoSU |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 431
HKG | 116 | 434_ME_FanCoilUnit_AirTreatmentModules42GM2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 432
HKG | 117 | 434_ME_FanCoilUnit_AirTreatmentModules42GM4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 433
HKG | 118 | 434_ME_FanCoilUnit_AirTreatmentModules42GR2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 434
HKG | 119 | 434_ME_FanCoilUnit_AirTreatmentModules42GR4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 435
HKG | 120 | 434_ME_FanCoilUnit_CeilingCassette_2pipes&42GW |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 436
HKG | 121 | 434_ME_FanCoilUnit_CeilingCassette_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 437
HKG | 122 | 434_ME_Fancoilunit_CeilingMounted_4wayblowcassetteFWFBF4pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 438
HKG | 123 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFBT2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 439
HKG | 124 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFCT2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 440
HKG | 125 | 434_ME_FanCoilUnit_CeilingMounted_CompactChassis42GW4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 441
HKG | 126 | 434_ME_FanCoilUnit_CeilingMounted_HybridTerminal36XB |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 442
HKG | 127 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC2Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 443
HKG | 128 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC4Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 444
HKG | 129 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWD2Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 445
HKG | 130 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH2Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 446
HKG | 131 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH4Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 447
HKG | 132 | 434_ME_FanCoilUnit_CeilingMounted_LargeChassis42GW4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 448
HKG | 133 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBF4pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 449
HKG | 134 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBT2pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 450
HKG | 135 | 434_ME_FanCoilUnit_CeilingMounted_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 451
HKG | 136 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJF4pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 452
HKG | 137 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJT2pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 453
HKG | 138 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAF4pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 454
HKG | 139 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAT2pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 455
HKG | 140 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDF4pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 456
HKG | 141 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDT2pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 457
HKG | 142 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAF4pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 458
HKG | 143 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAT2pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 459
HKG | 144 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE2Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 460
HKG | 145 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE4Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 461
HKG | 146 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS2Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 462
HKG | 147 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS4Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 463
HKG | 148 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize0x |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 464
HKG | 149 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize1x |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 465
HKG | 150 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize2x&3x |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 466
HKG | 151 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize0x |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 467
HKG | 152 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize1x |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 468
HKG | 153 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize2x&3x |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 469
HKG | 154 | 434_ME_FanCoilUnit_CeilingPlenum_Ultra |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 470
HKG | 155 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 471
HKG | 156 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 472
HKG | 157 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAF4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 473
HKG | 158 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAT2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 474
HKG | 159 | 434_ME_FanCoilUnit_FloorStanding_FWVDAF4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 475
HKG | 160 | 434_ME_FanCoilUnit_FloorStanding_FWVDAT2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 476
HKG | 161 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK2Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 477
HKG | 162 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK4Pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 478
HKG | 163 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHKE |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 479
HKG | 164 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermID |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 480
HKG | 165 | 434_ME_FanCoilUnit_WallMounted_FWBBT2pipe |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 481
HKG | 166 | 434_ME_FanCoilUnit_WallMounted_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 482
HKG | 167 | 434_ME_FillsoftI |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 483
HKG | 168 | 434_ME_FlatCompactDryCooler |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 484
HKG | 169 | 434_ME_HeatedAndChilledBaffleCeilings_CeilingMounted_L608 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 485
HKG | 170 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD315 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 486
HKG | 171 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD320 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 487
HKG | 172 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs125_NoSystem |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 488
HKG | 173 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs78_NoSystem |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 489
HKG | 174 | 434_ME_HeatedAndChilledCorridorCeilings_CeilingMounted_E312 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 490
HKG | 175 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E200 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 491
HKG | 176 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E210 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 492
HKG | 177 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E213 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 493
HKG | 178 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E214 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 494
HKG | 179 | 434_ME_HeatedAndChilledHybridCeilings_CeilingMounted_DSTAS |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 495
HKG | 180 | 434_ME_HeatedAndChilledPlasterboardCeilings_CeilingMounted_GKHEKDA2Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 496
HKG | 181 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 497
HKG | 182 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100SD |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 498
HKG | 183 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B110 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 499
HKG | 184 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B147SD |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 500
HKG | 185 | 434_ME_HeatExchanger_Brazed&DoublePass&Flanged |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 501
HKG | 186 | 434_ME_HeatExchanger_BrazedSinglePass&Thread |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 502
HKG | 187 | 434_ME_HeatExchanger_Brazed_DoublePass |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 503
HKG | 188 | 434_ME_HeatExchanger_Brazed_SinglePass&Flanged |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 504
HKG | 189 | 434_ME_HeatExchanger_Gasketed&Flanged |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 505
HKG | 190 | 434_ME_HeatExchanger_Gasketed&Thread |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 506
HKG | 191 | 434_ME_HeatExchanger_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 507
HKG | 192 | 434_ME_InLinePump_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 508
HKG | 193 | 434_ME_ManifoldWithFlowMeter_10Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 509
HKG | 194 | 434_ME_ManifoldWithFlowMeter_11Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 510
HKG | 195 | 434_ME_ManifoldWithFlowMeter_12Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 511
HKG | 196 | 434_ME_ManifoldWithFlowMeter_2Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 512
HKG | 197 | 434_ME_ManifoldWithFlowMeter_3Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 513
HKG | 198 | 434_ME_ManifoldWithFlowMeter_4Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 514
HKG | 199 | 434_ME_ManifoldWithFlowMeter_5Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 515
HKG | 200 | 434_ME_ManifoldWithFlowMeter_6Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 5 | 2026-07-22 | 2026-07-28 | 2026-08-03 | 2026-08-07 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 516
HKG | 201 | 434_ME_ManifoldWithFlowMeter_7Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 517
HKG | 202 | 434_ME_ManifoldWithFlowMeter_8Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 518
HKG | 203 | 434_ME_ManifoldWithFlowMeter_9Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 519
HKG | 204 | 434_ME_ManifoldWithPump_1Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 520
HKG | 205 | 434_ME_ManifoldWithPump_2Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 521
HKG | 206 | 434_ME_ManifoldWithPump_3Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 522
HKG | 207 | 434_ME_ManifoldWithPump_4Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 523
HKG | 208 | 434_ME_ManifoldWithPump_5Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 524
HKG | 209 | 434_ME_ManifoldWithPump_6Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 525
HKG | 210 | 434_ME_ManifoldWithPump_7Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 526
HKG | 211 | 434_ME_ManifoldWithPump_8Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 527
HKG | 212 | 434_ME_Manifold_10Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 528
HKG | 213 | 434_ME_Manifold_11Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 529
HKG | 214 | 434_ME_Manifold_12Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 530
HKG | 215 | 434_ME_Manifold_2Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 531
HKG | 216 | 434_ME_Manifold_3Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 532
HKG | 217 | 434_ME_Manifold_4Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 533
HKG | 218 | 434_ME_Manifold_5Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 534
HKG | 219 | 434_ME_Manifold_6Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 535
HKG | 220 | 434_ME_Manifold_7Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 536
HKG | 221 | 434_ME_Manifold_8Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 537
HKG | 222 | 434_ME_Manifold_9Circuits |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 538
HKG | 223 | 434_ME_OutDoorUnit_VRV5HeatRecoveryREYA |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 539
HKG | 224 | 434_ME_PrecisionPressureMaintenance_TransferoTI |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 540
HKG | 225 | 434_ME_PrecisionPressureMaintenance_TransferoTV1 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 541
HKG | 226 | 434_ME_PrecisionPressureMaintenance_TransferoTV2 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 542
HKG | 227 | 434_ME_PrecisionPressureMaintenance_TransferoTVI1 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 543
HKG | 228 | 434_ME_PrecisionPressuremaintenance_TransferoTVI2 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 544
HKG | 229 | 434_ME_PrecisionPressurisation_CompressoC |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 545
HKG | 230 | 434_ME_PrecisionPressurisation_CompressoF |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 546
HKG | 231 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 547
HKG | 232 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9F |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 548
HKG | 233 | 434_ME_PressureMaintenanceMonitoring_PlenoPIX |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 549
HKG | 234 | 434_ME_PressureMaintenanceMonitoring_PlenoPX |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 550
HKG | 235 | 434_ME_PumpCirculator_FloorStand_Round_CronoLineILE |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 551
HKG | 236 | 434_ME_Pump_CirculatorAtmosGIGA&B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 552
HKG | 237 | 434_ME_Pump_CirculatorStratosGIGA&B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 553
HKG | 238 | 434_ME_Pump_CirculatorStratosGIGA&D |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 554
HKG | 239 | 434_ME_Pump_CirculatorStratosGIGA |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 555
HKG | 240 | 434_ME_Pump_CirculatorStratosGIGA20&D |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 556
HKG | 241 | 434_ME_Pump_CirculatorStratosGIGA20&I |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 557
HKG | 242 | 434_ME_Pump_CirculatorStratosMAXO&D |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 558
HKG | 243 | 434_ME_Pump_CirculatorStratosMAXO |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 559
HKG | 244 | 434_ME_Pump_CirculatorStratosPICO |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 560
HKG | 245 | 434_ME_Pump_CirculatorVeroLineIPL |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 561
HKG | 246 | 434_ME_Pump_CirculatorYonosMAXO&D |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 562
HKG | 247 | 434_ME_Pump_CirculatorYonosMAXO |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 563
HKG | 248 | 434_ME_Pump_CirculatorYonosPICO&D |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 564
HKG | 249 | 434_ME_Pump_CirculatorYonosPICO |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 565
HKG | 250 | 434_ME_Pump_Circulator_CronoTwin_DL_E |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 566
HKG | 251 | 434_ME_Pump_Circulator_VeroTwinDPL_DN100 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 567
HKG | 252 | 434_ME_Pump_Circulator_VeroTwinDPL_DN32 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 568
HKG | 253 | 434_ME_Pump_Circulator_VeroTwinDPL_DN40 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 569
HKG | 254 | 434_ME_Pump_Circulator_VeroTwinDPL_DN50 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 570
HKG | 255 | 434_ME_Pump_Circulator_VeroTwinDPL_DN65 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 571
HKG | 256 | 434_ME_Pump_Circulator_VeroTwinDPL_DN80 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 572
HKG | 257 | 434_ME_Pump_Circulator_YonosGIGA20D |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 573
HKG | 258 | 434_ME_Pump_Circulator_YonosGIGA20_I |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 574
HKG | 259 | 434_ME_Pump_SingleStageGlandedBM |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 575
HKG | 260 | 434_ME_Pump_SingleStageLowPressureBAC |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 576
HKG | 261 | 434_ME_Pump_SingleStageLowPressureBAC65 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 577
HKG | 262 | 434_ME_Pump_WaterSupplyAtmosGIGA&N |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 578
HKG | 263 | 434_ME_Pump_WaterSupplyAtmosI |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 579
HKG | 264 | 434_ME_Pump_WaterSupplyAtmosTERA&SCH |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 580
HKG | 265 | 434_ME_Pump_WaterSupplyCronoBlocBLE |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 581
HKG | 266 | 434_ME_Pump_WaterSupplyCronoNorm&NLG |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 582
HKG | 267 | 434_ME_Pump_WaterSupplySCP |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 583
HKG | 268 | 434_ME_Pump_WaterSupplyVeroLineIPE |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 584
HKG | 269 | 434_ME_Pump_WaterSupplyVeroTwinDPE |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 585
HKG | 270 | 434_ME_Pump_WaterSupplyYonosGIGA&N |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 586
HKG | 271 | 434_ME_SplitCasePump_Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 587
HKG | 272 | 434_ME_TwoOutletPump_Flanged |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 588
HKG | 273 | 434_ME_VariableSpeedWaterCooledLiquidChiller_SingleCompressor30XW&V |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 589
HKG | 274 | 434_ME_VRVInDoorUnit_CeilingMouted_FXFA&A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 590
HKG | 275 | 434_ME_VRVInDoorUnit_CeilingMouted_FXZA&A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 591
HKG | 276 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXHA&A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 592
HKG | 277 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXUA&A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 593
HKG | 278 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXDA |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 594
HKG | 279 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 595
HKG | 280 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA200and250A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 596
HKG | 281 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXSA |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 597
HKG | 282 | 434_ME_VRVInDoorUnit_WallMounted_FXAA&A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 598
HKG | 283 | 434_ME_VRVMultiBranchSelector_BS&10A14AV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 599
HKG | 284 | 434_ME_VRVMultiBranchSelector_BS&12A14AV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 600
HKG | 285 | 434_ME_VRVMultiBranchSelector_BS&4A14AV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 601
HKG | 286 | 434_ME_VRVMultiBranchSelector_BS&6A14AV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 602
HKG | 287 | 434_ME_VRVMultiBranchSelector_BS&8A14AV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 603
HKG | 288 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA14&20A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 604
HKG | 289 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA8&12A |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 605
HKG | 290 | 434_ME_VRVOutDoorUnit_HeatPumpRXYSA&AV1&AY1 |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 606
HKG | 291 | 434_ME_VRVShutOffValveBox_SV1A25AJV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 607
HKG | 292 | 434_ME_VRVShutOffValveBox_SV4A14AJV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 608
HKG | 293 | 434_ME_VRVShutOffValveBox_SV6A14AJV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 609
HKG | 294 | 434_ME_VRVShutOffValveBox_SV8A14AJV1B |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 610
HKG | 295 | 434_ME_WateCooledCondenserlessLiquidChillers_WithHydraulicModule_30RW |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 611
HKG | 296 | 434_ME_WatercooledCondenserlessliquidchillers_30RW_WithoutHydraulicModule |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 612
HKG | 297 | 434_ME_WaterCooledCondenserlessLiquidChillers_30WG |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 613
HKG | 298 | 434_ME_WaterCooledCondenserlessLiquidchillers_30WGA |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 614
HKG | 299 | 434_ME_WaterCooledLiquidChillers_30XW |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 615
HKG | 300 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC4Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 616
HKG | 301 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC5Pipes |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 617
HKG | 302 | 434_ME_Watercooled_Condenserlessliquidchillers_30RW_30RWA_VerticalConnection |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 618
HKG | 303 | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard |  | 434_ME | Cooling Revit Family | .rfa | MEP | DIG | 6 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-19 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 619
HKG | 303 | HGR | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 620
HKG | 1 | 491_NF_GussetPlate90dHexagon |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 621
HKG | 2 | 491_NF_GussetPlate90dRectangular |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 622
HKG | 3 | 491_NF_GussetPlate90dTCenter |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 623
HKG | 4 | 491_NF_GussetPlate90dTSide |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 624
HKG | 5 | 491_NF_GussetPlateAngularAxial |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 625
HKG | 6 | 491_NF_GussetPlateAngularDoubleAdjustableBrace |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 626
HKG | 7 | 491_NF_GussetPlateAngularRectangular |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 627
HKG | 8 | 491_NF_GussetPlateAngularSingleAdjustableBrace |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 628
HKG | 9 | 491_NF_GussetPlateBase |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 629
HKG | 10 | 491_NF_GussetPlateCantileverBracket |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 630
HKG | 11 | 491_NF_GussetPlateFlatHexagon |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 631
HKG | 12 | 491_NF_GussetPlateFlatRectangular |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 632
HKG | 13 | 491_NF_GussetPlateFlatSemiCircle |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 633
HKG | 14 | 491_NF_GussetPlateFlatT |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 634
HKG | 15 | 491_NF_GussetPlateTrailingArm |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 635
HKG | 16 | 491_NF_GussetPlateTrailingArmBrace |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 636
HKG | 17 | 491_NF_GussetPlateUShape |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 637
HKG | 18 | 491_NF_GussetPlateUShape_2Layers |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 638
HKG | 19 | 491_NF_GussetPlateUShape_Hanger |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 639
HKG | 20 | 491_NF_GussetPlateUShape_Omega |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 640
HKG | 21 | 491_NF_GussetPlateUShape_Side |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 641
HKG | 22 | 491_NF_GussetPlateWingShape |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 642
HKG | 23 | 491_NF_GussetPlateWShape |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 643
HKG | 24 | 491_NF_GussetPlateZShape |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 644
HKG | 25 | 491_NF_GussetPlate_StairTreadSupport |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 645
HKG | 26 | 491_NF_PipeClampAccessoriesPunchedAngle |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 646
HKG | 27 | 491_NF_PipeClampAccessoriesSquareWasher |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 647
HKG | 28 | 491_NF_PipeClampAccessories_BladeEnd |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 648
HKG | 29 | 491_NF_PipeClampAccessories_Clevis |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 649
HKG | 30 | 491_NF_PipeClampAccessories_EyeNut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 650
HKG | 31 | 491_NF_PipeClampAccessories_HangerStrap |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 651
HKG | 32 | 491_NF_PipeClampAccessories_LinkPlate |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 652
HKG | 33 | 491_NF_PipeClampAccessories_Turnbuckle |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 653
HKG | 34 | 491_NF_PipeClampBeamAttachmentsPurlinClip |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 654
HKG | 35 | 491_NF_PipeClampBeamAttachmentsSwivelFlangeClamp |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 655
HKG | 36 | 491_NF_PipeClampBeamAttachmentsUBracket |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 656
HKG | 37 | 491_NF_PipeClampBeamAttachmentsWeldOnBracket |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 657
HKG | 38 | 491_NF_PipeClampBeamAttachments_AngleBracket |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 658
HKG | 39 | 491_NF_PipeClampBeamAttachments_BeamClip |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 659
HKG | 40 | 491_NF_PipeClampBeamAttachments_FlangeClamp |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 660
HKG | 41 | 491_NF_PipeClampBeamAttachments_PipeBeamClip |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 661
HKG | 42 | 491_NF_PipeClampBeamAttachments_SphericalWasher |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 662
HKG | 43 | 491_NF_PipeClampBeamAttachments_SwivelCage |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 663
HKG | 44 | 491_NF_PipeClampDoubleBoltStrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 664
HKG | 45 | 491_NF_PipeClampFourBolt |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 665
HKG | 46 | 491_NF_PipeClampHangedSaddle |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 666
HKG | 47 | 491_NF_PipeClampPearHanger |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 667
HKG | 48 | 491_NF_PipeClampSingleBoltStrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 668
HKG | 49 | 491_NF_PipeClampThreeBolt |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 669
HKG | 50 | 491_NF_PipeClampTwistClip |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 670
HKG | 51 | 491_NF_PipeClampTwoPiece |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 671
HKG | 52 | 491_NF_PipeClampTwoPieceWithYoke |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 672
HKG | 53 | 491_NF_PipeClampUBolt |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 673
HKG | 54 | 491_NF_PipeClamp_OnePiece |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 674
HKG | 55 | 491_NF_PipeClamp_StandOffBracket |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 675
HKG | 56 | 491_NF_Steel_A1000_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 676
HKG | 57 | 491_NF_Steel_AnchorScrew |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 677
HKG | 58 | 491_NF_Steel_CantileverBrackets_Triangle |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 678
HKG | 59 | 491_NF_Steel_FlatWashers |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 679
HKG | 60 | 491_NF_Steel_HexagonHeadScrew |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 680
HKG | 61 | 491_NF_Steel_HexagonNut_Threaded |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 681
HKG | 62 | 491_NF_Steel_P1000B_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 682
HKG | 63 | 491_NF_Steel_P1000C41_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 683
HKG | 64 | 491_NF_Steel_P1000C_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 684
HKG | 65 | 491_NF_Steel_P1000_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 685
HKG | 66 | 491_NF_Steel_P10013_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 686
HKG | 67 | 491_NF_Steel_P1001A_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 687
HKG | 68 | 491_NF_Steel_P1001C3_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 688
HKG | 69 | 491_NF_Steel_P1001D3_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 689
HKG | 70 | 491_NF_Steel_P1001_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 690
HKG | 71 | 491_NF_Steel_P1003_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 691
HKG | 72 | 491_NF_Steel_P1004A_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 692
HKG | 73 | 491_NF_Steel_P2001A_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 693
HKG | 74 | 491_NF_Steel_P2001B_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 694
HKG | 75 | 491_NF_Steel_P2001C3_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 695
HKG | 76 | 491_NF_Steel_P3300_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 696
HKG | 77 | 491_NF_Steel_P4000_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 697
HKG | 78 | 491_NF_Steel_P40021_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 698
HKG | 79 | 491_NF_Steel_P4003_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 699
HKG | 80 | 491_NF_Steel_P5500_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 700
HKG | 81 | 491_NF_Steel_P5501_Unistrut |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 701
HKG | 82 | 491_NF_Steel_UnirodThreadedRod |  | 491_NF | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 702
HKG | 83 | 491_SE_ArmFromDoublePerpendicularArm |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 703
HKG | 84 | 491_SE_ArmWithAngleBracket |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 704
HKG | 85 | 491_SE_BracingArmSKOF80 |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 705
HKG | 86 | 491_SE_CantileverBracketAKF80 |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 706
HKG | 87 | 491_SE_ClampDoublePiece |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 707
HKG | 88 | 491_SE_ConductorHolders_FloorStand |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 708
HKG | 89 | 491_SE_DoublePillarWithPlate |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 709
HKG | 90 | 491_SE_DouleClampWithFoundationPlate |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 710
HKG | 91 | 491_SE_EndSupportSTAF80 |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 711
HKG | 92 | 491_SE_FixedpointsetXS |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 712
HKG | 93 | 491_SE_FrameHangerTopBase |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 713
HKG | 94 | 491_SE_GuidingBracketFWF |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 714
HKG | 95 | 491_SE_PillarOnTopAndDoubleArmWithThread |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 715
HKG | 96 | 491_SE_PillarOnTopAndSingleArmWithThread |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 716
HKG | 97 | 491_SE_PillarWithPlate |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 717
HKG | 98 | 491_SE_PipeClampWithRubberRing |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 718
HKG | 99 | 491_SE_PipeClampWithShadeNut |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 719
HKG | 100 | 491_SE_PipeStrapWithUType |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 720
HKG | 101 | 491_SE_PipeSupport_FloorStandingType |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 721
HKG | 102 | 491_SE_PipeSupport_RiserType |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 722
HKG | 103 | 491_SE_PipeSupport_Riser_ClampType |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 723
HKG | 104 | 491_SE_PipeTrapezeHangerDoubleFrame |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 724
HKG | 105 | 491_SE_PipeTrapezeHangerSingleFrame |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 725
HKG | 106 | 491_SE_RectangularDuctHanger_Standard |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 726
HKG | 107 | 491_SE_RoundDuctHanger_Standard |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 727
HKG | 108 | 491_SE_ShouderWithDoubleArm |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 728
HKG | 109 | 491_SE_SingleArmWithDoubleBracket |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 729
HKG | 110 | 491_SE_SingleArmWithPillarOnTop |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 730
HKG | 111 | 491_SE_SingleArmWithPlate |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 731
HKG | 112 | 491_SE_SlidesetFS |  | 491_SE | Hanger Revit Family | .rfa | MEP | DIG | 7 | 2026-08-13 | 2026-08-19 | 2026-08-25 | 2026-08-31 | Yes | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 732
HKG | 112 | Create the Revit templates for each LPH HKG | [5 empty] | DIG | [6 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 733
HKG | 112 | TGA_Revit Template | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 734
HKG | 1 | LPH3 |  | HKG | Revit Template | .rte | MEP | DIG | 8 | 2026-08-19 | 2026-08-25 | 2026-08-31 | 2026-09-04 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 735
HKG | 2 | LPH5 |  | HKG | Revit Template | .rte | MEP | DIG | 8 | 2026-08-19 | 2026-08-25 | 2026-08-31 | 2026-09-04 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 736
HKG | 3 | LPH8 |  | HKG | Revit Template | .rte | MEP | DIG | 8 | 2026-08-19 | 2026-08-25 | 2026-08-31 | 2026-09-04 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 737
HKG | D | TGA_Output Checklists | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 738
HKG | 1 | LPH3 Check list for HKG discipline |  |  |  | .xlsx | MEP | DIG | 9 | 2026-08-25 | 2026-08-31 | 2026-09-04 | 2026-09-10 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 739
HKG | 2 | LPH3_Check list_HKG 01 |  |  | Define Checklist_layout Plan |  | MEP | DIG | 9 | 2026-08-25 | 2026-08-31 | 2026-09-04 | 2026-09-10 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 740
HKG | 3 | LPH3_Check list_HKG 02 |  |  | Define Checklist_Section |  | MEP | DIG | 9 | 2026-08-25 | 2026-08-31 | 2026-09-04 | 2026-09-10 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 741
HKG | 4 | LPH3_Check list_HKG 03 |  |  | Define Checklist_Isometric Drawing |  | MEP | DIG | 9 | 2026-08-25 | 2026-08-31 | 2026-09-04 | 2026-09-10 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 742
HKG | 5 | LPH3_Check list_HKG 04 |  |  | Define Checklist_Schematic Diagram |  | MEP | DIG | 9 | 2026-08-25 | 2026-08-31 | 2026-09-04 | 2026-09-10 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 743
HKG | E | Sample Model + Out Put Data |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 744
HKG | E | Sample Model + Out Put Data For HKG | [12 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 745
HKG | 1 | Delivery layout Sample for HKG LPH3 |  |  | Execute a sample layout for the HKG discipline | .pdf | MEP | DIG | 10 | 2026-08-31 | 2026-09-04 | 2026-09-10 | 2026-09-16 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 746
HKG | 2 | Delivery layout Sample for HKG LPH5 |  |  | Execute a sample layout for the HKG discipline | .pdf | MEP | DIG | 10 | 2026-08-31 | 2026-09-04 | 2026-09-10 | 2026-09-16 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 747
HKG | 3 | Delivery layout Sample for HKG LPH8 |  |  | Execute a sample layout for the HKG discipline | .pdf | MEP | DIG | 10 | 2026-08-31 | 2026-09-04 | 2026-09-10 | 2026-09-16 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 748
HKG | 4 | Delivery Schematic Drawing Sample for HKG LPH3 |  |  | Execute a sample schematic for the HKG discipline | .pdf | MEP | DIG | 10 | 2026-08-31 | 2026-09-04 | 2026-09-10 | 2026-09-16 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 749
HKG | 5 | Delivery Schematic Drawing Sample for HKG LPH5 |  |  | Execute a sample schematic for the HKG discipline | .pdf | MEP | DIG | 10 | 2026-08-31 | 2026-09-04 | 2026-09-10 | 2026-09-16 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 750
HKG | F | Export layouts to Revizto & set up 3D Review HKG |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 751
HKG | 1 | Export layouts to Revizto & set up 3D Review HKG _LPH3 |  |  |  | .pdf | MEP | DIG | 11 | 2026-09-04 | 2026-09-10 | 2026-09-16 | 2026-09-22 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 752
HKG | 2 | Export layouts to Revizto & set up 3D Review HKG _LPH5 |  |  |  | .pdf | MEP | DIG | 11 | 2026-09-04 | 2026-09-10 | 2026-09-16 | 2026-09-22 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 753
HKG | 3 | Export layouts to Revizto & set up 3D Review HKG _LPH8 |  |  |  | .pdf | MEP | DIG | 11 | 2026-09-04 | 2026-09-10 | 2026-09-16 | 2026-09-22 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 754
HKG | G | Lesson Learned |  |  |  |  | MEP | DIG | [6 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 755
HKG | G | Lesson Learned HKG |  |  |  | .pdf | MEP | DIG | 12 | 2026-09-10 | 2026-09-16 | 2026-09-22 | 2026-09-28 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 756
HKG | 1 | What went well. |  |  | What went well. | .pdf | MEP | DIG | 12 | 2026-09-10 | 2026-09-16 | 2026-09-22 | 2026-09-28 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 757
HKG | 2 | What need to be improved |  |  | What didn’t go well | .pdf | MEP | DIG | 12 | 2026-09-10 | 2026-09-16 | 2026-09-22 | 2026-09-28 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 758
HKG | 3 | What we learned, |  |  | What we learned | .pdf | MEP | DIG | 12 | 2026-09-10 | 2026-09-16 | 2026-09-22 | 2026-09-28 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 759
HKG | 4 | Action items / Improvements |  |  | Action items / Improvements | .pdf | MEP | DIG | 12 | 2026-09-10 | 2026-09-16 | 2026-09-22 | 2026-09-28 |  | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 760
HKG | TRM | Transmital |  | MEP | [10 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 763
HKG | AUD | Auditting |  | DIG | [10 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 764
HKG | REV | Revision |  | MEP | [10 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 765
HKG | CFM | Confirmation/REVal Submission |  | MEP/DIG | [10 empty] | DCMvn_HKG_TIDP_Rev 01.xlsx | TIDP 410_Rev 02 | 766