## By_Ticket
Ticket ID | Summary | Start Date | End Date | Duration | Start_Method | End_Method | Evidence | Missing_Start | Missing_End | Flag | In_Matrix | In_Family
66575 | 2025_TL & TM Time allocation | 2025-11-12 | 2026-01-02 | 38 | handler_assign | status_closed | START: handler→l.truong @ 2025-11-12T08:18:39+01:00 ¦¦ END: status→closed @ 2026-01-02T01:39:32+01:00 | N | N |  | Y | N
66578 | 2025_TL & TM Time allocation_Nhut Le | 2025-11-12 | 2026-01-06 | 40 | handler_assign | status_closed | START: handler→n.le @ 2025-11-12T09:22:57+01:00 ¦¦ END: status→closed @ 2026-01-06T09:42:47+01:00 | N | N |  | Y | N
66592 | RLT_Creation Sheet | 2025-11-13 | 2025-11-17 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2025-11-13T04:54:44+01:00 ¦¦ END: status→resolved @ 2025-11-17T10:40:07+01:00 | N | N |  | Y | N
66598 | Anotation_General_Create the target drawing for set out layout_RLT_O1 | 2025-11-13 | 2026-01-30 | 57 | handler_assign | confirm_note:confirm_other | START: handler→n.le @ 2025-11-13T08:23:54+01:00 ¦¦ END: n.le: @hu.dam This ticket is a test task in the beginning of the project. It is outdated and can be closed @ 2026-01-30T08:24:11+01:00 | N | N |  | Y | N
66599 | Anotation_General_Create the target drawing for set out layout_RLT_HG | 2025-11-13 | 2026-05-11 | 128 | handler_assign | status_resolved | START: handler→l.truong @ 2025-11-13T08:24:11+01:00 ¦¦ END: status→resolved @ 2026-05-11T06:38:18+02:00 | N | N |  | Y | N
66600 | Anotation_DIG_Upgrade Library to Revit Version 2022 | 2025-11-13 | 2025-11-14 | 2 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-11-13T08:45:27+01:00 ¦¦ END: status→resolved @ 2025-11-14T02:34:30+01:00 | N | N |  | Y | N
66601 | Anotation_DIG_Assess the symbol of rfa | 2025-11-13 | 2025-11-17 | 3 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-11-13T08:51:57+01:00 ¦¦ END: status→resolved @ 2025-11-17T09:35:16+01:00 | N | N |  | Y | N
66613 | O1_Creating Floor Plan | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | START: handler→t.tran @ 2025-11-14T03:39:04+01:00 ¦¦ END: status→resolved @ 2025-11-25T02:47:01+01:00 | N | N |  | Y | N
66614 | O1_Floor Plan_Creating View Template | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | START: handler→t.tran @ 2025-11-14T03:38:53+01:00 ¦¦ END: status→resolved @ 2025-11-25T02:28:24+01:00 | N | N |  | Y | N
66615 | O1_3D_Creating View Template | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | START: handler→t.tran @ 2025-11-14T03:38:58+01:00 ¦¦ END: status→resolved @ 2025-11-25T02:31:14+01:00 | N | N |  | Y | N
66616 | O1_Creating 3D Views | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | START: handler→t.tran @ 2025-11-14T03:39:09+01:00 ¦¦ END: status→resolved @ 2025-11-25T01:47:59+01:00 | N | N |  | Y | N
66617 | O1_Creating RLT Legend | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | START: handler→t.tran @ 2025-11-14T03:39:17+01:00 ¦¦ END: status→resolved @ 2025-11-25T02:43:41+01:00 | N | N |  | Y | N
66659 | RLT_Creation Sheet List of Proposal | 2025-11-17 | 2025-11-18 | 2 | handler_assign | status_resolved | START: handler→tk.pham @ 2025-11-17T02:55:32+01:00 ¦¦ END: status→resolved @ 2025-11-18T04:50:02+01:00 | N | N |  | Y | N
66673 | RLT_Anotation_Update DF family | 2025-11-18 | 2025-11-21 | 4 | handler_assign | status_resolved | START: handler→ha.phan @ 2025-11-18T02:51:53+01:00 ¦¦ END: status→resolved @ 2025-11-21T09:59:13+01:00 | N | N |  | Y | N
66674 | RLT_Anotation_Update DA family | 2025-11-18 | 2025-11-21 | 4 | handler_assign | status_resolved | START: handler→d.nguyen @ 2025-11-18T02:51:12+01:00 ¦¦ END: status→resolved @ 2025-11-21T08:37:30+01:00 | N | N |  | Y | N
66675 | RLT_Anotation_Update Air Terminal family | 2025-11-18 | 2025-11-24 | 5 | handler_assign | status_resolved | START: handler→tk.pham @ 2025-11-18T02:53:27+01:00 ¦¦ END: status→resolved @ 2025-11-24T02:21:53+01:00 | N | N |  | Y | N
66676 | RLT_Anotation_Update RLT Equipment family | 2025-11-18 | 2025-11-20 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2025-11-18T02:53:17+01:00 ¦¦ END: status→resolved @ 2025-11-20T10:27:21+01:00 | N | N |  | Y | N
66677 | RLT_Anotation_Legend Creation | 2025-11-18 | 2025-11-24 | 5 | handler_assign | status_resolved | START: handler→ha.phan @ 2025-11-18T02:53:05+01:00 ¦¦ END: status→resolved @ 2025-11-24T08:49:03+01:00 | N | N |  | Y | N
66678 | RLT_Anotation_Creation View Template | 2025-11-18 | 2025-11-24 | 5 | handler_assign | status_resolved | START: handler→tk.pham @ 2025-11-18T02:51:29+01:00 ¦¦ END: status→resolved @ 2025-11-24T09:12:12+01:00 | N | N |  | Y | N
66706 | O1_Creating detailed items | 2025-11-18 | 2025-11-25 | 6 | handler_assign | confirm_note:confirm_other | START: handler→t.tran @ 2025-11-18T08:53:22+01:00 ¦¦ END: t.tran: @n.le The ticket is done. Please see an image for the details. Link PDF: https://dcm-vn.com/index.ph @ 2025-11-25T01:53:02+01:00 | N | N |  | Y | N
66709 | Annotation_DIG_Propose process to integrate the the symbol to rfa_DA | 2025-11-18 | 2025-11-28 | 9 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-11-18T09:37:46+01:00 ¦¦ END: status→resolved @ 2025-11-28T10:37:42+01:00 | N | N |  | Y | N
66785 | RLT_Anotation_Update layout based on new family | 2025-11-20 | 2025-11-24 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2025-11-20T10:21:24+01:00 ¦¦ END: status→resolved @ 2025-11-24T09:17:22+01:00 | N | N |  | Y | N
66840 | PD Tasks | 2025-11-24 | 2026-01-05 | 31 | handler_assign | status_closed | START: handler→f.imbrogno @ 2025-11-24T05:34:58+01:00 ¦¦ END: status→closed @ 2026-01-05T10:00:51+01:00 | N | N |  | Y | N
66853 | HZG/KLT_Accessing Revit families | 2025-11-24 | 2025-12-03 | 8 | handler_assign | confirm_note:confirm_other | START: handler→n.le @ 2025-11-24T07:08:38+01:00 ¦¦ END: t.tran: @n.le The ticket is done. All the required information is fulfilled in each Revit Family. Link: http @ 2025-12-03T08:56:27+01:00 | N | N |  | Y | N
66854 | HZG/KLT_Revit family and required information list | 2025-11-24 | 2025-11-24 | 1 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-11-24T07:09:37+01:00 ¦¦ END: status→resolved @ 2025-11-24T07:57:38+01:00 | N | N |  | Y | N
66855 | RLT_Accessing Revit families | 2025-11-25 | 2026-01-23 | 44 | handler_assign | confirm_note:confirm_other | START: handler→da.nguyen @ 2025-11-25T01:15:01+01:00 ¦¦ END: l.truong: The task is used in pilot time to create the comment documentation. This ticket is no longer needed. @ 2026-01-23T09:00:53+01:00 | N | N |  | Y | N
66896 | SAN_Revit family and required information list | 2025-11-25 | 2025-11-26 | 2 | handler_assign | confirm_note:confirm_other | START: handler→hu.dam @ 2025-11-25T01:21:26+01:00 ¦¦ END: n.le: @hu.dam Thank you. Ticket is closed. @ 2025-11-26T01:26:52+01:00 | N | N |  | Y | N
66897 | SPR_Revit family and required information list | 2025-11-25 | 2025-11-25 | 1 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-11-25T01:17:21+01:00 ¦¦ END: status→resolved @ 2025-11-25T03:30:15+01:00 | N | N |  | Y | N
66898 | ELE_Revit family and required information list | 2025-11-25 | 2025-11-26 | 2 | handler_assign | confirm_note:confirm_other | START: handler→hu.dam @ 2025-11-25T01:21:23+01:00 ¦¦ END: n.le: @hu.dam Thank you. Ticket is closed. @ 2025-11-26T01:27:07+01:00 | N | N |  | Y | N
66899 | SAN_Accessing Revit families | 2025-11-25 | 2025-12-03 | 7 | handler_assign | status_resolved | START: handler→n.le @ 2025-11-25T01:30:53+01:00 ¦¦ END: status→resolved @ 2025-12-03T09:03:19+01:00 | N | N |  | Y | N
66900 | ELE_Accessing Revit families | 2025-11-25 | 2025-12-03 | 7 | handler_assign | status_resolved | START: handler→n.le @ 2025-11-25T01:30:41+01:00 ¦¦ END: status→resolved @ 2025-12-03T08:49:58+01:00 | N | N |  | Y | N
66901 | Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2026-05-21 | 128 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-11-25T02:14:33+01:00 ¦¦ END: status→resolved @ 2026-05-21T08:50:59+02:00 | N | N |  | Y | N
66904 | SPR_Accessing Revit families | 2025-11-25 | 2026-01-23 | 44 | handler_assign | confirm_note:confirm_other | START: handler→tk.pham @ 2025-11-25T09:25:43+01:00 ¦¦ END: l.truong: The task is used in pilot time to create the comment documentation. This ticket is no longer needed. @ 2026-01-23T09:00:53+01:00 | N | N |  | Y | N
66916 | HZG_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-11 | 13 | handler_assign | confirm_note:confirm_other | START: handler→d.phan @ 2025-11-25T08:59:03+01:00 ¦¦ END: d.phan: @n.le The ticket is done. Please see the link below. Checking and filling in the data from the HZG ( @ 2025-12-11T07:15:13+01:00 | N | N |  | Y | N
66917 | KLT_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-04 | 8 | handler_assign | confirm_note:confirm_other | START: handler→t.tran @ 2025-11-25T08:58:48+01:00 ¦¦ END: t.tran: @n.le The ticket is done. Please see the link below. Checking and filling in the data from the KLT ( @ 2025-12-04T09:37:35+01:00 | N | N |  | Y | N
66918 | SAN_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-12 | 14 | handler_assign | status_closed | START: handler→th.nguyen @ 2025-11-25T08:58:34+01:00 ¦¦ END: status→closed @ 2025-12-12T07:48:51+01:00 | N | N |  | Y | N
66919 | ELE_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-11-25 | 1 | handler_assign | status_closed | START: handler→n.le @ 2025-11-25T08:56:26+01:00 ¦¦ END: status→closed @ 2025-11-25T08:56:26+01:00 | N | N |  | Y | N
66922 | RLT_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-04 | 8 | handler_assign | status_resolved | START: handler→tn.nguyen @ 2025-11-25T08:59:36+01:00 ¦¦ END: status→resolved @ 2025-12-04T10:39:29+01:00 | N | N |  | Y | N
66924 | SPR_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-11 | 13 | handler_assign | status_resolved | START: handler→n.bui @ 2025-11-25T09:00:24+01:00 ¦¦ END: status→resolved @ 2025-12-11T10:22:05+01:00 | N | N |  | Y | N
66926 | MED_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2026-01-30 | 49 | handler_assign | confirm_note:confirm_other | START: handler→h.le @ 2025-11-25T09:02:56+01:00 ¦¦ END: l.truong: @hu.dam, @s.duong The MED was confirmed in ticket #68005. Then this ticket is closed and assigned ba @ 2026-01-30T03:57:03+01:00 | N | N |  | Y | N
66927 | MSR_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2026-02-04 | 52 | handler_assign | confirm_note:will_be_closed | START: handler→l.pham @ 2025-11-25T09:05:11+01:00 ¦¦ END: hu.dam: This ticket will be closed based on validation in ticket #0068008 @ 2026-02-04T10:45:19+01:00 | N | N |  | Y | N
66984 | MSR_Accessing Revit families | 2025-12-01 | 2026-01-23 | 40 | handler_assign | confirm_note:confirm_other | START: handler→tn.nguyen @ 2025-12-01T01:04:30+01:00 ¦¦ END: l.truong: The task is used in pilot time to create the comment documentation. This ticket is no longer needed. @ 2026-01-23T09:00:53+01:00 | N | N |  | Y | N
66985 | MED_Accessing Revit families | 2025-11-27 | 2026-01-23 | 42 | handler_assign | confirm_note:confirm_other | START: handler→l.pham @ 2025-11-27T09:37:43+01:00 ¦¦ END: l.truong: The task is used in pilot time to create the comment documentation. This ticket is no longer needed. @ 2026-01-23T09:00:53+01:00 | N | N |  | Y | N
67010 | Anotation_DIG_Devlope the guideline and process to implement the rfa adjustment | 2025-11-27 | 2025-12-05 | 7 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-11-27T10:15:07+01:00 ¦¦ END: status→resolved @ 2025-12-05T09:41:13+01:00 | N | N |  | Y | N
67108 | Annotation_General_Graphical expectation for Layout | 2025-12-02 | 2025-12-04 | 3 | handler_assign | status_resolved | START: handler→l.truong @ 2025-12-02T09:17:31+01:00 ¦¦ END: status→resolved @ 2025-12-04T02:46:21+01:00 | N | N |  | Y | N
67116 | Annotation_DIG_Question and Answer Meeting Support | 2025-12-04 |  |  | handler_assign | none | START: handler→hu.dam @ 2025-12-04T11:32:07+01:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
67214 | Annotation_DIG_Prepare the workshop material | 2025-12-05 | 2025-12-12 | 6 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-12-05T09:51:29+01:00 ¦¦ END: status→resolved @ 2025-12-12T07:32:39+01:00 | N | N |  | Y | N
67242 | 2025_TL & TM Time allocation_Sang Duong | 2025-12-08 | 2026-02-09 | 46 | handler_assign | status_closed | START: handler→s.duong @ 2025-12-08T05:41:38+01:00 ¦¦ END: status→closed @ 2026-02-09T04:53:56+01:00 | N | N |  | Y | N
67259 | SAN_Annotation_General_Populate the graphical expectation for Layout | 2025-12-10 | 2025-12-26 | 13 | handler_assign | status_resolved | START: handler→d.nguyen @ 2025-12-10T01:47:13+01:00 ¦¦ END: status→resolved @ 2025-12-26T10:40:31+01:00 | N | N |  | Y | N
67262 | Annotation_DIG_Create the checklist and Template report for Detail Item Creation | 2025-12-09 | 2025-12-15 | 5 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-12-09T03:34:55+01:00 ¦¦ END: status→resolved @ 2025-12-15T09:36:06+01:00 | N | N |  | Y | N
67300 | 2025_TL & TM Time allocation_Thuong Huynh | 2025-12-10 | 2026-01-02 | 18 | handler_assign | status_closed | START: handler→tv.huynh @ 2025-12-10T03:21:00+01:00 ¦¦ END: status→closed @ 2026-01-02T02:54:38+01:00 | N | N |  | Y | N
67303 | SAN_Annotation_General_Populate the graphical expectation for Layout_Pipe Fitting | 2025-12-10 | 2025-12-19 | 8 | handler_assign | status_resolved | START: handler→d.nguyen @ 2025-12-10T04:08:58+01:00 ¦¦ END: status→resolved @ 2025-12-19T10:11:33+01:00 | N | N |  | Y | N
67305 | Annotation_General_Assess and Populate the data requirement | 2025-12-10 | 2026-09-10 | 197 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-12-10T04:27:38+01:00 ¦¦ END: status→resolved @ 2026-09-10T10:13:03+02:00 | N | N |  | Y | N
67307 | Annotation_KLT_General_Assess and Populate the data requirement | 2025-12-16 | 2025-12-26 | 9 | handler_assign | status_resolved | START: handler→ht.pham @ 2025-12-16T01:26:18+01:00 ¦¦ END: status→resolved @ 2025-12-26T09:34:34+01:00 | N | N |  | Y | N
67308 | Annotation_HZG_General_Assess and Populate the data requirement | 2025-12-16 | 2026-05-27 | 117 | handler_assign | confirm_note:confirm_other | START: handler→d.phan @ 2025-12-16T01:32:36+01:00 ¦¦ END: n.le: Thank you. This ticket is closed accordingly. @ 2026-05-27T09:13:23+02:00 | N | N |  | Y | N
67340 | Annotation_RLT_General_Assess and Populate the data requirement | 2025-12-12 | 2026-01-30 | 36 | handler_assign | confirm_note:confirm_other | START: handler→n.bui @ 2025-12-12T08:03:42+01:00 ¦¦ END: l.truong: @hu.dam, @h.pham The RLT was confirmed in ticket #0068004. Then this ticket is closed and assigned b @ 2026-01-30T03:58:26+01:00 | N | N |  | Y | N
67341 | Annotation_SPR_General_Assess and Populate the data requirement | 2025-12-15 | 2025-12-26 | 10 | handler_assign | status_resolved | START: handler→tk.pham @ 2025-12-15T02:06:40+01:00 ¦¦ END: status→resolved @ 2025-12-26T10:20:32+01:00 | N | N |  | Y | N
67342 | Annotation_MSR_General_Assess and Populate the data requirement | 2026-01-02 | 2026-01-07 | 4 | handler_assign | status_resolved | START: handler→n.bui @ 2026-01-02T01:07:16+01:00 ¦¦ END: status→resolved @ 2026-01-07T08:57:34+01:00 | N | N |  | Y | N
67343 | Annotation_MED_General_Assess and Populate the data requirement | 2026-01-02 | 2026-01-07 | 4 | handler_assign | status_resolved | START: handler→tn.nguyen @ 2026-01-02T01:06:59+01:00 ¦¦ END: status→resolved @ 2026-01-07T09:33:13+01:00 | N | N |  | Y | N
67375 | Annotation_DIG_Pilot the process to integrate the symbol to 3D object | 2025-12-12 | 2025-12-23 | 8 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-12-12T07:46:34+01:00 ¦¦ END: status→resolved @ 2025-12-23T10:25:39+01:00 | N | N |  | Y | N
67565 | BMA_Annotation_General_Populate the graphical expectation for Layout | 2025-12-22 | 2025-12-23 | 2 | handler_assign | status_resolved | START: handler→k.mai @ 2025-12-22T02:21:10+01:00 ¦¦ END: status→resolved @ 2025-12-23T10:08:35+01:00 | N | N |  | Y | N
67566 | Lighting_Annotation_General_Populate the graphical expectation for Layout | 2025-12-22 | 2025-12-23 | 2 | handler_assign | status_resolved | START: handler→k.mai @ 2025-12-22T02:46:38+01:00 ¦¦ END: status→resolved @ 2025-12-23T10:09:48+01:00 | N | N |  | Y | N
67567 | EDV_Annotation_General_Populate the graphical expectation for Layout | 2025-12-22 | 2025-12-23 | 2 | handler_assign | status_resolved | START: handler→tv.huynh @ 2025-12-22T02:24:55+01:00 ¦¦ END: status→resolved @ 2025-12-23T10:09:02+01:00 | N | N |  | Y | N
67672 | Annotation_RLT_DA_VolumeFlowRateMeasuringUnits_VMLK | 2025-12-23 | 2025-12-25 | 3 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-12-23T11:27:49+01:00 ¦¦ END: status→resolved @ 2025-12-25T11:26:15+01:00 | N | N |  | Y | N
67691 | 2025_TL & TM Time allocation_Hanh Pham | 2025-12-24 | 2026-01-02 | 8 | handler_assign | status_closed | START: handler→h.pham @ 2025-12-24T09:14:09+01:00 ¦¦ END: status→closed @ 2026-01-02T01:35:47+01:00 | N | N |  | Y | N
67713 | ELT_Annotation_General_Populate the graphical expectation for Layout_CF | 2025-12-24 | 2025-12-30 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2025-12-24T09:55:21+01:00 ¦¦ END: status→resolved @ 2025-12-30T08:32:34+01:00 | N | N |  | Y | N
67716 | Annotation_DIG_Tracking and backup the file | 2025-12-24 | 2025-12-31 | 6 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-12-24T10:37:53+01:00 ¦¦ END: status→resolved @ 2025-12-31T04:40:15+01:00 | N | N |  | Y | N
67736 | ELT_Annotation_General_Populate the graphical expectation for Layout_CI | 2025-12-25 | 2026-01-02 | 7 | handler_assign | status_resolved | START: handler→th.le @ 2025-12-25T08:58:09+01:00 ¦¦ END: status→resolved @ 2026-01-02T10:06:05+01:00 | N | N |  | Y | N
67737 | Annotation_General_Link the ticket number to family as recommendation | 2025-12-25 | 2025-12-30 | 4 | handler_assign | status_resolved | START: handler→nd.huynh @ 2025-12-25T09:10:38+01:00 ¦¦ END: status→resolved @ 2025-12-30T07:46:24+01:00 | N | N |  | Y | N
67741 | Annotation_SPR_PA_YStrainer_Grooved | 2025-12-25 | 2026-01-06 | 9 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-12-25T09:32:58+01:00 ¦¦ END: status→resolved @ 2026-01-06T09:36:51+01:00 | N | N |  | Y | N
67743 | Annotation_SPR_FA_FireAlarmZoneModuleControl | 2025-12-25 | 2026-04-28 | 89 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-12-25T09:40:34+01:00 ¦¦ END: status→resolved @ 2026-04-28T11:44:42+02:00 | N | N |  | Y | N
67744 | Annotation_RLT_ME_Fan_Roof_Exhaust | 2025-12-25 | 2025-12-31 | 5 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-12-25T09:48:56+01:00 ¦¦ END: status→resolved @ 2025-12-31T08:13:24+01:00 | N | N |  | Y | N
67745 | Annotation_RLT_ME_PowerSupplyUnitAccessControl_WallMounted | 2025-12-25 | 2025-12-31 | 5 | handler_assign | status_resolved | START: handler→hu.dam @ 2025-12-25T09:55:45+01:00 ¦¦ END: status→resolved @ 2025-12-31T10:12:56+01:00 | N | N |  | Y | N
67812 | ELT_Annotation_General_Populate the graphical expectation for Layout_EF | 2025-12-30 | 2026-01-09 | 9 | handler_assign | status_resolved | START: handler→t.do @ 2025-12-30T09:56:57+01:00 ¦¦ END: status→resolved @ 2026-01-09T09:34:21+01:00 | N | N |  | Y | N
67814 | ELT_Annotation_General_Populate the graphical expectation for Layout_LF | 2025-12-31 | 2026-01-09 | 8 | handler_assign | status_resolved | START: handler→c.le @ 2025-12-31T01:45:40+01:00 ¦¦ END: status→resolved @ 2026-01-09T09:35:23+01:00 | N | N |  | Y | N
67815 | ELT_Annotation_General_Populate the graphical expectation for Layout_EE | 2025-12-31 | 2026-01-09 | 8 | handler_assign | status_resolved | START: handler→n.vo @ 2025-12-31T01:45:25+01:00 ¦¦ END: status→resolved @ 2026-01-09T09:56:26+01:00 | N | N |  | Y | N
67838 | 2026Q1_DCMvn_Annotation Project_TL & TM Time allocation_Hanh Pham | 2026-01-02 | 2026-03-31 | 63 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-02T01:35:31+01:00 ¦¦ END: status→resolved @ 2026-03-31T10:24:09+02:00 | N | N |  | Y | N
67839 | 2026Q1_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-01-02 | 2026-04-17 | 76 | handler_assign | status_closed | START: handler→l.truong @ 2026-01-02T01:40:13+01:00 ¦¦ END: status→closed @ 2026-04-17T09:30:45+02:00 | N | N |  | Y | N
67855 | 2026Q1_Annotation Project_TL & TM Time allocation_Thuong Van Huynh | 2026-01-02 | 2026-04-10 | 71 | handler_assign | status_closed | START: handler→tv.huynh @ 2026-01-02T02:55:35+01:00 ¦¦ END: status→closed @ 2026-04-10T03:07:43+02:00 | N | N |  | Y | N
67890 | PD Tasks_2026Q1 | 2026-01-05 | 2026-04-07 | 67 | handler_assign | status_closed | START: handler→f.imbrogno @ 2026-01-05T10:00:13+01:00 ¦¦ END: status→closed @ 2026-04-07T05:23:33+02:00 | N | N |  | Y | N
67908 | BOS_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | START: handler→t.bui @ 2026-01-06T07:06:26+01:00 ¦¦ END: status→resolved @ 2026-01-07T08:48:25+01:00 | N | N |  | Y | N
67909 | KIT_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-01-08 | 3 | handler_assign | status_resolved | START: handler→t.bui @ 2026-01-06T07:11:33+01:00 ¦¦ END: status→resolved @ 2026-01-08T09:27:16+01:00 | N | N |  | Y | N
67910 | SE_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-03-04 | 42 | handler_assign | confirm_note:confirm_other | START: handler→t.bui @ 2026-01-06T07:17:28+01:00 ¦¦ END: l.truong: @hu.dam As discussed with other team lead, the system go to other team lead. This ticket is closed. @ 2026-03-04T02:40:52+01:00 | N | N |  | Y | N
67914 | HRG_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-01-09 | 4 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-01-06T07:20:32+01:00 ¦¦ END: status→resolved @ 2026-01-09T09:02:46+01:00 | N | N |  | Y | N
67918 | Annotation_HZG/KLT_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-01-06T07:48:14+01:00 ¦¦ END: status→resolved @ 2026-01-07T09:53:42+01:00 | N | N |  | Y | N
67919 | Annotation_RLT_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-01-06T07:47:39+01:00 ¦¦ END: status→resolved @ 2026-01-07T08:43:59+01:00 | N | N |  | Y | N
67920 | Annotation_SAN_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-01-06T07:47:58+01:00 ¦¦ END: status→resolved @ 2026-01-07T09:42:55+01:00 | N | N |  | Y | N
67921 | Annotation_ELE_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | START: handler→b.tran @ 2026-01-06T07:47:47+01:00 ¦¦ END: status→resolved @ 2026-01-07T09:41:04+01:00 | N | N |  | Y | N
67927 | 2026Q1_Annotation Project_TL & TM Time allocation_Nhut Minh Le | 2026-01-06 | 2026-04-01 | 62 | handler_assign | status_closed | START: handler→n.le @ 2026-01-06T08:59:49+01:00 ¦¦ END: status→closed @ 2026-04-01T02:31:15+02:00 | N | N |  | Y | N
67935 | Annotation_General_MIDP | 2026-01-07 | 2026-01-21 | 11 | handler_assign | status_resolved | START: handler→hu.dam @ 2026-01-07T02:29:58+01:00 ¦¦ END: status→resolved @ 2026-01-21T11:53:04+01:00 | N | N |  | Y | N
67944 | Annotation_Data Requirement Framework_Row 3_All System_Data Information Proposal | 2026-01-07 | 2026-01-13 | 5 | handler_assign | status_resolved | START: handler→n.bui @ 2026-01-07T07:08:48+01:00 ¦¦ END: status→resolved @ 2026-01-13T10:53:51+01:00 | N | N |  | Y | N
67971 | Annotation_Row 3_Data Requirement Proposal for TGA System Elements | 2026-01-08 | 2026-01-09 | 2 | handler_assign | status_resolved | START: handler→y.nguyen @ 2026-01-08T04:07:46+01:00 ¦¦ END: status→resolved @ 2026-01-09T09:34:56+01:00 | N | N |  | Y | N
68004 | RLT_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-01-12T02:22:13+01:00 ¦¦ END: status→resolved @ 2026-01-14T09:52:50+01:00 | N | N |  | Y | N
68005 | MED_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | START: handler→l.pham @ 2026-01-12T02:28:56+01:00 ¦¦ END: status→resolved @ 2026-01-14T09:40:01+01:00 | N | N |  | Y | N
68007 | ELT_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-12T03:05:34+01:00 ¦¦ END: status→resolved @ 2026-01-14T10:56:06+01:00 | N | N |  | Y | N
68008 | MSR_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-12T03:06:17+01:00 ¦¦ END: status→resolved @ 2026-01-14T10:30:01+01:00 | N | N |  | Y | N
68009 | ELT_Annotation_General_Populate the graphical expectation for Layout_Remaining Items | 2026-01-12 | 2026-01-12 | 1 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-12T03:20:38+01:00 ¦¦ END: status→resolved @ 2026-01-12T09:05:39+01:00 | N | N |  | Y | N
68010 | Data Requirement Proposal for SAN discipline through LPH3,LPH5 and LPH8 | 2026-01-12 | 2026-02-02 | 16 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-01-12T03:22:37+01:00 ¦¦ END: status→resolved @ 2026-02-02T08:53:38+01:00 | N | N |  | Y | N
68011 | Data Requirement Proposal for SPR discipline through LPH3,LPH5 and LPH8 | 2026-01-12 | 2026-02-02 | 16 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-01-12T03:22:29+01:00 ¦¦ END: status→resolved @ 2026-02-02T07:16:17+01:00 | N | N |  | Y | N
68012 | System Family_Annotation_General_Populate the graphical expectation for Layout_Part 1 | 2026-01-12 | 2026-01-13 | 2 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-12T03:24:10+01:00 ¦¦ END: status→resolved @ 2026-01-13T10:11:49+01:00 | N | N |  | Y | N
68013 | SAN_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-16 | 5 | handler_assign | status_resolved | START: handler→t.luu @ 2026-01-12T03:26:41+01:00 ¦¦ END: status→resolved @ 2026-01-16T09:52:45+01:00 | N | N |  | Y | N
68014 | SPR_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-16 | 5 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-01-12T03:27:52+01:00 ¦¦ END: status→resolved @ 2026-01-16T09:44:12+01:00 | N | N |  | Y | N
68015 | HZG_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-04-10 | 65 | handler_assign | confirm_note:confirm_other | START: handler→ht.pham @ 2026-01-12T07:16:12+01:00 ¦¦ END: n.le: Thank you all. Ticket is closed. @ 2026-04-10T02:53:18+02:00 | N | N |  | Y | N
68016 | KLT_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-04-10 | 65 | handler_assign | confirm_note:confirm_other | START: handler→dx.quach @ 2026-01-12T07:17:09+01:00 ¦¦ END: n.le: Thank you all. Ticket is closed. @ 2026-04-10T02:52:45+02:00 | N | N |  | Y | N
68017 | HGR_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-15 | 4 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-01-12T07:14:22+01:00 ¦¦ END: status→resolved @ 2026-01-15T09:24:35+01:00 | N | N |  | Y | N
68018 | Annotation_HGR_General_Assess and Populate the data requirement | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-01-12T07:11:48+01:00 ¦¦ END: status→resolved @ 2026-01-14T07:58:10+01:00 | N | N |  | Y | N
68031 | Annotation_ELT_General_Assess and Populate the data requirement_Part 2 | 2026-01-13 | 2026-01-16 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-13T02:04:31+01:00 ¦¦ END: status→resolved @ 2026-01-16T10:32:25+01:00 | N | N |  | Y | N
68032 | Annotation_MSR_General_Assess and Populate the data requirement_Part 2 | 2026-01-13 | 2026-01-16 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-13T02:05:36+01:00 ¦¦ END: status→resolved @ 2026-01-16T10:24:29+01:00 | N | N |  | Y | N
68054 | Annotation_Data Requirement Framework_Row 4_All System_Data Information Proposal | 2026-01-14 | 2026-01-19 | 4 | handler_assign | status_resolved | START: handler→h.le @ 2026-01-14T02:51:36+01:00 ¦¦ END: status→resolved @ 2026-01-19T09:50:32+01:00 | N | N |  | Y | N
68061 | Annotation_DIG_Create the Revit sample file | 2026-01-14 | 2026-01-21 | 6 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-01-14T05:31:12+01:00 ¦¦ END: status→resolved @ 2026-01-21T01:51:55+01:00 | N | N |  | Y | N
68105 | Revising Family_440_EF_DataConnectionSocket_Wall.rfa_Part 1 | 2026-01-19 | 2026-01-21 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-19T03:00:26+01:00 ¦¦ END: status→resolved @ 2026-01-21T10:22:00+01:00 | N | N |  | Y | N
68106 | Revising Family_440_LF_CoreLineLEDLight_CeilingSuspended.rfa_Part 1 | 2026-01-19 | 2026-01-22 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-19T03:01:34+01:00 ¦¦ END: status→resolved @ 2026-01-22T10:16:56+01:00 | N | N |  | Y | N
68107 | Revising Family_440_LF_EscapeSign_CeilingRecessed.rfa_Part 1 | 2026-01-19 | 2026-01-22 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-19T03:02:13+01:00 ¦¦ END: status→resolved @ 2026-01-22T10:17:40+01:00 | N | N |  | Y | N
68108 | Revising Family_440_NC_EmergencyPullCordSwitch_Wall.rfa_Part 1 | 2026-01-19 | 2026-01-20 | 2 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-19T03:03:00+01:00 ¦¦ END: status→resolved @ 2026-01-20T09:59:36+01:00 | N | N |  | Y | N
68109 | Revising Family_480_CD_CabinetLoudspeaker6W_WallMounted_Circular.rfa_Part 1 | 2026-01-19 | 2026-01-20 | 2 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-19T03:03:57+01:00 ¦¦ END: status→resolved @ 2026-01-20T10:45:51+01:00 | N | N |  | Y | N
68131 | RLT_Detail Item_Symbol Proposal | 2026-01-27 | 2026-02-25 | 22 | handler_assign | status_resolved | START: handler→tk.pham @ 2026-01-27T01:28:43+01:00 ¦¦ END: status→resolved @ 2026-02-25T10:09:26+01:00 | N | N |  | Y | N
68132 | MED_Detail Item_Symbol Proposal | 2026-01-27 | 2026-02-06 | 9 | handler_assign | status_resolved | START: handler→l.pham @ 2026-01-27T01:28:06+01:00 ¦¦ END: status→resolved @ 2026-02-06T09:28:10+01:00 | N | N |  | Y | N
68138 | Annotation_DIG_Confirm the possibility of reflection data by native Revit Parameter | 2026-01-20 | 2026-02-02 | 10 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-01-20T05:18:51+01:00 ¦¦ END: status→resolved @ 2026-02-02T09:01:41+01:00 | N | N |  | Y | N
68139 | Annotation_DIG_Create the testing and confirming environment | 2026-01-20 | 2026-01-28 | 7 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-01-20T05:39:59+01:00 ¦¦ END: status→resolved @ 2026-01-28T08:36:23+01:00 | N | N |  | Y | N
68140 | Annotation_General_TIDP Set up and creation_Digital Coordinator | 2026-01-20 | 2026-01-21 | 2 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-01-20T05:53:48+01:00 ¦¦ END: status→resolved @ 2026-01-21T08:42:17+01:00 | N | N |  | Y | N
68142 | Annotation_General_TIDP Set up and creation_Lam Truong | 2026-01-20 | 2026-02-27 | 29 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-01-20T07:17:51+01:00 ¦¦ END: status→resolved @ 2026-02-27T08:10:21+01:00 | N | N |  | Y | N
68143 | Annotation_General_TIDP Set up and creation_Thuong Huynh | 2026-01-20 | 2026-02-03 | 11 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-01-20T07:23:12+01:00 ¦¦ END: status→resolved @ 2026-02-03T04:15:29+01:00 | N | N |  | Y | N
68144 | Annotation_General_TIDP Set up and creation_Nhut Le | 2026-01-20 | 2026-02-06 | 14 | handler_assign | status_resolved | START: handler→n.le @ 2026-01-20T07:24:14+01:00 ¦¦ END: status→resolved @ 2026-02-06T10:18:26+01:00 | N | N |  | Y | N
68145 | Annotation_General_TIDP Set up and creation_Sang Duong | 2026-01-20 | 2026-05-11 | 80 | handler_assign | status_resolved | START: handler→n.le @ 2026-01-20T07:27:01+01:00 ¦¦ END: status→resolved @ 2026-05-11T03:54:32+02:00 | N | N |  | Y | N
68146 | Annotation_General_TIDP Set up and creation_Hanh Pham | 2026-01-20 | 2026-02-09 | 15 | handler_assign | status_resolved | START: handler→n.le @ 2026-01-20T07:29:03+01:00 ¦¦ END: status→resolved @ 2026-02-09T10:00:04+01:00 | N | N |  | Y | N
68148 | Revising Family_474_PA_AlarmCheckValve_European.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | START: handler→dhn.nguyen @ 2026-01-20T08:35:50+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:15:59+02:00 | N | N |  | Y | N
68149 | Revising Family_474_SP_Pendent.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | START: handler→hoa.le @ 2026-01-20T08:35:17+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:16:20+02:00 | N | N |  | Y | N
68150 | Revising Family_410_ME_CentrifugalPump.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | START: handler→k.mai @ 2026-01-20T08:34:10+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:14:59+02:00 | N | N |  | Y | N
68151 | Revising Family_410_ME_WastewaterLiftingStation_DouPump.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | START: handler→n.vo @ 2026-01-20T08:33:48+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:18:38+02:00 | N | N |  | Y | N
68152 | Revising Family_410_PX_FloorDrain_Horizontal_QuickCoupling_Plastic_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | START: handler→y.nguyen @ 2026-01-20T08:32:47+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:15:18+02:00 | N | N |  | Y | N
68153 | Revising Family_410_PA_StainlessSteel_ShutoffValve_MapressGeberit.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | START: handler→c.le @ 2026-01-20T08:31:45+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:15:42+02:00 | N | N |  | Y | N
68160 | DCMvn_Annotation_SAN_Detail Item_Symbol Proposal | 2026-01-21 | 2026-04-10 | 58 | handler_assign | confirm_note:task_completed_closed | START: handler→ht.pham @ 2026-01-21T02:43:16+01:00 ¦¦ END: tv.huynh: The task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:09:54+02:00 | N | N |  | Y | N
68161 | DCMvn_Annotation_SPR_Detail Item_Symbol Proposal | 2026-01-21 | 2026-04-10 | 58 | handler_assign | confirm_note:task_completed_closed | START: handler→tv.huynh @ 2026-01-21T02:20:08+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:17:26+02:00 | N | N |  | Y | N
68162 | Revising Family_420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-01-21T02:42:16+01:00 ¦¦ END: status→resolved @ 2026-01-23T08:12:30+01:00 | N | N |  | Y | N
68163 | Revising Family_420_PA_BalancingValve_Flanged.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-01-21T02:43:05+01:00 ¦¦ END: status→resolved @ 2026-01-23T09:58:08+01:00 | N | N |  | Y | N
68164 | Revising Family_420_PF_Copper_Elbow.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→t.tran @ 2026-01-21T02:42:49+01:00 ¦¦ END: status→resolved @ 2026-01-23T08:20:02+01:00 | N | N |  | Y | N
68165 | Revising Family_434_ME_FanCoilUnit_CeilingCassette_Standard.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-01-21T02:42:32+01:00 ¦¦ END: status→resolved @ 2026-01-23T07:28:29+01:00 | N | N |  | Y | N
68166 | Revising Family_434_PA_RefnetJoint_KHRPGas.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→d.phan @ 2026-01-21T02:43:31+01:00 ¦¦ END: status→resolved @ 2026-01-23T08:39:16+01:00 | N | N |  | Y | N
68167 | Revising Family_434_PF_CO_Bend_Mapress.rfa_Part 1 | 2026-01-21 | 2026-01-22 | 2 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-01-21T02:43:23+01:00 ¦¦ END: status→resolved @ 2026-01-22T09:30:13+01:00 | N | N |  | Y | N
68171 | Revising Family_491_NF_GussetPlateBase.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→b.tran @ 2026-01-21T02:47:38+01:00 ¦¦ END: status→resolved @ 2026-01-23T04:51:24+01:00 | N | N |  | Y | N
68172 | Revising Family_491_SE_ArmWithAngleBracket.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-01-21T02:47:27+01:00 ¦¦ END: status→resolved @ 2026-01-23T08:54:59+01:00 | N | N |  | Y | N
68173 | Revising Family_420_ME_AirCurtain_WallMounted.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | START: handler→dx.quach @ 2026-01-21T02:49:01+01:00 ¦¦ END: status→resolved @ 2026-01-23T08:58:07+01:00 | N | N |  | Y | N
68179 | RLT_Revising Family_430_AT_DisplacementFlowDiffusers_Wall_QLV_Supply.rfa _Part 1 | 2026-01-22 | 2026-01-30 | 7 | handler_assign | status_resolved | START: handler→ha.phan @ 2026-01-22T01:32:38+01:00 ¦¦ END: status→resolved @ 2026-01-30T10:25:15+01:00 | N | N |  | Y | N
68180 | RLT_Revising Family_430_DA_FireDampers_FireProtectionValve_FV_EU.rfa _Part 1 | 2026-01-22 | 2026-01-29 | 6 | handler_assign | status_resolved | START: handler→d.nguyen @ 2026-01-22T01:32:45+01:00 ¦¦ END: status→resolved @ 2026-01-29T09:39:00+01:00 | N | N |  | Y | N
68181 | DCMvn_Annotation_ELT_Detail Item_Symbol Proposal | 2026-01-21 | 2026-01-27 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-21T07:28:57+01:00 ¦¦ END: status→resolved @ 2026-01-27T09:57:22+01:00 | N | N |  | Y | N
68182 | DCMvn_Annotation_MSR_Detail Item_Symbol Proposal | 2026-01-21 | 2026-01-27 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-21T07:29:29+01:00 ¦¦ END: status→resolved @ 2026-01-27T09:09:02+01:00 | N | N |  | Y | N
68190 | Annotation_General_TIDP Set up and creation_Hanh Pham | 2026-01-22 | 2026-01-22 | 1 | handler_assign | status_closed | START: handler→h.pham @ 2026-01-22T02:27:05+01:00 ¦¦ END: status→closed @ 2026-01-22T09:03:00+01:00 | N | N |  | Y | N
68192 | Annotation_DIG_Set up and config the Database of information | 2026-01-22 | 2026-05-18 | 83 | handler_assign | status_resolved | START: handler→hu.dam @ 2026-01-22T02:37:51+01:00 ¦¦ END: status→resolved @ 2026-05-18T12:44:26+02:00 | N | N |  | Y | N
68199 | Test update error | 2026-01-22 | 2026-01-22 | 1 | handler_assign | status_closed | START: handler→bn.hoai @ 2026-01-22T04:05:32+01:00 ¦¦ END: status→closed @ 2026-01-22T04:28:47+01:00 | N | N |  | Y | N
68201 | Annotation_DIG_Create the testing and confirming environment_SubTask01and02 | 2026-01-22 | 2026-01-22 | 1 | handler_assign | status_resolved | START: handler→pv.tran @ 2026-01-22T05:36:37+01:00 ¦¦ END: status→resolved @ 2026-01-22T10:17:56+01:00 | N | N |  | Y | N
68202 | Annotation_DIG_Create the testing and confirming environment_SubTask03and04 | 2026-01-22 | 2026-01-28 | 5 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-01-22T05:37:58+01:00 ¦¦ END: status→resolved @ 2026-01-28T08:35:40+01:00 | N | N |  | Y | N
68223 | Revising Family_473_ME_HeatlessRegenerationAdsorptionDryers_ActivatedCarbonTower.rfa_Part 1 | 2026-01-23 | 2026-01-30 | 6 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-01-23T03:58:04+01:00 ¦¦ END: status→resolved @ 2026-01-30T07:26:27+01:00 | N | N |  | Y | N
68227 | Revising Family_473_PA_CondensateDistributor2Branch_WOSCD.rfa_Part 1 | 2026-01-23 | 2026-01-30 | 6 | handler_assign | status_resolved | START: handler→t.bui @ 2026-01-23T07:21:08+01:00 ¦¦ END: status→resolved @ 2026-01-30T10:07:26+01:00 | N | N |  | Y | N
68249 | HZG_Create sample layout + schematic | 2026-01-26 | 2026-01-27 | 2 | handler_assign | status_resolved | START: handler→t.tran @ 2026-01-26T01:59:44+01:00 ¦¦ END: status→resolved @ 2026-01-27T09:20:05+01:00 | N | N |  | Y | N
68250 | KLT_Create sample layout + schematic | 2026-01-26 | 2026-01-27 | 2 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-01-26T01:59:54+01:00 ¦¦ END: status→resolved @ 2026-01-27T08:54:58+01:00 | N | N |  | Y | N
68263 | Revising Family_480_FA_Bell.rfa_Part 1 | 2026-01-26 | 2026-01-28 | 3 | handler_assign | status_resolved | START: handler→t.doan @ 2026-01-26T09:26:50+01:00 ¦¦ END: status→resolved @ 2026-01-28T10:15:07+01:00 | N | N |  | Y | N
68276 | HZG_Detail Item_Symbol Proposal | 2026-01-27 | 2026-02-04 | 7 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-01-27T09:46:35+01:00 ¦¦ END: status→resolved @ 2026-02-04T09:27:03+01:00 | N | N |  | Y | N
68277 | KLT_Detail Item_Symbol Proposal | 2026-01-28 | 2026-02-04 | 6 | handler_assign | status_resolved | START: handler→d.phan @ 2026-01-28T01:49:35+01:00 ¦¦ END: status→resolved @ 2026-02-04T09:08:42+01:00 | N | N |  | Y | N
68278 | HZG_Propose Drawing List_LPH3 + LPH5 + LPH8 | 2026-01-28 | 2026-02-02 | 4 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-01-28T01:49:06+01:00 ¦¦ END: status→resolved @ 2026-02-02T09:03:55+01:00 | N | N |  | Y | N
68279 | KLT_Propose Drawing List_LPH3 + LPH5 + LPH8 | 2026-01-28 | 2026-02-02 | 4 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-01-28T01:49:20+01:00 ¦¦ END: status→resolved @ 2026-02-02T09:37:58+01:00 | N | N |  | Y | N
68280 | HZG_Inspecting system for LPH3 + LPH5 + LPH8 output | 2026-01-28 | 2026-03-06 | 28 | handler_assign | status_closed | START: handler→t.tran @ 2026-01-28T01:48:52+01:00 ¦¦ END: status→closed @ 2026-03-06T09:49:57+01:00 | N | N |  | Y | N
68281 | KLT_Inspecting system for LPH3 + LPH5 + LPH8 output | 2026-01-28 | 2026-03-06 | 28 | handler_assign | status_closed | START: handler→l.nguyen @ 2026-01-28T01:48:41+01:00 ¦¦ END: status→closed @ 2026-03-06T09:50:03+01:00 | N | N |  | Y | N
68287 | ELT_Installations_LPH3_Sample Layout_Multiple Scales | 2026-01-27 | 2026-01-30 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-01-27T09:50:42+01:00 ¦¦ END: status→resolved @ 2026-01-30T10:04:54+01:00 | N | N |  | Y | N
68288 | Annotation_General_Exchange Information Requirement Creation | 2026-01-27 | 2026-02-05 | 8 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-01-27T10:02:27+01:00 ¦¦ END: status→resolved @ 2026-02-05T08:55:37+01:00 | N | N |  | Y | N
68297 | Revising Family_440_EE_Generator_Standard.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | START: handler→n.chau @ 2026-01-28T02:00:42+01:00 ¦¦ END: status→resolved @ 2026-01-29T09:52:14+01:00 | N | N |  | Y | N
68298 | Revising Family_440_CI_PVC_cMarkerforConnectionLugs.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | START: handler→dv.nguyen @ 2026-01-28T02:05:40+01:00 ¦¦ END: status→resolved @ 2026-01-29T10:15:56+01:00 | N | N |  | Y | N
68299 | Revising Family_440_EF_EquipotentialBondingBusbars_WallMounted.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | START: handler→tu.le @ 2026-01-28T02:07:36+01:00 ¦¦ END: status→resolved @ 2026-01-29T09:53:47+01:00 | N | N |  | Y | N
68300 | Revising Family_440_EF_MotionDetector360_CeilingSurface.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | START: handler→t.le @ 2026-01-28T02:10:31+01:00 ¦¦ END: status→resolved @ 2026-01-29T10:13:51+01:00 | N | N |  | Y | N
68322 | Revising Family_480_FA_PushButton_WallMounted_RWA_Part 1 | 2026-01-29 | 2026-01-30 | 2 | handler_assign | status_resolved | START: handler→t.doan @ 2026-01-29T01:58:26+01:00 ¦¦ END: status→resolved @ 2026-01-30T10:38:03+01:00 | N | N |  | Y | N
68323 | MSR_LPH3_Sample Layout_Multiple Scales | 2026-01-29 | 2026-02-03 | 4 | handler_assign | status_resolved | START: handler→n.chau @ 2026-01-29T02:02:08+01:00 ¦¦ END: status→resolved @ 2026-02-03T10:01:19+01:00 | N | N |  | Y | N
68325 | Revising Family_410_ME_CompactPressureBoostingSystem_Part 1 | 2026-01-29 | 2026-04-10 | 52 | handler_assign | confirm_note:task_completed_closed | START: handler→t.luu @ 2026-01-29T03:37:19+01:00 ¦¦ END: tv.huynh: Part 1 of the task is completed. The ticket is closed accordingly. Thank you. @ 2026-04-10T03:14:45+02:00 | N | N |  | Y | N
68340 | Annotation_General_Verify the family name and ticket summary matching | 2026-01-29 | 2026-05-15 | 77 | handler_assign | status_resolved | START: handler→hu.dam @ 2026-01-29T09:18:21+01:00 ¦¦ END: status→resolved @ 2026-05-15T10:36:29+02:00 | N | N |  | Y | N
68400 | Annotation_DIG_Revise RFA_Implement and Debate | 2026-02-02 | 2026-02-04 | 3 | handler_assign | status_resolved | START: handler→lk.dang @ 2026-02-02T08:58:04+01:00 ¦¦ END: status→resolved @ 2026-02-04T11:05:44+01:00 | N | N |  | Y | N
68436 | Annotation_General_Create RACI Table | 2026-02-04 | 2026-02-06 | 3 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-02-04T05:06:06+01:00 ¦¦ END: status→resolved @ 2026-02-06T04:33:34+01:00 | N | N |  | Y | N
68438 | ELT_LPH3_Sample Schematic | 2026-02-04 | 2026-02-06 | 3 | handler_assign | status_resolved | START: handler→n.chau @ 2026-02-04T09:13:13+01:00 ¦¦ END: status→resolved @ 2026-02-06T10:06:39+01:00 | N | N |  | Y | N
68450 | Revising Family_410_ME_PumpGlandlessCirculator_StarZD._Part 1 | 2026-02-05 | 2026-04-10 | 47 | handler_assign | status_closed | START: handler→hoa.le @ 2026-02-05T08:37:54+01:00 ¦¦ END: status→closed @ 2026-04-10T03:18:02+02:00 | N | N |  | Y | N
68476 | 2026_Annotation Project_TL & TM Time allocation_Sang Xui Duong | 2026-02-06 |  |  | handler_assign | none | START: handler→tv.huynh @ 2026-02-06T08:56:46+01:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
68484 | MSR_LPH3_Sample Schematic | 2026-02-09 | 2026-02-11 | 3 | handler_assign | status_resolved | START: handler→n.chau @ 2026-02-09T02:51:00+01:00 ¦¦ END: status→resolved @ 2026-02-11T09:54:11+01:00 | N | N |  | Y | N
68489 | ELT_Installations_LPH5_Sample Layout_Multiple Scales | 2026-02-09 | 2026-02-11 | 3 | handler_assign | status_resolved | START: handler→d.le @ 2026-02-09T03:31:07+01:00 ¦¦ END: status→resolved @ 2026-02-11T10:33:22+01:00 | N | N |  | Y | N
68493 | Annotation_General_Assess and Populate the data requirement | 2026-02-09 |  |  | handler_assign | none | START: handler→s.duong @ 2026-02-09T03:51:00+01:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
68542 | 630_Annotation_General_Populate the graphical expectation for Layout_Part 1 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-02-11T03:15:09+01:00 ¦¦ END: status→resolved @ 2026-02-13T10:05:30+01:00 | N | N |  | Y | N
68550 | MEP_Revise RFA_440_NC_EmergencyPullCordSwitch_Wall_Part 2 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | START: handler→th.le @ 2026-02-11T08:11:13+01:00 ¦¦ END: status→resolved @ 2026-02-13T09:32:35+01:00 | N | N |  | Y | N
68551 | MEP_Revise RFA_440_EF_EquipotentialBondingBusbars_WallMounted.rfa_Part 2 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | START: handler→tu.le @ 2026-02-11T08:15:21+01:00 ¦¦ END: status→resolved @ 2026-02-13T10:09:06+01:00 | N | N |  | Y | N
68552 | MEP_Revise RFA_440_LF_CoreLineLEDLight_CeilingSuspended.rfa_Part 2 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | START: handler→t.le @ 2026-02-11T08:17:13+01:00 ¦¦ END: status→resolved @ 2026-02-13T10:16:57+01:00 | N | N |  | Y | N
68553 | MEP_Revise RFA_480_FA_Bell.rfa_Part 2 | 2026-02-11 | 2026-02-23 | 9 | handler_assign | status_resolved | START: handler→l.su @ 2026-02-11T08:19:44+01:00 ¦¦ END: status→resolved @ 2026-02-23T08:43:18+01:00 | N | N |  | Y | N
68554 | MEP_Revise RFA_440_LF_EscapeSign_CeilingRecessed.rfa_Part 2 | 2026-02-11 | 2026-02-24 | 10 | handler_assign | status_resolved | START: handler→t.doan @ 2026-02-11T08:21:30+01:00 ¦¦ END: status→resolved @ 2026-02-24T09:52:56+01:00 | N | N |  | Y | N
68615 | MEP_Revise RFA_440_CI_PVC_cMarkerforConnectionLugs_Part 2 | 2026-02-23 | 2026-02-24 | 2 | handler_assign | status_resolved | START: handler→th.le @ 2026-02-23T08:14:53+01:00 ¦¦ END: status→resolved @ 2026-02-24T09:58:20+01:00 | N | N |  | Y | N
68617 | MEP_Revise RFA_480_FA_PushButton_WallMounted_RWA_Part 2 | 2026-02-23 | 2026-02-25 | 3 | handler_assign | status_resolved | START: handler→l.su @ 2026-02-23T09:10:03+01:00 ¦¦ END: status→resolved @ 2026-02-25T09:51:02+01:00 | N | N |  | Y | N
68654 | MEP_Revise RFA_430_DF_GalvanizedSteel_Ubergangsstutzen_Flanged | 2026-02-26 | 2026-05-07 | 51 | handler_assign | status_resolved | START: handler→h.le @ 2026-02-26T01:27:10+01:00 ¦¦ END: status→resolved @ 2026-05-07T11:34:18+02:00 | N | N |  | Y | N
68655 | MEP_Revise RFA_430_DF_GS_cBoden_Flanged | 2026-02-26 | 2026-05-06 | 50 | handler_assign | status_resolved | START: handler→ha.phan @ 2026-02-26T01:27:26+01:00 ¦¦ END: status→resolved @ 2026-05-06T09:53:53+02:00 | N | N |  | Y | N
68656 | MEP_Revise RFA_430_DF_GS_cCapEnd_Spigot_Round | 2026-02-27 | 2026-03-02 | 2 | handler_assign | status_resolved | START: handler→t.bui @ 2026-02-27T09:17:22+01:00 ¦¦ END: status→resolved @ 2026-03-02T09:52:02+01:00 | N | N |  | Y | N
68657 | MEP_Revise RFA_430_DF_GS_eBogen_Flanged | 2026-02-25 | 2026-03-02 | 4 | handler_assign | status_resolved | START: handler→l.pham @ 2026-02-25T09:27:02+01:00 ¦¦ END: status→resolved @ 2026-03-02T10:27:48+01:00 | N | N |  | Y | N
68658 | MEP_Revise RFA_430_DF_GS_eEckbogen_Flanged | 2026-02-26 | 2026-02-27 | 2 | handler_assign | status_resolved | START: handler→t.bui @ 2026-02-26T01:25:44+01:00 ¦¦ END: status→resolved @ 2026-02-27T09:27:20+01:00 | N | N |  | Y | N
68659 | MEP_Revise RFA_430_DF_GS_eRoundElbow_Spigot | 2026-02-26 | 2026-03-02 | 3 | handler_assign | status_resolved | START: handler→tn.nguyen @ 2026-02-26T01:28:50+01:00 ¦¦ END: status→resolved @ 2026-03-02T09:45:57+01:00 | N | N |  | Y | N
68744 | MEP_Revise RFA_430_DF_GS_eTransitionElbow_Flanged | 2026-03-05 | 2026-05-07 | 46 | handler_assign | status_resolved | START: handler→t.bui @ 2026-03-05T02:19:36+01:00 ¦¦ END: status→resolved @ 2026-05-07T11:08:30+02:00 | N | N |  | Y | N
68745 | MEP_Revise RFA_430_DF_GS_rReducer_Spigot_Round. | 2026-03-04 | 2026-04-29 | 41 | handler_assign | status_resolved | START: handler→n.bui @ 2026-03-04T07:17:51+01:00 ¦¦ END: status→resolved @ 2026-04-29T10:22:08+02:00 | N | N |  | Y | N
68746 | MEP_Revise RFA_430_DF_GS_rUbergang_Flanged | 2026-03-04 | 2026-03-09 | 4 | handler_assign | status_resolved | START: handler→n.bui @ 2026-03-04T07:17:29+01:00 ¦¦ END: status→resolved @ 2026-03-09T03:00:38+01:00 | N | N |  | Y | N
68747 | MEP_Revise RFA_430_DF_GS_rUbergang_Flanged | 2026-03-03 | 2026-03-04 | 2 | handler_assign | status_resolved | START: handler→l.pham @ 2026-03-03T02:27:04+01:00 ¦¦ END: status→resolved @ 2026-03-04T10:16:10+01:00 | N | N |  | Y | N
68748 | MEP_Revise RFA_430_DF_GS_rUbergangRechteckRund_Flanged_SlipJoint | 2026-03-04 | 2026-03-05 | 2 | handler_assign | status_resolved | START: handler→tk.pham @ 2026-03-04T03:52:43+01:00 ¦¦ END: status→resolved @ 2026-03-05T02:25:08+01:00 | N | N |  | Y | N
68749 | MEP_Revise RFA_430_DF_GS_sRoundTaps_Spigot | 2026-03-04 | 2026-03-05 | 2 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-03-04T03:53:11+01:00 ¦¦ END: status→resolved @ 2026-03-05T10:32:34+01:00 | N | N |  | Y | N
68750 | MEP_Revise RFA_430_DF_GS_Tee_Spigot_Round | 2026-03-02 | 2026-03-04 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-03-02T07:04:48+01:00 ¦¦ END: status→resolved @ 2026-03-04T07:41:44+01:00 | N | N |  | Y | N
68752 | MEP_Revise RFA_430_DF_GS_tTStuck_Flanged | 2026-03-02 | 2026-03-04 | 3 | handler_assign | status_resolved | START: handler→n.bui @ 2026-03-02T02:27:10+01:00 ¦¦ END: status→resolved @ 2026-03-04T08:54:35+01:00 | N | N |  | Y | N
68753 | MEP_Revise RFA_430_DF_GS_uCoupling_Spigot_Round | 2026-03-02 | 2026-03-03 | 2 | handler_assign | status_resolved | START: handler→t.bui @ 2026-03-02T10:01:01+01:00 ¦¦ END: status→resolved @ 2026-03-03T09:22:51+01:00 | N | N |  | Y | N
68754 | MEP_Revise RFA_430_DF_GS_uUnion_Flanged | 2026-03-02 | 2026-03-04 | 3 | handler_assign | status_resolved | START: handler→tk.pham @ 2026-03-02T07:05:16+01:00 ¦¦ END: status→resolved @ 2026-03-04T03:50:12+01:00 | N | N |  | Y | N
68755 | MEP_Revise RFA_430_DF_GS_wHosenStuck_Flanged | 2026-03-03 | 2026-03-04 | 2 | handler_assign | status_resolved | START: handler→t.bui @ 2026-03-03T09:48:56+01:00 ¦¦ END: status→resolved @ 2026-03-04T10:48:07+01:00 | N | N |  | Y | N
68757 | MEP_Revise RFA_430_DF_GS_xKreuzstuck_Flanged | 2026-03-02 | 2026-05-06 | 48 | handler_assign | status_resolved | START: handler→tn.nguyen @ 2026-03-02T08:58:42+01:00 ¦¦ END: status→resolved @ 2026-05-06T05:56:32+02:00 | N | N |  | Y | N
68896 | MEP_Revise RFA_430_AT_Test | 2026-03-05 | 2026-05-11 | 48 | handler_assign | status_resolved | START: handler→l.pham @ 2026-03-05T02:24:24+01:00 ¦¦ END: status→resolved @ 2026-05-11T05:01:41+02:00 | N | N |  | Y | N
68897 | MEP_Revise RFA_430_AT_DeflectorHood_Roof_Round_Exhaust | 2026-03-05 | 2026-05-19 | 54 | handler_assign | status_resolved | START: handler→tk.pham @ 2026-03-05T02:28:03+01:00 ¦¦ END: status→resolved @ 2026-05-19T09:26:21+02:00 | N | N |  | Y | N
69617 | Annotation_DIG_Confirm the database and project material | 2026-03-10 | 2026-04-10 | 24 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-03-10T02:46:21+01:00 ¦¦ END: status→resolved @ 2026-04-10T11:43:47+02:00 | N | N |  | Y | N
69618 | Annotation_DIG_BEP Creation | 2026-03-10 | 2026-04-29 | 37 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-03-10T02:52:30+01:00 ¦¦ END: status→resolved @ 2026-04-29T11:04:06+02:00 | N | N |  | Y | N
70869 | 2026Q2_DCMvn_Annotation Project_TL & TM Time allocation_Hanh Pham | 2026-03-31 | 2026-06-30 | 66 | handler_assign | status_resolved | START: handler→h.pham @ 2026-03-31T10:17:43+02:00 ¦¦ END: status→resolved @ 2026-06-30T07:00:23+02:00 | N | N |  | Y | N
70900 | 2026Q2_Annotation Project_TL & TM Time allocation_Nhut Minh Le | 2026-04-01 | 2026-07-02 | 67 | handler_assign | status_closed | START: handler→n.le @ 2026-04-01T02:30:53+02:00 ¦¦ END: status→closed @ 2026-07-02T09:32:31+02:00 | N | N |  | Y | N
70988 | PD Tasks_2026Q2 | 2026-04-07 | 2026-07-02 | 63 | handler_assign | status_closed | START: handler→f.imbrogno @ 2026-04-07T05:23:12+02:00 ¦¦ END: status→closed @ 2026-07-02T09:11:08+02:00 | N | N |  | Y | N
71063 | 2026Q2_Annotation Project_TL & TM Time allocation_Thuong Van Huynh | 2026-04-10 | 2026-07-02 | 60 | handler_assign | status_closed | START: handler→tv.huynh @ 2026-04-10T03:21:39+02:00 ¦¦ END: status→closed @ 2026-07-02T11:24:49+02:00 | N | N |  | Y | N
71142 | KLT_Inspecting system for LPH3 + LPH5 + LPH8 | 2026-04-14 | 2026-04-24 | 9 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-04-14T10:40:46+02:00 ¦¦ END: status→resolved @ 2026-04-24T09:28:01+02:00 | N | N |  | Y | N
71143 | HZG_Inspecting system for LPH3 + LPH5 + LPH8 | 2026-04-14 | 2026-04-24 | 9 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-04-14T10:40:23+02:00 ¦¦ END: status→resolved @ 2026-04-24T11:44:59+02:00 | N | N |  | Y | N
71208 | 2026Q2_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-04-17 | 2026-07-06 | 57 | handler_assign | status_closed | START: handler→l.truong @ 2026-04-17T09:29:16+02:00 ¦¦ END: status→closed @ 2026-07-06T03:24:03+02:00 | N | N |  | Y | N
71224 | MEP_Revise 420_PA_BallValve3Way_LPort. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | START: handler→s.duong @ 2026-04-20T04:16:30+02:00 ¦¦ END: status→resolved @ 2026-04-24T10:29:11+02:00 | N | N |  | Y | N
71225 | MEP_Revise 420_PA_BallValve3Way_TPort. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | START: handler→s.duong @ 2026-04-20T04:17:54+02:00 ¦¦ END: status→resolved @ 2026-04-24T09:33:22+02:00 | N | N |  | Y | N
71226 | MEP_Revise 420_PA_BasketStrainerValve_Flanged_Standard. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | START: handler→s.duong @ 2026-04-20T04:18:31+02:00 ¦¦ END: status→resolved @ 2026-04-24T10:43:56+02:00 | N | N |  | Y | N
71227 | MEP_Revise 420_PA_BasketStrainerValve_Thread_Standard. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | START: handler→s.duong @ 2026-04-20T04:19:34+02:00 ¦¦ END: status→resolved @ 2026-04-24T10:34:43+02:00 | N | N |  | Y | N
71228 | MEP_Revise 420_PA_ButterflyValve_Flanged_GearStandard. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | START: handler→s.duong @ 2026-04-20T04:20:29+02:00 ¦¦ END: status→resolved @ 2026-04-24T10:20:07+02:00 | N | N |  | Y | N
71229 | MEP_Revise 420_PA_ButterflyValve_Flanged_Handle. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | START: handler→s.duong @ 2026-04-20T04:21:17+02:00 ¦¦ END: status→resolved @ 2026-04-24T11:07:06+02:00 | N | N |  | Y | N
71342 | MEP_Revise 420_PA_ButterflyValve_Flanged_LeverStandard. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | START: handler→n.nguyen @ 2026-04-23T10:16:09+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:40:19+02:00 | N | N |  | Y | N
71343 | MEP_Revise 420_PA_ButterflyValve_Thread_GearStandard. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | START: handler→tt.bui @ 2026-04-23T10:17:08+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:30:01+02:00 | N | N |  | Y | N
71344 | MEP_Revise 420_PA_ButterflyValve_Thread_LeverStandard. | 2026-04-23 | 2026-05-07 | 11 | handler_assign | status_resolved | START: handler→u.nguyen @ 2026-04-23T10:18:39+02:00 ¦¦ END: status→resolved @ 2026-05-07T11:13:04+02:00 | N | N |  | Y | N
71345 | MEP_Revise 420_PA_ButterflyValveHandwheel_Flanged. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | START: handler→n.dinh @ 2026-04-23T10:19:51+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:55:18+02:00 | N | N |  | Y | N
71347 | MEP_Revise 420_PA_ButterflyvalveMotor_Flanged. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | START: handler→n.dinh @ 2026-04-23T10:21:35+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:10:13+02:00 | N | N |  | Y | N
71348 | MEP_Revise 420_PA_CapValve_Thread. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | START: handler→tu.nguyen @ 2026-04-23T10:22:17+02:00 ¦¦ END: status→resolved @ 2026-05-08T11:28:31+02:00 | N | N |  | Y | N
71349 | MEP_Revise 420_PA_CheckValveWithThermometer_Thread. | 2026-04-23 | 2026-06-18 | 41 | handler_assign | status_closed | START: handler→t.huynh @ 2026-04-23T10:22:55+02:00 ¦¦ END: status→closed @ 2026-06-18T08:45:13+02:00 | N | N |  | Y | N
71431 | ELT_LES_LPH3_Sample Layout_Multiple Scales | 2026-05-04 | 2026-05-08 | 5 | handler_assign | status_resolved | START: handler→t.do @ 2026-05-04T03:13:33+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:47:28+02:00 | N | N |  | Y | N
71432 | ELT_Installations_LPH8_Sample Layout_Multiple Scales | 2026-05-04 | 2026-05-08 | 5 | handler_assign | status_resolved | START: handler→n.chau @ 2026-05-04T03:16:52+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:43:52+02:00 | N | N |  | Y | N
71435 | SAN_Inspecting Water Supply System for LPH3 + LPH5 + LPH8 | 2026-05-04 | 2026-05-15 | 10 | handler_assign | status_resolved | START: handler→y.nguyen @ 2026-05-04T04:26:23+02:00 ¦¦ END: status→resolved @ 2026-05-15T03:57:50+02:00 | N | N |  | Y | N
71437 | SAN_Inspecting Drainage System for LPH3 + LPH5 + LPH8 | 2026-05-04 | 2026-05-15 | 10 | handler_assign | status_resolved | START: handler→t.luu @ 2026-05-04T04:26:12+02:00 ¦¦ END: status→resolved @ 2026-05-15T05:58:31+02:00 | N | N |  | Y | N
71456 | ELT_Cable tray_LPH3_Sample Layout_Multiple Scales | 2026-05-04 | 2026-05-11 | 6 | handler_assign | status_resolved | START: handler→th.le @ 2026-05-04T10:54:30+02:00 ¦¦ END: status→resolved @ 2026-05-11T11:04:25+02:00 | N | N |  | Y | N
71481 | MEP_Revise RFA_430_DF_GS_rReducer_Spigot_Round. | 2026-05-06 | 2026-05-08 | 3 | handler_assign | status_resolved | START: handler→n.bui @ 2026-05-06T02:16:36+02:00 ¦¦ END: status→resolved @ 2026-05-08T11:06:24+02:00 | N | N |  | Y | N
71482 | MEP_Revise RFA_430_DF_GS_rUbergang_Flanged | 2026-05-06 | 2026-05-06 | 1 | handler_assign | status_closed | START: handler→tn.nguyen @ 2026-05-06T02:17:17+02:00 ¦¦ END: status→closed @ 2026-05-06T02:33:42+02:00 | N | N |  | Y | N
71483 | MEP_Revise RFA_430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Return | 2026-05-06 | 2026-05-11 | 4 | handler_assign | status_resolved | START: handler→l.pham @ 2026-05-06T02:35:49+02:00 ¦¦ END: status→resolved @ 2026-05-11T10:44:36+02:00 | N | N |  | Y | N
71484 | MEP_Revise RFA_430_AT_Test | 2026-05-06 | 2026-05-08 | 3 | handler_assign | status_resolved | START: handler→tn.nguyen @ 2026-05-06T02:36:32+02:00 ¦¦ END: status→resolved @ 2026-05-08T05:10:50+02:00 | N | N |  | Y | N
71496 | Annotation_ELT_MSR_Execution Planning | 2026-05-06 | 2026-05-08 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-06T04:09:37+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:57:36+02:00 | N | N |  | Y | N
71520 | MEP_Revise RFA_30_ME_Fan_Axial | 2026-05-07 | 2026-05-07 | 1 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-05-07T02:32:19+02:00 ¦¦ END: status→resolved @ 2026-05-07T11:30:57+02:00 | N | N |  | Y | N
71540 | MEP_Revise RFA_430_AT_CircularDiscValves_LVS_Return | 2026-05-08 | 2026-05-11 | 2 | handler_assign | status_resolved | START: handler→l.pham @ 2026-05-08T02:48:42+02:00 ¦¦ END: status→resolved @ 2026-05-11T11:02:43+02:00 | N | N |  | Y | N
71541 | MEP_Revise RFA_30_AT_CircularDiscValves_ZLVS_Supply | 2026-05-08 | 2026-05-20 | 9 | handler_assign | status_closed | START: handler→tk.pham @ 2026-05-08T02:49:10+02:00 ¦¦ END: status→closed @ 2026-05-20T03:21:27+02:00 | N | N |  | Y | N
71542 | MEP_Revise RFA_430_DA_CircularSilencers_CA_100 | 2026-05-08 | 2026-05-08 | 1 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-05-08T02:49:52+02:00 ¦¦ END: status→resolved @ 2026-05-08T10:59:38+02:00 | N | N |  | Y | N
71543 | MEP_Revise RFA_430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowEN | 2026-05-08 | 2026-05-11 | 2 | handler_assign | status_resolved | START: handler→t.bui @ 2026-05-08T02:50:34+02:00 ¦¦ END: status→resolved @ 2026-05-11T11:07:15+02:00 | N | N |  | Y | N
71544 | MEP_Revise RFA_430_DA_FireDampersForCeiling_KU_K30 | 2026-05-08 | 2026-05-11 | 2 | handler_assign | status_resolved | START: handler→ha.phan @ 2026-05-08T02:51:39+02:00 ¦¦ END: status→resolved @ 2026-05-11T11:08:42+02:00 | N | N |  | Y | N
71576 | Annotation_General_Ticket Template | 2026-05-08 |  |  | handler_assign | none | START: handler→hu.dam @ 2026-05-08T10:27:43+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
71581 | Test_Update_430_DA_CircularSilencers_CA_100 | 2026-05-11 | 2026-05-22 | 10 | handler_assign | status_closed | START: handler→n.bui @ 2026-05-11T03:22:26+02:00 ¦¦ END: status→closed @ 2026-05-22T02:14:14+02:00 | N | N |  | Y | N
71582 | Test_Revised family | 2026-05-11 | 2026-09-07 | 86 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-05-11T03:54:04+02:00 ¦¦ END: status→resolved @ 2026-09-07T08:07:47+02:00 | N | N |  | Y | N
71584 | 440_EF_SocketOutlet_Wall | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-11T04:48:32+02:00 ¦¦ END: status→resolved @ 2026-05-13T11:13:11+02:00 | N | N |  | Y | N
71586 | 440_EF_Thermosat | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-11T04:52:23+02:00 ¦¦ END: status→resolved @ 2026-05-13T09:59:30+02:00 | N | N |  | Y | N
71587 | 440_EF_DataConnectionSocket_Wall | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-11T04:53:19+02:00 ¦¦ END: status→resolved @ 2026-05-13T09:21:19+02:00 | N | N |  | Y | N
71588 | 440_EF_EarthingFixedPoint_WallSurface | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-11T04:54:10+02:00 ¦¦ END: status→resolved @ 2026-05-13T09:57:19+02:00 | N | N |  | Y | N
71589 | 440_EF_AirTerminationRodsForMetalRoofs | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-11T04:55:06+02:00 ¦¦ END: status→resolved @ 2026-05-13T10:27:05+02:00 | N | N |  | Y | N
71590 | 440_EF_AirTerminationRods_FloorStand | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-11T04:55:57+02:00 ¦¦ END: status→resolved @ 2026-05-13T10:45:34+02:00 | N | N |  | Y | N
71591 | MEP_Revise 474_PA_CS_YStrainer_Grooved. | 2026-05-11 | 2026-05-14 | 4 | handler_assign | status_resolved | START: handler→n.nguyen @ 2026-05-11T04:57:13+02:00 ¦¦ END: status→resolved @ 2026-05-14T10:10:45+02:00 | N | N |  | Y | N
71592 | MEP_474_PA_ShutoffValve_Motorized. | 2026-05-11 | 2026-07-15 | 48 | handler_assign | confirm_note:will_be_closed | START: handler→n.dinh @ 2026-05-11T04:57:48+02:00 ¦¦ END: s.duong: This ticket and ticket #0071593 are the same. Therefore, this ticket will be closed. @ 2026-07-15T12:05:10+02:00 | N | N |  | Y | N
71593 | MEP_Revise 474_PA_ShutoffValve_Motorized. | 2026-05-11 | 2026-09-30 | 103 | handler_assign | confirm_note:will_be_closed | START: handler→n.dinh @ 2026-05-11T04:58:14+02:00 ¦¦ END: s.duong: @hu.dam This family is the same with ticket 0072295. Therefore, this ticket will be closed. Thank yo @ 2026-09-30T06:40:09+02:00 | N | N |  | Y | N
71594 | MEP_Revise 474_PA_GateValve. | 2026-05-11 | 2026-08-14 | 70 | handler_assign | confirm_note:stored_full | START: handler→tt.bui @ 2026-05-11T04:58:59+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T05:51:22+02:00 | N | N |  | Y | Y
71595 | MEP_474_PA_AlarmCheckValve | 2026-05-11 | 2026-05-14 | 4 | handler_assign | status_resolved | START: handler→u.nguyen @ 2026-05-11T05:00:31+02:00 ¦¦ END: status→resolved @ 2026-05-14T11:18:44+02:00 | N | N |  | Y | N
71596 | MEP_Revise 474_PA_MaintenanceUnit. | 2026-05-11 | 2026-08-21 | 75 | handler_assign | confirm_note:stored_full | START: handler→t.huynh @ 2026-05-11T05:01:39+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-21T02:53:15+02:00 | N | N |  | Y | Y
71597 | MEP_Revise 474_PA_DischargeValve. | 2026-05-11 | 2026-09-04 | 85 | handler_assign | confirm_note:stored_full | START: handler→tu.nguyen @ 2026-05-11T05:02:19+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-04T05:08:32+02:00 | N | N |  | Y | Y
71598 | 410_PF_CI_tBranch68Deg_Coupling | 2026-05-15 | 2026-05-26 | 8 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-15T11:09:42+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-05-26T06:42:30+02:00 | N | N |  | Y | Y
71599 | 410_PF_CI_uCleaningPipeWithRectangularcover_Coupling | 2026-05-15 | 2026-05-19 | 3 | handler_assign | status_resolved | START: handler→c.le @ 2026-05-15T11:10:30+02:00 ¦¦ END: status→resolved @ 2026-05-19T10:29:11+02:00 | N | N |  | Y | N
71601 | RLT_LPH8_Sample Layout_Multiple Scales | 2026-05-11 | 2026-05-18 | 6 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-05-11T06:12:05+02:00 ¦¦ END: status→resolved @ 2026-05-18T11:16:56+02:00 | N | N |  | Y | N
71602 | RLT_LPH3_Sample Layout_Multiple Scales | 2026-05-11 | 2026-05-18 | 6 | handler_assign | status_resolved | START: handler→t.do @ 2026-05-11T06:12:56+02:00 ¦¦ END: status→resolved @ 2026-05-18T11:49:33+02:00 | N | N |  | Y | N
71603 | RLT_LPH5_Sample Layout_Multiple Scales | 2026-05-11 | 2026-05-18 | 6 | handler_assign | status_resolved | START: handler→n.bui @ 2026-05-11T06:14:14+02:00 ¦¦ END: status→resolved @ 2026-05-18T11:40:46+02:00 | N | N |  | Y | N
71604 | DCMvn_Annotation_SAN Detail Item and model lines Symbol Proposal | 2026-05-11 | 2026-05-15 | 5 | handler_assign | status_resolved | START: handler→n.vo @ 2026-05-11T08:43:00+02:00 ¦¦ END: status→resolved @ 2026-05-15T10:58:25+02:00 | N | N |  | Y | N
71622 | MSR_LPH5_Sample Layout_Multiple Scales | 2026-05-12 | 2026-05-18 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-12T02:52:43+02:00 ¦¦ END: status→resolved @ 2026-05-18T10:34:38+02:00 | N | N |  | Y | N
71632 | Annotation_General_TIDP Set up and creation_SRP & MED systems_Sang Duong | 2026-05-12 | 2026-05-19 | 6 | handler_assign | status_resolved | START: handler→hu.dam @ 2026-05-12T12:57:27+02:00 ¦¦ END: status→resolved @ 2026-05-19T08:04:35+02:00 | N | N |  | Y | N
71633 | MSR_LPH8_Sample Layout_Multiple Scales | 2026-05-13 | 2026-05-18 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-13T02:17:14+02:00 ¦¦ END: status→resolved @ 2026-05-18T10:44:47+02:00 | N | N |  | Y | N
71634 | ELT_LES_LPH5_Sample Layout_Multiple Scales | 2026-05-13 | 2026-05-18 | 4 | handler_assign | status_resolved | START: handler→d.le @ 2026-05-13T03:03:18+02:00 ¦¦ END: status→resolved @ 2026-05-18T11:05:36+02:00 | N | N |  | Y | N
71659 | 440_EF_EmergencyStopPushButtons | 2026-05-13 | 2026-05-13 | 1 | handler_assign | status_resolved | START: handler→d.le @ 2026-05-13T06:31:19+02:00 ¦¦ END: status→resolved @ 2026-05-13T10:40:50+02:00 | N | N |  | Y | N
71660 | Annotation_General_TIDP Set up and creation_Digital Coordinator_Danh Nguyen | 2026-05-13 | 2026-05-18 | 4 | handler_assign | status_resolved | START: handler→dahn.nguyen @ 2026-05-13T08:12:22+02:00 ¦¦ END: status→resolved @ 2026-05-18T11:26:15+02:00 | N | N |  | Y | N
71666 | Revise the RFA library for the SAN system. | 2026-05-13 |  |  | handler_assign | none | START: handler→tv.huynh @ 2026-05-13T10:32:33+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
71679 | 410_PF_CI_uCleaningPipeWithRoundCover_Coupling | 2026-05-15 | 2026-05-28 | 10 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-15T11:11:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-05-28T10:21:04+02:00 | N | N |  | Y | Y
71680 | 410_PF_CI_xCombinationBranch88Degree_Coupling | 2026-05-15 | 2026-06-17 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-15T11:12:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-17T08:33:03+02:00 | N | N |  | Y | Y
71681 | 410_PF_CastIron_DownPipeBracket_Coupling | 2026-05-26 | 2026-05-26 | 1 | handler_assign | status_closed | START: handler→tv.huynh @ 2026-05-26T06:27:04+02:00 ¦¦ END: status→closed @ 2026-05-26T06:27:04+02:00 | N | N |  | Y | N
71682 | 410_PF_CI_rEccentricReducer_Coupling | 2026-05-15 | 2026-05-18 | 2 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-05-15T11:13:01+02:00 ¦¦ END: status→resolved @ 2026-05-18T11:16:45+02:00 | N | N |  | Y | Y
71683 | 410_PF_CI_cPlug_Coupling | 2026-05-15 | 2026-05-21 | 5 | handler_assign | status_resolved | START: handler→t.luu @ 2026-05-15T11:14:21+02:00 ¦¦ END: status→resolved @ 2026-05-21T02:39:46+02:00 | N | N |  | Y | Y
71684 | 410_CI_eRainwaterSiphon_Coupling | 2026-05-18 | 2026-06-02 | 12 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-18T06:04:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-02T08:08:24+02:00 | N | N |  | Y | Y
71685 | 410_PF_CI_uSMLRainwaterSiphonVertical_Coupling | 2026-05-18 | 2026-06-01 | 11 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-18T06:05:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-01T08:19:30+02:00 | N | N |  | Y | Y
71686 | 410_PF_cHDPE_BlindFlange_Flanged | 2026-05-18 | 2026-06-16 | 22 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-18T06:06:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T09:36:05+02:00 | N | N |  | Y | Y
71687 | 410_PF_CI_fAngleDoubleBranch88Degree_Coupling | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-18T06:07:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T08:15:59+02:00 | N | N |  | Y | Y
71688 | 410_PF_CI_Bearing | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-05-18T06:08:19+02:00 ¦¦ END: status→resolved @ 2026-05-20T02:39:02+02:00 | N | N |  | Y | Y
71689 | 410_PF_CI_tBranch45Deg_Coupling | 2026-05-18 | 2026-06-09 | 17 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-18T06:09:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T10:27:09+02:00 | N | N |  | Y | Y
71691 | 410_PF_CI_tBranch45Deg_Coupling_HOST | 2026-05-18 | 2026-06-09 | 17 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-18T06:09:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T10:27:35+02:00 | N | N |  | Y | Y
71692 | 410_PF_CI_cPushinPlug_Clamp | 2026-05-19 | 2026-05-22 | 4 | handler_assign | status_resolved | START: handler→y.nguyen @ 2026-05-19T03:38:13+02:00 ¦¦ END: status→resolved @ 2026-05-22T10:52:25+02:00 | N | N |  | Y | Y
71693 | 410_PF_CI_DoubleBranch_Coupling | 2026-05-19 | 2026-05-28 | 8 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-19T03:38:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-05-28T11:31:54+02:00 | N | N |  | Y | Y
71694 | 410_PF_CI_eAccessBendLong_Clamp | 2026-05-19 | 2026-06-18 | 23 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-19T03:39:44+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T08:15:17+02:00 | N | N |  | Y | Y
71695 | 410_PF_CI_eAccessBendShort_Clamp | 2026-05-19 | 2026-06-10 | 17 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-19T03:40:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-10T04:25:49+02:00 | N | N |  | Y | Y
71696 | 410_PF_CI_eBend15Degrees_Standard_Clamp | 2026-05-19 | 2026-06-03 | 12 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-19T03:41:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-03T10:05:44+02:00 | N | N |  | Y | Y
71697 | 410_PF_CI_eBend30Degrees_Standard_Clamp | 2026-05-19 | 2026-05-29 | 9 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-19T03:41:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-05-29T06:06:13+02:00 | N | N |  | Y | Y
71698 | 410_PF_CI_eBend68Degree_Clamp | 2026-05-19 | 2026-06-03 | 12 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-19T03:42:42+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-03T10:21:04+02:00 | N | N |  | Y | Y
71699 | 410_PF_CI_eBend88Degree_SpigotAndClamp | 2026-05-19 | 2026-05-28 | 8 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-19T03:43:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-05-28T10:21:21+02:00 | N | N |  | Y | Y
71700 | 410_PF_CI_eBend88Deg_Clamp | 2026-05-19 | 2026-05-29 | 9 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-19T03:43:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-05-29T04:06:12+02:00 | N | N |  | Y | Y
71701 | 410_PF_CI_eBendWC_Clamp_Standard | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved | START: handler→k.mai @ 2026-05-19T03:44:38+02:00 ¦¦ END: status→resolved @ 2026-05-25T09:36:41+02:00 | N | N |  | Y | Y
71702 | 410_PF_CI_eBend_Clamp | 2026-05-19 | 2026-06-02 | 11 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-19T03:45:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-02T09:48:37+02:00 | N | N |  | Y | Y
71703 | 410_PF_CI_eBend_Coupling | 2026-05-19 | 2026-06-01 | 10 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-19T03:46:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-01T08:33:48+02:00 | N | N |  | Y | Y
71704 | 410_PF_CI_eBend_Coupling_HOST | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-05-19T03:47:36+02:00 ¦¦ END: status→resolved @ 2026-05-25T08:47:15+02:00 | N | N |  | Y | Y
71705 | 410_PF_CI_eConectionBend_Clamp | 2026-05-19 | 2026-05-22 | 4 | handler_assign | status_resolved | START: handler→t.luu @ 2026-05-19T03:48:25+02:00 ¦¦ END: status→resolved @ 2026-05-22T06:38:55+02:00 | N | N |  | Y | Y
71706 | 410_PF_CI_eDoubleBend45Deg_Coupling_HOST | 2026-05-21 | 2026-05-29 | 7 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-21T04:02:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-05-29T03:56:17+02:00 | N | N |  | Y | Y
71709 | RLT_LPH3_5_8_Sample Schematic_Multiple Scales | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-05-14T08:28:22+02:00 ¦¦ END: status→resolved @ 2026-05-18T11:49:03+02:00 | N | N |  | Y | N
71711 | Revise the RFA library for the SPR system. | 2026-05-14 |  |  | handler_assign | none | START: handler→s.duong @ 2026-05-14T09:33:28+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
71712 | Revise the RFA library for the MED system. | 2026-05-14 |  |  | handler_assign | none | START: handler→s.duong @ 2026-05-14T09:33:14+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
71713 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC12kg | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | START: handler→n.nguyen @ 2026-05-14T09:44:12+02:00 ¦¦ END: status→resolved @ 2026-05-18T10:27:55+02:00 | N | N |  | Y | N
71714 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC1kg | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | START: handler→n.dinh @ 2026-05-14T09:45:25+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T05:23:35+02:00 | N | N |  | Y | Y
71715 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC3kg | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | START: handler→t.trinh @ 2026-05-14T09:46:19+02:00 ¦¦ END: status→resolved @ 2026-05-18T10:23:43+02:00 | N | N |  | Y | N
71716 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC6kg | 2026-05-14 | 2026-06-29 | 33 | handler_assign | confirm_note:stored_full | START: handler→tt.bui @ 2026-05-14T09:46:54+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-06-29T09:20:47+02:00 | N | N |  | Y | Y
71717 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC14kg | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | START: handler→u.nguyen @ 2026-05-14T09:47:42+02:00 ¦¦ END: status→resolved @ 2026-05-18T10:52:39+02:00 | N | N |  | Y | N
71718 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC4d5kg | 2026-05-14 | 2026-05-25 | 8 | handler_assign | status_resolved | START: handler→t.huynh @ 2026-05-14T09:48:26+02:00 ¦¦ END: status→resolved @ 2026-05-25T11:22:35+02:00 | N | N |  | Y | N
71719 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC8kg | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | START: handler→tu.nguyen @ 2026-05-14T09:49:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:05:23+02:00 | N | N |  | Y | Y
71720 | MEP_Revise 474_ME_Cabinet_ExtinguishingWaterSupply | 2026-05-14 | 2026-05-19 | 4 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:03:32+02:00 ¦¦ END: status→resolved @ 2026-05-19T10:54:29+02:00 | N | N |  | Y | N
71721 | MEP_Revise 474_ME_CO2_ControlBox | 2026-05-14 | 2026-05-19 | 4 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:07:19+02:00 ¦¦ END: status→resolved @ 2026-05-19T11:01:54+02:00 | N | N |  | Y | N
71722 | MEP_Revise 474_ME_CO2_CylinderAssemblies | 2026-05-14 | 2026-05-19 | 4 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:07:54+02:00 ¦¦ END: status→resolved @ 2026-05-19T11:04:39+02:00 | N | N |  | Y | Y
71723 | MEP_Revise 474_PA_CylinderValve_CO2 | 2026-05-14 | 2026-08-19 | 70 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:10:51+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T04:44:39+02:00 | N | N |  | Y | Y
71724 | MEP_Revise 474_PA_DelugeValve | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:11:30+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T12:43:36+02:00 | N | N |  | Y | Y
71725 | MEP_Revise 474_ME_SlaveCylinderWithTopOfValve_CO2 | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:12:20+02:00 ¦¦ END: status→resolved @ 2026-05-27T10:25:53+02:00 | N | N |  | Y | N
71726 | MEP_Revise 474_ME_EndSuctionFirePump | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:14:36+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-10T03:15:44+02:00 | N | N |  | Y | Y
71727 | MEP_Revise 474_ME_FE_AutomaticDryPowerCeiling_HFC17_NoSystem | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:16:02+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-10T05:24:57+02:00 | N | N |  | Y | Y
71728 | MEP_Revise 474_ME_FireExtinguisherPortable_Powder | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:17:25+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-06-25T11:27:06+02:00 | N | N |  | Y | Y
71729 | MEP_Revise 474_ME_FireHoseReel_WallSurface | 2026-05-14 | 2026-07-13 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:18:19+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-13T06:35:42+02:00 | N | N |  | Y | Y
71731 | MEP_Revise 474_PA_ZoneControlRiserModule_Residential | 2026-05-14 | 2026-08-21 | 72 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:19:34+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-21T10:28:08+02:00 | N | N |  | Y | Y
71732 | MEP_Revise 474_ME_FirePump_Horizontal_SplitCase | 2026-05-14 | 2026-08-18 | 69 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:21:10+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T08:25:51+02:00 | N | N |  | Y | Y
71733 | MEP_Revise 474_ME_FireValveBox | 2026-05-14 | 2026-08-12 | 65 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:24:45+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T08:59:09+02:00 | N | N |  | Y | Y
71734 | MEP_Revise 474_ME_FM200_CylinderTank | 2026-05-14 | 2026-08-19 | 70 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:25:47+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T09:12:38+02:00 | N | N |  | Y | N
71735 | MEP_Revise 474_ME_FoamBladderTank_HorizontalType | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:27:27+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T11:14:05+02:00 | N | N |  | Y | Y
71736 | MEP_Revise 474_ME_FoamBladderTank_VerticalType | 2026-05-14 | 2026-05-22 | 7 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:27:59+02:00 ¦¦ END: status→resolved @ 2026-05-22T09:56:49+02:00 | N | N |  | Y | N
71737 | MEP_Revise 474_ME_FoamPump | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:28:38+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T05:14:45+02:00 | N | N |  | Y | Y
71738 | MEP_Revise 474_ME_HorizontalPresssureTank | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:29:57+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T05:14:48+02:00 | N | N |  | Y | Y
71739 | MEP_Revise 474_ME_JockeyPump | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:30:40+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T11:11:45+02:00 | N | N |  | Y | Y
71740 | MEP_Revise 474_ME_DieselPump_FloorSurface_AURORA481 | 2026-05-14 | 2026-06-12 | 22 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:31:04+02:00 ¦¦ END: status→resolved @ 2026-06-12T10:48:42+02:00 | N | N |  | Y | N
71741 | MEP_Revise 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T10:32:07+02:00 ¦¦ END: s.duong: Ticket is the same with ticket #0071762 Therefore, this ticket will be closed. Thank you. @ 2026-08-13T12:30:02+02:00 | N | N |  | Y | N
71742 | MEP_Revise 474_ME_NitrogenPilotCylinderWithTopValve | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:34:33+02:00 ¦¦ END: status→resolved @ 2026-05-27T11:03:47+02:00 | N | N |  | Y | N
71743 | MEP_Revise 474_ME_CylinderTank_FM200 | 2026-05-14 | 2026-07-09 | 41 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:36:25+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-09T03:57:53+02:00 | N | N |  | Y | Y
71744 | MEP_Revise 474_ME_ProtectiveCabinetWithVentilationValve | 2026-05-14 | 2026-06-11 | 21 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:37:00+02:00 ¦¦ END: status→resolved @ 2026-06-11T04:56:48+02:00 | N | N |  | Y | N
71745 | MEP_Revise 474_ME_ReceiverTank | 2026-05-14 | 2026-06-11 | 21 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:37:57+02:00 ¦¦ END: status→resolved @ 2026-06-11T06:35:28+02:00 | N | N |  | Y | N
71746 | MEP_Revise 474_ME_SolventTank | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:40:42+02:00 ¦¦ END: status→resolved @ 2026-05-27T04:11:31+02:00 | N | N |  | Y | N
71747 | MEP_Revise 474_ME_VerticalFirePump | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T10:41:22+02:00 ¦¦ END: status→resolved @ 2026-05-27T04:16:20+02:00 | N | N |  | Y | N
71748 | MEP_Revise 474_PA_AirMaintenanceCompressorAssembly | 2026-05-14 | 2026-07-09 | 41 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:41:55+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-09T05:39:19+02:00 | N | N |  | Y | Y
71749 | MEP_Revise 474_ME_FireExtinguisherCarbonDioxide | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:42:23+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-06-25T05:37:44+02:00 | N | N |  | Y | Y
71750 | MEP_Revise 474_PA_AirVentValve | 2026-05-14 | 2026-07-01 | 35 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:43:17+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-01T06:34:38+02:00 | N | N |  | Y | Y
71751 | MEP_Revise 474_ME_FireExtinguisherPortable_Foam | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:44:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-06-25T04:46:06+02:00 | N | N |  | Y | Y
71752 | MEP_Revise 474_PA_AlarmPressureSwitch | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:45:30+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-10T05:24:22+02:00 | N | N |  | Y | Y
71753 | MEP_Revise 474_ME_JunctionBox_VESDA | 2026-05-14 | 2026-10-01 | 101 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:46:41+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T06:31:06+02:00 | N | N |  | Y | N
71754 | MEP_Revise 474_PA_AlarmTestModulePressureReliefValve_ThreadEnd | 2026-05-14 | 2026-08-20 | 71 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:47:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-20T03:06:34+02:00 | N | N |  | Y | Y
71755 | MEP_Revise 474_PA_AlarmTestModuleThreadEnd | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:47:55+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T04:21:45+02:00 | N | N |  | Y | Y
71756 | MEP_Revise 474_PA_AngleHoseValve | 2026-05-14 | 2026-07-02 | 36 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:48:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-02T03:47:26+02:00 | N | N |  | Y | Y
71757 | MEP_Revise 474_PA_AutoConvertAssembly | 2026-05-14 | 2026-08-20 | 71 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:49:25+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-20T03:05:58+02:00 | N | N |  | Y | Y
71758 | MEP_Revise 474_PA_AutoDrainValve_FloatType_Threaded | 2026-05-14 | 2026-07-27 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:51:44+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T05:13:05+02:00 | N | N |  | Y | Y
71759 | MEP_Revise 474_SP_GE_WindowOpenNozzle | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T10:52:48+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T05:39:10+02:00 | N | N |  | Y | Y
71760 | MEP_Revise 474_PA_ButterflyValveSupervisedOpen | 2026-05-14 | 2026-08-04 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:00:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-04T03:37:30+02:00 | N | N |  | Y | Y
71761 | MEP_Revise 474_ME_AirSamplingPump | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:05:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-16T06:01:10+02:00 | N | N |  | Y | Y
71762 | MEP_Revise 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:06:34+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:30:07+02:00 | N | N |  | Y | Y
71763 | MEP_Revise 474_ME_Cabinet_FlushMountedWall | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:08:24+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:27:41+02:00 | N | N |  | Y | Y
71764 | MEP_Revise 474_ME_Compressor | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:09:03+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:29:53+02:00 | N | N |  | Y | Y
71765 | MEP_Revise 474_ME_ControlBox_CO2 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:09:31+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T04:09:30+02:00 | N | N |  | Y | Y
71766 | MEP_Revise 474_ME_CylinderWithCylinderValve_CO2 | 2026-05-14 | 2026-07-23 | 51 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:10:16+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-23T05:52:38+02:00 | N | N |  | Y | N
71767 | MEP_Revise 474_ME_MasterCylinderWithTopValveOfActuator_CO2 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:11:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T11:11:49+02:00 | N | N |  | Y | Y
71768 | MEP_Revise 474_PA_DiaphragmValves | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:14:58+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T12:43:24+02:00 | N | N |  | Y | Y
71769 | MEP_Revise 474_PA_DuplexPressureGauges | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:15:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T05:50:10+02:00 | N | N |  | Y | Y
71770 | MEP_Revise 474_PA_3WayBronzeGlobeValve | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:17:17+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:29:40+02:00 | N | N |  | Y | Y
71771 | MEP_Revise 474_PA_AerationVentilationValve | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:19:30+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:29:28+02:00 | N | N |  | Y | Y
71772 | MEP_Revise 474_PA_FlexibleMetalHose | 2026-05-14 | 2026-07-27 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:20:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T05:44:16+02:00 | N | N |  | Y | Y
71773 | MEP_Revise 474_PA_FlowTestMeter_Flange | 2026-05-14 | 2026-08-21 | 72 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:23:30+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-21T06:22:26+02:00 | N | N |  | Y | Y
71774 | MEP_Revise 474_PA_Flushing_Connection | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:24:40+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T09:28:53+02:00 | N | N |  | Y | Y
71777 | MEP_Revise 474_PA_FM200_ActuatorBox | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T11:42:24+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T09:28:04+02:00 | N | N |  | Y | Y
71778 | MEP_Revise 474_PA_FM200_DischargePressureSwitch | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T12:00:23+02:00 ¦¦ END: s.duong: Ticket is the same with ticket #0072266 Therefore, this ticket will be closed. Thank you. @ 2026-07-16T10:38:56+02:00 | N | N |  | Y | N
71779 | MEP_Revise 474_PA_FM200_Manifold_CheckValve | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T12:01:10+02:00 ¦¦ END: s.duong: Ticket is the same with ticket #0072274 Therefore, this ticket will be closed. Thank you. @ 2026-07-16T10:42:58+02:00 | N | N |  | Y | N
71780 | MEP_Revise 474_PA_FM200_ManualPneumaticActuator | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T12:01:48+02:00 ¦¦ END: s.duong: Ticket is the same with ticket #0072276 Therefore, this ticket will be closed. Thank you. @ 2026-07-16T10:45:05+02:00 | N | N |  | Y | N
71781 | MEP_Revise 474_PA_FM200_SectorValve_Flanged | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:03:36+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T10:00:45+02:00 | N | N |  | Y | Y
71782 | MEP_Revise 474_PA_FM200_SectorValve_Threaded | 2026-05-14 | 2026-08-14 | 67 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:03:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T03:10:16+02:00 | N | N |  | Y | Y
71783 | MEP_Revise 474_PA_FM200_SolenoidValve | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:06:54+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-10T05:41:27+02:00 | N | N |  | Y | Y
71784 | MEP_Revise 474_PA_Foam_AutomaticConcentrateControlValve | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T12:08:42+02:00 ¦¦ END: s.duong: Ticket is the same with ticket #0072248 Therefore, this ticket will be closed. Thank you. @ 2026-07-16T10:45:58+02:00 | N | N |  | Y | N
71785 | MEP_Revise 474_PA_Foam_AutomaticControlValve_Flanged | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:38:48+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-10T05:22:22+02:00 | N | N |  | Y | Y
71786 | MEP_Revise 474_PA_Foam_DuctileIron_DelugeValve_AngleStype | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:40:49+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-10T05:40:51+02:00 | N | N |  | Y | Y
71787 | MEP_Revise 474_PA_Foam_InLineBalancedPressureProportioners | 2026-05-14 | 2026-08-03 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:41:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T04:18:51+02:00 | N | N |  | Y | Y
71788 | MEP_Revise 474_PA_FoamLineProportioner | 2026-05-14 | 2026-06-24 | 30 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T12:41:55+02:00 ¦¦ END: status→resolved @ 2026-06-24T10:42:16+02:00 | N | N |  | Y | N
71789 | MEP_Revise 474_PA_InlineCheckValve_CO2 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:42:47+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T08:27:51+02:00 | N | N |  | Y | Y
71790 | MEP_Revise 474_PA_LevelControlValves_Flange | 2026-05-14 | 2026-09-30 | 100 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T12:43:52+02:00 ¦¦ END: s.duong: This ticket will be closed. Thank you. @ 2026-09-30T06:23:26+02:00 | N | N |  | Y | N
71791 | MEP_Revise 474_PA_ManifoldCheckValve_Grooved | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:44:52+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T10:06:49+02:00 | N | N |  | Y | Y
71792 | MEP_Revise 474_PA_ManifoldCheckValve_Threaded | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:45:16+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T03:39:34+02:00 | N | N |  | Y | Y
71793 | MEP_Revise 474_PA_MeasuringOrificeAssembly | 2026-05-14 | 2026-07-17 | 47 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T12:51:01+02:00 ¦¦ END: s.duong: The family is not exist on 474_SPR_Confirmed. Therefore, this ticket will be closed. Thank you. @ 2026-07-17T04:03:48+02:00 | N | N |  | Y | N
71794 | MEP_Revise 474_PA_NRSOS&YGateValves_GrooveAndGroove | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:51:31+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T11:22:48+02:00 | N | N |  | Y | Y
71795 | MEP_Revise 474_PA_NRSOS&YGateValvesGrooveandGroove | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-14T12:53:12+02:00 ¦¦ END: s.duong: As discussed, this family and family 474_PA_NRSOS&YGateValves_GrooveandGroove are the same. Therefor @ 2026-06-25T05:56:06+02:00 | N | N |  | Y | N
71796 | MEP_Revise 474_PA_OS&YGateValves_GrooveAndGroove | 2026-05-14 | 2026-07-08 | 40 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:53:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-08T04:57:34+02:00 | N | N |  | Y | Y
71797 | MEP_Revise 474_PA_PressureGauge_AnalogueType | 2026-05-14 | 2026-06-24 | 30 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T12:55:10+02:00 ¦¦ END: status→resolved @ 2026-06-24T07:08:47+02:00 | N | N |  | Y | N
71798 | MEP_Revise 474_PA_PressureReducingControlValveThread | 2026-05-14 | 2026-08-14 | 67 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-14T12:56:26+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T05:50:57+02:00 | N | N |  | Y | Y
71799 | MEP_Revise 474_PA_PressureReducingValve_Flanged | 2026-05-14 | 2026-06-19 | 27 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-14T12:56:41+02:00 ¦¦ END: status→resolved @ 2026-06-19T10:04:13+02:00 | N | N |  | Y | N
71805 | 410_PF_CI_xDoubleBend88Degrees_Standard_Clamp | 2026-05-21 | 2026-05-26 | 4 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-05-21T04:02:48+02:00 ¦¦ END: status→resolved @ 2026-05-26T11:16:03+02:00 | N | N |  | Y | Y
71806 | 410_PF_CI_eDoubleBend88Deg_Coupling | 2026-05-21 | 2026-06-05 | 12 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-21T04:04:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-05T08:44:07+02:00 | N | N |  | Y | Y
71807 | 410_PF_CI_eOffsetBend130_Clamp | 2026-05-22 | 2026-06-04 | 10 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-22T06:30:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-04T07:23:45+02:00 | N | N |  | Y | Y
71808 | 410_PF_CI_eOffsetBend200_Clamp | 2026-05-22 | 2026-05-25 | 2 | handler_assign | status_resolved | START: handler→y.nguyen @ 2026-05-22T08:30:48+02:00 ¦¦ END: status→resolved @ 2026-05-25T10:48:51+02:00 | N | N |  | Y | Y
71820 | 410_PF_CI_eOffsetBend65_Clamp | 2026-05-22 | 2026-06-01 | 7 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-22T08:31:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-01T10:13:54+02:00 | N | N |  | Y | Y
71821 | 410_PF_CI_ePlainTrap_Clamp | 2026-05-22 | 2026-06-01 | 7 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-22T08:32:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-01T06:21:15+02:00 | N | N |  | Y | Y
71822 | 410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp | 2026-05-22 | 2026-06-05 | 11 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-22T08:33:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-05T09:49:07+02:00 | N | N |  | Y | Y
71823 | 410_PF_CI_eRestBend88_Clamp | 2026-05-22 | 2026-05-26 | 3 | handler_assign | status_resolved | START: handler→t.luu @ 2026-05-22T08:34:08+02:00 ¦¦ END: status→resolved @ 2026-05-26T06:05:25+02:00 | N | N |  | Y | Y
71824 | 410_PF_CI_eVentilationBend88Axial_Clamp | 2026-05-22 | 2026-05-29 | 6 | handler_assign | status_resolved | START: handler→n.vo @ 2026-05-22T08:35:10+02:00 ¦¦ END: status→resolved @ 2026-05-29T04:36:03+02:00 | N | N |  | Y | Y
71825 | 410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp | 2026-05-22 | 2026-06-18 | 20 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-22T08:36:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T03:51:26+02:00 | N | N |  | Y | Y
71826 | 410_PF_CI_eGutterAngleUniversal | 2026-05-22 | 2026-06-10 | 14 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-22T10:12:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-10T10:51:48+02:00 | N | N |  | Y | Y
71828 | 410_PF_CI_cGutterCap_ExternalStopEnd | 2026-05-25 | 2026-06-17 | 18 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-25T02:49:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-17T11:13:17+02:00 | N | N |  | Y | Y
71830 | 410_PF_CI_cGutterCap_InternalStopEnd | 2026-05-25 | 2026-06-17 | 18 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-25T03:11:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-17T11:09:21+02:00 | N | N |  | Y | Y
71831 | 410_PF_CI_eGutterElbow_ExternalDropEndOutlet | 2026-05-25 | 2026-06-19 | 20 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-25T03:12:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T09:19:54+02:00 | N | N |  | Y | Y
71832 | 410_PF_CI_eGutterElbow_InternalDropEndOutlet | 2026-05-25 | 2026-06-18 | 19 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-25T03:13:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T10:36:11+02:00 | N | N |  | Y | Y
71833 | 410_PF_CI_GutterHalfRound | 2026-05-25 | 2026-06-18 | 19 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-25T03:14:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T03:43:14+02:00 | N | N |  | Y | Y
71834 | 410_PF_CI_tGutterTee_RunningOutlet | 2026-05-26 | 2026-08-13 | 58 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-26T09:14:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T11:11:53+02:00 | N | N |  | Y | Y
71842 | 410_PF_CI_GutterUnionConnector | 2026-05-26 | 2026-06-19 | 19 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-26T09:16:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:46:09+02:00 | N | N |  | Y | Y
71843 | 410_PF_CI_mShortPipeRectangularAccessDoor_Standard | 2026-05-26 | 2026-06-09 | 11 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-26T09:20:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T05:34:30+02:00 | N | N |  | Y | Y
71846 | 410_PF_CI_mVerticalTrap_Standard | 2026-05-26 | 2026-06-09 | 11 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-26T09:25:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T04:43:38+02:00 | N | N |  | Y | Y
71847 | 410_PF_CI_rEccentricReducer_WithoutCoupling | 2026-05-26 | 2026-08-12 | 57 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-26T09:33:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:53:18+02:00 | N | N |  | Y | Y
71850 | 410_PF_CI_uDownPipeBracket_Coupling | 2026-05-15 | 2026-06-17 | 24 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-15T11:24:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-17T05:21:09+02:00 | N | N |  | Y | Y
71851 | ELT_LES_LPH8_Sample Layout_Multiple Scales | 2026-05-18 | 2026-05-21 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-18T02:53:18+02:00 ¦¦ END: status→resolved @ 2026-05-21T11:57:23+02:00 | N | N |  | Y | N
71852 | ELT_Cable tray_LPH5_Sample Layout_Multiple Scales | 2026-05-18 | 2026-05-26 | 7 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-18T02:58:25+02:00 ¦¦ END: status→resolved @ 2026-05-26T10:34:48+02:00 | N | N |  | Y | N
71853 | ELT_Cable tray_LPH8_Sample Layout_Multiple Scales | 2026-05-18 | 2026-05-21 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-18T03:02:13+02:00 ¦¦ END: status→resolved @ 2026-05-21T11:05:24+02:00 | N | N |  | Y | N
71854 | ELT_LPH5_Sample Schematic | 2026-05-18 | 2026-05-29 | 10 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-18T03:24:37+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:33:48+02:00 | N | N |  | Y | N
71855 | ELT_LPH8_Sample Schematic | 2026-05-18 | 2026-05-26 | 7 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-18T03:27:25+02:00 ¦¦ END: status→resolved @ 2026-05-26T11:17:18+02:00 | N | N |  | Y | N
71856 | MSR_LPH5_Sample Schematic | 2026-05-18 | 2026-05-29 | 10 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-18T03:29:24+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:29:56+02:00 | N | N |  | Y | N
71857 | MSR_LPH8_Sample Schematic | 2026-05-18 | 2026-05-29 | 10 | handler_assign | status_resolved | START: handler→h.pham @ 2026-05-18T03:30:17+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:51:32+02:00 | N | N |  | Y | N
71858 | LPH3_SAN Discipline Output Checklist Definition | 2026-05-18 | 2026-09-22 | 92 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-05-18T03:54:44+02:00 ¦¦ END: status→resolved @ 2026-09-22T05:31:51+02:00 | N | N |  | Y | N
71860 | 430_DF_GS_tTee_Spigot_Round.rfa | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | START: handler→l.truong @ 2026-05-18T05:32:08+02:00 ¦¦ END: status→resolved @ 2026-05-20T10:47:18+02:00 | N | N |  | Y | Y
71861 | 430_DF_GS_tTStuck_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:33:35+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T10:46:50+02:00 | N | N |  | Y | Y
71862 | 430_DF_GS_uCoupling_Spigot_Round.rfa | 2026-05-18 | 2026-06-05 | 15 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:36:50+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-05T09:23:35+02:00 | N | N |  | Y | Y
71863 | 430_DF_GS_uUnion_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:38:34+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T03:49:16+02:00 | N | N |  | Y | Y
71864 | 430_DF_GS_wHosenStuck_Flanged.rfa | 2026-05-18 | 2026-06-19 | 25 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:39:08+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T07:13:25+02:00 | N | N |  | Y | Y
71865 | 430_DF_GS_xKreuzstuck_Flanged.rfa | 2026-05-18 | 2026-06-19 | 25 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:39:49+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:36:28+02:00 | N | N |  | Y | Y
71866 | 430_DF_GS_sUbergangsstutzen_Flanged.rfa | 2026-05-18 | 2026-09-18 | 90 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:40:17+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:08:55+02:00 | N | N |  | Y | Y
71867 | 430_DF_GS_cBoden_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:40:56+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T08:15:35+02:00 | N | N |  | Y | Y
71868 | 430_DF_GS_cCapEnd_Spigot_Round.rfa | 2026-05-18 | 2026-06-02 | 12 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:41:22+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-02T05:55:21+02:00 | N | N |  | Y | Y
71869 | 430_DF_GS_eBogen_Flanged.rfa | 2026-05-18 | 2026-09-18 | 90 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:41:40+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:08:58+02:00 | N | N |  | Y | Y
71870 | 430_DF_GS_eEckbogen_Flanged.rfa | 2026-05-18 | 2026-07-09 | 39 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:43:27+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-09T06:08:30+02:00 | N | N |  | Y | Y
71871 | 430_DF_GS_eRoundElbow_Spigot.rfa | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | START: handler→l.truong @ 2026-05-18T05:44:50+02:00 ¦¦ END: status→resolved @ 2026-05-20T09:12:09+02:00 | N | N |  | Y | Y
71872 | 430_DF_GS_eTransitionElbow_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:47:26+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T08:14:55+02:00 | N | N |  | Y | Y
71873 | 430_DF_GS_rEtage_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:48:14+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T10:09:36+02:00 | N | N |  | Y | Y
71874 | 430_DF_GS_rReducer_Spigot_Round.rfa | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | START: handler→l.truong @ 2026-05-18T05:49:26+02:00 ¦¦ END: status→resolved @ 2026-05-20T09:30:29+02:00 | N | N |  | Y | Y
71875 | 430_DF_GS_rUbergang_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:50:44+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T10:10:13+02:00 | N | N |  | Y | Y
71876 | 430_DF_GS_rUbergangRechteckRund_Flanged_SlipJoint.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:51:36+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-18T10:52:14+02:00 | N | N |  | Y | Y
71877 | 430_DF_GS_sRoundTaps_Spigot.rfa | 2026-05-18 | 2026-06-04 | 14 | handler_assign | confirm_note:stored_full | START: handler→l.truong @ 2026-05-18T05:52:40+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-04T11:02:32+02:00 | N | N |  | Y | Y
71899 | Annotation_Platform_Deploy the feature | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-05-19T06:55:54+02:00 ¦¦ END: status→resolved @ 2026-05-25T04:20:36+02:00 | N | N |  | Y | N
71902 | Annotation_General_Integrate the TIDP to MIDP | 2026-05-19 | 2026-05-20 | 2 | handler_assign | status_resolved | START: handler→dahn.nguyen @ 2026-05-19T08:33:52+02:00 ¦¦ END: status→resolved @ 2026-05-20T11:26:40+02:00 | N | N |  | Y | N
71918 | 410_PF_CI_rEccentricReducer_Coupling_HOST | 2026-05-26 | 2026-06-08 | 10 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-26T09:36:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-08T10:05:51+02:00 | N | N |  | Y | Y
71919 | 410_PF_CI_rReducingEccentric_Clamp | 2026-05-26 | 2026-05-27 | 2 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-05-26T09:39:49+02:00 ¦¦ END: status→resolved @ 2026-05-27T10:53:56+02:00 | N | N |  | Y | Y
71920 | 410_PF_CI_tBranch45_Clamp | 2026-05-26 | 2026-06-05 | 9 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-26T09:41:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-05T03:21:44+02:00 | N | N |  | Y | Y
71921 | 410_PF_CI_tBranch70_Clamp | 2026-05-26 | 2026-06-04 | 8 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-26T09:45:04+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-04T05:40:30+02:00 | N | N |  | Y | Y
71922 | 410_PF_CI_tBranch88Deg_Coupling | 2026-05-26 | 2026-05-29 | 4 | handler_assign | status_resolved | START: handler→t.luu @ 2026-05-26T09:46:25+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:00:36+02:00 | N | N |  | Y | Y
71923 | 410_PF_CI_tBranch88Deg_Coupling_HOST | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-26T09:48:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T04:39:17+02:00 | N | N |  | Y | Y
71924 | 410_PF_CI_tBranch88Long_Spigot_Clamp | 2026-05-28 | 2026-06-04 | 6 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-28T09:52:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-04T03:58:24+02:00 | N | N |  | Y | Y
71925 | 410_PF_CI_tBranch88_Clamp | 2026-05-28 | 2026-05-29 | 2 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-05-28T09:53:22+02:00 ¦¦ END: status→resolved @ 2026-05-29T11:08:39+02:00 | N | N |  | Y | Y
71926 | 410_PF_CI_tCombinationBranch90_Standard | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-28T09:53:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-10T08:51:04+02:00 | N | N |  | Y | Y
71927 | 410_PF_CI_tCornerBranch88_Clamp | 2026-05-29 | 2026-07-01 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T02:48:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T10:11:27+02:00 | N | N |  | Y | Y
71928 | 410_PF_CI_tSweptEntryBranch88_Spigot_Clamp | 2026-05-29 | 2026-06-01 | 2 | handler_assign | status_resolved | START: handler→c.le @ 2026-05-29T02:50:13+02:00 ¦¦ END: status→resolved @ 2026-06-01T10:35:21+02:00 | N | N |  | Y | Y
71929 | 410_PF_CI_uShortPipeRoundAccessDoor_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-29T02:52:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T09:35:42+02:00 | N | N |  | Y | Y
71930 | 410_PF_CI_uTrapHorizontal_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-29T02:53:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T09:36:40+02:00 | N | N |  | Y | Y
71931 | 410_PF_CI_xDoubleBranch45_Clamp | 2026-05-29 | 2026-06-02 | 3 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T02:53:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-02T05:54:03+02:00 | N | N |  | Y | Y
71988 | 410_PF_CI_xDoubleBranch70Deg_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T02:54:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T07:35:57+02:00 | N | N |  | Y | Y
71989 | 410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-29T02:55:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-23T07:29:50+02:00 | N | N |  | Y | Y
71990 | 410_PF_CS_cEndCaps_Welded | 2026-05-29 | 2026-06-01 | 2 | handler_assign | status_resolved | START: handler→y.nguyen @ 2026-05-29T02:55:55+02:00 ¦¦ END: status→resolved @ 2026-06-01T10:39:45+02:00 | N | N |  | Y | Y
71991 | 410_PF_CS_eLongRadiusElbows_Welded | 2026-06-17 | 2026-08-25 | 50 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-17T06:57:10+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T07:22:50+02:00 | N | N |  | Y | Y
71992 | 410_PF_CS_eLongRadiusReturnBends_Welded | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T02:56:50+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-15T03:30:03+02:00 | N | N |  | Y | Y
71994 | 410_PF_CS_eRadiusElbows_Welded | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-29T02:57:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-23T10:13:47+02:00 | N | N |  | Y | Y
71996 | 410_PF_CS_fPlaneFlange_Flanged | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-29T02:57:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:44:37+02:00 | N | N |  | Y | Y
71997 | 410_PF_CS_rConcentricReducers_Welded | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T02:58:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-29T07:29:19+02:00 | N | N |  | Y | Y
71998 | 410_PF_CS_rConnector_MapressAndFemaleThread | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T02:59:42+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-29T07:28:20+02:00 | N | N |  | Y | Y
71999 | 410_PF_CS_uConnector_MapressAndFemaleThread | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T03:00:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T03:36:41+02:00 | N | N |  | Y | Y
72000 | 410_PF_DI_cBellmouth_Flanged | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T03:01:17+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:37:22+02:00 | N | N |  | Y | Y
72001 | 410_PF_DI_cBlind_Flanged | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T03:02:05+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T06:43:42+02:00 | N | N |  | Y | Y
72002 | 410_PF_DI_cCap_KType | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T03:03:10+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:33:59+02:00 | N | N |  | Y | Y
72003 | 410_PF_DI_cPlug_TType | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T03:03:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T08:23:51+02:00 | N | N |  | Y | Y
72005 | 410_PF_DI_eBend_Flange | 2026-05-29 | 2026-06-17 | 14 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-29T03:05:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-17T10:57:01+02:00 | N | N |  | Y | Y
72006 | 410_PF_DI_eBend_Socket | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T03:05:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T07:32:46+02:00 | N | N |  | Y | Y
72007 | 410_PF_DI_eDuckfoodBend90Deg_Flanged | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T03:05:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T07:36:26+02:00 | N | N |  | Y | Y
72008 | 410_PF_DI_fFlange_RFType | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T03:06:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-29T07:28:48+02:00 | N | N |  | Y | Y
72009 | 410_PF_DI_rFlangedCover | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-29T03:07:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T09:00:41+02:00 | N | N |  | Y | Y
72010 | 410_PF_DI_uConnector_FlangedAndSocket | 2026-05-29 | 2026-06-05 | 6 | handler_assign | status_resolved | START: handler→t.luu @ 2026-05-29T03:08:19+02:00 ¦¦ END: status→resolved @ 2026-06-05T09:11:45+02:00 | N | N |  | Y | N
72011 | 410_PF_DI_fFlange_Spigot | 2026-05-29 | 2026-06-05 | 6 | handler_assign | status_resolved | START: handler→t.luu @ 2026-05-29T03:09:00+02:00 ¦¦ END: status→resolved @ 2026-06-05T09:08:08+02:00 | N | N |  | Y | N
72012 | 410_PF_DI_rTapper_Flanged | 2026-05-29 | 2026-07-28 | 43 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-29T03:09:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T07:22:26+02:00 | N | N |  | Y | Y
72013 | 410_PF_DI_rTapper_Socket | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T03:10:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T03:10:43+02:00 | N | N |  | Y | Y
72014 | 410_PF_DI_tLevelInvertTee_Flanged | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-29T03:11:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T09:35:06+02:00 | N | N |  | Y | Y
72015 | 410_PF_DI_tTee_SocketAndFlangedBranch | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T03:13:05+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T11:57:18+02:00 | N | N |  | Y | Y
72016 | 410_PF_DI_tTee_SocketAndLevelInvertFlangedBranch | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T03:13:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T07:34:09+02:00 | N | N |  | Y | Y
72017 | 410_PF_DI_tTee_Flanged | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T03:13:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T06:20:00+02:00 | N | N |  | Y | Y
72018 | 410_PF_DI_tTee_Socket | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-29T03:17:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T07:32:22+02:00 | N | N |  | Y | Y
72019 | 410_PF_DI_uAdaptorRestrained_Flanged | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-01T04:15:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T11:55:21+02:00 | N | N |  | Y | Y
72020 | 410_PF_DI_uFlangeAdaptor | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-29T03:20:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T05:50:46+02:00 | N | N |  | Y | Y
72021 | 410_PF_DI_uUnionFlange_RFType | 2026-05-29 | 2026-07-07 | 28 | handler_assign | confirm_note:will_be_closed | START: handler→k.mai @ 2026-05-29T03:21:00+02:00 ¦¦ END: tv.huynh: @hu.dam @k.mai @kd.doan This family is duplicated with the RFA in ticket #0072008. The related infor @ 2026-07-07T08:58:21+02:00 | N | N |  | Y | N
72022 | 410_PF_DI_uUnion_Socket | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T03:24:17+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T06:00:52+02:00 | N | N |  | Y | Y
72023 | 410_PF_DI_tDoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T03:24:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:54:03+02:00 | N | N |  | Y | Y
72024 | 410_PF_EPDM_mKonfixConnector_PushOnJoint | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T03:26:17+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T05:23:02+02:00 | N | N |  | Y | Y
72025 | 410_PF_eSweptBendLong_Medium_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-29T03:36:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T04:23:23+02:00 | N | N |  | Y | Y
72032 | 410_PF_fHDPE_LooseFlange | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-17T05:41:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T08:33:19+02:00 | N | N |  | Y | Y
72035 | 410_PF_GS_cFrogFlap_Socket_GMX | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-29T03:39:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T11:29:08+02:00 | N | N |  | Y | Y
72037 | 410_SE_FireCollar_Horizontal | 2026-05-29 | 2026-09-15 | 78 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-29T03:37:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T11:11:06+02:00 | N | N |  | Y | Y
72038 | Revise the RFA library for the RLT system | 2026-05-22 |  |  | handler_assign | none | START: handler→l.truong @ 2026-05-22T08:39:35+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
72039 | 410_SE_FireCollar_Vertical | 2026-05-29 | 2026-06-08 | 7 | handler_assign | status_resolved | START: handler→ttc.bui @ 2026-05-29T03:38:31+02:00 ¦¦ END: status→resolved @ 2026-06-08T08:51:22+02:00 | N | N |  | Y | N
72040 | 410_PF_GS_cSealingPlugsWithVentilationSlots_PushOnJoint | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-17T09:53:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T09:21:47+02:00 | N | N |  | Y | Y
72041 | 410_PF_GS_eAngleBend_1PushShortSocket_GMX | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T03:40:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T11:28:17+02:00 | N | N |  | Y | Y
72042 | 410_PF_GS_eBasinConnector_1PushSocket_GMX | 2026-05-29 | 2026-06-04 | 5 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-29T03:41:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-04T03:41:22+02:00 | N | N |  | Y | Y
72043 | 410_PF_GS_eBendWithCalm_1PushSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-29T03:41:42+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-06T09:33:42+02:00 | N | N |  | Y | Y
72046 | 410_PF_GS_eBend_1PushSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-29T03:42:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-06T06:08:14+02:00 | N | N |  | Y | Y
72048 | 410_PF_GS_eBend_NoSocket_GMX | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T03:42:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-23T05:35:57+02:00 | N | N |  | Y | Y
72049 | 410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX | 2026-06-17 | 2026-08-03 | 34 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T07:03:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-03T04:19:09+02:00 | N | N |  | Y | Y
72050 | 410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX | 2026-06-17 | 2026-07-08 | 16 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-17T07:04:51+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-08T10:53:54+02:00 | N | N |  | Y | Y
72051 | 410_PF_GS_eReductionAngleBend_1PushSocket_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T03:44:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-15T04:15:34+02:00 | N | N |  | Y | Y
72052 | 410_PF_GS_uGutterRound_SocketAndStandard | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T03:45:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:56:39+02:00 | N | N |  | Y | Y
72053 | 410_PF_GS_mOptimisationPart_1PushSocket | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-29T03:45:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:36:02+02:00 | N | N |  | Y | Y
72054 | 430_ME_FanCoilUnit_WithPlenumBox_ThreeConnector_Standard.rfa | 2026-05-22 | 2026-05-26 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-05-22T09:49:43+02:00 ¦¦ END: status→resolved @ 2026-05-26T09:50:34+02:00 | N | N |  | Y | N
72055 | 430_DA_AirtightLouverDamper.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-05-25T03:08:46+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-24T10:22:41+02:00 | N | N |  | Y | Y
72056 | 430_DA_CircularSilencers_CA_050.rfa | 2026-05-25 | 2026-07-10 | 35 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-05-25T03:09:32+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-10T06:26:28+02:00 | N | N |  | Y | Y
72057 | 430_DA_CircularSilencers_CA_100.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-05-25T03:10:20+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-24T09:34:27+02:00 | N | N |  | Y | Y
72058 | 430_DA_CircularSilencers_CB.rfa | 2026-05-25 | 2026-07-13 | 36 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-05-25T03:10:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-13T02:43:57+02:00 | N | N |  | Y | Y
72059 | 410_PF_GS_mSBendTrap_1PushSocket_GMX | 2026-06-17 | 2026-06-19 | 3 | handler_assign | status_resolved | START: handler→t.luu @ 2026-06-17T07:05:57+02:00 ¦¦ END: status→resolved @ 2026-06-19T11:01:57+02:00 | N | N |  | Y | N
72060 | 430_DA_CircularSilencers_CS.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-05-25T03:11:28+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-24T07:30:45+02:00 | N | N |  | Y | Y
72061 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowEN.rfa | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-05-25T03:12:30+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T05:36:53+02:00 | N | N |  | Y | Y
72062 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowENEx.rfa | 2026-05-25 | 2026-07-06 | 31 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-05-25T03:13:01+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-06T04:22:24+02:00 | N | N |  | Y | Y
72063 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRN.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-05-25T03:14:12+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-24T05:47:49+02:00 | N | N |  | Y | Y
72064 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRNEx.rfa | 2026-05-25 | 2026-07-09 | 34 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-05-25T03:14:48+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-09T10:28:32+02:00 | N | N |  | Y | Y
72065 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFL.rfa | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-05-25T03:15:59+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T06:32:45+02:00 | N | N |  | Y | Y
72066 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFC | 2026-05-25 | 2026-09-18 | 85 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-05-25T03:16:35+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T07:47:02+02:00 | N | N |  | Y | Y
72067 | 430_DA_PressureOverflowElements.rfa | 2026-05-26 | 2026-08-31 | 70 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-05-26T02:54:01+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T02:23:03+02:00 | N | N |  | Y | Y
72068 | 430_DA_FireDampersForCeiling_KU_K30.rfa | 2026-05-25 | 2026-07-08 | 33 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-05-25T03:35:19+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-08T05:42:25+02:00 | N | N |  | Y | Y
72069 | 430_DA_FireDampers_CommercialKitchens_KA_EU.rfa | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-05-25T03:20:12+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T06:35:01+02:00 | N | N |  | Y | Y
72070 | 430_DA_FireDampers_FireProtectionValve_FV_EU.rfa | 2026-05-25 | 2026-07-23 | 44 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-05-25T03:20:28+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T06:14:32+02:00 | N | N |  | Y | Y
72071 | 430_DA_FireInsulationSheets_Fitting_Promat_L90.rfa | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-05-26T02:51:34+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T08:42:16+02:00 | N | N |  | Y | Y
72072 | 430_DA_FireInsulationSheets_Promat_L90.rfa | 2026-05-26 | 2026-06-19 | 19 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-05-26T09:07:23+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:03:26+02:00 | N | N |  | Y | Y
72073 | 430_DA_FireProtectionDamper_Round_FLIVE.rfa | 2026-05-26 | 2026-07-13 | 35 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-05-26T04:54:28+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-13T04:19:09+02:00 | N | N |  | Y | Y
72074 | 430_DA_FlexibleConnection_Rectangular.rfa | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-05-26T09:07:53+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T04:23:17+02:00 | N | N |  | Y | Y
72076 | 410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX | 2026-05-29 | 2026-08-19 | 59 | handler_assign | confirm_note:task_completed_closed | START: handler→n.vo @ 2026-05-29T03:47:14+02:00 ¦¦ END: tv.huynh: The task is completed. The ticket is closed accordingly. Thank you all. @ 2026-08-19T04:00:54+02:00 | N | N |  | Y | Y
72077 | 410_PF_GS_rAdapterConcentric_1PushSocket_GMX | 2026-05-29 | 2026-06-10 | 9 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-29T03:47:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-10T07:21:46+02:00 | N | N |  | Y | Y
72078 | 410_PF_GS_rAdapterEccentric_1PushSocket_GMX | 2026-05-29 | 2026-09-30 | 89 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-05-29T03:48:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T05:43:05+02:00 | N | N |  | Y | Y
72079 | 410_PF_GS_rConcentricOptimiser_1PushSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T03:52:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-06T09:32:26+02:00 | N | N |  | Y | Y
72080 | 410_PF_GS_rTransitiontoCastIron_PushSocket_GMX | 2026-05-29 | 2026-08-17 | 57 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T03:52:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T02:42:42+02:00 | N | N |  | Y | Y
72081 | 410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T04:07:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T09:14:55+02:00 | N | N |  | Y | Y
72082 | 410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-29T04:07:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-15T03:30:31+02:00 | N | N |  | Y | Y
72083 | 410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-29T04:09:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-06T10:06:32+02:00 | N | N |  | Y | Y
72084 | 410_PF_GS_tTeeBranches_2PushSocket_GMX | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-29T04:10:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-23T07:24:36+02:00 | N | N |  | Y | Y
72085 | 410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T04:11:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T04:24:54+02:00 | N | N |  | Y | Y
72086 | 410_PF_GS_uBends_1PushSocket_GMX | 2026-06-01 | 2026-06-15 | 11 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-01T04:04:34+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-15T03:30:57+02:00 | N | N |  | Y | Y
72087 | 410_PF_GS_uGutterPipes_1PushSocket_GMX | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-17T07:06:50+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T06:11:51+02:00 | N | N |  | Y | Y
72088 | 410_PF_GS_uLongCleaningOpening_1PushSocket_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T04:21:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-15T08:38:40+02:00 | N | N |  | Y | Y
72089 | 410_PF_GS_uLongUnion_1PushSocket_GMX | 2026-05-29 | 2026-07-07 | 28 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T04:23:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-07T06:40:42+02:00 | N | N |  | Y | Y
72090 | 410_PF_GS_uLongCleaningOpening_NoSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T04:22:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-06T11:52:00+02:00 | N | N |  | Y | Y
72091 | 410_PF_GS_uSpigottoPlastic_1PushSocket_GMX | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T04:24:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-09T03:21:00+02:00 | N | N |  | Y | Y
72092 | 410_PF_GS_uTransitionSMLtoGMX_1PushSocket | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T04:24:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:40:39+02:00 | N | N |  | Y | Y
72093 | 410_PF_GS_uTranstiontoCastIron_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-05-29T04:25:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-15T03:49:18+02:00 | N | N |  | Y | Y
72094 | Annotation_General_BEP_Aquire and Signoff V000_Lam Truong | 2026-05-22 | 2026-06-04 | 10 | handler_assign | status_resolved | START: handler→l.truong @ 2026-05-22T09:37:34+02:00 ¦¦ END: status→resolved @ 2026-06-04T08:28:36+02:00 | N | N |  | Y | N
72095 | 410_PF_GS_uUnion_2PushSocket_GMX | 2026-05-29 | 2026-07-27 | 42 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-05-29T04:26:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T05:17:11+02:00 | N | N |  | Y | Y
72096 | Annotation_General_BEP_Aquire and Signoff V000_Thuong Huynh | 2026-05-22 | 2026-05-29 | 6 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-05-22T09:37:53+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:58:42+02:00 | N | N |  | Y | N
72097 | Annotation_General_BEP_Aquire and Signoff V000_Nhut Le | 2026-05-22 | 2026-06-01 | 7 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-05-22T09:38:07+02:00 ¦¦ END: status→resolved @ 2026-06-01T04:42:24+02:00 | N | N |  | Y | N
72098 | Annotation_General_BEP_Aquire and Signoff V000_Sang Duong | 2026-05-22 | 2026-06-05 | 11 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-05-22T09:38:16+02:00 ¦¦ END: status→resolved @ 2026-06-05T10:09:03+02:00 | N | N |  | Y | N
72099 | Annotation_General_BEP_Aquire and Signoff V000_Hanh Pham | 2026-05-22 | 2026-06-05 | 11 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-05-22T09:38:31+02:00 ¦¦ END: status→resolved @ 2026-06-05T05:40:33+02:00 | N | N |  | Y | N
72100 | 410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX | 2026-05-29 | 2026-07-27 | 42 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-05-29T04:26:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T05:17:24+02:00 | N | N |  | Y | Y
72101 | 410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T04:27:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T11:53:43+02:00 | N | N |  | Y | Y
72102 | 410_PF_HDPE_cProtectionCap | 2026-05-29 | 2026-07-14 | 33 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-05-29T04:28:34+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T10:13:50+02:00 | N | N |  | Y | Y
72103 | 410_PF_HDPE_cProtectionCapForPipeEnd_Standard | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-05-29T04:31:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T03:15:29+02:00 | N | N |  | Y | Y
72104 | 410_PF_HDPE_cThreadedConnectorWithScrewCap | 2026-05-29 | 2026-07-14 | 33 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-05-29T04:31:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T10:16:20+02:00 | N | N |  | Y | Y
72105 | 410_PF_HDPE_eBend90Deg_Reducer_Welded | 2026-05-29 | 2026-07-15 | 34 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-05-29T04:35:14+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T05:55:02+02:00 | N | N |  | Y | Y
72106 | 410_PF_HDPE_eBend_Welded | 2026-06-02 | 2026-08-14 | 54 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-02T10:31:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T10:11:26+02:00 | N | N |  | Y | Y
72111 | HZG_LPH8_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-05-25T03:38:33+02:00 ¦¦ END: status→resolved @ 2026-05-29T11:50:00+02:00 | N | N |  | Y | N
72112 | HZG_LPH5_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-05-25T03:38:28+02:00 ¦¦ END: status→resolved @ 2026-05-29T11:41:58+02:00 | N | N |  | Y | N
72113 | HZG_LPH3_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-05-25T03:38:24+02:00 ¦¦ END: status→resolved @ 2026-05-29T11:45:17+02:00 | N | N |  | Y | N
72114 | KLT_LPH3_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-05-25T03:37:43+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:21:05+02:00 | N | N |  | Y | N
72115 | KLT_LPH5_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-05-25T03:37:53+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:27:37+02:00 | N | N |  | Y | N
72116 | KLT_LPH8_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | START: handler→t.tran @ 2026-05-25T03:38:01+02:00 ¦¦ END: status→resolved @ 2026-05-29T10:16:48+02:00 | N | N |  | Y | N
72129 | Annotation_Platform_Integrate the change proposal | 2026-05-25 | 2026-05-27 | 3 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-05-25T06:29:04+02:00 ¦¦ END: status→resolved @ 2026-05-27T03:32:41+02:00 | N | N |  | Y | N
72130 | Annotation_Platform_Deploy the Upload and Download Feature | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-05-25T06:39:31+02:00 ¦¦ END: status→resolved @ 2026-05-29T09:20:54+02:00 | N | N |  | Y | N
72136 | Revise the RFA library for the ELT system. | 2026-05-25 |  |  | handler_assign | none | START: handler→h.pham @ 2026-05-25T10:07:04+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
72156 | Revise the RFA library for the HZG system | 2026-05-27 | 2026-10-01 | 92 | handler_assign | status_closed | START: handler→n.le @ 2026-05-27T08:16:30+02:00 ¦¦ END: status→closed @ 2026-10-01T06:09:07+02:00 | N | N |  | Y | N
72157 | Revise the RFA library for the KLT system | 2026-05-27 | 2026-10-01 | 92 | handler_assign | status_closed | START: handler→n.le @ 2026-05-27T08:16:28+02:00 ¦¦ END: status→closed @ 2026-10-01T06:09:02+02:00 | N | N |  | Y | N
72158 | Revise the RFA library for the HGR system | 2026-05-27 | 2026-10-01 | 92 | handler_assign | status_closed | START: handler→n.le @ 2026-05-27T08:16:26+02:00 ¦¦ END: status→closed @ 2026-10-01T06:08:56+02:00 | N | N |  | Y | N
72167 | 420_PF_PE_eElbow.rfa | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-05-28T10:36:44+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-15T09:09:05+02:00 | N | N |  | Y | Y
72168 | 420_PF_MapressCarbonSteel_Union_SlipJoin | 2026-05-28 | 2026-07-22 | 40 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-05-28T10:36:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T02:28:49+02:00 | N | N |  | Y | Y
72169 | 420_PF_MapressCarbonSteel_Transition_SlipJoin | 2026-05-28 | 2026-07-17 | 37 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-05-28T10:24:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-17T11:48:09+02:00 | N | N |  | Y | Y
72170 | 420_PF_MapressCarbonSteel_Tee_SlipJoin | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-05-28T10:24:08+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T09:33:57+02:00 | N | N |  | Y | Y
72171 | 420_PF_MapressCarbonSteel_SocketFlangeAdaptor_SlipJoin | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-05-28T10:24:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T08:46:25+02:00 | N | N |  | Y | Y
72172 | 420_PF_MapressCarbonSteel_SocketAdaptor_SlipJoin | 2026-05-28 | 2026-07-23 | 41 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-05-28T10:22:43+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-23T09:46:27+02:00 | N | N |  | Y | Y
72173 | 420_PF_MapressCarbonSteel_FlangeAdaptor_SlipJoin | 2026-05-28 | 2026-07-17 | 37 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-05-28T10:22:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-17T09:22:12+02:00 | N | N |  | Y | N
72174 | 420_PF_MapressCarbonSteel_Elbow_SlipJoin | 2026-05-28 | 2026-09-10 | 76 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-05-28T10:22:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T06:27:19+02:00 | N | N |  | Y | Y
72175 | 420_PF_MapressCarbonSteel_Cross_SlipJoin | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-05-28T10:22:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-15T09:09:34+02:00 | N | N |  | Y | Y
72176 | 420_PF_MapressCarbonSteel_Cap_SlipJoin | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-05-28T10:21:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-15T09:10:10+02:00 | N | N |  | Y | Y
72177 | 420_PF_Copper_Elbow.rfa | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-05-28T10:21:32+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T05:23:02+02:00 | N | N |  | Y | Y
72195 | 420_PF_Brass_ThreeWayEqualTee_Compression | 2026-05-28 | 2026-06-19 | 17 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-05-28T10:21:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-19T08:34:31+02:00 | N | N |  | Y | Y
72196 | 420_PF_CO_cCap_Soldered | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-05-28T10:20:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T05:17:44+02:00 | N | N |  | Y | Y
72198 | 420_PF_CO_eElbow_Soldered | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-05-28T10:20:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-08T05:48:06+02:00 | N | N |  | Y | Y
72199 | 420_PF_CS_xCross_Welded | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-05-28T10:19:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-10T08:51:37+02:00 | N | N |  | Y | Y
72200 | 420_PF_CS_uUnion_Welded | 2026-05-28 | 2026-06-01 | 3 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-05-28T09:14:15+02:00 ¦¦ END: status→resolved @ 2026-06-01T10:21:21+02:00 | N | N |  | Y | Y
72201 | 420_PF_CS_tTee_Welded | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-05-28T09:13:36+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-08T08:32:37+02:00 | N | N |  | Y | Y
72202 | 420_PF_CS_sTap_Welded | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-05-28T09:07:35+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-08T08:57:59+02:00 | N | N |  | Y | Y
72203 | 420_PF_CS_rReducer_Welded | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-05-28T09:07:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-03T09:23:49+02:00 | N | N |  | Y | Y
72204 | 420_PF_CS_fConnectionFlanged_Welded | 2026-05-28 | 2026-06-04 | 6 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-05-28T09:06:41+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-04T03:13:51+02:00 | N | N |  | Y | Y
72205 | MEP_Revise 474_PF_CarbonSteel_LowProfileSprinklerTee_Threaded | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:37:59+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-15T11:16:24+02:00 | N | N |  | Y | Y
72206 | MEP_Revise 474_PF_CarbonSteel_AdapterNipple_Flanged | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:38:34+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-16T08:38:14+02:00 | N | N |  | Y | Y
72207 | MEP_Revise 474_PF_CarbonSteel_LateralTee_Grooved | 2026-05-27 | 2026-07-23 | 42 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:39:07+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-23T06:26:51+02:00 | N | N |  | Y | Y
72208 | MEP_Revise 474_PF_CarbonSteel_LateralThread_Standard | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:39:34+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-16T09:46:34+02:00 | N | N |  | Y | Y
72209 | MEP_Revise 474_PF_CarbonSteel_OutletTeeReducing_Coupling | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:40:12+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-16T10:24:54+02:00 | N | N |  | Y | Y
72210 | MEP_Revise 474_PF_CarbonSteel_OutletTeeReducing_Threaded | 2026-05-27 | 2026-06-23 | 20 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:40:39+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-06-23T03:45:02+02:00 | N | N |  | Y | Y
72211 | MEP_Revise 474_PF_CS_tReducingLateralTee_Grooved | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:41:06+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-03T03:33:18+02:00 | N | N |  | Y | Y
72212 | MEP_Revise 474_PF_CarbonSteel_TeeGroovedEnd_Standard | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:41:32+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-15T11:11:11+02:00 | N | N |  | Y | Y
72213 | MEP_Revise 474_PF_CarbonSteel_TeeReducing_Grooved | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:42:00+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-03T05:02:37+02:00 | N | N |  | Y | Y
72214 | MEP_Revise 474_PF_CastIron_Cap_Threaded | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:42:36+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-15T09:48:50+02:00 | N | N |  | Y | Y
72215 | MEP_Revise 474_PF_Castiron_Cross_Thread | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:43:26+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-03T08:57:13+02:00 | N | N |  | Y | Y
72216 | MEP_Revise 474_PF_CastIron_Elbow_Threaded_ShortBend | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:44:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-13T08:39:39+02:00 | N | N |  | Y | Y
72217 | MEP_Revise 474_PF_Castiron_HexNipple | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:44:43+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-03T11:25:18+02:00 | N | N |  | Y | Y
72218 | MEP_Revise 474_PF_CastIron_Reducer_Threaded | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:45:12+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-03T11:53:51+02:00 | N | N |  | Y | Y
72219 | MEP_Revise 474_PF_CastIron_SocketUnion_Threaded | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:45:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-06T06:56:00+02:00 | N | N |  | Y | Y
72220 | MEP_Revise 474_PF_CastIron_Tee_Thread | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:46:06+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-06T06:54:12+02:00 | N | N |  | Y | Y
72221 | MEP_Revise 474_PF_CastIron_TeeReducing_Thread | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:46:34+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-06T09:19:33+02:00 | N | N |  | Y | Y
72222 | MEP_Revise 474_PF_CI_uUnion_Threaded | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:47:02+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-14T08:49:30+02:00 | N | N |  | Y | Y
72223 | MEP_Revise 474_PF_CS_cCap_Grooved | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:47:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-13T06:36:29+02:00 | N | N |  | Y | Y
72224 | MEP_Revise 474_PF_CS_eElbow_Grooved | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:48:24+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-13T08:59:43+02:00 | N | N |  | Y | Y
72225 | MEP_Revise 474_PF_CS_eElbowEndOfRun_Grooved | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:48:59+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-15T09:48:54+02:00 | N | N |  | Y | Y
72226 | MEP_Revise 474_PF_CS_fConnection_Coupling_FireLockEZRigid | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:49:26+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-13T10:03:32+02:00 | N | N |  | Y | Y
72227 | MEP_Revise 474_PF_CS_fConnection_Coupling_FireLockRigid | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:49:58+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-14T06:13:07+02:00 | N | N |  | Y | Y
72228 | MEP_Revise 474_PF_CS_rConcentricReducer_Grooved | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:50:32+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-14T08:51:25+02:00 | N | N |  | Y | Y
72229 | MEP_Revise 474_PF_CS_rEccentricReducer_Grooved | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:51:03+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-14T11:35:06+02:00 | N | N |  | Y | Y
72231 | MEP_Revise 474_PF_CS_tOutletReducingCouplingTee_Grooved | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:51:32+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-14T10:18:54+02:00 | N | N |  | Y | Y
72232 | MEP_Revise 474_PF_CS_tSprinkerTeeCoupling_Grooved_Threaded | 2026-05-27 | 2026-06-02 | 5 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T10:52:22+02:00 ¦¦ END: status→resolved @ 2026-06-02T11:06:23+02:00 | N | N |  | Y | N
72233 | MEP_Revise 474_PF_CS_tTee_Grooved | 2026-05-27 | 2026-06-03 | 6 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T10:52:49+02:00 ¦¦ END: status→resolved @ 2026-06-03T09:36:12+02:00 | N | N |  | Y | N
72234 | MEP_Revise 474_PF_CS_uAdaptorNipple_Grooved | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:53:14+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-15T05:11:42+02:00 | N | N |  | Y | Y
72235 | MEP_Revise 474_PF_CS_wTrueWye_Grooved | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:53:41+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-15T05:01:17+02:00 | N | N |  | Y | Y
72236 | MEP_Revise 474_PF_CS_xCross_Grooved | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:56:16+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-15T08:08:35+02:00 | N | N |  | Y | Y
72237 | MEP_Revise 474_PF_DuctileIron_CapFemale_Thread | 2026-05-27 | 2026-06-04 | 7 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T10:56:38+02:00 ¦¦ END: status→resolved @ 2026-06-04T06:50:01+02:00 | N | N |  | Y | N
72238 | MEP_Revise 474_PF_DuctileIron_DrainElbow_Grooved | 2026-05-27 | 2026-06-05 | 8 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T10:57:02+02:00 ¦¦ END: status→resolved @ 2026-06-05T10:56:04+02:00 | N | N |  | Y | N
72239 | MEP_Revise 474_PF_DuctileIron_SmallReducer_Thread | 2026-05-27 | 2026-06-05 | 8 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T10:58:01+02:00 ¦¦ END: status→resolved @ 2026-06-05T10:57:53+02:00 | N | N |  | Y | N
72240 | MEP_Revise 474_PF_GalvanizedSteel_NippleReducer_Threaded | 2026-05-27 | 2026-06-04 | 7 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T10:59:14+02:00 ¦¦ END: status→resolved @ 2026-06-04T06:49:18+02:00 | N | N |  | Y | N
72241 | MEP_Revise 474_PF_SS_eUnionElbow_Threaded | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T10:59:46+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-15T07:02:25+02:00 | N | N |  | Y | Y
72242 | MEP_Revise 474_PF_SS_sHaftCoupling | 2026-05-27 | 2026-06-09 | 10 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T11:00:13+02:00 ¦¦ END: status→resolved @ 2026-06-09T11:02:55+02:00 | N | N |  | Y | N
72243 | MEP_Revise 474_PF_StainlessSteel_FlexibleCoupling_Grooved | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T11:00:40+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T05:09:21+02:00 | N | N |  | Y | N
72244 | MEP_Revise 474_PA_AlarmCheckValve_Dry | 2026-05-27 | 2026-06-11 | 12 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:06:59+02:00 ¦¦ END: status→resolved @ 2026-06-11T06:48:18+02:00 | N | N |  | Y | N
72245 | MEP_Revise 474_PA_AlarmCheckValve_European | 2026-05-27 | 2026-08-21 | 63 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:07:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-21T03:11:55+02:00 | N | N |  | Y | Y
72246 | MEP_Revise 474_PA_AlarmCheckValve_Preaction | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:08:02+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T11:30:53+02:00 | N | N |  | Y | Y
72247 | MEP_Revise 474_PA_AlarmTestModuleGrooveEnd | 2026-05-27 | 2026-07-24 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:09:23+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-24T03:59:52+02:00 | N | N |  | Y | Y
72248 | MEP_Revise 474_PA_AutomaticConcentrateControlValve_Foam | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:13:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T11:31:51+02:00 | N | N |  | Y | Y
72249 | MEP_Revise 474_PA_BallValve | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:15:14+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T05:38:58+02:00 | N | N |  | Y | Y
72250 | MEP_Revise 474_PA_BallValves_GrooveAndGroove | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:15:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T11:17:43+02:00 | N | N |  | Y | Y
72251 | MEP_Revise 474_PA_BallValvesThreadandThread | 2026-05-27 | 2026-07-31 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:16:51+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-31T03:29:54+02:00 | N | N |  | Y | Y
72252 | MEP_Revise 474_PA_BrassBodyBallValves_Threaded | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:18:02+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-02T06:17:39+02:00 | N | N |  | Y | Y
72253 | MEP_Revise 474_PA_ButterflyValve | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:18:41+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-02T07:45:28+02:00 | N | N |  | Y | Y
72254 | MEP_Revise 474_PA_CheckValve | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:19:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-02T09:29:02+02:00 | N | N |  | Y | Y
72255 | MEP_Revise 474_PA_CheckValveAlternateWetDrySystem | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:20:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-02T10:03:33+02:00 | N | N |  | Y | Y
72256 | MEP_Revise 474_PA_CS_BalancingValve_Flanged | 2026-05-27 | 2026-06-15 | 14 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:20:44+02:00 ¦¦ END: status→resolved @ 2026-06-15T02:34:36+02:00 | N | N |  | Y | N
72257 | MEP_Revise 474_PA_CS_GateValveWithElectricActuator | 2026-05-27 | 2026-08-21 | 63 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:21:11+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-21T10:40:51+02:00 | N | N |  | Y | Y
72258 | MEP_Revise 474_PA_WaterFlowDetector | 2026-05-27 | 2026-06-11 | 12 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:22:04+02:00 ¦¦ END: status→resolved @ 2026-06-11T02:48:45+02:00 | N | N |  | Y | N
72259 | MEP_Revise 474_PA_CurrentDetector_ZoneCheck | 2026-05-27 | 2026-08-12 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:22:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T11:33:35+02:00 | N | N |  | Y | Y
72260 | MEP_Revise 474_PA_FireHoseAngleValveWithCap | 2026-05-27 | 2026-08-13 | 57 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:24:26+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T03:56:51+02:00 | N | N |  | Y | Y
72261 | MEP_Revise 474_PA_DoubleDoorCheckValve | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:24:53+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T11:11:55+02:00 | N | N |  | Y | Y
72262 | MEP_Revise 474_PA_DryAccelerator | 2026-05-27 | 2026-07-22 | 41 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:25:45+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-22T11:05:21+02:00 | N | N |  | Y | Y
72263 | MEP_Revise 474_PA_DryPilotActuator_ | 2026-05-27 | 2026-07-28 | 45 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:26:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-28T03:21:05+02:00 | N | N |  | Y | Y
72264 | MEP_Revise 474_PA_FireLockBallValve | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:26:51+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T05:45:45+02:00 | N | N |  | Y | Y
72265 | MEP_Revise 474_PA_FireLockAlarmCheckValve | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:29:15+02:00 ¦¦ END: hu.dam: s.duong This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T05:41:55+02:00 | N | N |  | Y | Y
72266 | MEP_Revise 474_PA_FM200_DischagePressureSwitch | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:30:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T05:41:09+02:00 | N | N |  | Y | Y
72267 | MEP_Revise 474_PA_FootValve | 2026-05-27 | 2026-06-24 | 21 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:31:55+02:00 ¦¦ END: status→resolved @ 2026-06-24T10:48:05+02:00 | N | N |  | Y | N
72268 | MEP_Revise 474_PA_GateValve | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-27T12:32:22+02:00 ¦¦ END: s.duong: Ticket is the same with ticket #0071594 Therefore, this ticket will be closed. Thank you. @ 2026-07-16T10:57:40+02:00 | N | N |  | Y | N
72269 | MEP_Revise 474_PA_HighPressureCheckValve | 2026-05-27 | 2026-06-24 | 21 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:32:43+02:00 ¦¦ END: status→resolved @ 2026-06-24T10:51:09+02:00 | N | N |  | Y | N
72270 | MEP_Revise 474_PA_HighPressureRiserCheckValve | 2026-05-27 | 2026-06-25 | 22 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:33:02+02:00 ¦¦ END: status→resolved @ 2026-06-25T10:04:05+02:00 | N | N |  | Y | N
72271 | MEP_Revise 474_PA_HydrantGateValve | 2026-05-27 | 2026-06-23 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:33:34+02:00 ¦¦ END: status→resolved @ 2026-06-23T03:31:09+02:00 | N | N |  | Y | N
72272 | MEP_Revise 474_PA_LevelControlValves_Flange | 2026-05-27 | 2026-07-17 | 38 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:34:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-17T04:15:40+02:00 | N | N |  | Y | Y
72273 | MEP_Revise 474_PA_LevelControlValves_Grooved | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-27T12:34:35+02:00 ¦¦ END: s.duong: Thank you. This ticket will be closed. @ 2026-08-07T05:28:03+02:00 | N | N |  | Y | Y
72274 | MEP_Revise 474_PA_ManifoldCheckValve_FM200 | 2026-05-27 | 2026-06-25 | 22 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:35:06+02:00 ¦¦ END: status→resolved @ 2026-06-25T08:14:15+02:00 | N | N |  | Y | N
72275 | MEP_Revise 474_PA_ManuallyActuatedBallValve_CO2 | 2026-05-27 | 2026-06-25 | 22 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:36:47+02:00 ¦¦ END: status→resolved @ 2026-06-25T03:43:18+02:00 | N | N |  | Y | N
72276 | MEP_Revise 474_PA_ManualPneumaticActuator_FM200 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:37:11+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T03:10:32+02:00 | N | N |  | Y | Y
72277 | MEP_Revise 474_PA_NRSOS&YGateValvesGrooveandFlange | 2026-05-27 | 2026-09-11 | 78 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:37:47+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-11T03:48:05+02:00 | N | N |  | Y | Y
72279 | MEP_Revise 474_PA_OS&YGateValves_GrooveAndFlange | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:38:34+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-15T11:47:01+02:00 | N | N |  | Y | Y
72280 | MEP_Revise 474_PA_PressureGauge_withBallValve | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:39:38+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T10:34:17+02:00 | N | N |  | Y | Y
72281 | MEP_Revise 474_PA_PressureMeter | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:41:10+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T11:31:27+02:00 | N | N |  | Y | Y
72282 | MEP_Revise 474_PA_PressureOperatedDirectionalValve_CO2 | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:41:36+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T05:39:31+02:00 | N | N |  | Y | Y
72283 | MEP_Revise 474_PA_PressureReducingControlValve_Groove | 2026-05-27 | 2026-08-13 | 57 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:41:58+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T05:24:24+02:00 | N | N |  | Y | Y
72284 | MEP_Revise 474_PA_PressureReliefControlValve | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:44:43+02:00 ¦¦ END: status→resolved @ 2026-06-19T10:06:20+02:00 | N | N |  | Y | N
72285 | MEP_Revise 474_PA_PressureReliefValve | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:45:12+02:00 ¦¦ END: status→resolved @ 2026-06-19T10:08:17+02:00 | N | N |  | Y | N
72286 | MEP_Revise 474_PA_PressureSensor | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:45:58+02:00 ¦¦ END: status→resolved @ 2026-06-19T10:11:22+02:00 | N | N |  | Y | N
72287 | MEP_Revise 474_PA_PressureSwitch_FM200 | 2026-05-27 | 2026-08-05 | 51 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:46:22+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T11:42:44+02:00 | N | N |  | Y | Y
72288 | MEP_Revise 474_PA_RiserCheckValve | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:47:01+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-09-03T03:51:43+02:00 | N | N |  | Y | Y
72289 | MEP_Revise 474_PA_RubberExpansionJoint_Flanged | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:47:22+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-09-03T03:42:32+02:00 | N | N |  | Y | Y
72290 | MEP_Revise 474_PA_RubberExpansionJoint_Threaded | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:47:53+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T09:52:59+02:00 | N | N |  | Y | Y
72292 | MEP_Revise 474_PA_SafertyReliefValve_CO2 | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:48:45+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-09-03T03:27:20+02:00 | N | N |  | Y | Y
72293 | MEP_Revise 474_PA_SafetyValve | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:49:15+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-09-03T03:06:49+02:00 | N | N |  | Y | Y
72294 | MEP_Revise 474_PA_SelectorValve_CO2 | 2026-05-27 | 2026-08-11 | 55 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:49:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-11T02:51:11+02:00 | N | N |  | Y | N
72295 | MEP_Revise 474_PA_ShutoffValve_Motorized | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:50:25+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T09:53:03+02:00 | N | N |  | Y | Y
72296 | MEP_Revise 474_PA_SightGlasses | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:50:54+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T09:53:09+02:00 | N | N |  | Y | Y
72297 | MEP_Revise 474_PA_SolenoidValve | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:51:22+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T10:50:49+02:00 | N | N |  | Y | Y
72298 | MEP_Revise 474_PA_SS_CompoundPressureGauge | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:51:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T10:50:53+02:00 | N | N |  | Y | Y
72299 | MEP_Revise 474_PA_StoneCatcher | 2026-05-27 | 2026-08-17 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:52:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-17T07:14:32+02:00 | N | N |  | Y | Y
72300 | MEP_Revise 474_PA_SwingCheckValve_Grooved | 2026-05-27 | 2026-06-18 | 17 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:52:45+02:00 ¦¦ END: status→resolved @ 2026-06-18T09:08:29+02:00 | N | N |  | Y | N
72301 | MEP_Revise 474_PA_WaterflowSwitches | 2026-05-27 | 2026-09-11 | 78 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-27T12:53:10+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-09-11T04:42:33+02:00 | N | N |  | Y | Y
72302 | MEP_Revise 474_PA_WaterMeter | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-27T12:53:37+02:00 ¦¦ END: status→resolved @ 2026-06-19T03:54:52+02:00 | N | N |  | Y | N
72313 | MEP_Revise 474_PROMAT_4Sided_Horizontal_CeilingMount | 2026-05-28 | 2026-06-24 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:04:43+02:00 ¦¦ END: status→resolved @ 2026-06-24T07:04:05+02:00 | N | N |  | Y | N
72315 | MEP_Revise 474_PROMAT_4Sided_Horizontal_Vertical_CeilingMount | 2026-05-28 | 2026-06-23 | 19 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:11:15+02:00 ¦¦ END: status→resolved @ 2026-06-23T04:36:03+02:00 | N | N |  | Y | N
72316 | MEP_Revise 474_PROMAT_4Sided_Vertical_CeilingMount | 2026-05-28 | 2026-06-23 | 19 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:11:51+02:00 ¦¦ END: status→resolved @ 2026-06-23T09:17:54+02:00 | N | N |  | Y | N
72317 | MEP_Revise 474_PROMAT_Horizontal_Vertical_WallMount | 2026-05-28 | 2026-08-31 | 68 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:12:35+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T03:08:35+02:00 | N | N |  | Y | Y
72318 | MEP_Revise 474_PROMAT_Horizontal_WallMount | 2026-05-28 | 2026-06-25 | 21 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:13:15+02:00 ¦¦ END: status→resolved @ 2026-06-25T10:01:05+02:00 | N | N |  | Y | N
72319 | MEP_Revise 474_PROMAT_Vertical_WallMount | 2026-05-28 | 2026-06-25 | 21 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:13:59+02:00 ¦¦ END: status→resolved @ 2026-06-25T08:30:13+02:00 | N | N |  | Y | N
72320 | MEP_Revise 474_SP_DischargeNozzle_CO2 | 2026-05-28 | 2026-07-13 | 33 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:14:40+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-13T09:35:01+02:00 | N | N |  | Y | N
72321 | MEP_Revise 474_SP_FM200_180RadialNozzle_2Port | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:15:08+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T11:43:45+02:00 | N | N |  | Y | Y
72322 | MEP_Revise 474_SP_FM200_360RadialNozzle_1Port | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:15:42+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T11:43:12+02:00 | N | N |  | Y | Y
72323 | MEP_Revise 474_SP_FM200_360RadialNozzle_4Port | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:16:25+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T11:44:52+02:00 | N | N |  | Y | Y
72324 | MEP_Revise 474_SP_FM200_DischargeNozzle | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:17:03+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-10T06:19:07+02:00 | N | N |  | Y | Y
72325 | MEP_Revise 474_SP_FoamNozzle_Pendent | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:18:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-10T08:35:27+02:00 | N | N |  | Y | Y
72326 | MEP_Revise 474_SP_FoamNozzle_Upright | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:19:16+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-11T03:15:30+02:00 | N | N |  | Y | Y
72327 | MEP_Revise 474_SP_GE_DoubleSprinkler | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:19:53+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-11T03:10:45+02:00 | N | N |  | Y | Y
72328 | MEP_Revise 474_SP_GE_HorizontalSideWall | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:20:39+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T09:20:52+02:00 | N | N |  | Y | Y
72329 | MEP_Revise 474_SP_GE_HVSprayNozzles | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:21:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T10:20:01+02:00 | N | N |  | Y | Y
72330 | MEP_Revise 474_SP_GE_Pendent | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:21:47+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T09:49:28+02:00 | N | N |  | Y | Y
72331 | MEP_Revise 474_SP_GE_PendentCover | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:22:22+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T09:19:36+02:00 | N | N |  | Y | Y
72332 | MEP_Revise 474_SP_GE_SprayNozzles | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:22:57+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T04:00:56+02:00 | N | N |  | Y | Y
72333 | MEP_Revise 474_SP_GE_Upright | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:23:27+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T11:41:38+02:00 | N | N |  | Y | Y
72334 | MEP_Revise 474_SP_GE_UprightCover | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:23:59+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T11:42:30+02:00 | N | N |  | Y | Y
72335 | Revise the RFA library for the MED system. | 2026-05-28 |  |  | handler_assign | none | START: handler→s.duong @ 2026-05-28T05:25:12+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
72336 | MEP_Revise 473_PF_CO_rReducer_FemaleSoldered | 2026-05-28 | 2026-06-29 | 23 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:29:17+02:00 ¦¦ END: status→resolved @ 2026-06-29T10:44:13+02:00 | N | N |  | Y | Y
72337 | MEP_Revise 473_PF_CO_rReducerMF_Soldered | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:30:48+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T11:26:56+02:00 | N | N |  | Y | Y
72338 | MEP_Revise 473_PF_CO_tEqualTee_FemaleSoldered | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:31:23+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T09:21:33+02:00 | N | N |  | Y | Y
72339 | MEP_Revise 473_PF_CO_tTee_Reducing_FemaleSoldered | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:31:58+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-27T05:17:55+02:00 | N | N |  | Y | Y
72340 | MEP_Revise 473_PF_CO_uCoupling_Soldered | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-28T05:32:34+02:00 ¦¦ END: s.duong: Thank you. This ticket will be closed. @ 2026-08-07T05:27:12+02:00 | N | N |  | Y | N
72341 | MEP_Revise 473_PF_CO_uOffsetFF_Soldered | 2026-05-28 | 2026-07-14 | 34 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:32:59+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-14T09:29:58+02:00 | N | N |  | Y | Y
72342 | MEP_Revise 473_PF_SS_tTee_Welded | 2026-05-28 | 2026-07-29 | 45 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:33:39+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-29T11:48:39+02:00 | N | N |  | Y | Y
72343 | MEP_Revise 473_PF_SS_uClampConnector | 2026-05-28 | 2026-07-01 | 25 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:34:18+02:00 ¦¦ END: status→resolved @ 2026-07-01T09:50:25+02:00 | N | N |  | Y | N
72344 | MEP_Revise 473_PF_SS_uClampConnectorWithWeldedConnection | 2026-05-28 | 2026-06-30 | 24 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:34:56+02:00 ¦¦ END: status→resolved @ 2026-06-30T11:20:51+02:00 | N | N |  | Y | N
72345 | MEP_Revise 473_EF_BathroomCallUnit_PullCord | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:35:35+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-11T08:18:06+02:00 | N | N |  | Y | Y
72346 | MEP_Revise 473_EF_BathroomCallUnit_PushButton | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:36:38+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T04:46:09+02:00 | N | N |  | Y | Y
72347 | MEP_Revise 473_EF_BiomedicalCallPlugandSocket | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:37:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T06:31:18+02:00 | N | N |  | Y | N
72348 | MEP_Revise 473_EF_CallDisplayUnit | 2026-05-28 | 2026-07-09 | 31 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:37:45+02:00 ¦¦ END: status→resolved @ 2026-07-09T03:48:09+02:00 | N | N |  | Y | N
72349 | MEP_Revise 473_EF_CallTranferUnitForCorridors | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:38:09+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T06:46:49+02:00 | N | N |  | Y | N
72350 | MEP_Revise 473_EF_DoorUnit | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:38:51+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:36:49+02:00 | N | N |  | Y | Y
72351 | MEP_Revise 473_EF_ElectronicBuzzer_WallSurface | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:39:30+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:31:41+02:00 | N | N |  | Y | Y
72352 | MEP_Revise 473_EF_RemoteControlModules | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:40:06+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:31:29+02:00 | N | N |  | Y | Y
72353 | MEP_Revise 473_EF_SocketForCordedPushButton_WallSurface | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:40:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-06T11:31:00+02:00 | N | N |  | Y | Y
72354 | MEP_Revise 473_EF_SocketforHandPushButton | 2026-05-28 | 2026-08-28 | 67 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:41:45+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-28T10:43:23+02:00 | N | N |  | Y | Y
72355 | MEP_Revise 473_EF_TableControlUnit | 2026-05-28 | 2026-07-08 | 30 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:42:26+02:00 ¦¦ END: status→resolved @ 2026-07-08T06:21:03+02:00 | N | N |  | Y | N
72356 | MEP_Revise 473_ME_ActivatedCarbonTower | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:42:52+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T04:28:31+02:00 | N | N |  | Y | Y
72357 | MEP_Revise 473_ME_AirDryer | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:43:25+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T04:28:34+02:00 | N | N |  | Y | Y
72358 | MEP_Revise 473_ME_AirDryer_Vertical | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:43:55+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-11T03:03:29+02:00 | N | N |  | Y | Y
72359 | MEP_Revise 473_ME_AirPurifiers | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:44:23+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-10T10:58:32+02:00 | N | N |  | Y | Y
72360 | MEP_Revise 473_ME_AirReceiverTank | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:44:58+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-10T10:55:49+02:00 | N | N |  | Y | Y
72361 | MEP_Revise 473_ME_AreaAlarmPanel | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:45:29+02:00 ¦¦ END: status→resolved @ 2026-07-31T04:13:20+02:00 | N | N |  | Y | N
72362 | MEP_Revise 473_ME_AutomatedH2O2AirlockAccessible | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:46:15+02:00 ¦¦ END: status→resolved @ 2026-07-31T04:32:17+02:00 | N | N |  | Y | N
72363 | MEP_Revise 473_ME_BHU_DK2014 | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:46:49+02:00 ¦¦ END: status→resolved @ 2026-07-31T06:23:30+02:00 | N | N |  | Y | N
72364 | MEP_Revise 473_ME_BHU_DK2014M | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:47:44+02:00 ¦¦ END: status→resolved @ 2026-07-31T09:53:44+02:00 | N | N |  | Y | N
72365 | MEP_Revise 473_ME_BHU_HY2017 | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T05:48:19+02:00 ¦¦ END: status→resolved @ 2026-07-31T10:04:46+02:00 | N | N |  | Y | N
72366 | MEP_Revise 473_ME_BHU_HY2017D | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:48:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-11T06:23:35+02:00 | N | N |  | Y | Y
72367 | MEP_Revise 473_ME_BHU_HY2017DS | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:49:33+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-11T04:59:09+02:00 | N | N |  | Y | Y
72368 | MEP_Revise 473_ME_BHU_SC2015 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:50:14+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T10:04:16+02:00 | N | N |  | Y | Y
72369 | MEP_Revise 473_ME_BHU_Vertical | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:51:08+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T09:57:24+02:00 | N | N |  | Y | Y
72370 | MEP_Revise 473_ME_BottleFillingPlant | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:52:16+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-10T05:30:40+02:00 | N | N |  | Y | Y
72371 | MEP_Revise 473_ME_CompactH2O2DecontaminationAirlock | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:52:53+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T09:56:45+02:00 | N | N |  | Y | Y
72372 | MEP_Revise 473_ME_CylinderTank_NoSystem | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:54:16+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T11:47:20+02:00 | N | N |  | Y | Y
72373 | MEP_Revise 473_ME_DesiccantAdsorptionCompressedAirDryers | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:55:01+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T11:53:50+02:00 | N | N |  | Y | Y
72374 | MEP_Revise 473_ME_DryVacuumPump | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:55:42+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T05:22:50+02:00 | N | N |  | Y | Y
72375 | MEP_Revise 473_ME_ExternalHeatRecoveryUnits | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:56:14+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T05:50:35+02:00 | N | N |  | Y | Y
72376 | MEP_Revise 473_ME_HeatlessRegenerationAdsorptionDryers | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:56:53+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T08:54:49+02:00 | N | N |  | Y | Y
72377 | MEP_Revise 473_ME_HeatlessRegenerationAdsorptionDryers_ActivatedCarbonTower | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:57:40+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T08:52:52+02:00 | N | N |  | Y | Y
72378 | MEP_Revise 473_ME_HeatRegenerationAdsorptionDryers | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:58:15+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T09:28:40+02:00 | N | N |  | Y | Y
72379 | MEP_Revise 473_ME_ICU_Eurocare | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:58:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-13T09:37:33+02:00 | N | N |  | Y | Y
72380 | MEP_Revise 473_ME_ICU_EurocareD | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T05:59:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:55:05+02:00 | N | N |  | Y | Y
72381 | MEP_Revise 473_ME_ICU_SMICare | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:00:09+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T09:31:30+02:00 | N | N |  | Y | N
72382 | MEP_Revise 473_ME_ICU_SMICAREDS | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:00:53+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T09:31:44+02:00 | N | N |  | Y | N
72383 | MEP_Revise 473_ME_IntensiveCareUnits_WallMounted_SMICAREDS | 2026-05-28 | 2026-07-29 | 45 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:01:29+02:00 ¦¦ END: status→resolved @ 2026-07-29T11:05:28+02:00 | N | N |  | Y | N
72384 | MEP_Revise 473_ME_IntensiveCareUnits_WallMounted_SMICareHD | 2026-05-28 | 2026-07-28 | 44 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:02:23+02:00 ¦¦ END: status→resolved @ 2026-07-28T11:05:03+02:00 | N | N |  | Y | N
72385 | MEP_Revise 473_ME_MedicalAirCompressors_FloorMounted | 2026-05-28 | 2026-08-14 | 57 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:03:26+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T03:25:44+02:00 | N | N |  | Y | Y
72386 | MEP_Revise 473_ME_MedicalAirCompressors_TankMounted | 2026-05-28 | 2026-07-27 | 43 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:04:05+02:00 ¦¦ END: status→resolved @ 2026-07-27T11:40:18+02:00 | N | N |  | Y | N
72387 | MEP_Revise 473_ME_NitrogenGenerators | 2026-05-28 | 2026-07-28 | 44 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:04:51+02:00 ¦¦ END: status→resolved @ 2026-07-28T10:33:34+02:00 | N | N |  | Y | N
72388 | MEP_Revise 473_ME_OxygenGenerators | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:05:37+02:00 ¦¦ END: status→resolved @ 2026-07-31T10:28:05+02:00 | N | N |  | Y | N
72389 | MEP_Revise 473_ME_RefrigerationAirDryer_Flanged | 2026-05-28 | 2026-07-30 | 46 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:06:29+02:00 ¦¦ END: status→resolved @ 2026-07-30T11:49:47+02:00 | N | N |  | Y | N
72390 | MEP_Revise 473_ME_RefrigerationAirDryer_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:07:12+02:00 ¦¦ END: status→resolved @ 2026-07-30T11:47:08+02:00 | N | N |  | Y | N
72391 | MEP_Revise 473_ME_VacuumPump | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:07:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:54:22+02:00 | N | N |  | Y | Y
72392 | MEP_Revise 473_ME_ZoneWallUnit_CZ200 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:08:21+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:53:28+02:00 | N | N |  | Y | Y
72393 | MEP_Revise 473_ME_ZoneWallUnit_HST100 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:08:52+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:49:31+02:00 | N | N |  | Y | Y
72394 | MEP_Revise 473_ME_ZoneWallUnit_HST200 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:09:42+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:38:30+02:00 | N | N |  | Y | Y
72395 | MEP_Revise 473_PA_3WayMotorControlValve_Threaded | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:10:17+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-12T08:58:50+02:00 | N | N |  | Y | Y
72396 | MEP_Revise 473_PA_AGSSOutletType1L | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:10:59+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T11:45:05+02:00 | N | N |  | Y | Y
72397 | MEP_Revise 473_PA_AirHeader_8Connection | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:11:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:37:58+02:00 | N | N |  | Y | Y
72398 | MEP_Revise 473_PA_AirHeader_10Connection | 2026-05-28 | 2026-08-17 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:12:08+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-17T11:34:00+02:00 | N | N |  | Y | Y
72399 | MEP_Revise 473_PA_AirHeader_12Connection | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:12:46+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-30T11:42:04+02:00 | N | N |  | Y | Y
72400 | MEP_Revise 473_PA_AirHeader_14Connection | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:13:29+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-30T11:41:50+02:00 | N | N |  | Y | Y
72401 | MEP_Revise 473_PA_AirHeader_16Connection | 2026-05-28 | 2026-07-31 | 47 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-28T06:14:12+02:00 ¦¦ END: s.duong: Thank you. This ticket will be closed. @ 2026-07-31T12:09:20+02:00 | N | N |  | Y | Y
72402 | MEP_Revise 473_PA_AirHeader_18Connection | 2026-05-28 | 2026-07-31 | 47 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-28T06:14:49+02:00 ¦¦ END: s.duong: Thank you. This ticket will be closed. @ 2026-07-31T12:10:07+02:00 | N | N |  | Y | Y
72403 | MEP_Revise 473_PA_AirPressureRegulator_Mapress | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:15:39+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-30T11:30:17+02:00 | N | N |  | Y | Y
72404 | MEP_Revise 473_PA_AirRegulatorValve_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:16:18+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-30T11:30:02+02:00 | N | N |  | Y | Y
72405 | MEP_Revise 473_PA_AirVentingFilters_Standard | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:16:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-04T04:50:53+02:00 | N | N |  | Y | Y
72406 | MEP_Revise 473_PA_AutoDrainValve_FloatType_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:17:27+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-30T11:28:59+02:00 | N | N |  | Y | Y
72407 | MEP_Revise 473_PA_AutomaticMechanicalCondensateDrain | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:18:03+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T11:10:06+02:00 | N | N |  | Y | Y
72408 | MEP_Revise 473_PA_BallValve_Threaded | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:18:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T11:09:41+02:00 | N | N |  | Y | Y
72409 | MEP_Revise 473_PA_BR_3WayMotorControlValve_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:19:18+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-30T11:28:46+02:00 | N | N |  | Y | N
72410 | MEP_Revise 473_PA_BR_3WayValveDN15toDN50_Threaded | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:20:00+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:47:27+02:00 | N | N |  | Y | Y
72411 | MEP_Revise 473_PA_BR_AirReliefValve_Threaded | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:20:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:47:39+02:00 | N | N |  | Y | Y
72412 | MEP_Revise 473_PA_Brass_CheckValve_Threaded | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:21:05+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:47:55+02:00 | N | N |  | Y | Y
72413 | MEP_Revise 473_PA_ClampedStraightSightGlass | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:21:39+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T05:29:54+02:00 | N | N |  | Y | Y
72414 | MEP_Revise 473_PA_CompressedAirFilters_DDp | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:22:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:48:22+02:00 | N | N |  | Y | Y
72416 | MEP_Revise 473_PA_CompressedAirFilters_QDT | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:23:08+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:48:33+02:00 | N | N |  | Y | Y
72417 | MEP_Revise 473_PA_CondensateDistributor2Branch_WOSCD | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:23:43+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:48:45+02:00 | N | N |  | Y | Y
72418 | MEP_Revise 473_PA_CondensateDistributor4Branch_WOSCD | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:24:13+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:49:45+02:00 | N | N |  | Y | Y
72419 | MEP_Revise 473_PA_CondensateDistributor8Branch_WOSCD | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:24:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T11:08:17+02:00 | N | N |  | Y | Y
72420 | MEP_Revise 473_PA_CondensateDistributor12Branch_WOSCD | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:26:10+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:50:01+02:00 | N | N |  | Y | Y
72421 | MEP_Revise 473_PA_CS_PressureReducingValve_Flanged | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:26:47+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-03T02:50:15+02:00 | N | N |  | Y | Y
72422 | MEP_Revise 473_PA_CycloneSeparator_Standard | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:27:27+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-04T04:52:36+02:00 | N | N |  | Y | Y
72424 | MEP_Revise 473_PA_ElectronicCondensateDrain | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:29:11+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-07T11:08:04+02:00 | N | N |  | Y | Y
72425 | MEP_Revise 473_PA_ElectronicMotorizedValve | 2026-05-28 | 2026-08-14 | 57 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:29:51+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-14T11:31:17+02:00 | N | N |  | Y | Y
72426 | MEP_Revise 473_PA_Filters_Flanged | 2026-05-28 | 2026-08-17 | 58 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:31:04+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-17T11:33:49+02:00 | N | N |  | Y | Y
72427 | MEP_Revise 473_PA_Filters_Welded | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:31:41+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T06:46:53+02:00 | N | N |  | Y | N
72428 | MEP_Revise 473_PA_GasN2_Outlet | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:32:04+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T09:31:46+02:00 | N | N |  | Y | N
72429 | MEP_Revise 473_PA_GasO2Outlet | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:33:14+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-04T04:51:50+02:00 | N | N |  | Y | Y
72430 | MEP_Revise 473_PA_LineBallValve_LV10_V | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:35:36+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:37:23+02:00 | N | N |  | Y | Y
72431 | MEP_Revise 473_PA_LineBallValve_LV10VF | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:36:10+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T11:56:11+02:00 | N | N |  | Y | Y
72432 | MEP_Revise 473_PA_LockableLineBallValve_LVL10 | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:37:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T09:31:50+02:00 | N | N |  | Y | N
72433 | MEP_Revise 473_PA_LockableLineBallValve_LVL20 | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:38:23+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T09:31:52+02:00 | N | N |  | Y | N
72434 | MEP_Revise 473_PA_LockableLineBallValve_NIST | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:38:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-10-01T09:31:54+02:00 | N | N |  | Y | N
72435 | MEP_Revise 473_PA_MembraneAirDryers | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:40:08+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-24T11:44:44+02:00 | N | N |  | Y | Y
72436 | MEP_Revise 473_PA_MotorizedPneumaticDiaphragmValve_Welded | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:40:43+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T05:31:01+02:00 | N | N |  | Y | Y
72438 | MEP_Revise 473_PA_N2OOutlet | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:41:24+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T05:31:42+02:00 | N | N |  | Y | Y
72439 | MEP_Revise 473_PA_NRVValve | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:41:56+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T04:47:48+02:00 | N | N |  | Y | Y
72440 | MEP_Revise 473_PA_PlasticBox_Air | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:42:28+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T06:31:46+02:00 | N | N |  | Y | Y
72441 | MEP_Revise 473_PA_PneumaticButterflyValve_Welded | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:43:05+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-24T11:44:47+02:00 | N | N |  | Y | Y
72442 | MEP_Revise 473_PA_PneumaticDiaphragmValveWithAlarm | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:43:36+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-24T11:44:51+02:00 | N | N |  | Y | Y
72443 | MEP_Revise 473_PA_PneumaticManualDiaphragmValve | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:44:06+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-24T11:44:54+02:00 | N | N |  | Y | Y
72444 | MEP_Revise 473_PA_PressureGauge_ElectricalContactCodeA | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:44:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-24T11:44:57+02:00 | N | N |  | Y | Y
72445 | MEP_Revise 473_PA_RectangularPressureRegulator | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:45:01+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T03:23:15+02:00 | N | N |  | Y | Y
72446 | MEP_Revise 473_PA_SafetyValve | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:45:29+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T03:23:18+02:00 | N | N |  | Y | Y
72447 | MEP_Revise 473_PA_ShutOffValveBox_MultiConnection | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:46:01+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T03:23:21+02:00 | N | N |  | Y | Y
72448 | MEP_Revise 473_PA_SingleZone_ValveBox | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:46:32+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T11:41:19+02:00 | N | N |  | Y | Y
72449 | MEP_Revise 473_PA_SS_AirHeader_4Connection | 2026-05-28 | 2026-07-23 | 41 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:47:04+02:00 ¦¦ END: status→resolved @ 2026-07-23T09:37:38+02:00 | N | N |  | Y | N
72450 | MEP_Revise 473_PA_SS_AirHeader_6Connection | 2026-05-28 | 2026-07-24 | 42 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T06:47:33+02:00 ¦¦ END: status→resolved @ 2026-07-24T09:58:08+02:00 | N | N |  | Y | N
72451 | MEP_Revise 473_PA_SS_CouplingsFemale_Threaded | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:47:57+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T03:23:25+02:00 | N | N |  | Y | Y
72452 | MEP_Revise 473_PA_SS_HighPressureProcessFilters_Welded | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:48:33+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T11:41:22+02:00 | N | N |  | Y | Y
72453 | MEP_Revise 473_PA_SS_PressureGauge_AnalogueType | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:49:03+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T11:41:25+02:00 | N | N |  | Y | Y
72454 | MEP_Revise 473_PA_SS_PressureReducingValve_Flanged | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:50:02+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T11:41:29+02:00 | N | N |  | Y | Y
72455 | MEP_Revise 473_PA_SS_WeldedCondensateSeparators | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:50:31+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T06:33:13+02:00 | N | N |  | Y | Y
72456 | MEP_Revise 473_PA_StainlessSteel1WayValve | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:51:06+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T06:48:39+02:00 | N | N |  | Y | Y
72457 | MEP_Revise 473_PA_StainlessSteelFlexibleConnection | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:51:40+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T07:44:01+02:00 | N | N |  | Y | Y
72458 | MEP_Revise 473_PA_SterileFilters_SFSeries_Flanged | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:52:08+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-19T07:54:46+02:00 | N | N |  | Y | Y
72459 | MEP_Revise 473_PA_VAC_Outlet | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:52:30+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T11:48:32+02:00 | N | N |  | Y | Y
72460 | MEP_Revise 473_PA_WaterOilSeparators_WOS | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:52:57+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-25T11:48:29+02:00 | N | N |  | Y | Y
72461 | MEP_Revise 473_PA_WaterOilSeparators_WOSm | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T06:53:39+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-27T04:28:37+02:00 | N | N |  | Y | Y
72464 | 410_PF_GS_eAngleBend_1PushSocket_GMX | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-17T07:02:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T08:03:53+02:00 | N | N |  | Y | Y
72465 | 434_PF_CO_uAdaptorUnion_PlainEnd_WithMeplaFix | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-05-28T09:15:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-08T08:25:22+02:00 | N | N |  | Y | Y
72466 | 434_PF_CO_uAdaptorUnion_PlainEndAndThreadGas | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-05-28T09:09:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-03T08:32:46+02:00 | N | N |  | Y | Y
72467 | 434_PF_CO_uAdaptorUnion_MapressAndThreadGas | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-05-28T09:08:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-03T06:29:32+02:00 | N | N |  | Y | Y
72468 | 434_PF_CO_uAdaptorUnion_MapressAndThreadFKMBlue | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-05-28T09:08:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-08T08:03:35+02:00 | N | N |  | Y | Y
72471 | 434_PF_CO_uAdaptorUnion_MapressAndThread | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-05-28T09:15:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-30T08:25:13+02:00 | N | N |  | Y | Y
72478 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThreadFKMBlue_WithNut | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-05-28T10:36:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-10T08:50:34+02:00 | N | N |  | Y | Y
72479 | 434_PF_CO_uAdaptorUnion_Mapress | 2026-05-28 | 2026-08-20 | 61 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-05-28T10:35:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T08:15:21+02:00 | N | N |  | Y | Y
72480 | 434_PF_CO_rReducerAdaptor_PlainEnd_WithMeplaFixAdaptor | 2026-05-28 | 2026-06-09 | 9 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-05-28T10:35:52+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-09T10:25:10+02:00 | N | N |  | Y | Y
72481 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFixAdaptor | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-05-28T10:26:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-08T05:29:50+02:00 | N | N |  | Y | Y
72482 | 434_PF_CO_eAdaptorBend_MapressAndThreadGas | 2026-05-28 | 2026-06-24 | 20 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-05-28T10:26:08+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-24T03:02:00+02:00 | N | N |  | Y | Y
72483 | 434_PF_CO_eAdaptorBend_MapressAndThreadFKMBlue | 2026-05-28 | 2026-07-29 | 45 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-05-28T10:25:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T06:32:58+02:00 | N | N |  | Y | Y
72484 | 434_PF_CO_eAdaptorBend_MapressAndThread | 2026-05-28 | 2026-06-09 | 9 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-05-28T10:25:48+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-09T10:26:36+02:00 | N | N |  | Y | Y
72485 | 434_PF_CO_Union_MapressGas | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-05-28T10:25:36+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-10T08:56:09+02:00 | N | N |  | Y | Y
72486 | MEP_Revise 473_PF_CO_cEndCap_Soldered | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:31:31+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-28T12:00:01+02:00 | N | N |  | Y | Y
72487 | MEP_Revise 473_PF_CO_eElbow_Reduce_Soldered | 2026-05-28 | 2026-06-29 | 23 | handler_assign | status_resolved | START: handler→s.duong @ 2026-05-28T10:42:24+02:00 ¦¦ END: status→resolved @ 2026-06-29T04:16:33+02:00 | N | N |  | Y | N
72488 | MEP_Revise 473_PF_CO_eElbow45_FemaleAndFemaleSoldered | 2026-05-28 | 2026-07-16 | 36 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:43:01+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-16T10:06:51+02:00 | N | N |  | Y | Y
72489 | MEP_Revise 473_PF_CO_eElbow45_MaleAndFemaleSoldered | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:43:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-10T04:26:07+02:00 | N | N |  | Y | Y
72490 | MEP_Revise 473_PF_CO_eElbow180_Soldered | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:will_be_closed | START: handler→s.duong @ 2026-05-28T10:44:58+02:00 ¦¦ END: s.duong: Thank you. This ticket will be closed. @ 2026-07-28T11:06:56+02:00 | N | N |  | Y | Y
72491 | MEP_Revise 473_PF_CO_eElbowLongRadiusFF_Soldered | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:46:27+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-28T03:18:54+02:00 | N | N |  | Y | Y
72492 | MEP_Revise 473_PF_CO_eElbowShortRadiusMF_Soldered | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:47:18+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-10T08:36:19+02:00 | N | N |  | Y | Y
72493 | MEP_Revise 473_PF_CO_eLongRadius_MFSoldered | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:48:00+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T06:56:22+02:00 | N | N |  | Y | Y
72494 | MEP_Revise 473_PF_CO_eLongRadius_Soldered | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:48:49+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-18T06:56:09+02:00 | N | N |  | Y | Y
72495 | MEP_Revise 473_PF_CO_eOffset_M_F_Soldered | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:49:50+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T05:52:07+02:00 | N | N |  | Y | Y
72496 | MEP_Revise 473_PF_CO_eShortRadiusFF_Soldered | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | START: handler→s.duong @ 2026-05-28T10:50:37+02:00 ¦¦ END: hu.dam: @s.duong This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-07-30T11:31:08+02:00 | N | N |  | Y | Y
72519 | RLT_Symbol_Detail Item Setup | 2026-05-29 | 2026-06-04 | 5 | handler_assign | status_resolved | START: handler→n.bui @ 2026-05-29T09:02:46+02:00 ¦¦ END: status→resolved @ 2026-06-04T03:09:17+02:00 | N | N |  | Y | N
72521 | 410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC | 2026-06-02 | 2026-07-15 | 32 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-02T10:30:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T05:54:20+02:00 | N | N |  | Y | Y
72522 | 410_PF_HDPE_eBend88DegWithLateralSupplementary_Standard_ForFloorStandingWC | 2026-06-02 | 2026-06-05 | 4 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-02T10:32:09+02:00 ¦¦ END: status→resolved @ 2026-06-05T10:55:04+02:00 | N | N |  | Y | N
72523 | 410_PF_HDPE_eConnectionBend90Deg_Standard_ForSleeve | 2026-06-02 | 2026-06-05 | 4 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-02T10:33:05+02:00 ¦¦ END: status→resolved @ 2026-06-05T10:58:15+02:00 | N | N |  | Y | N
72524 | 410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC | 2026-06-02 | 2026-09-15 | 76 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-02T10:33:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T07:12:33+02:00 | N | N |  | Y | Y
72525 | 410_PF_HDPE_eRightOffsetBend90Deg_Standard_ForFloorStandingWC | 2026-06-02 | 2026-06-08 | 5 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-02T10:34:16+02:00 ¦¦ END: status→resolved @ 2026-06-08T11:09:18+02:00 | N | N |  | Y | N
72526 | 410_PF_HDPE_eScrewCap | 2026-06-16 | 2026-07-14 | 21 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-16T10:24:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T09:41:09+02:00 | N | N |  | Y | Y
72527 | 410_PF_HDPE_eSegmentBend_Welded | 2026-06-02 | 2026-08-14 | 54 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-02T10:35:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T11:32:40+02:00 | N | N |  | Y | Y
72528 | 410_PF_HDPE_tDoubleConnectionBend90Deg_ForSleeve | 2026-06-02 | 2026-09-21 | 80 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-02T10:36:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T10:25:58+02:00 | N | N |  | Y | Y
72529 | 410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC | 2026-06-02 | 2026-06-16 | 11 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-02T10:36:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-16T07:34:40+02:00 | N | N |  | Y | Y
72530 | 410_PF_HDPE_tDoubleConnectionBend90Deg_SlipJoint_VerticalForWallHungWC | 2026-06-02 | 2026-09-17 | 78 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-02T10:38:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:50:00+02:00 | N | N |  | Y | Y
72531 | 410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded | 2026-06-03 | 2026-08-14 | 53 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-03T06:12:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T05:50:31+02:00 | N | N |  | Y | Y
72532 | 410_PF_HDPE_mRunningTrap_Standard | 2026-06-03 | 2026-08-14 | 53 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-03T06:12:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T05:51:09+02:00 | N | N |  | Y | Y
72533 | 410_PF_HDPE_mSoventFitting_Welded | 2026-06-03 | 2026-07-14 | 30 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-03T06:13:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T10:56:51+02:00 | N | N |  | Y | Y
72534 | 440_EE_AutomaticTranferSwitchPanel.rfa | 2026-05-29 | 2026-08-18 | 58 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-05-29T10:50:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T05:29:06+02:00 | N | N |  | Y | Y
72535 | 440_EE_BatteryStorage.rfa | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-05-29T10:56:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:26:18+02:00 | N | N |  | Y | Y
72536 | 442_EE_ChargeController.rfa | 2026-05-29 | 2026-09-15 | 78 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-05-29T10:59:19+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:15+02:00 | N | N |  | Y | Y
72537 | 410_PF_HDPE_mSTrap_Standard | 2026-06-03 | 2026-06-22 | 14 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-03T06:14:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-22T03:24:10+02:00 | N | N |  | Y | Y
72538 | 440_EE_CircuitBreakerEnclosure.rfa | 2026-05-29 | 2026-09-18 | 81 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-05-29T11:01:43+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:42:58+02:00 | N | N |  | Y | Y
72539 | 410_PF_HDPE_mUniversalTrap_WithFlangeBushing | 2026-06-03 | 2026-06-19 | 13 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-03T06:15:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T08:45:07+02:00 | N | N |  | Y | Y
72540 | 440_EE_DCtoAC_Inverter.rfa | 2026-05-29 | 2026-08-14 | 56 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-05-29T11:04:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T05:50:45+02:00 | N | N |  | Y | Y
72541 | 410_PF_HDPE_mWasteManifold | 2026-06-03 | 2026-07-15 | 31 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-03T06:17:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T05:41:47+02:00 | N | N |  | Y | Y
72542 | 410_PF_HDPE_rAdaptorSocket_DN90xDN100 | 2026-06-03 | 2026-07-03 | 23 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-03T09:46:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T05:53:33+02:00 | N | N |  | Y | Y
72543 | 440_EE_DieselGenerator.rfa | 2026-05-29 | 2026-09-18 | 81 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-05-29T11:06:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:06:26+02:00 | N | N |  | Y | Y
72544 | 410_PF_HDPE_rCompressionJoint_MechanicalJoint | 2026-06-03 | 2026-09-17 | 77 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-03T06:22:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:50:05+02:00 | N | N |  | Y | Y
72545 | 440_EE_DieselTankGenerator.rfa | 2026-05-29 | 2026-08-17 | 57 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-05-29T11:08:38+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T11:34:12+02:00 | N | N |  | Y | Y
72546 | 410_PF_HDPE_rReducer_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-03T06:23:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T03:16:53+02:00 | N | N |  | Y | Y
72547 | 410_PF_HDPE_mReducedRingSealSocket_Socket | 2026-06-03 | 2026-09-17 | 77 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-03T06:23:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:50:10+02:00 | N | N |  | Y | Y
72548 | 410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC | 2026-06-03 | 2026-07-03 | 23 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-03T09:46:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T05:52:16+02:00 | N | N |  | Y | Y
72549 | 410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded | 2026-06-03 | 2026-06-19 | 13 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-03T06:28:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-19T09:29:50+02:00 | N | N |  | Y | Y
72550 | 410_PF_HDPE_tLateralTee_Welded | 2026-06-10 | 2026-07-15 | 26 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-10T03:25:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T06:10:31+02:00 | N | N |  | Y | Y
72551 | 410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-03T06:30:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T03:32:08+02:00 | N | N |  | Y | Y
72552 | 410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded | 2026-06-03 | 2026-07-06 | 24 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-03T06:30:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-06T04:20:57+02:00 | N | N |  | Y | Y
72553 | 410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-03T06:31:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T03:33:35+02:00 | N | N |  | Y | Y
72554 | 410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-03T06:31:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T03:35:06+02:00 | N | N |  | Y | Y
72555 | 410_PF_HDPE_uAdapterUnion_FemaleThreaded | 2026-06-03 | 2026-08-21 | 58 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-03T06:32:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T10:27:51+02:00 | N | N |  | Y | Y
72556 | 410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint | 2026-06-03 | 2026-07-08 | 26 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-03T06:32:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-08T05:22:56+02:00 | N | N |  | Y | Y
72557 | 410_PF_HDPE_rReducerAdaptor_MaleThreaded | 2026-06-10 | 2026-08-21 | 53 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-10T03:19:11+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T10:34:21+02:00 | N | N |  | Y | Y
72558 | 410_PF_HDPE_uClampingConnector | 2026-06-10 | 2026-06-30 | 15 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-10T03:20:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-30T04:43:57+02:00 | N | N |  | Y | Y
72559 | 410_PF_HDPE_uExpansion_Socket | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T05:33:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T11:40:32+02:00 | N | N |  | Y | Y
72560 | 410_PF_HDPE_uFlangeAdapter_Standard | 2026-06-09 | 2026-09-17 | 73 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-09T06:42:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:50:14+02:00 | N | N |  | Y | Y
72561 | 410_PF_HDPE_uFlangeBushing_Standard | 2026-06-09 | 2026-09-17 | 73 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-09T06:43:17+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T09:11:58+02:00 | N | N |  | Y | Y
72565 | 434_PF_CO_Union_MapressFKMBlue | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T09:13:42+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-23T03:13:36+02:00 | N | N |  | Y | Y
72566 | 434_PF_CO_Union_Mapress | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T09:13:39+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T03:24:46+02:00 | N | N |  | Y | Y
72567 | 434_PF_CO_Transition_MapressGas | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T09:13:35+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T10:03:22+02:00 | N | N |  | Y | Y
72568 | 434_PF_CO_Transition_MapressFKMBlue | 2026-06-01 | 2026-07-30 | 44 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T03:37:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-30T03:22:28+02:00 | N | N |  | Y | Y
72569 | 434_PF_CO_Transition_Mapress | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T03:37:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-11T03:31:32+02:00 | N | N |  | Y | Y
72570 | 434_PF_CO_Tee_MapressGas | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T03:36:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T11:40:24+02:00 | N | N |  | Y | Y
72571 | 434_PF_CO_Tee_MapressGas&FemaleThread | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T03:29:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-11T06:07:34+02:00 | N | N |  | Y | Y
72572 | 434_PF_CO_Tee_MapressFKMBlue | 2026-06-01 | 2026-06-15 | 11 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T03:29:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-15T09:08:31+02:00 | N | N |  | Y | Y
72573 | 434_PF_CO_Tee_MapressFKMBlue&FemaleThread | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T03:29:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T10:41:10+02:00 | N | N |  | Y | Y
72574 | 434_PF_CO_Tee_Mapress | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T03:29:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T10:42:10+02:00 | N | N |  | Y | Y
72575 | 434_PF_CO_Tee_Mapress&FemaleThread | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-01T03:28:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T10:43:35+02:00 | N | N |  | Y | Y
72576 | 434_PF_CO_ReducerAdaptor_PlainEndAndClampingRing | 2026-06-01 | 2026-06-09 | 7 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-01T03:28:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-09T09:19:33+02:00 | N | N |  | Y | Y
72577 | 434_PF_CO_Cap_MapressGas | 2026-06-01 | 2026-06-09 | 7 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-01T03:27:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-09T09:20:04+02:00 | N | N |  | Y | Y
72578 | 434_PF_CO_Cap_MapressFKMBlue | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T03:26:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-28T10:47:51+02:00 | N | N |  | Y | Y
72579 | 434_PF_CO_Cap_Mapress | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T03:26:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-11T06:05:42+02:00 | N | N |  | Y | Y
72580 | 434_PF_CO_BridgeBendMultiPort_MapressGas | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T03:26:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T08:39:08+02:00 | N | N |  | Y | N
72581 | 434_PF_CO_Bend_MapressGas | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T03:26:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-11T05:45:07+02:00 | N | N |  | Y | Y
72582 | 420_PF_CS_eElbow_Welded | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-01T09:23:34+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-06T11:25:39+02:00 | N | N |  | Y | Y
72583 | 420_PF_CS_cCap_Welded | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-01T09:23:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-06T11:25:53+02:00 | N | N |  | Y | Y
72584 | 420_PF_CO_xCross_Soldered | 2026-06-01 | 2026-07-08 | 28 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-01T09:23:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-08T05:22:14+02:00 | N | N |  | Y | Y
72585 | 420_PF_CO_uUnion_Soldered | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-01T09:23:20+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-06T11:26:07+02:00 | N | N |  | Y | Y
72586 | 420_PF_CO_tTee_Soldered | 2026-06-01 | 2026-07-15 | 33 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-01T09:23:16+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-15T08:54:04+02:00 | N | N |  | Y | Y
72587 | 420_PA_YStrainer_Thread | 2026-06-01 | 2026-07-27 | 41 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-01T09:24:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-27T03:43:16+02:00 | N | N |  | Y | Y
72588 | 420_PA_YStrainer_Flanged | 2026-06-01 | 2026-08-12 | 53 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-01T09:24:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-12T04:24:10+02:00 | N | N |  | Y | Y
72589 | 420_PA_YStrainerValve_Thread_Standard | 2026-06-01 | 2026-07-27 | 41 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-01T09:24:16+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-27T03:43:01+02:00 | N | N |  | Y | Y
72590 | 420_PA_YStrainerValve_Flanged_Standard | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-01T09:24:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-23T03:08:40+02:00 | N | N |  | Y | Y
72591 | 420_PA_WaterMeter_Threaded | 2026-06-01 | 2026-06-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-01T09:24:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-19T08:45:41+02:00 | N | N |  | Y | Y
72592 | 410_PF_HDPE_fFlangeSet_Standard | 2026-06-09 | 2026-06-09 | 1 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-09T06:44:03+02:00 ¦¦ END: status→resolved @ 2026-06-09T11:14:52+02:00 | N | N |  | Y | N
72593 | 420_PA_WaterMeter_Flanged_Standard | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-01T09:25:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T07:31:40+02:00 | N | N |  | Y | Y
72594 | 420_PA_WaterMeter_Flanged | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-01T09:25:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:43:47+02:00 | N | N |  | Y | Y
72595 | 420_PA_WaferCheckValve_Flanged_Standard | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-01T09:25:08+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:43:50+02:00 | N | N |  | Y | Y
72596 | 410_PF_HDPE_uStraightAdapterToCastIronPipe | 2026-06-09 | 2026-07-07 | 21 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-09T06:44:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-07T03:45:02+02:00 | N | N |  | Y | Y
72597 | 420_PA_ThreeWayvalve_Thread_Standard | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-01T09:25:04+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T07:31:45+02:00 | N | N |  | Y | Y
72598 | 420_PA_ThreeWayvalve_Flanged_Standard | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-01T03:24:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-28T07:21:24+02:00 | N | N |  | Y | Y
72599 | 420_PA_Thermometergauge | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-01T03:24:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T10:27:49+02:00 | N | N |  | Y | Y
72600 | 420_PA_Thermometer | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-01T03:23:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-28T03:21:45+02:00 | N | N |  | Y | Y
72601 | 410_PF_HDPE_uStraightAdapterHDPEToPVC_ButtFusionAndPushOnJoint | 2026-06-10 | 2026-07-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-10T03:33:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T11:35:32+02:00 | N | N |  | Y | Y
72602 | 420_PA_TemperatureSensor | 2026-06-01 | 2026-07-03 | 25 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-01T03:23:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-03T08:50:36+02:00 | N | N |  | Y | Y
72603 | 420_PA_TemperatureGauge_Standard | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-01T03:22:29+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-28T03:10:58+02:00 | N | N |  | Y | Y
72604 | 420_PA_SwingcheckValve_Threaded | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-01T03:22:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T10:26:50+02:00 | N | N |  | Y | Y
72605 | 410_PF_HDPE_uStraightAdapter_CompressionAndSpigot | 2026-06-10 | 2026-08-11 | 45 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-10T03:34:05+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T11:21:45+02:00 | N | N |  | Y | Y
72606 | 410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard | 2026-06-10 | 2026-08-03 | 39 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-10T03:34:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-03T04:19:21+02:00 | N | N |  | Y | Y
72607 | 410_PF_HDPE_uStraightConnectorForWC_ButtFusionAndPushOnJoint | 2026-06-10 | 2026-07-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-10T03:36:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T10:24:13+02:00 | N | N |  | Y | Y
72608 | 410_PF_HDPE_uStraightConnector_ForFloorStandingWC | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-10T03:36:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T03:13:10+02:00 | N | N |  | Y | Y
72609 | 410_PF_HDPE_uUnion_FemaleThreadAndCompression | 2026-06-10 | 2026-08-12 | 46 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-10T03:37:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:56:50+02:00 | N | N |  | Y | Y
72610 | 410_PF_HDPE_uUnionConnection_WeldingJoints | 2026-06-10 | 2026-07-29 | 36 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-10T03:38:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T03:27:16+02:00 | N | N |  | Y | Y
72611 | 410_PF_HDPE_xDoubleBrandFitting45Deg_Welded | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-10T03:38:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T03:16:52+02:00 | N | N |  | Y | Y
72612 | 410_PF_GA_mPTrapGMX_Standard | 2026-06-10 | 2026-07-29 | 36 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-10T03:39:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T06:25:31+02:00 | N | N |  | Y | Y
72614 | 410_PF_mHDPE_PTrap | 2026-06-10 | 2026-08-04 | 40 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-10T03:39:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T04:54:04+02:00 | N | N |  | Y | Y
72618 | 410_PF_PE_eBendForWandWC | 2026-06-10 | 2026-08-04 | 40 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-10T03:44:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T06:44:56+02:00 | N | N |  | Y | Y
72621 | 434_PF_CO_Bend_MapressFKMBlue | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T09:13:32+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T03:16:17+02:00 | N | N |  | Y | Y
72622 | 434_PF_CO_Bend_Mapress | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-01T09:13:29+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T02:27:11+02:00 | N | N |  | Y | Y
72623 | 434_PF_CO_AdaptorUnion_PlainEndAndFlange | 2026-06-01 | 2026-06-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T09:12:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-19T08:48:24+02:00 | N | N |  | Y | Y
72624 | 434_PF_CO_AdaptorUnion_MapressAndFlangeGas | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T09:12:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T05:58:56+02:00 | N | N |  | Y | Y
72625 | 434_PF_CO_AdaptorUnion_FemaleThreadAndMeplaFix | 2026-06-01 | 2026-07-01 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T09:12:47+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-01T04:41:56+02:00 | N | N |  | Y | Y
72626 | 434_PF_CO_AdaptorMultiPort_MapressAndNut | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T09:12:44+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T02:26:54+02:00 | N | N |  | Y | Y
72627 | 434_PF_CO_30Cross_Mapress | 2026-06-01 | 2026-07-06 | 26 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-01T09:12:40+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-06T03:05:19+02:00 | N | N |  | Y | Y
72628 | 434_PA_RefnetJoint_KHRPLiquid | 2026-06-01 | 2026-06-10 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-01T09:10:22+02:00 ¦¦ END: status→resolved @ 2026-06-10T11:30:25+02:00 | N | N |  | Y | N
72629 | 434_PA_RefnetJoint_KHRPGas | 2026-06-01 | 2026-06-09 | 7 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-01T09:10:19+02:00 ¦¦ END: status→resolved @ 2026-06-09T08:43:45+02:00 | N | N |  | Y | N
72630 | 434_PA_RefnetJoint_KHRPDischarge | 2026-06-01 | 2026-06-09 | 7 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-01T09:10:15+02:00 ¦¦ END: status→resolved @ 2026-06-09T08:44:39+02:00 | N | N |  | Y | N
72631 | 434_PA_RefnetHeader_KHRPLiquid8Branches | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-01T09:10:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:43:55+02:00 | N | N |  | Y | Y
72632 | 434_PA_RefnetHeader_KHRPLiquid4Branches | 2026-06-01 | 2026-07-02 | 24 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-01T09:10:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-02T03:22:40+02:00 | N | N |  | Y | Y
72633 | 434_PA_RefnetHeader_KHRPHP&LPGas | 2026-06-01 | 2026-09-10 | 74 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-01T09:09:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T06:27:23+02:00 | N | N |  | Y | Y
72634 | 434_PA_RefnetHeader_KHRPGas8Branches | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-01T09:09:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T07:31:49+02:00 | N | N |  | Y | Y
72635 | 434_PA_RefnetHeader_KHRPGas4Branches | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-01T09:09:16+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T09:03:22+02:00 | N | N |  | Y | Y
72636 | 434_PA_MultiConnectionPipingKit2_BHFPLiquid | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-01T09:09:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T09:34:34+02:00 | N | N |  | Y | Y
72637 | 434_PF_CO_eBend_MapressFKMBlue.rfa | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-01T09:09:08+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-22T04:32:38+02:00 | N | N |  | Y | Y
72638 | 410_PF_PPR_cEndCap_SocketFusion | 2026-06-10 | 2026-07-02 | 17 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-10T03:45:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-02T03:48:20+02:00 | N | N |  | Y | Y
72639 | 434_PA_MultiConnectionPipingKit1_BHFPLiquid | 2026-06-01 | 2026-07-01 | 23 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T09:08:30+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-01T05:36:23+02:00 | N | N |  | Y | Y
72640 | 434_PA_MultiConnectionPipingKit1_BHFPGas | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T09:08:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T11:39:52+02:00 | N | N |  | Y | Y
72641 | 410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-10T03:46:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T03:15:53+02:00 | N | N |  | Y | Y
72642 | 434_PA_BranchProviderBox_BPMKS3Port | 2026-06-01 | 2026-06-30 | 22 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T09:08:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-30T04:45:58+02:00 | N | N |  | Y | Y
72643 | 434_PA_BranchProviderBox_BPMKS2Port | 2026-06-01 | 2026-06-30 | 22 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T09:08:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-30T04:43:02+02:00 | N | N |  | Y | Y
72644 | 434_ME_Watercooled_Condenserlessliquidchillers_30RW_30RWA_VerticalConnection | 2026-06-01 | 2026-09-22 | 82 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-01T09:08:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:08+02:00 | N | N |  | Y | Y
72645 | 410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-10T03:47:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T03:12:02+02:00 | N | N |  | Y | Y
72646 | 410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-10T03:48:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T03:14:50+02:00 | N | N |  | Y | Y
72647 | 410_PF_PPR_eElbow_SocketFusion | 2026-06-10 | 2026-07-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-10T03:58:04+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T10:48:21+02:00 | N | N |  | Y | Y
72648 | 410_PF_PPR_mCoupling_FemaleThreadAndSocketFusion | 2026-06-10 | 2026-08-21 | 53 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-10T04:00:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T10:28:23+02:00 | N | N |  | Y | Y
72649 | 410_PF_PPR_mCoupling_MaleThreadAndSocketFusion | 2026-06-10 | 2026-06-17 | 6 | handler_assign | status_resolved | START: handler→n.vo @ 2026-06-10T04:01:38+02:00 ¦¦ END: status→resolved @ 2026-06-17T09:18:03+02:00 | N | N |  | Y | N
72650 | 420_PA_SwingcheckValve_Flanged | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-01T09:24:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:43:57+02:00 | N | N |  | Y | Y
72651 | 410_PF_PPR_eElbow90Deg_MaleThreadAndSocketFusion | 2026-06-10 | 2026-07-30 | 37 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-10T04:02:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-30T08:29:07+02:00 | N | N |  | Y | Y
72652 | 420_PA_SwingCheckValve_Thread_Standard | 2026-06-01 | 2026-06-16 | 12 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-01T09:26:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-06-16T10:15:44+02:00 | N | N |  | Y | Y
72653 | 420_PA_SwingCheckValve_Flanged_Standard | 2026-06-01 | 2026-10-01 | 89 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-01T09:26:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:31:24+02:00 | N | N |  | Y | N
72654 | 420_PA_SpringCheckValve_Flanged_Standard | 2026-06-01 | 2026-07-13 | 31 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-01T09:26:08+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-13T09:38:49+02:00 | N | N |  | Y | Y
72655 | 420_PA_SafetyValveCorner_Thread_Standard | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-01T09:26:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T02:26:15+02:00 | N | N |  | Y | Y
72656 | 410_PF_PPR_rReducing_SocketFusion | 2026-06-10 | 2026-07-02 | 17 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-10T11:29:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-02T06:18:23+02:00 | N | N |  | Y | Y
72657 | 420_PA_SafetyValveCorner_Flanged_Standard | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-01T09:26:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T02:26:38+02:00 | N | N |  | Y | Y
72658 | 420_PA_SafetyReliefValveStraight_Flanged | 2026-06-01 | 2026-09-15 | 77 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-01T09:27:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:29:32+02:00 | N | N |  | Y | Y
72659 | 420_PA_SafetyReliefValveCorner_Flanged | 2026-06-01 | 2026-08-12 | 53 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-01T09:27:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-12T04:22:21+02:00 | N | N |  | Y | Y
72660 | 420_PA_SafetyReliefValveConer_Thread | 2026-06-01 | 2026-08-11 | 52 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-01T09:26:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-11T05:57:17+02:00 | N | N |  | Y | Y
72661 | 410_PF_PPR_tTee_FemaleThreadedAndSocketFusion | 2026-06-10 | 2026-06-24 | 11 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-10T11:29:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-24T04:08:44+02:00 | N | N |  | Y | Y
72662 | 420_PA_RegulatingValve_Threaded | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-01T09:26:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-23T10:52:53+02:00 | N | N |  | Y | Y
72663 | 420_PA_RegulatingValve_Thread_Standard | 2026-06-01 | 2026-08-11 | 52 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-01T09:26:47+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-11T05:45:15+02:00 | N | N |  | Y | Y
72664 | 410_PF_PPR_tTee_MaleThreadedAndSocketFusion | 2026-06-10 | 2026-06-25 | 12 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-10T11:30:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-25T11:26:36+02:00 | N | N |  | Y | Y
72665 | 410_PF_PPR_tTee_SocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-12T03:09:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T12:13:37+02:00 | N | N |  | Y | Y
72666 | 410_PF_PPR_uCoupling_FemaleThreadAndSocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-12T03:09:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T12:15:42+02:00 | N | N |  | Y | Y
72667 | 410_PF_PPR_uCoupling_MaleThreadAndSocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-12T05:16:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T12:17:04+02:00 | N | N |  | Y | Y
72668 | 410_PF_PPR_uUnion_BushSocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-12T05:16:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T12:17:54+02:00 | N | N |  | Y | Y
72669 | 410_PF_PPR_uUnion_BushSocketFusion | 2026-06-25 | 2026-06-30 | 4 | handler_assign | status_resolved | START: handler→k.mai @ 2026-06-25T05:34:20+02:00 ¦¦ END: status→resolved @ 2026-06-30T05:23:24+02:00 | N | N |  | Y | Y
72671 | 410_PF_PPMD_xDuctBranchSweptEntry88DegLeft_SocketAndSpigot_Silent | 2026-06-12 | 2026-07-29 | 34 | handler_assign | confirm_note:passed_audit | START: handler→k.mai @ 2026-06-12T05:19:31+02:00 ¦¦ END: lk.dang: @hu.dam The family has passed audit process, please update the name in the graphical to upload. @ 2026-07-29T11:44:28+02:00 | N | N |  | Y | Y
72672 | 410_PF_PPMD_tBranchSweptEntry88Deg_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-12T05:20:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:56:15+02:00 | N | N |  | Y | Y
72673 | 410_PF_PPMD_tDoubleConnectionBend90Deg_Extended_Silent | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-12T05:22:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:56:28+02:00 | N | N |  | Y | Y
72674 | 410_PF_PP_uAccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent | 2026-06-12 | 2026-07-14 | 23 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-12T05:23:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T11:33:03+02:00 | N | N |  | Y | Y
72676 | 410_PF_EPDM_mSleeveToCastlron_MechanicalJoint_Silent | 2026-06-12 | 2026-06-18 | 5 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-06-12T05:24:45+02:00 ¦¦ END: status→resolved @ 2026-06-18T08:39:10+02:00 | N | N |  | Y | N
72678 | 410_PF_PPMD_eBend_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-12T05:25:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T08:35:40+02:00 | N | N |  | Y | Y
72679 | 410_PF_PP_tBranch_SocketSpigot_Silent | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-12T05:25:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T11:47:52+02:00 | N | N |  | Y | Y
72680 | 410_PF_PPMD_cEndCap_Socket_Silent | 2026-06-12 | 2026-06-16 | 3 | handler_assign | status_resolved | START: handler→ttc.bui @ 2026-06-12T05:27:37+02:00 ¦¦ END: status→resolved @ 2026-06-16T10:28:09+02:00 | N | N |  | Y | N
72681 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-13 | 45 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-12T05:35:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T08:55:38+02:00 | N | N |  | Y | Y
72682 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-13 | 45 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-12T05:37:38+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T11:23:45+02:00 | N | N |  | Y | Y
72683 | 420_PA_RegulatingValve_Flanged_Standard | 2026-07-13 | 2026-07-31 | 15 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-07-13T08:48:29+02:00 ¦¦ END: status→resolved @ 2026-07-31T03:03:47+02:00 | N | N |  | Y | N
72684 | 420_PA_RegulatingValve_Flanged | 2026-07-13 | 2026-07-31 | 15 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-07-13T08:48:29+02:00 ¦¦ END: status→resolved @ 2026-07-31T03:03:53+02:00 | N | N |  | Y | N
72686 | 420_PA_RadiatorThermostaticStraightValve_Thread | 2026-07-13 | 2026-07-29 | 13 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-07-13T08:48:29+02:00 ¦¦ END: status→resolved @ 2026-07-29T04:47:07+02:00 | N | N |  | Y | N
72687 | 420_PA_RadiatorThermostaticAngleValve_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-13T08:47:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:29:35+02:00 | N | N |  | Y | Y
72688 | 420_PA_RadiatorThermostatic2PointAngleValve_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-13T08:47:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:29:38+02:00 | N | N |  | Y | Y
72689 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-12T05:38:17+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:56:02+02:00 | N | N |  | Y | Y
72690 | 420_PA_RadiatorShutOffValveStraight_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-13T08:47:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:11:19+02:00 | N | N |  | Y | Y
72691 | 420_PA_RadiatorShutOffValveAngle_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-13T08:47:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T06:01:35+02:00 | N | N |  | Y | Y
72692 | 410_PF_PP_mOdorTrapForSinkHorizontal_Standard | 2026-06-12 | 2026-06-16 | 3 | handler_assign | status_resolved | START: handler→t.luu @ 2026-06-12T05:43:11+02:00 ¦¦ END: status→resolved @ 2026-06-16T11:14:57+02:00 | N | N |  | Y | Y
72693 | 420_PA_RadiatorLockshield_Thread | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-13T08:47:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T11:40:55+02:00 | N | N |  | Y | Y
72694 | 420_PA_PressureSensor_Standard | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-13T08:47:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T11:40:58+02:00 | N | N |  | Y | Y
72695 | 420_PA_PressureSensor | 2026-07-13 | 2026-08-12 | 23 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-07-13T08:46:04+02:00 ¦¦ END: status→resolved @ 2026-08-12T04:34:46+02:00 | N | N |  | Y | N
72696 | 410_PF_PP_mOdorTrapForSinkVertical_Standard | 2026-06-12 | 2026-06-17 | 4 | handler_assign | status_resolved | START: handler→n.vo @ 2026-06-12T05:44:44+02:00 ¦¦ END: status→resolved @ 2026-06-17T08:28:37+02:00 | N | N |  | Y | Y
72697 | 410_PF_PP_mOdorTrapForSinkVerticalAndHorizontal_Standard | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-12T05:46:27+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T08:35:14+02:00 | N | N |  | Y | Y
72699 | 410_PF_PPMD_wParallelBrand45Deg_SocketAndSpigot_Silent | 2026-06-15 | 2026-06-16 | 2 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-15T02:36:09+02:00 ¦¦ END: status→resolved @ 2026-06-16T10:01:10+02:00 | N | N |  | Y | N
72700 | 410_PF_PP_rReducerEccentric_SocketAndSpigot_Silent | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-15T02:37:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T06:16:49+02:00 | N | N |  | Y | Y
72705 | 410_PF_PP_uSlipCoupling_Silent | 2026-06-15 | 2026-06-16 | 2 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-15T02:38:10+02:00 ¦¦ END: status→resolved @ 2026-06-16T11:13:33+02:00 | N | N |  | Y | N
72707 | 410_PF_SilentPro_cCapEnd_Socket | 2026-06-17 | 2026-06-17 | 1 | handler_assign | confirm_note:will_be_closed | START: handler→tv.huynh @ 2026-06-17T08:55:27+02:00 ¦¦ END: tv.huynh: This is a duplicate of ticket #72710. This ticket will be closed accordingly. Thank you. @ 2026-06-17T08:55:19+02:00 | N | N |  | Y | N
72710 | 410_PF_SilentPro_cCapEnd_Socket | 2026-06-15 | 2026-06-25 | 9 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-15T02:39:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-25T11:46:06+02:00 | N | N |  | Y | N
72715 | 440_EE_DistributionBox_DALI.rfa | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-06-02T02:42:29+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T05:14:12+02:00 | N | N |  | Y | Y
72716 | 440_EE_DryTransformer.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-06-02T02:45:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T05:28:56+02:00 | N | N |  | Y | Y
72717 | 440_EE_ElectricalCabinet_Standard.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-06-02T02:52:04+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T05:43:02+02:00 | N | N |  | Y | Y
72718 | 440_EE_FlatRoofSolar.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-06-02T02:55:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T05:31:58+02:00 | N | N |  | Y | Y
72719 | 440_EE_FlatRoofSolarFrameWithRoot_NoSystem.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-06-02T03:03:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T03:06:06+02:00 | N | N |  | Y | Y
72720 | 410_PF_PPMX_eElbow_SocketAndSpigot_SilentPro | 2026-06-16 | 2026-08-17 | 45 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-16T10:59:16+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T10:59:34+02:00 | N | N |  | Y | Y
72721 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-17T02:52:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T08:55:23+02:00 | N | N |  | Y | Y
72722 | Annotation_Platform_Upgrade the function of feature | 2026-06-02 | 2026-06-05 | 4 | handler_assign | status_resolved | START: handler→nd.huynh @ 2026-06-02T03:06:24+02:00 ¦¦ END: status→resolved @ 2026-06-05T08:02:14+02:00 | N | N |  | Y | N
72723 | 410_PF_PPMD_mCornerBranch88Deg_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-17T02:52:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T06:20:18+02:00 | N | N |  | Y | Y
72724 | Annotation_Platform_Maintain the platform | 2026-06-02 |  |  | handler_assign | none | START: handler→nd.huynh @ 2026-06-02T03:10:57+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
72725 | 410_PF_PPMX_rReducerEccentric_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-07 | 38 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-17T02:53:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-07T11:11:14+02:00 | N | N |  | Y | Y
72726 | 410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-17T02:54:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T04:03:52+02:00 | N | N |  | Y | Y
72728 | 410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot | 2026-06-17 | 2026-07-28 | 30 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-17T02:55:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T05:59:59+02:00 | N | N |  | Y | Y
72729 | 410_PF_SilentPro_tTeeBranch_SocketSpigot | 2026-06-25 | 2026-07-27 | 23 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-25T05:35:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T11:34:35+02:00 | N | N |  | Y | Y
72730 | 410_PF_PPMD_uAccessPipe90DegWithRoundServiceOpening_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-24 | 49 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-17T02:55:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T08:17:06+02:00 | N | N |  | Y | Y
72731 | 410_PF_PPMX_uSlipCoupling_PushOnJoint_SilentPro | 2026-06-17 | 2026-08-17 | 44 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-17T02:56:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T11:38:06+02:00 | N | N |  | Y | Y
72732 | 410_PF_PPMX_wParallelBrand45Deg_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-24 | 49 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-17T02:57:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T04:21:29+02:00 | N | N |  | Y | Y
72733 | 410_PF_SilentPro_xCrossDoubleBranchFitting88DegSweptEntry_SocketAndSpigot | 2026-06-17 | 2026-07-13 | 19 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-17T10:47:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-13T11:57:38+02:00 | N | N |  | Y | Y
72734 | 430_DA_ShutOffDevices_AK.rfa | 2026-06-02 | 2026-09-25 | 84 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-02T03:34:50+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-25T05:59:00+02:00 | N | N |  | Y | Y
72735 | 410_PF_SS_uUnion_Coupling | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-17T02:58:30+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T11:17:44+02:00 | N | N |  | Y | Y
72736 | 430_DA_ShutOffDevices_AKEx.rfa | 2026-06-02 | 2026-07-01 | 22 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-02T03:36:19+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T04:23:48+02:00 | N | N |  | Y | Y
72737 | 410_PF_SS_cCap_Mapress | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-17T02:59:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T03:40:33+02:00 | N | N |  | Y | Y
72738 | 430_DA_ShutOffDevices_AKK.rfa | 2026-06-02 | 2026-09-16 | 77 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-02T03:37:37+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T05:28:17+02:00 | N | N |  | Y | Y
72739 | 410_PF_SS_cDrainplugWithScrewedPlug | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-17T02:59:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T03:43:45+02:00 | N | N |  | Y | Y
72740 | 410_PF_SS_cSocketPlug | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-17T09:54:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T12:30:58+02:00 | N | N |  | Y | Y
72741 | 430_DA_Silencer_Round_Standard.rfa | 2026-06-02 | 2026-07-03 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-02T03:42:27+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T09:15:20+02:00 | N | N |  | Y | Y
72742 | 410_PF_SS_cSocketPlugWithClamp | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-17T03:00:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T03:02:49+02:00 | N | N |  | Y | Y
72743 | 430_DA_Silencer_Rectangular_Standard.rfa | 2026-06-02 | 2026-09-03 | 68 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-02T03:44:01+02:00 ¦¦ END: nd.huynh: @l.truong On behalf of @hu.dam on vacation leave, this family is now fully completed and securely st @ 2026-09-03T02:44:38+02:00 | N | N |  | Y | Y
72744 | 410_PF_SS_cVentCowl_Standard | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T03:02:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T05:05:55+02:00 | N | N |  | Y | Y
72745 | 430_DA_SchakoSilencer_Round_RS.rfa | 2026-06-02 | 2026-07-07 | 26 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-02T03:46:11+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-07T03:28:57+02:00 | N | N |  | Y | Y
72746 | 430_DA_SilencersVAV_Rectangular_TS.rfa | 2026-06-02 | 2026-06-03 | 2 | handler_assign | status_resolved | START: handler→ha.phan @ 2026-06-02T03:48:11+02:00 ¦¦ END: status→resolved @ 2026-06-03T08:52:30+02:00 | N | N |  | Y | Y
72747 | 410_PF_SS_eBend45Degrees_SocketAndStandard | 2026-06-17 | 2026-07-22 | 26 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T03:03:38+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T04:44:06+02:00 | N | N |  | Y | Y
72748 | 430_DA_SilencersVAV_Rectangular_TX.rfa | 2026-06-02 | 2026-07-27 | 40 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-02T03:49:04+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T03:45:05+02:00 | N | N |  | Y | Y
72750 | 410_PF_SS_eBend87_Socket | 2026-06-17 | 2026-08-14 | 43 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T09:54:11+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T11:31:05+02:00 | N | N |  | Y | Y
72751 | 430_DA_FlowAdjustmentDampers.rfa | 2026-06-02 | 2026-07-07 | 26 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-02T03:54:03+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-07T03:30:47+02:00 | N | N |  | Y | Y
72753 | 430_DA_IntumescentDamper_OverflowGrill_NoSystem.rfa | 2026-06-02 | 2026-07-15 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-02T03:55:24+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T04:38:18+02:00 | N | N |  | Y | Y
72754 | 410_PF_SS_eBendWith250mmOblong_Clamp | 2026-06-17 | 2026-08-17 | 44 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T03:04:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T04:47:13+02:00 | N | N |  | Y | Y
72755 | 410_PF_SS_eBend_15_1Socket | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-17T03:05:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T12:30:43+02:00 | N | N |  | Y | Y
72756 | 430_DA_SmokeControlDamper_EKEU.rfa | 2026-06-02 | 2026-06-23 | 16 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-02T03:58:31+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-23T06:50:51+02:00 | N | N |  | Y | Y
72757 | 410_PF_SS_eBend_30_1Socket | 2026-06-17 | 2026-08-10 | 39 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-17T03:05:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T04:45:18+02:00 | N | N |  | Y | Y
72758 | 430_DA_SmokeControlDamper_EKJZ.rfa | 2026-06-02 | 2026-07-27 | 40 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-02T03:59:35+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T05:13:44+02:00 | N | N |  | Y | Y
72759 | 410_PF_SS_eElbow90DegAdaptor_FemaleThreadedAndPlainEndAndMapress | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-17T03:06:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T11:49:12+02:00 | N | N |  | Y | Y
72760 | 430_DA_SchakoConstantVolumeFlowControl_Round_ConstantFlowVLV.rfa | 2026-06-02 | 2026-07-03 | 24 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-02T04:01:29+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T08:56:24+02:00 | N | N |  | Y | Y
72761 | 410_PF_SS_eElbow90DegAdaptor_MaleThreadAndMapress | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-17T03:06:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T11:32:02+02:00 | N | N |  | Y | Y
72762 | 410_PF_SS_eElbow90DegTapConnector_Mapress | 2026-06-17 | 2026-07-22 | 26 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-17T03:07:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T04:44:48+02:00 | N | N |  | Y | Y
72763 | 410_PF_SS_eElbow90Deg_FemaleThreadAndMapress | 2026-06-17 | 2026-06-23 | 5 | handler_assign | status_resolved | START: handler→c.le @ 2026-06-17T03:07:41+02:00 ¦¦ END: status→resolved @ 2026-06-23T10:34:57+02:00 | N | N |  | Y | Y
72764 | 410_PF_SS_eElbowTapConector90Degree_Mapress | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-17T03:08:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T11:14:56+02:00 | N | N |  | Y | Y
72766 | 410_PF_SS_eElbow_Mapress | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T03:09:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T11:33:32+02:00 | N | N |  | Y | Y
72767 | 410_PF_SS_eLongBend_1Socket | 2026-06-17 | 2026-07-03 | 13 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T03:09:51+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T03:32:28+02:00 | N | N |  | Y | Y
72768 | 410_PF_SS_ePTrap_SocketAndSpigot | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T03:10:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T11:24:07+02:00 | N | N |  | Y | Y
72769 | 440_EE_FlatRoofSolarFrame_NoSystem.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-02T04:31:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T11:33:22+02:00 | N | N |  | Y | Y
72776 | 410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset | 2026-06-17 | 2026-08-14 | 43 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-17T09:53:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T03:11:01+02:00 | N | N |  | Y | Y
72777 | 410_PF_SS_mCornerElbow90Deg_Mapress | 2026-06-17 | 2026-06-23 | 5 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-17T09:05:58+02:00 ¦¦ END: status→resolved @ 2026-06-23T10:50:14+02:00 | N | N |  | Y | Y
72779 | 410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress | 2026-06-17 | 2026-08-04 | 35 | handler_assign | confirm_note:task_completed_closed | START: handler→dhn.nguyen @ 2026-06-17T09:06:19+02:00 ¦¦ END: tv.huynh: The task is completed. The ticket is closed accordingly. Thank you all. @ 2026-08-04T05:43:48+02:00 | N | N |  | Y | Y
72781 | 410_PF_SS_uRapid_Coupling | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-17T09:10:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T11:11:30+02:00 | N | N |  | Y | Y
72782 | 410_PF_SS_rConcentricIncreaserCoupling_Standard | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-17T09:12:47+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T10:23:46+02:00 | N | N |  | Y | Y
72783 | 410_PF_SS_rConnectorExternalThreadSpigot | 2026-06-17 | 2026-07-28 | 30 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-17T09:13:27+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T05:29:23+02:00 | N | N |  | Y | Y
72784 | 410_PF_SS_rConnectorInternal_ThreadSpigot | 2026-06-17 | 2026-07-01 | 11 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-17T09:53:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-01T11:31:17+02:00 | N | N |  | Y | Y
72797 | 410_PF_SS_rTransition_SocketAndFlanged | 2026-06-17 | 2026-09-30 | 76 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-17T09:24:42+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T10:16:51+02:00 | N | N |  | Y | Y
72798 | 410_PF_SS_rConnector_Socket | 2026-06-17 | 2026-07-30 | 32 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-17T09:25:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-30T08:22:33+02:00 | N | N |  | Y | Y
72800 | 410_PF_SS_rConnector_SocketAndThreaded | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-17T09:27:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T03:09:46+02:00 | N | N |  | Y | Y
72802 | 410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot | 2026-06-17 | 2026-09-25 | 73 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-17T09:28:04+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-25T05:59:03+02:00 | N | N |  | Y | Y
72803 | 430_DA_SmokeDetectorinDucts_RMO3D.rfa | 2026-06-02 | 2026-09-25 | 84 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-02T06:29:18+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-25T05:59:06+02:00 | N | N |  | Y | Y
72804 | 430_DA_SmokeDetectorinDucts_RMOVSD.rfa | 2026-06-02 | 2026-09-14 | 75 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-02T06:30:42+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-14T05:22:56+02:00 | N | N |  | Y | Y
72805 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSEVU.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-06-02T06:45:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T11:37:08+02:00 | N | N |  | Y | Y
72806 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSKälte.rfa | 2026-06-02 | 2026-09-22 | 81 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-02T06:47:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-22T03:29:44+02:00 | N | N |  | Y | Y
72807 | 410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-17T09:29:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T05:06:36+02:00 | N | N |  | Y | Y
72808 | 410_PF_SS_rReducerWithPlainEnd_Mapress | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-17T09:33:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T04:29:15+02:00 | N | N |  | Y | Y
72809 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSNord.rfa | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-02T06:48:36+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T05:03:36+02:00 | N | N |  | Y | Y
72810 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MsPvAnlage.rfa | 2026-06-02 | 2026-06-04 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-02T06:50:15+02:00 ¦¦ END: status→resolved @ 2026-06-04T11:19:53+02:00 | N | N |  | Y | N
72811 | 410_PF_SS_rTransition_SocketAndFemaleThreaded | 2026-06-17 | 2026-07-03 | 13 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-17T09:33:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T11:26:01+02:00 | N | N |  | Y | Y
72812 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSSud.rfa | 2026-06-02 | 2026-06-04 | 3 | handler_assign | status_closed | START: handler→h.pham @ 2026-06-02T06:52:02+02:00 ¦¦ END: status→closed @ 2026-06-04T10:45:56+02:00 | N | N |  | Y | N
72813 | 410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot | 2026-06-18 | 2026-07-03 | 12 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-18T08:45:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T11:26:52+02:00 | N | N |  | Y | Y
72814 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSSud.rfa | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-02T07:10:58+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T04:46:55+02:00 | N | N |  | Y | Y
72815 | 440_EE_Generator_Standard.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-02T07:12:59+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T03:05:41+02:00 | N | N |  | Y | Y
72816 | 440_EE_IndoorTransformer.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-02T07:17:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T11:39:47+02:00 | N | N |  | Y | Y
72817 | 440_EE_kwhMeter_3Phases.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-02T07:19:28+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T04:45:55+02:00 | N | N |  | Y | Y
72818 | 440_EE_LowVoltagePanel.rfa | 2026-06-02 | 2026-06-04 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-02T07:21:30+02:00 ¦¦ END: status→resolved @ 2026-06-04T10:07:48+02:00 | N | N |  | Y | Y
72819 | 430_DA_MultileafDamperRec_LowLeakage.rfa | 2026-06-02 | 2026-07-02 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-02T08:34:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-02T02:56:33+02:00 | N | N |  | Y | Y
72820 | 410_PF_SS_tTPiece_Mapress_Equal | 2026-06-23 | 2026-08-06 | 33 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-23T04:27:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T07:30:20+02:00 | N | N |  | Y | Y
72821 | 410_PF_SS_tReducingDoubleBranch45_Socket | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-23T04:28:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T11:15:13+02:00 | N | N |  | Y | Y
72822 | 410_PF_SS_tReducingSingleBranch45Degree_Socket | 2026-06-23 | 2026-08-24 | 45 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-23T04:29:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T11:45:01+02:00 | N | N |  | Y | Y
72823 | 410_PF_SS_tReducingSingleBranch87Deg_Socket | 2026-06-23 | 2026-08-24 | 45 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-23T04:30:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T11:45:04+02:00 | N | N |  | Y | Y
72824 | 410_PF_SS_tSingleBranch45_SocketAndSpigot | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-23T04:31:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T11:41:30+02:00 | N | N |  | Y | Y
72825 | 410_PF_SS_tSweptBranch87Deg_SocketAndSpigot | 2026-06-23 | 2026-08-07 | 34 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-23T04:33:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-07T04:10:16+02:00 | N | N |  | Y | Y
72826 | 410_PF_SS_tTeePiece_FemaleThreadedAndMapress | 2026-06-23 | 2026-08-21 | 44 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-06-23T04:33:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T11:36:35+02:00 | N | N |  | Y | Y
72827 | 410_PF_SS_tTeePiece_MaleThreadedAndMapress | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-23T04:39:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T04:52:55+02:00 | N | N |  | Y | Y
72828 | 410_PF_SS_tTeePiece_Mapress | 2026-06-23 | 2026-07-27 | 25 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-23T04:40:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T10:16:37+02:00 | N | N |  | Y | Y
72829 | 410_PF_SS_tPieceReducer_Mapress | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-23T04:42:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T07:31:41+02:00 | N | N |  | Y | Y
72830 | 410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress | 2026-06-23 | 2026-07-27 | 25 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-23T04:43:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T11:29:03+02:00 | N | N |  | Y | Y
72831 | 410_PF_SS_uAdaptorUnion_MaleThreadAndMapress | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-23T04:43:30+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T03:18:34+02:00 | N | N |  | Y | Y
72832 | 410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress | 2026-06-23 | 2026-09-21 | 65 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-23T04:45:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T11:44:00+02:00 | N | N |  | Y | Y
72833 | 410_PF_SS_uAdaptor_WithFemaleThreadAndMapress | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-23T04:44:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T11:16:13+02:00 | N | N |  | Y | Y
72834 | 410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-23T04:46:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T10:48:46+02:00 | N | N |  | Y | Y
72835 | 410_PF_SS_uAdaptor_WithMaleThreadAndMapress | 2026-06-23 | 2026-07-17 | 19 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-23T04:47:14+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T04:36:20+02:00 | N | N |  | Y | Y
72836 | 410_PF_SS_uAdaptorWithPlainEnd_MaleThreadAndMapress | 2026-06-23 | 2026-08-18 | 41 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-23T04:46:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-18T11:48:53+02:00 | N | N |  | Y | Y
72837 | 410_PF_SS_uAxialExpansion_PressingSockets | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-23T04:48:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T12:13:59+02:00 | N | N |  | Y | Y
72838 | 410_PF_SS_uBulkhead_Welded | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-23T04:48:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T10:41:50+02:00 | N | N |  | Y | Y
72839 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndWelded | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-23T04:48:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T10:41:18+02:00 | N | N |  | Y | Y
72840 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndMapress | 2026-06-23 | 2026-08-13 | 38 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-23T04:54:51+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T11:11:43+02:00 | N | N |  | Y | Y
72841 | 410_PF_SS_uConnector_FlangedAndSpigot | 2026-06-23 | 2026-08-13 | 38 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-23T04:56:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T11:26:31+02:00 | N | N |  | Y | Y
72851 | 430_DA_NonReturnValves.rfa | 2026-06-03 | 2026-07-08 | 26 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-03T03:17:03+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-08T05:21:50+02:00 | N | N |  | Y | Y
72853 | 430_DA_PressureReliefDamper_Rectangular_Standard_NoSystem.rfa | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-03T03:18:11+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T05:50:16+02:00 | N | N |  | Y | Y
72854 | 430_DA_RecFireDampers_FKEU.rfa | 2026-06-03 | 2026-09-16 | 76 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-03T03:19:28+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T05:28:19+02:00 | N | N |  | Y | Y
72855 | 410_PF_SS_uConnector_SocketAndThreaded | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T04:57:27+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T06:32:12+02:00 | N | N |  | Y | Y
72856 | 410_PF_SS_uCoupling_Mapress | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T04:57:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T08:24:42+02:00 | N | N |  | Y | Y
72857 | 410_PF_SS_uExpansionSocket | 2026-06-23 | 2026-07-22 | 22 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T05:01:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T02:39:06+02:00 | N | N |  | Y | Y
72858 | 410_PF_SS_uPeakPressure_Standard | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T05:01:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T11:41:01+02:00 | N | N |  | Y | Y
72859 | 410_PF_SS_uRatStop_SocketAndSpigot | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T05:03:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T04:47:53+02:00 | N | N |  | Y | Y
72860 | 410_PF_SS_uRepairCoupling_Socket | 2026-06-23 | 2026-08-03 | 30 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T05:25:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-03T10:27:33+02:00 | N | N |  | Y | Y
72861 | 410_PF_SS_uSocketClamp_Special | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T05:25:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:39:06+02:00 | N | N |  | Y | Y
72863 | 410_PF_SS_uSocketClamp_Twopiece | 2026-06-23 | 2026-07-15 | 17 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T05:28:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T11:47:54+02:00 | N | N |  | Y | Y
72864 | 410_PF_SS_uStraightCoupling | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-23T05:30:14+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T11:40:44+02:00 | N | N |  | Y | Y
72865 | 410_PF_SS_uUnion_Mapress | 2026-06-23 | 2026-06-30 | 6 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-06-23T05:31:12+02:00 ¦¦ END: status→resolved @ 2026-06-30T11:09:06+02:00 | N | N |  | Y | Y
72867 | 410_PF_SS_wCleaningPipes | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-23T05:32:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:38:54+02:00 | N | N |  | Y | Y
72868 | 410_PF_SS_xCornerBranch87Deg_SocketAndSpigot | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T05:36:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T04:47:21+02:00 | N | N |  | Y | Y
72869 | 410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot | 2026-06-25 | 2026-07-14 | 14 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-06-25T05:37:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T11:30:39+02:00 | N | N |  | Y | Y
72870 | 410_PF_SS_xDoubleBranch87_Socket | 2026-06-25 | 2026-07-15 | 15 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-25T05:38:27+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T11:48:32+02:00 | N | N |  | Y | Y
72871 | 410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-06-25T05:40:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T12:01:29+02:00 | N | N |  | Y | Y
72872 | 410_PF_ST_SanpressDoubleWallPane_Threaded_DN15 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T03:19:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T08:36:27+02:00 | N | N |  | Y | Y
72875 | 410_PF_UPVC_cCap_FemaleThreaded | 2026-06-25 | 2026-07-30 | 26 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T03:20:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-30T11:34:57+02:00 | N | N |  | Y | Y
72876 | 430_DA_RoundFireDampers_FKREU.rfa | 2026-06-03 | 2026-07-27 | 39 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-03T04:20:50+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T03:43:36+02:00 | N | N |  | Y | Y
72877 | 430_DA_RoundFireDampers_FKRS_EU.rfa | 2026-06-03 | 2026-09-14 | 74 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-03T04:21:24+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-14T06:00:33+02:00 | N | N |  | Y | Y
72878 | 410_PF_UPVC_cCap_Socket | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T03:20:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T10:41:27+02:00 | N | N |  | Y | Y
72879 | 410_PF_UPVC_eBend90Deg_Socket | 2026-06-25 | 2026-07-30 | 26 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T05:18:47+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-30T11:29:35+02:00 | N | N |  | Y | Y
72880 | 410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T03:21:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T09:47:19+02:00 | N | N |  | Y | Y
72881 | 410_PF_UPVC_eElbow90Deg_FemaleThreaded | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T03:22:05+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:38:39+02:00 | N | N |  | Y | Y
72882 | 410_PF_UPVC_eElbow_Socket | 2026-06-25 | 2026-08-10 | 33 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-25T05:41:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T05:31:33+02:00 | N | N |  | Y | Y
72883 | 410_PF_UPVC_eReducerElbow_Socket | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-06-25T05:42:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:38:26+02:00 | N | N |  | Y | Y
72884 | 410_PF_UPVC_eShortBend90Deg_Socket | 2026-06-25 | 2026-08-10 | 33 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-25T05:44:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T05:00:20+02:00 | N | N |  | Y | Y
72885 | 410_PF_UPVC_rBushReducing_Socket | 2026-06-30 | 2026-08-07 | 29 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-30T10:09:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-07T12:30:27+02:00 | N | N |  | Y | Y
72886 | 410_PF_UPVC_rLongBushReducing_Socket | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-25T05:46:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:38:13+02:00 | N | N |  | Y | Y
72887 | 410_PF_UPVC_rShortBushReducing_Socket | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-23T04:26:14+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T10:17:19+02:00 | N | N |  | Y | Y
72888 | 410_PF_UPVC_tLateralTee90Deg_Socket | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-23T04:23:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:40:50+02:00 | N | N |  | Y | Y
72889 | 410_PF_UPVC_tTee90Deg_FemaleThreaded | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-23T04:22:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T04:08:55+02:00 | N | N |  | Y | Y
72890 | 410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-23T04:20:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T11:34:03+02:00 | N | N |  | Y | Y
72891 | 410_PF_UPVC_tTee_Socket | 2026-06-23 | 2026-07-30 | 28 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-06-23T04:19:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-30T11:31:20+02:00 | N | N |  | Y | Y
72892 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-23T04:17:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T11:04:21+02:00 | N | N |  | Y | Y
72893 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-23T04:15:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T11:35:38+02:00 | N | N |  | Y | Y
72894 | 410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-23T04:14:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T10:07:50+02:00 | N | N |  | Y | Y
72895 | 410_PF_UPVC_uCoupling_Socket | 2026-06-17 | 2026-07-02 | 12 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-17T10:00:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-02T09:47:40+02:00 | N | N |  | Y | Y
72896 | 410_PF_UPVC_uInspectionPort_Glue | 2026-06-23 | 2026-07-13 | 15 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-23T03:40:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-13T11:57:05+02:00 | N | N |  | Y | Y
72897 | 410_PF_UPVC_uSiphon_Socket | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-06-23T03:43:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T11:40:18+02:00 | N | N |  | Y | Y
72898 | 410_PF_UPVC_xCross_Socket | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-06-23T03:44:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T03:14:59+02:00 | N | N |  | Y | Y
72899 | 430_DA_SmokeProtectionDamper_JZRS.rfa | 2026-06-03 | 2026-08-21 | 58 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-03T04:58:40+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:10:06+02:00 | N | N |  | Y | Y
72917 | 430_DA_TunnelDampers_JF.rfa | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-04T03:58:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T03:19:53+02:00 | N | N |  | Y | Y
72919 | 430_DA_VariableAirVolume_Rectangular_MQTH.rfa | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-04T04:01:04+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:10:40+02:00 | N | N |  | Y | Y
72920 | 430_DA_VariableAirVolume_Round_MQTH.rfa | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-04T04:03:07+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:12:12+02:00 | N | N |  | Y | Y
72931 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTASilenzio.rfa | 2026-06-04 | 2026-09-14 | 73 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-04T04:49:44+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-14T08:18:07+02:00 | N | N |  | Y | Y
72932 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVA.rfa | 2026-06-04 | 2026-07-08 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-04T04:50:54+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-08T05:19:11+02:00 | N | N |  | Y | Y
72933 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVJ.rfa | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-04T04:53:55+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T03:19:31+02:00 | N | N |  | Y | Y
72934 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVM.rfa | 2026-06-04 | 2026-08-05 | 45 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-04T04:57:10+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:52:19+02:00 | N | N |  | Y | Y
72935 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVT.rfa | 2026-06-04 | 2026-06-30 | 19 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-04T05:03:15+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-30T09:12:21+02:00 | N | N |  | Y | Y
72937 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVZ.rfa | 2026-06-04 | 2026-09-24 | 81 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-04T05:04:31+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-24T03:53:12+02:00 | N | N |  | Y | Y
72938 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTZSilenzio.rfa | 2026-06-04 | 2026-09-16 | 75 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-04T05:09:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T05:28:22+02:00 | N | N |  | Y | Y
72939 | 430_DA_VariableVolumeFlowControl_Round_VarycontrolTVLK.rfa | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-04T05:12:24+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:26:31+02:00 | N | N |  | Y | Y
72940 | 430_DA_VariableVolumeFlowControl_Round_VaryControlTVREX.rfa | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-04T05:13:25+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T03:13:23+02:00 | N | N |  | Y | Y
72999 | 440_EE_LowVoltageSwitchboard_GHVNord_HOST.rfa | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-06-05T02:37:38+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T11:39:34+02:00 | N | N |  | Y | Y
73000 | 440_EE_LowVoltageSwitchboard_GHVSüd_HOST.rfa | 2026-06-05 | 2026-09-22 | 78 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-06-05T02:39:46+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-22T03:29:47+02:00 | N | N |  | Y | Y
73001 | 440_EE_LowVoltageSwitchboard_NshvKälte_HOST.rfa | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-06-05T02:42:45+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T04:38:40+02:00 | N | N |  | Y | Y
73002 | 440_EE_LowVoltageSwitchboard_NshvPV_HOST.rfa | 2026-06-05 | 2026-07-22 | 34 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-06-05T02:46:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-07-22T04:45:07+02:00 | N | N |  | Y | Y
73003 | 440_EE_MainDistributionBoard_WallMounted.rfa | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-06-05T02:48:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T04:28:40+02:00 | N | N |  | Y | Y
73004 | 440_EE_MainSupply_GEVBnetwork.rfa | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-06-05T03:02:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:38:38+02:00 | N | N |  | Y | Y
73005 | 440_EE_MainSupply_UPSmains.rfa | 2026-06-05 | 2026-08-17 | 52 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-06-05T03:10:20+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T10:59:47+02:00 | N | N |  | Y | Y
73006 | 440_EE_MainSwitchBoard.rfa | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-06-05T03:12:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T05:48:20+02:00 | N | N |  | Y | Y
73007 | 440_EE_Manhole_Standard.rfa | 2026-06-05 | 2026-09-18 | 76 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-06-05T03:15:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:06:29+02:00 | N | N |  | Y | Y
73009 | 440_EE_MediumVoltageSwitchgear.rfa | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-06-05T03:21:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T05:47:42+02:00 | N | N |  | Y | Y
73011 | 440_EE_MotorControlCenter_SwitchBoard.rfa | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-06-05T03:23:36+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T03:07:00+02:00 | N | N |  | Y | Y
73012 | 440_EE_OilTransformer.rfa | 2026-06-05 | 2026-06-24 | 14 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-06-05T03:26:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-06-24T09:34:46+02:00 | N | N |  | Y | Y
73014 | 440_EE_OutdoorTransformer.rfa | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-06-05T03:29:24+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T04:23:53+02:00 | N | N |  | Y | Y
73015 | 440_EE_PanelBoard.rfa | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-06-05T03:31:19+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T03:05:15+02:00 | N | N |  | Y | Y
73016 | 440_EE_SilentDieselGenerator.rfa | 2026-06-05 | 2026-06-05 | 1 | handler_assign | status_resolved | START: handler→th.le @ 2026-06-05T03:40:56+02:00 ¦¦ END: status→resolved @ 2026-06-05T10:54:43+02:00 | N | N |  | Y | Y
73017 | 440_EE_SinglePhase_Panel.rfa | 2026-06-05 | 2026-09-18 | 76 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-06-05T03:47:04+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:06:33+02:00 | N | N |  | Y | Y
73018 | 440_EE_SpringVibration.rfa | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-06-05T03:49:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T05:47:29+02:00 | N | N |  | Y | Y
73019 | 440_EE_SubmainSwitchBoard.rfa | 2026-06-05 | 2026-08-25 | 58 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-06-05T03:52:15+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T07:22:53+02:00 | N | N |  | Y | Y
73020 | 440_EE_SwitchCabinet_OutgoingPanel.rfa | 2026-06-05 | 2026-08-19 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-05T03:55:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T11:33:57+02:00 | N | N |  | Y | Y
73021 | 440_EE_SwitchCabinet_SupplyPanel.rfa | 2026-06-05 | 2026-08-24 | 57 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-05T03:56:32+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:36:38+02:00 | N | N |  | Y | Y
73022 | 440_EE_SynchronizationPanel.rfa | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-05T03:58:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T04:28:44+02:00 | N | N |  | Y | Y
73023 | 440_EE_TransferDistributor.rfa | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-05T03:59:48+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam **440_EE_TransferDistributor.rfa** Based on the spreadsheet input, the MEP Team @ 2026-08-31T04:12:08+02:00 | N | N |  | Y | Y
73024 | 456_EE_BMABusCoupler.rfa | 2026-06-05 | 2026-08-26 | 59 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-05T04:02:13+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T11:38:09+02:00 | N | N |  | Y | Y
73063 | Annotation_Model_Upgrade LIB model to Revit 2023 | 2026-06-05 | 2026-06-09 | 3 | handler_assign | status_resolved | START: handler→dahn.nguyen @ 2026-06-05T11:16:51+02:00 ¦¦ END: status→resolved @ 2026-06-09T05:57:11+02:00 | N | N |  | Y | N
73064 | Annotation_Model_Compare and markup for replacement rfa | 2026-06-05 |  |  | handler_assign | none | START: handler→nd.huynh @ 2026-06-05T11:27:59+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
73069 | 430_DA_VariableVolumeFlowControl_VaryControl_Round_LVC.rfa | 2026-06-08 | 2026-09-09 | 68 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-08T04:25:09+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T05:15:30+02:00 | N | N |  | Y | Y
73070 | 430_DA_VariableVolumeFlowControl_VaryControl_Round_TVR.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-08T04:26:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T03:12:47+02:00 | N | N |  | Y | Y
73071 | 430_DA_FlexibleConnection_Round.rfa | 2026-06-08 | 2026-06-30 | 17 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-08T04:29:12+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-30T09:11:58+02:00 | N | N |  | Y | Y
73072 | 430_DA_VariableVolumeFlowControl_Varycontrol_Round_TVRK.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-08T04:31:36+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T02:50:27+02:00 | N | N |  | Y | Y
73073 | 430_DA_VolumeFlowRateMeasuringUnits_VME.rfa | 2026-06-08 | 2026-07-22 | 33 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-08T04:33:34+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T04:25:48+02:00 | N | N |  | Y | Y
73074 | 430_DA_VolumeFlowRateMeasuringUnits_VMLK.rfa | 2026-06-08 | 2026-06-23 | 12 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-08T04:34:49+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-06-23T03:33:09+02:00 | N | N |  | Y | Y
73075 | 430_DA_VolumeFlowRateMeasuringUnits_VMR.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-08T04:36:21+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T08:47:40+02:00 | N | N |  | Y | Y
73076 | 430_DA_RecFireDamperMechanism_FK2EU.rfa | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-08T04:40:10+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T09:51:13+02:00 | N | N |  | Y | Y
73077 | 430_DA_VolumeFlowRateMeasuringUnits_VMRK.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-08T04:42:42+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-14T08:45:05+02:00 | N | N |  | Y | Y
73078 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC5Pipes | 2026-06-08 | 2026-08-24 | 56 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-08T06:23:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T11:45:07+02:00 | N | N |  | Y | Y
73079 | 434_ME_WaterCooledLiquidChillers_30XW | 2026-06-08 | 2026-08-25 | 57 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-08T06:23:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T03:14:31+02:00 | N | N |  | Y | Y
73080 | 434_ME_VRVShutOffValveBox_SV8A14AJV1B | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-08T06:23:52+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-14T03:36:04+02:00 | N | N |  | Y | Y
73081 | 434_ME_VRVShutOffValveBox_SV6A14AJV1B | 2026-06-08 | 2026-07-03 | 20 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-08T06:23:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-03T03:54:47+02:00 | N | N |  | Y | Y
73082 | 434_ME_VRVShutOffValveBox_SV4A14AJV1B | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-08T06:22:31+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-08-31T04:00:37+02:00 | N | N |  | Y | Y
73083 | 434_ME_VRVShutOffValveBox_SV1A25AJV1B | 2026-06-08 | 2026-09-11 | 70 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-08T06:22:29+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T03:18:00+02:00 | N | N |  | Y | Y
73084 | 434_ME_VRVOutDoorUnit_HeatPumpRXYSA&AV1&AY1 | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-08T06:22:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T04:37:27+02:00 | N | N |  | Y | Y
73085 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA8&12A | 2026-06-08 | 2026-08-28 | 60 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-08T06:22:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T10:36:12+02:00 | N | N |  | Y | Y
73086 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA14&20A | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-08T06:22:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-18T03:43:08+02:00 | N | N |  | Y | Y
73087 | 434_ME_VRVMultiBranchSelector_BS&8A14AV1B | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-08T06:22:20+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-18T11:09:09+02:00 | N | N |  | Y | Y
73088 | 434_ME_VRVMultiBranchSelector_BS&6A14AV1B | 2026-06-08 | 2026-06-16 | 7 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-08T06:21:33+02:00 ¦¦ END: status→resolved @ 2026-06-16T11:29:33+02:00 | N | N |  | Y | N
73089 | 434_ME_VRVMultiBranchSelector_BS&4A14AV1B | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-08T06:21:30+02:00 ¦¦ END: status→resolved @ 2026-06-17T12:01:55+02:00 | N | N |  | Y | N
73090 | 434_ME_VRVMultiBranchSelector_BS&12A14AV1B | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-08T06:21:28+02:00 ¦¦ END: status→resolved @ 2026-06-17T12:02:01+02:00 | N | N |  | Y | N
73091 | 434_ME_VRVMultiBranchSelector_BS&10A14AV1B | 2026-06-08 | 2026-09-21 | 76 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-08T06:21:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:44:02+02:00 | N | N |  | Y | Y
73092 | 434_ME_VRVInDoorUnit_WallMounted_FXAA&A | 2026-06-08 | 2026-09-22 | 77 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-08T06:21:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:13+02:00 | N | N |  | Y | Y
73093 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXSA | 2026-06-08 | 2026-06-12 | 5 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-06-08T06:20:41+02:00 ¦¦ END: status→resolved @ 2026-06-12T11:44:25+02:00 | N | N |  | Y | N
73094 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA200and250A | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-06-08T06:20:36+02:00 ¦¦ END: status→resolved @ 2026-06-17T11:46:20+02:00 | N | N |  | Y | N
73095 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-06-08T06:20:32+02:00 ¦¦ END: status→resolved @ 2026-06-17T11:54:20+02:00 | N | N |  | Y | N
73096 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXDA | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-06-08T06:20:27+02:00 ¦¦ END: status→resolved @ 2026-06-17T11:48:38+02:00 | N | N |  | Y | N
73097 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXUA&A | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-08T06:20:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:21+02:00 | N | N |  | Y | Y
73098 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXHA&A | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-08T06:19:47+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-04T03:30:26+02:00 | N | N |  | Y | Y
73099 | 434_ME_VRVInDoorUnit_CeilingMouted_FXZA&A | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-08T06:19:42+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-08-31T03:54:37+02:00 | N | N |  | Y | Y
73100 | 434_ME_VRVInDoorUnit_CeilingMouted_FXFA&A | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-08T06:19:37+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T03:25:27+02:00 | N | N |  | Y | Y
73101 | 434_ME_TwoOutletPump_Flanged | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-08T06:19:32+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:11:52+02:00 | N | N |  | Y | Y
73102 | 434_ME_SplitCasePump_Standard | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-08T06:19:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:11:56+02:00 | N | N |  | Y | Y
73103 | 434_ME_Pump_SingleStageLowPressureBAC65 | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-08T06:19:21+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-04T03:20:33+02:00 | N | N |  | Y | Y
73104 | 434_ME_Pump_Circulator_YonosGIGA20_I | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-08T06:19:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T03:18:32+02:00 | N | N |  | Y | Y
73105 | 420_PA_PressureReducingValveWithGauge_Thread | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-13T08:46:04+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T11:41:02+02:00 | N | N |  | Y | Y
73106 | 420_PA_PressureIndependentControlValve_Threaded | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-13T08:46:04+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T11:41:05+02:00 | N | N |  | Y | Y
73107 | 420_PA_PressureIndependentControlValve_Flanged | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-13T08:46:04+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T11:41:08+02:00 | N | N |  | Y | Y
73108 | 420_PA_PressureIndependentControlValveCompact_Threaded | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-13T08:46:04+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:24+02:00 | N | N |  | Y | Y
73109 | 420_PA_PressureGauge_Standard | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-13T08:45:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T04:50:11+02:00 | N | N |  | Y | Y
73110 | 420_PA_PressureGauge_2Connection | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-13T08:45:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T04:50:14+02:00 | N | N |  | Y | Y
73111 | 420_PA_PressureGauge | 2026-07-13 | 2026-09-07 | 41 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-13T08:45:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T06:17:43+02:00 | N | N |  | Y | Y
73112 | 420_PA_PneumaticGlobeControlValve_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-13T08:45:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T06:01:38+02:00 | N | N |  | Y | Y
73113 | 420_PA_PneumaticGlobeControlValve_Flanged | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-12T06:28:44+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T12:26:24+02:00 | N | N |  | Y | Y
73114 | 420_PA_PneumaticControlValve_Flanged | 2026-06-12 | 2026-06-18 | 5 | handler_assign | status_resolved | START: handler→b.tran @ 2026-06-12T06:28:41+02:00 ¦¦ END: status→resolved @ 2026-06-18T09:23:27+02:00 | N | N |  | Y | N
73115 | 420_PA_PIQCV6WayValve_Thread | 2026-06-12 | 2026-06-17 | 4 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-06-12T06:28:03+02:00 ¦¦ END: status→resolved @ 2026-06-17T03:31:58+02:00 | N | N |  | Y | N
73116 | 420_PA_PICCV3WayValve_Thread | 2026-06-12 | 2026-07-24 | 31 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-12T06:27:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-24T11:33:03+02:00 | N | N |  | Y | Y
73117 | 420_PA_PICCV2WayValve_Thread | 2026-06-12 | 2026-07-24 | 31 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-12T06:27:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-24T11:36:06+02:00 | N | N |  | Y | Y
73118 | 420_PA_NonReturnFlap_Flanged | 2026-06-12 | 2026-06-19 | 6 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-06-12T06:26:37+02:00 ¦¦ END: status→resolved @ 2026-06-19T10:33:45+02:00 | N | N |  | Y | N
73119 | 420_PA_MotorizedThreeWayvalve_Thread_Standard | 2026-06-12 | 2026-09-21 | 72 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-12T06:26:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:44:06+02:00 | N | N |  | Y | Y
73120 | 420_PA_MotorizedThreeWayValve_Flanged_Standard | 2026-06-08 | 2026-09-16 | 73 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-08T06:17:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-16T11:28:22+02:00 | N | N |  | Y | Y
73121 | 420_PA_MotorizedGlobeValve_Thread_Standard | 2026-06-08 | 2026-07-24 | 35 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-08T06:18:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-24T11:36:37+02:00 | N | N |  | Y | Y
73122 | 420_PA_MotorizedGlobeValve_Flanged_Standard | 2026-06-08 | 2026-07-31 | 40 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-08T06:18:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-31T04:56:02+02:00 | N | N |  | Y | Y
73123 | 420_PA_MotorizedGateValve_Thread_Standard | 2026-06-08 | 2026-07-31 | 40 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-08T06:18:07+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-31T04:56:27+02:00 | N | N |  | Y | Y
73124 | 420_PA_MotorizedGateValve_Flanged_Standard | 2026-06-08 | 2026-07-29 | 38 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-08T06:18:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T06:32:27+02:00 | N | N |  | Y | Y
73125 | 420_PA_MotorizedButterflyValve_Flanged_Standard | 2026-06-08 | 2026-07-17 | 30 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-08T06:17:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-17T03:11:32+02:00 | N | N |  | Y | Y
73126 | 420_PA_MotorizedBallValve_Thread_Standard | 2026-06-08 | 2026-10-01 | 84 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-08T06:17:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:31:27+02:00 | N | N |  | Y | N
73127 | 420_PA_MotorizedBallValve_Flanged_Standard | 2026-06-08 | 2026-08-25 | 57 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-08T06:17:07+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T07:22:57+02:00 | N | N |  | Y | Y
73128 | 420_PA_LiftCheckValve_Thread_Standard | 2026-06-08 | 2026-09-11 | 70 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-08T06:17:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T03:18:04+02:00 | N | N |  | Y | Y
73129 | 420_PA_LiftCheckValve_Flanged_Standard | 2026-06-08 | 2026-09-21 | 76 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-08T06:17:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T10:26:06+02:00 | N | N |  | Y | Y
73130 | 420_PA_HeatingBallValve_Thread | 2026-06-08 | 2026-09-03 | 64 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-08T06:17:01+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-03T03:04:25+02:00 | N | N |  | Y | Y
73131 | 420_PA_HeatMeter_Thread_Standard | 2026-06-08 | 2026-06-19 | 10 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-06-08T06:16:26+02:00 ¦¦ END: status→resolved @ 2026-06-19T10:05:24+02:00 | N | N |  | Y | N
73132 | 420_PA_HeatMeter_Flanged_Standard | 2026-06-08 | 2026-06-19 | 10 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-06-08T06:16:15+02:00 ¦¦ END: status→resolved @ 2026-06-19T10:04:07+02:00 | N | N |  | Y | N
73133 | 420_PA_HeatMeter_Flanged | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-08T06:16:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-18T11:09:12+02:00 | N | N |  | Y | Y
73134 | 420_PA_GlobeValve_Thread_Standard | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-08T06:16:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T05:59:10+02:00 | N | N |  | Y | Y
73135 | 420_PA_GlobeValve_Thread | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-08T06:16:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T05:59:13+02:00 | N | N |  | Y | Y
73136 | 420_PA_GlobeValve_Flanged_Standard | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-08T06:15:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T05:59:17+02:00 | N | N |  | Y | Y
73137 | 420_PA_GlobeValve_Flanged | 2026-06-08 | 2026-06-15 | 6 | handler_assign | confirm_note:confirm_other | START: handler→l.nguyen @ 2026-06-08T06:15:06+02:00 ¦¦ END: n.le: This is duplicated. Ticket is closed. @ 2026-06-15T05:01:20+02:00 | N | N |  | Y | N
73138 | 420_PA_GlobeValve_Flanged | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-08T06:15:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-16T06:37:04+02:00 | N | N |  | Y | N
73139 | 420_PA_GateValve_Thread_Standard | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-08T06:15:01+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-08-31T03:46:55+02:00 | N | N |  | Y | Y
73140 | 420_PA_GateValve_Thread | 2026-06-08 | 2026-09-08 | 67 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-08T06:14:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T05:29:04+02:00 | N | N |  | Y | Y
73141 | 420_PA_GateValve_Flanged_Standard | 2026-06-08 | 2026-09-14 | 71 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-08T06:14:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T11:14:38+02:00 | N | N |  | Y | Y
73142 | 420_PA_GateValve_Flanged | 2026-06-08 | 2026-06-18 | 9 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-06-08T06:14:14+02:00 ¦¦ END: status→resolved @ 2026-06-18T10:39:50+02:00 | N | N |  | Y | N
73143 | 420_PA_FlowSensor_Thread_Standard | 2026-06-08 | 2026-09-10 | 69 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-08T06:14:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T03:14:04+02:00 | N | N |  | Y | Y
73144 | 420_PA_FlowSensor_Flanged_Standard | 2026-06-08 | 2026-08-10 | 46 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-08T06:14:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-10T07:24:15+02:00 | N | N |  | Y | Y
73145 | 420_PA_FlowSensor | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-08T06:14:01+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-04T03:59:31+02:00 | N | N |  | Y | Y
73146 | 420_PA_FlexibleConnection_Thread_Standard | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-08T06:13:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-16T09:51:47+02:00 | N | N |  | Y | Y
73147 | 434_ME_Pump_Circulator_VeroTwinDPL_DN80 | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | START: handler→dx.quach @ 2026-06-08T06:23:45+02:00 ¦¦ END: status→resolved @ 2026-06-17T08:03:52+02:00 | N | N |  | Y | N
73162 | 440_EF_360DegreeRadiusMotionDetector_CeilingMounted.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-06-09T10:45:10+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T11:25:28+02:00 | N | N |  | Y | Y
73163 | 446_EF_AirTerminationRodsForMetalRoofs.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-09T10:47:59+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:38:41+02:00 | N | N |  | Y | Y
73164 | 446_EF_AirTerminationRods_FloorStand.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-09T10:49:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T04:28:47+02:00 | N | N |  | Y | Y
73165 | 440_EF_AL_SideFeedingUnitForTransformer_Busway.rfa | 2026-06-09 | 2026-08-24 | 55 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-09T10:51:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:36:41+02:00 | N | N |  | Y | Y
73166 | 440_EF_AL_TakeOffUnitWithFuseSwitch_Busway.rfa | 2026-06-09 | 2026-08-24 | 55 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-09T10:53:20+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:36:44+02:00 | N | N |  | Y | Y
73167 | 440_EF_AL_TopFeedingUnitForTransformer_Busway.rfa | 2026-06-09 | 2026-08-11 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-09T10:54:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T11:55:20+02:00 | N | N |  | Y | Y
73168 | 481_EF_OutdoorAirTemperatureSensor.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-09T10:55:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:38:44+02:00 | N | N |  | Y | Y
73173 | 430_AT_AirDiffuser_Standard.rfa | 2026-06-10 | 2026-07-30 | 37 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-10T02:34:12+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-30T11:32:40+02:00 | N | N |  | Y | Y
73174 | 430_AT_CircularDiscValves_LVS_Return.rfa | 2026-06-10 | 2026-08-13 | 47 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-10T02:35:57+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T05:23:48+02:00 | N | N |  | Y | Y
73182 | 440_EF_CableConnection_PluginSystem.rfa | 2026-06-10 | 2026-08-13 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T08:44:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:28:54+02:00 | N | N |  | Y | Y
73183 | 440_EF_ConnectionBrackets.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:03:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:36:48+02:00 | N | N |  | Y | Y
73184 | 440_EF_DALIPresenceDetectorCombineLightingSensor_CeilingSurface.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:36:58+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:36:51+02:00 | N | N |  | Y | Y
73185 | 440_EF_DALIPresenceDetector_CeilingSurface.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:40:04+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:36:54+02:00 | N | N |  | Y | Y
73186 | 440_EF_DataConnectionSocket_Audio_Out_HDMI.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:41:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:36:57+02:00 | N | N |  | Y | Y
73187 | 440_EF_DataConnectionSocket_Ceiling.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:43:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:37:01+02:00 | N | N |  | Y | Y
73188 | 457_EF_DataConnectionSocket_CeilingMounted_WaterProof.rfa | 2026-06-10 | 2026-09-16 | 71 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:44:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T10:46:53+02:00 | N | N |  | Y | Y
73189 | 440_EF_DataConnectionSocket_Floor.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:46:15+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T04:07:00+02:00 | N | N |  | Y | Y
73190 | 440_EF_DataConnectionSocket_Wall.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:50:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:24:45+02:00 | N | N |  | Y | Y
73191 | 440_EF_DaylightSensor_Ceiling.rfa | 2026-06-10 | 2026-09-28 | 79 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:51:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T11:00:18+02:00 | N | N |  | Y | Y
73192 | 440_EF_DaylightSensor_Wall.rfa | 2026-06-10 | 2026-08-31 | 59 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:52:55+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T06:43:48+02:00 | N | N |  | Y | Y
73193 | 440_EF_DimmerSwitch_WallRecessed.rfa | 2026-06-10 | 2026-08-31 | 59 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-10T10:55:32+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T06:36:06+02:00 | N | N |  | Y | Y
73200 | 440_EF_DoorbellPushButton_WallMounted.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T03:53:20+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T06:28:26+02:00 | N | N |  | Y | Y
73201 | 440_EF_DoubleSocketOutletHorizontal_Wall.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T03:56:21+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T06:20:26+02:00 | N | N |  | Y | Y
73202 | 440_EF_DoubleSocketOutletUSBTypeAC_WallSurface.rfa | 2026-06-11 | 2026-08-11 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T03:58:04+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T11:23:30+02:00 | N | N |  | Y | Y
73203 | 440_EF_DoubleSocketOutletVertical_Wall.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T03:59:40+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T04:28:51+02:00 | N | N |  | Y | Y
73204 | 440_EF_DoubleSocketOutletVertical_WallFlush.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T04:01:20+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T06:12:22+02:00 | N | N |  | Y | Y
73205 | 440_EF_DoubleSocketOutlet_Ceiling.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T04:03:23+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:38:48+02:00 | N | N |  | Y | Y
73206 | 440_EF_DoubleSocketOutlet_Floor.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T04:05:10+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:38:51+02:00 | N | N |  | Y | Y
73207 | 440_EF_DoubleSocketOutlet_Wall.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T04:06:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:38:54+02:00 | N | N |  | Y | Y
73208 | 446_EF_EarthingFixedPoint_WallSurface.rfa | 2026-06-11 | 2026-09-16 | 70 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T04:08:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T10:46:55+02:00 | N | N |  | Y | Y
73209 | 446_EF_Earthing_WallSurface.rfa | 2026-06-11 | 2026-08-11 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T04:09:49+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T11:20:59+02:00 | N | N |  | Y | Y
73221 | 440_EF_EarthPit.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-11T09:21:59+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T05:59:53+02:00 | N | N |  | Y | Y
73241 | 430_AT_CrossflowCFE_TPP_NoSystem.rfa | 2026-06-12 | 2026-07-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-12T03:30:35+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-08T06:53:12+02:00 | N | N |  | Y | Y
73243 | 430_AT_DeflectorHood_Roof_Rectangular_Exhaust Air.rfa | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-12T04:07:58+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T05:48:49+02:00 | N | N |  | Y | Y
73287 | 434_PF_CO_xOffsetCross_Mapress | 2026-07-13 | 2026-09-14 | 46 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-13T08:44:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T11:07:32+02:00 | N | N |  | Y | Y
73288 | 434_PF_CO_uTap_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-13T08:44:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T04:49:59+02:00 | N | N |  | Y | Y
73289 | 434_PF_CO_uAdaptorUnion_PlainEndAndThread | 2026-07-13 | 2026-09-21 | 51 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-13T08:43:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T03:13:54+02:00 | N | N |  | Y | Y
73290 | 434_PF_CO_uAdaptorUnion_PlainEndAndClampingRing | 2026-07-13 | 2026-09-07 | 41 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-13T08:43:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T06:49:20+02:00 | N | N |  | Y | Y
73291 | 434_PF_CO_uAdaptorUnion_MapressAndNutGas | 2026-07-13 | 2026-08-10 | 21 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-07-13T08:42:49+02:00 ¦¦ END: status→resolved @ 2026-08-10T11:50:14+02:00 | N | N |  | Y | N
73292 | 434_PF_CO_uAdaptorUnion_MapressAndMaleThreadFKMBlue_WithNut | 2026-07-13 | 2026-08-10 | 21 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-07-13T08:42:42+02:00 ¦¦ END: status→resolved @ 2026-08-10T11:54:22+02:00 | N | N |  | Y | N
73293 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThread_WithNut | 2026-07-09 | 2026-08-06 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-09T03:50:52+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-06T07:36:21+02:00 | N | N |  | Y | Y
73294 | 434_PF_CO_uAdaptorUnion_MaleThread_MeplaFix | 2026-07-09 | 2026-07-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-09T03:50:42+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T06:31:58+02:00 | N | N |  | Y | Y
73295 | 434_PF_CO_uAdaptorUnion_MaleThreadAndMeplaFix | 2026-07-08 | 2026-08-05 | 21 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-08T03:05:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-05T05:47:53+02:00 | N | N |  | Y | Y
73296 | 434_PF_CO_rReducerAdaptor_PlainEndAndThreadGas | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-19T05:38:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-27T05:12:14+02:00 | N | N |  | Y | Y
73297 | 434_PF_CO_rReducerAdaptor_PlainEndAndThread | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-19T05:37:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-27T05:12:32+02:00 | N | N |  | Y | Y
73298 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFix | 2026-06-19 | 2026-07-17 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-19T05:37:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-17T06:24:56+02:00 | N | N |  | Y | Y
73299 | 434_PF_CO_rReducerAdaptor_MapressAndThreadGas | 2026-06-19 | 2026-07-17 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-19T05:37:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-17T04:16:07+02:00 | N | N |  | Y | Y
73300 | 434_PF_CO_rReducerAdaptor_MapressAndThreadFKMBlue | 2026-06-19 | 2026-08-20 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-19T05:37:51+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T08:19:13+02:00 | N | N |  | Y | Y
73301 | 434_PF_CO_rReducerAdaptor_MapressAndThread | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-19T05:37:48+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-14T03:14:08+02:00 | N | N |  | Y | Y
73302 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThread_WithNut | 2026-06-19 | 2026-08-04 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-19T05:37:46+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-04T11:54:24+02:00 | N | N |  | Y | Y
73303 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThreadFKMBlue_WithNut | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-19T05:36:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-27T03:38:59+02:00 | N | N |  | Y | Y
73304 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThread_WithNut | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-19T05:36:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-27T03:39:16+02:00 | N | N |  | Y | Y
73305 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThreadFKMBlue_WithNut | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-19T05:36:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-16T03:29:07+02:00 | N | N |  | Y | Y
73306 | 434_PF_CO_rReducerAdaptor_MaleThread_MeplaFix | 2026-06-12 | 2026-07-28 | 33 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-12T08:48:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-28T03:22:09+02:00 | N | N |  | Y | Y
73307 | 434_PF_CO_mTeeReturn_Mapress | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-12T08:48:46+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T05:09:08+02:00 | N | N |  | Y | Y
73308 | 434_PF_CO_mTeeInletReturn_Mapress | 2026-06-12 | 2026-07-28 | 33 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-12T08:48:41+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-28T03:17:42+02:00 | N | N |  | Y | Y
73309 | 434_PF_CO_mTeeInletReturnUnion_Mapress | 2026-06-12 | 2026-09-11 | 66 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-12T08:47:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T04:42:36+02:00 | N | N |  | Y | Y
73310 | 434_PF_CO_mTeeCrossing_Mapress | 2026-06-12 | 2026-09-07 | 62 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-12T08:47:20+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T11:29:30+02:00 | N | N |  | Y | Y
73311 | 434_PF_CO_mElbow_MapressAndFemaleThread | 2026-06-12 | 2026-09-14 | 67 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-12T08:47:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T11:07:35+02:00 | N | N |  | Y | Y
73312 | 434_PF_CO_mElbowOffset_MapressAndFemaleThread | 2026-06-12 | 2026-07-22 | 29 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-12T08:47:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T02:27:42+02:00 | N | N |  | Y | Y
73313 | 434_PF_CO_mDouble90Elbow_Mapress_PreMounted | 2026-06-12 | 2026-06-19 | 6 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-06-12T08:45:53+02:00 ¦¦ END: status→resolved @ 2026-06-19T11:30:46+02:00 | N | N |  | Y | N
73314 | 434_PF_CO_mBridgeBend_Mapress | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-12T08:45:46+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T05:09:11+02:00 | N | N |  | Y | Y
73329 | 430_AT_CircularDiscValves_ZLVS_Supply.rfa | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-15T02:55:02+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T11:22:31+02:00 | N | N |  | Y | Y
73330 | 430_AT_DeflectorHood_Roof_Rectangular_FreshAirIntake.rfa | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-15T02:57:30+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T11:22:48+02:00 | N | N |  | Y | Y
73331 | 430_AT_DeflectorHood_Roof_Round_Exhaust.rfa | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-15T03:14:53+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T11:22:11+02:00 | N | N |  | Y | Y
73332 | 430_AT_DeflectorHood_Roof_Round_FreshAirIntake.rfa | 2026-06-15 | 2026-06-19 | 5 | handler_assign | status_resolved | START: handler→d.nguyen @ 2026-06-15T03:15:10+02:00 ¦¦ END: status→resolved @ 2026-06-19T11:00:13+02:00 | N | N |  | Y | N
73333 | 430_AT_Diffusers_Floor_FBK_Return.rfa | 2026-06-15 | 2026-08-10 | 41 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-15T03:15:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T05:50:09+02:00 | N | N |  | Y | Y
73334 | 430_AT_Diffusers_Floor_FBK_Supply.rfa | 2026-06-15 | 2026-08-24 | 51 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-15T03:15:21+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T04:21:42+02:00 | N | N |  | Y | Y
73335 | 430_AT_Diffusers_Wall_CHM_Supply.rfa | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-15T03:08:37+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T06:16:51+02:00 | N | N |  | Y | Y
73336 | 430_AT_Diffusers_Wall_CHS_Supply.rfa | 2026-06-15 | 2026-07-10 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-15T03:09:37+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-10T03:19:45+02:00 | N | N |  | Y | Y
73337 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Return.rfa | 2026-06-15 | 2026-07-29 | 33 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-15T03:11:07+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:39:32+02:00 | N | N |  | Y | Y
73338 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Supply.rfa | 2026-06-15 | 2026-07-10 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-15T03:14:31+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-10T04:02:08+02:00 | N | N |  | Y | Y
73339 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-09-28 | 76 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-15T03:19:24+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-28T03:39:46+02:00 | N | N |  | Y | Y
73340 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-07-29 | 33 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-15T03:22:15+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T11:39:20+02:00 | N | N |  | Y | Y
73341 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Return.rfa | 2026-06-15 | 2026-08-04 | 37 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-15T03:24:01+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T03:37:13+02:00 | N | N |  | Y | Y
73342 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Supply.rfa | 2026-06-15 | 2026-08-03 | 36 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-15T03:25:29+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-03T08:32:25+02:00 | N | N |  | Y | Y
73343 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-09-23 | 73 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-15T03:28:36+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T07:20:20+02:00 | N | N |  | Y | Y
73345 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-09-18 | 70 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-15T03:29:43+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T03:43:11+02:00 | N | N |  | Y | Y
73346 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-07-09 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-15T03:31:46+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-09T04:25:08+02:00 | N | N |  | Y | Y
73347 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-07-09 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-15T03:33:12+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-09T03:50:51+02:00 | N | N |  | Y | Y
73348 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-08-13 | 44 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-15T03:35:18+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T05:53:25+02:00 | N | N |  | Y | Y
73349 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-07-03 | 15 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-15T03:36:34+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-03T09:16:22+02:00 | N | N |  | Y | Y
73350 | 440_EF_EarthRod.rfa | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:39:04+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T05:52:12+02:00 | N | N |  | Y | Y
73351 | 446_EF_EarthTestBox.rfa | 2026-06-15 | 2026-08-19 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:40:33+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T06:30:01+02:00 | N | N |  | Y | Y
73352 | 440_EF_EmergencyStopPushButtons.rfa | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:41:50+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T05:42:06+02:00 | N | N |  | Y | Y
73353 | 440_EF_EnergyBollard.rfa | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:42:53+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T05:32:52+02:00 | N | N |  | Y | Y
73354 | 440_EF_Equipotentialbondingbar.rfa | 2026-06-15 | 2026-06-17 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-15T03:44:37+02:00 ¦¦ END: status→resolved @ 2026-06-17T11:09:10+02:00 | N | N |  | Y | N
73355 | 446_EF_EquipotentialBondingBusbars_WallMounted.rfa | 2026-06-15 | 2026-08-21 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:45:40+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:31:57+02:00 | N | N |  | Y | Y
73356 | 440_EF_FixedConnection_1Pole.rfa | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:47:05+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-08-31T05:23:15+02:00 | N | N |  | Y | Y
73357 | 440_EF_FixedConnection_400V.rfa | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:48:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T03:05:27+02:00 | N | N |  | Y | Y
73359 | 444_EF_GooseneckBushing_NoSystem.rfa | 2026-06-15 | 2026-08-28 | 55 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:52:40+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T09:58:50+02:00 | N | N |  | Y | Y
73360 | 481_EF_Hygrostat.rfa | 2026-06-15 | 2026-08-27 | 54 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:54:11+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:38:58+02:00 | N | N |  | Y | Y
73361 | 444_EF_InstallationTrunking.rfa | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:55:36+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T08:30:08+02:00 | N | N |  | Y | Y
73362 | 440_EF_Isolator_3Phases.rfa | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:56:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T05:32:37+02:00 | N | N |  | Y | Y
73363 | 440_EF_Isolator_SinglePhase.rfa | 2026-06-15 | 2026-08-11 | 42 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:57:54+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T11:23:14+02:00 | N | N |  | Y | Y
73364 | 440_EF_JunctionBox_Ceiling_3Pole.rfa | 2026-06-15 | 2026-09-28 | 76 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:59:03+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T12:26:29+02:00 | N | N |  | Y | Y
73365 | 440_EF_JunctionBox_Floor_3Pole.rfa | 2026-06-15 | 2026-09-04 | 60 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T03:59:58+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:08:35+02:00 | N | N |  | Y | Y
73366 | 440_EF_BasementVentilationControl.rfa | 2026-06-15 | 2026-08-13 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:01:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T12:36:22+02:00 | N | N |  | Y | Y
73367 | 440_EF_KeySwitch_WallRecessed.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:02:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T05:42:49+02:00 | N | N |  | Y | Y
73368 | 440_EF_KNXPresenceDetection_Ceiling.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:03:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T04:46:15+02:00 | N | N |  | Y | Y
73369 | 440_EF_KNX_PushButtonSensor_2gang.rfa | 2026-06-15 | 2026-09-18 | 70 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:05:13+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:06:36+02:00 | N | N |  | Y | Y
73370 | 440_EF_MainEquipotentialBondingBar.rfa | 2026-06-15 | 2026-08-07 | 40 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:06:20+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T11:13:23+02:00 | N | N |  | Y | Y
73371 | 440_EF_MotionDetector360_CeilingSurface.rfa | 2026-06-15 | 2026-06-29 | 11 | handler_assign | status_closed | START: handler→h.pham @ 2026-06-15T04:07:36+02:00 ¦¦ END: status→closed @ 2026-06-29T10:37:19+02:00 | N | N |  | Y | N
73372 | 440_EF_PanelBoard.rfa | 2026-06-15 | 2026-09-04 | 60 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:08:52+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:08:39+02:00 | N | N |  | Y | Y
73373 | 440_EF_PresenceDetector_Ceiling.rfa | 2026-06-15 | 2026-08-19 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:09:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T11:27:08+02:00 | N | N |  | Y | Y
73374 | 440_EF_PresenceDetector_Wall.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:11:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T04:46:38+02:00 | N | N |  | Y | Y
73375 | 440_EF_PushButtonSensorKNX_4gang.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-15T04:12:11+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T04:46:50+02:00 | N | N |  | Y | Y
73435 | 440_EF_Raumluftfühler.rfa | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:41:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T04:47:01+02:00 | N | N |  | Y | Y
73436 | 440_EF_RoomSignallight.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:42:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T11:27:19+02:00 | N | N |  | Y | Y
73437 | 440_EF_RotaryDimmer.rfa | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:43:32+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T07:13:34+02:00 | N | N |  | Y | Y
73438 | 440_EF_ShaverSocketOutlet_Wall.rfa | 2026-06-18 | 2026-08-12 | 40 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:44:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T04:23:10+02:00 | N | N |  | Y | Y
73439 | 440_EF_SocketDistributionBox_Ceiling.rfa | 2026-06-18 | 2026-09-23 | 70 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:44:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-23T11:37:32+02:00 | N | N |  | Y | Y
73440 | 440_EF_SocketDistributionBox_Wall.rfa | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:45:52+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-09-04T05:06:17+02:00 | N | N |  | Y | Y
73441 | 440_EF_SocketOutletCombination_Ceiling.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:46:53+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T11:36:49+02:00 | N | N |  | Y | Y
73442 | 440_EF_SocketOutletRound_Floor.rfa | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:47:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T07:14:18+02:00 | N | N |  | Y | Y
73443 | 440_EF_SocketOutlet_FloorRecessed_Round.rfa | 2026-06-18 | 2026-08-11 | 39 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:48:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T02:51:54+02:00 | N | N |  | Y | Y
73444 | 440_EF_SocketOutlet_Horizontal_4Gangs_Wall.rfa | 2026-06-18 | 2026-08-11 | 39 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:49:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T11:21:15+02:00 | N | N |  | Y | Y
73445 | 444_EF_SocketOutlet_Rec_Floor.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:50:25+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T05:14:52+02:00 | N | N |  | Y | Y
73446 | 444_EF_USBSocketOutlet_WallFlush.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:52:33+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T04:28:54+02:00 | N | N |  | Y | Y
73447 | 444_EF_SocketOutlet_VerticalWallSurface_4Gangs.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:53:28+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T05:14:56+02:00 | N | N |  | Y | Y
73448 | 440_EF_SocketOutlet_Wall.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:54:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:26:00+02:00 | N | N |  | Y | Y
73449 | 440_EF_SocketOutlet_WallMounted_WaterProof.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:55:26+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:25:07+02:00 | N | N |  | Y | Y
73450 | 440_EF_SocketOutlet_Wall_3Phase.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T02:59:31+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:24:55+02:00 | N | N |  | Y | Y
73451 | 440_EF_SocketOutlet_Wall_4Gangs.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:01:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:24:30+02:00 | N | N |  | Y | Y
73452 | 440_EF_SocketOutlet_Wall_Combination.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:01:46+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:28:43+02:00 | N | N |  | Y | Y
73453 | 440_EF_SwitchableSocketOutlet_Ceiling.rfa | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:02:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T05:49:52+02:00 | N | N |  | Y | Y
73454 | 440_EF_SwitchableSocketOutlet_Floor.rfa | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:02:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T05:49:40+02:00 | N | N |  | Y | Y
73455 | 444_EF_SwitchableSocketOutlet_WallSurface.rfa | 2026-06-18 | 2026-08-21 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:03:31+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:31:46+02:00 | N | N |  | Y | Y
73456 | 440_EF_SwitchPushButton_FlushMounted.rfa | 2026-06-18 | 2026-08-20 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:04:09+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T03:07:01+02:00 | N | N |  | Y | Y
73457 | 440_EF_Switch_1Gang.rfa | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:04:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T10:10:57+02:00 | N | N |  | Y | Y
73458 | 440_EF_Switch_2Gang.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:05:13+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T11:27:33+02:00 | N | N |  | Y | Y
73459 | 440_EF_Switch_2Gang2Way.rfa | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:05:40+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:08:42+02:00 | N | N |  | Y | Y
73460 | 440_EF_Switch_3Gang.rfa | 2026-06-18 | 2026-08-20 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:06:15+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T03:05:43+02:00 | N | N |  | Y | Y
73461 | 451_EF_TelephoneOutlet_Single.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:06:43+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T05:59:23+02:00 | N | N |  | Y | Y
73462 | 440_EF_Thermosat.rfa | 2026-06-18 | 2026-08-26 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:07:23+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T11:32:24+02:00 | N | N |  | Y | Y
73463 | 440_EF_TouchPanelRoomOperating_WallMounted.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:07:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T11:36:39+02:00 | N | N |  | Y | Y
73464 | 440_EF_TripleSocketOutlet_Ceiling.rfa | 2026-06-18 | 2026-08-07 | 37 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:08:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T11:12:36+02:00 | N | N |  | Y | Y
73465 | 440_EF_TripleSocketOutlet_Floor.rfa | 2026-06-18 | 2026-08-25 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:09:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:23:28+02:00 | N | N |  | Y | Y
73466 | 440_EF_TripleSocketOutlet_Wall.rfa | 2026-06-18 | 2026-08-12 | 40 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:09:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T04:20:30+02:00 | N | N |  | Y | Y
73467 | 440_EF_WindowMotor_WallMounted.rfa | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:10:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:08:46+02:00 | N | N |  | Y | Y
73468 | 457_EF_VideoModul.rfa | 2026-06-18 | 2026-08-07 | 37 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-18T03:10:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T11:07:51+02:00 | N | N |  | Y | Y
73481 | 410_PF_CS_eRadiusReturnBends_Welded | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-19T04:10:42+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam **410_PF_CS_eRadiusReturnBends_Welded.rfa** Based on the spreadsheet input, the @ 2026-08-31T02:47:15+02:00 | N | N |  | Y | Y
73482 | 410_PF_CS_tTee_Welded | 2026-06-19 | 2026-09-16 | 64 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-06-19T04:12:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T05:28:25+02:00 | N | N |  | Y | Y
73483 | 434_PF_CO_fFlange_Mapress | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-19T05:36:47+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-16T09:38:08+02:00 | N | N |  | Y | Y
73484 | 434_PF_CO_eElbowDouble90Deg_MaleThread_MeplaFixAndPremounted | 2026-06-19 | 2026-07-29 | 29 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-19T05:36:43+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T06:34:51+02:00 | N | N |  | Y | Y
73485 | 434_PF_CO_eElbow90Deg_MaleThread_MeplaFixAndPremounted | 2026-06-19 | 2026-07-29 | 29 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-19T05:36:40+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-29T06:34:40+02:00 | N | N |  | Y | Y
73486 | 434_PF_CO_eDouble90ElbowMultiPort_Mapress | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-19T05:36:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T02:27:28+02:00 | N | N |  | Y | Y
73487 | 434_PF_CO_eAdaptorBend_MapressAndMeplaFix | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-19T05:35:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-13T08:01:40+02:00 | N | N |  | Y | Y
73488 | 434_PF_CO_eAdaptorBend_MapressAndFemaleThread_WithNut | 2026-06-19 | 2026-08-11 | 38 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-19T05:35:42+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-11T04:59:52+02:00 | N | N |  | Y | Y
73489 | 434_PF_CO_e90Elbow_ThreadAndMeplaFix | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-19T05:35:39+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-13T05:01:36+02:00 | N | N |  | Y | Y
73490 | 434_ME_WatercooledCondenserlessliquidchillers_30RW_WithoutHydraulicModule | 2026-06-19 | 2026-06-30 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-19T05:35:36+02:00 ¦¦ END: status→resolved @ 2026-06-30T05:42:54+02:00 | N | N |  | Y | N
73491 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC4Pipes | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-19T05:35:32+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-30T08:25:28+02:00 | N | N |  | Y | Y
73492 | 434_ME_WaterCooledCondenserlessLiquidchillers_30WGA | 2026-06-19 | 2026-06-23 | 3 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-19T05:35:29+02:00 ¦¦ END: status→resolved @ 2026-06-23T11:35:01+02:00 | N | N |  | Y | N
73493 | 434_ME_WaterCooledCondenserlessLiquidChillers_30WG | 2026-06-19 | 2026-06-23 | 3 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-19T05:35:26+02:00 ¦¦ END: status→resolved @ 2026-06-23T11:35:09+02:00 | N | N |  | Y | N
73494 | 434_ME_WateCooledCondenserlessLiquidChillers_WithHydraulicModule_30RW | 2026-06-19 | 2026-08-28 | 51 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-19T05:34:32+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T04:50:17+02:00 | N | N |  | Y | Y
73495 | 434_ME_VariableSpeedWaterCooledLiquidChiller_SingleCompressor30XW&V | 2026-06-19 | 2026-09-25 | 71 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-19T05:34:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T05:59:20+02:00 | N | N |  | Y | Y
73497 | 434_ME_Pump_WaterSupplyYonosGIGA&N | 2026-06-19 | 2026-08-27 | 50 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-19T05:34:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:11:59+02:00 | N | N |  | Y | Y
73498 | 434_ME_Pump_WaterSupplyVeroTwinDPE | 2026-06-19 | 2026-08-17 | 42 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-19T05:34:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-17T05:01:09+02:00 | N | N |  | Y | Y
73499 | 434_ME_Pump_WaterSupplyVeroLineIPE | 2026-06-19 | 2026-08-27 | 50 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-19T05:34:08+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:12:02+02:00 | N | N |  | Y | Y
73500 | 434_ME_Pump_WaterSupplySCP | 2026-06-19 | 2026-08-17 | 42 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-19T05:34:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-17T04:45:00+02:00 | N | N |  | Y | N
73501 | 434_ME_Pump_WaterSupplyCronoNorm&NLG | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-19T05:34:00+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-08-31T03:41:31+02:00 | N | N |  | Y | Y
73502 | 434_ME_Pump_WaterSupplyCronoBlocBLE | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-19T05:32:52+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-14T08:37:31+02:00 | N | N |  | Y | Y
73503 | 434_ME_Pump_WaterSupplyAtmosTERA&SCH | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-19T05:32:47+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-13T05:31:58+02:00 | N | N |  | Y | Y
73504 | 434_ME_Pump_WaterSupplyAtmosI | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-19T05:32:43+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-30T08:24:58+02:00 | N | N |  | Y | Y
73505 | 434_ME_Pump_WaterSupplyAtmosGIGA&N | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-19T05:32:37+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-16T09:20:37+02:00 | N | N |  | Y | Y
73506 | 434_ME_Pump_SingleStageLowPressureBAC | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-19T05:32:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-15T11:49:53+02:00 | N | N |  | Y | Y
73507 | 434_ME_Pump_SingleStageGlandedBM | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-19T05:32:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-30T08:24:40+02:00 | N | N |  | Y | Y
73508 | 434_ME_Pump_Circulator_YonosGIGA20D | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-19T05:32:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-15T05:10:53+02:00 | N | N |  | Y | Y
73509 | 420_PF_CO_rReducer_Soldered | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-13T08:45:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T02:49:27+02:00 | N | N |  | Y | Y
73510 | 410_PA_AdapterAndExpansionPiece_Flanged | 2026-06-24 | 2026-06-30 | 5 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-06-24T03:19:03+02:00 ¦¦ END: status→resolved @ 2026-06-30T11:09:45+02:00 | N | N |  | Y | N
73511 | 420_PA_WaterMeter_Threaded_Standard | 2026-07-08 | 2026-08-17 | 29 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-08T03:05:36+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-17T11:37:38+02:00 | N | N |  | Y | Y
73512 | 420_PA_ThreeWayMotorisedControlValve_Thread | 2026-06-25 | 2026-06-30 | 4 | handler_assign | status_resolved | START: handler→d.phan @ 2026-06-25T08:56:04+02:00 ¦¦ END: status→resolved @ 2026-06-30T09:35:01+02:00 | N | N |  | Y | N
73513 | 420_PA_ThreeWayMotorisedControlValve_Flanged | 2026-06-25 | 2026-07-27 | 23 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-25T08:56:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-27T11:30:09+02:00 | N | N |  | Y | Y
73514 | 420_PA_TemperatureRegulatorValve_SelfOperated | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-25T08:55:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-05T05:29:47+02:00 | N | N |  | Y | Y
73515 | 420_PA_SmartForEnergyManagement_Thread | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-25T08:55:52+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T06:49:23+02:00 | N | N |  | Y | Y
73516 | 420_PA_SmartForEnergyManagement_Flanged | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-25T08:55:48+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T06:17:46+02:00 | N | N |  | Y | Y
73517 | 420_PA_SixWayMotorisedControlValve_Threaded | 2026-06-25 | 2026-08-13 | 36 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-25T08:55:44+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-13T11:23:29+02:00 | N | N |  | Y | Y
73518 | 410_PA_AirReleaseValve_Threaded | 2026-07-02 | 2026-08-20 | 36 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-02T03:15:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-20T04:53:18+02:00 | N | N |  | Y | Y
73519 | 410_PA_AngleSafetyValve_Threaded | 2026-07-02 | 2026-08-03 | 23 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-02T03:15:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-03T05:41:49+02:00 | N | N |  | Y | Y
73520 | 420_PA_ShutoffValve_Motorized | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | START: handler→d.phan @ 2026-06-25T08:55:40+02:00 ¦¦ END: status→resolved @ 2026-07-01T08:36:15+02:00 | N | N |  | Y | N
73521 | 420_PA_ShutOffValveWithSafetyFunction_Flanged | 2026-06-25 | 2026-07-16 | 16 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-25T08:55:37+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-16T12:03:28+02:00 | N | N |  | Y | Y
73522 | 420_PA_PIQCVValve_Thread | 2026-06-25 | 2026-07-08 | 10 | handler_assign | status_resolved | START: handler→b.tran @ 2026-06-25T08:54:58+02:00 ¦¦ END: status→resolved @ 2026-07-08T09:44:48+02:00 | N | N |  | Y | N
73523 | 410_PA_AngleSeatPistonValve_Flanged | 2026-07-02 | 2026-08-20 | 36 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-02T03:16:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-20T04:57:38+02:00 | N | N |  | Y | Y
73524 | 420_PA_PICVValve_Thread | 2026-06-19 | 2026-08-07 | 36 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-19T05:31:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-07T11:12:10+02:00 | N | N |  | Y | Y
73525 | 420_PA_ManifoldConnection_Thread | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-06-19T05:30:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T11:05:43+02:00 | N | N |  | Y | Y
73526 | 420_PA_FlexibleConnection_Flanged_Standard | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-19T05:29:42+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-16T03:54:14+02:00 | N | N |  | Y | Y
73527 | 420_PA_FilterValve_Thread | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-19T05:29:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-15T11:46:02+02:00 | N | N |  | Y | Y
73528 | 420_PA_FilterValve_Flanged | 2026-06-19 | 2026-09-21 | 67 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-19T05:29:36+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T10:26:13+02:00 | N | N |  | Y | Y
73529 | 420_PA_FillAndDrainBallValve_Threaded | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-19T05:29:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-13T05:08:56+02:00 | N | N |  | Y | Y
73530 | 420_PA_ExpansionJoint_Weld | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-19T05:29:30+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T09:52:51+02:00 | N | N |  | Y | Y
73531 | 420_PA_ExpansionJoint_Threaded | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-19T05:29:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-14T08:50:48+02:00 | N | N |  | Y | Y
73532 | 420_PA_ExpansionJoint_Flanged | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-19T05:29:23+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-03T02:59:35+02:00 | N | N |  | Y | Y
73533 | 420_PA_DrainValve_Threaded | 2026-06-19 | 2026-06-25 | 5 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-06-19T05:28:44+02:00 ¦¦ END: status→resolved @ 2026-06-25T04:04:42+02:00 | N | N |  | Y | N
73534 | 420_PA_DrainValve_Thread_Standard | 2026-06-19 | 2026-09-28 | 72 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-19T05:28:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T05:09:15+02:00 | N | N |  | Y | Y
73535 | 420_PA_DiscCheckValve_Flanged_Standard | 2026-06-19 | 2026-09-07 | 57 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-19T05:28:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T04:37:30+02:00 | N | N |  | Y | Y
73536 | 420_PA_DifferentialPressureSensor_Standard | 2026-06-19 | 2026-08-14 | 41 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-19T05:28:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-14T11:32:05+02:00 | N | N |  | Y | Y
73537 | 420_PA_DifferentialPressureSensor | 2026-06-19 | 2026-09-11 | 61 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-19T05:28:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T04:42:45+02:00 | N | N |  | Y | Y
73538 | 420_PA_DifferentialPressureSensor | 2026-06-19 | 2026-06-25 | 5 | handler_assign | status_closed | START: handler→ht.tran @ 2026-06-19T05:28:19+02:00 ¦¦ END: status→closed @ 2026-06-25T04:21:48+02:00 | N | N |  | Y | N
73539 | 420_PA_DifferentialPressureGauge_Standard | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-19T05:28:13+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-04T03:45:33+02:00 | N | N |  | Y | Y
73540 | 420_PA_DifferentialPressureControlValve_Thread | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-19T05:27:30+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T05:38:32+02:00 | N | N |  | Y | Y
73541 | 420_PA_CheckValveWithThermometer_Thread | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-19T05:27:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T04:45:41+02:00 | N | N |  | Y | Y
73542 | 420_PA_CapValve_Thread | 2026-06-19 | 2026-07-10 | 16 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-19T05:27:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-10T08:44:11+02:00 | N | N |  | Y | Y
73543 | 420_PA_ButterflyvalveMotor_Flanged | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-19T05:27:21+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-08-31T04:05:14+02:00 | N | N |  | Y | Y
73544 | 420_PA_ButterflyValve_Thread_LeverStandard | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-19T05:27:18+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-04T03:13:10+02:00 | N | N |  | Y | Y
73545 | 420_PA_ButterflyValve_Thread_GearStandard | 2026-06-19 | 2026-10-01 | 75 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-19T05:27:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:31:30+02:00 | N | N |  | Y | N
73546 | 420_PA_ButterflyValve_Flanged_LeverStandard | 2026-06-19 | 2026-08-05 | 34 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-19T05:27:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-05T05:48:03+02:00 | N | N |  | Y | Y
73547 | 420_PA_ButterflyValve_Flanged_GearStandard | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-19T05:26:30+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-30T08:24:24+02:00 | N | N |  | Y | Y
73548 | 420_PA_ButterflyValveHandwheel_Flanged | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-19T05:26:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-30T11:34:14+02:00 | N | N |  | Y | Y
73549 | 420_PA_BasketStrainerValve_Thread_Standard | 2026-06-19 | 2026-06-24 | 4 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-06-19T05:26:19+02:00 ¦¦ END: status→resolved @ 2026-06-24T11:53:09+02:00 | N | N |  | Y | Y
73550 | 420_PA_BasketStrainerValve_Flanged_Standard | 2026-06-19 | 2026-07-10 | 16 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-19T05:26:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-10T09:27:53+02:00 | N | N |  | Y | N
73551 | 420_PA_BallValve_Threaded | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-19T05:26:09+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-04T02:58:26+02:00 | N | N |  | Y | Y
73552 | 420_PA_BallValve_Thread_WheelStandard | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-19T05:26:04+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-03T03:11:52+02:00 | N | N |  | Y | Y
73553 | 420_PA_BallValve_Thread_LeverStandard | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-19T05:26:00+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-03T03:07:41+02:00 | N | N |  | Y | Y
73554 | 410_PA_AngleSeatPistonValve_Threaded | 2026-07-02 | 2026-07-08 | 5 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-02T08:43:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-08T06:09:03+02:00 | N | N |  | Y | Y
73555 | 410_PA_AngleValve_Threaded_WithRegulatingFunction | 2026-07-03 | 2026-08-20 | 35 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-03T03:44:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-20T03:06:10+02:00 | N | N |  | Y | Y
73556 | 410_PA_AutomaticBackwashFilter_Flanged | 2026-07-03 | 2026-07-10 | 6 | handler_assign | status_resolved | START: handler→k.mai @ 2026-07-03T03:45:33+02:00 ¦¦ END: status→resolved @ 2026-07-10T10:58:28+02:00 | N | N |  | Y | Y
73557 | 410_PA_AutomaticCirculationRegulatingValve | 2026-07-03 | 2026-07-09 | 5 | handler_assign | status_resolved | START: handler→k.mai @ 2026-07-03T03:46:00+02:00 ¦¦ END: status→resolved @ 2026-07-09T10:51:24+02:00 | N | N |  | Y | Y
73558 | 410_PA_AutomaticHygieneFlushingStationHS10_Geberit | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-03T03:46:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T04:53:36+02:00 | N | N |  | Y | Y
73559 | 410_PA_BackflowPreventerValve_Threaded | 2026-07-03 | 2026-07-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-03T03:46:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-30T11:32:00+02:00 | N | N |  | Y | Y
73561 | 410_PA_BallValve_Flanged | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-03T03:48:38+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T06:36:36+02:00 | N | N |  | Y | Y
73562 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Return.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-25T11:19:37+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T04:52:17+02:00 | N | N |  | Y | Y
73563 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Supply.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-06-25T11:19:37+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T04:52:05+02:00 | N | N |  | Y | Y
73564 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Exhaust.rfa | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-25T11:19:27+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T03:30:10+02:00 | N | N |  | Y | Y
73565 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Supply.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-25T11:19:27+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T04:10:12+02:00 | N | N |  | Y | Y
73566 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Return.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-25T11:18:42+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T04:09:12+02:00 | N | N |  | Y | Y
73567 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Supply.rfa | 2026-06-25 | 2026-07-15 | 15 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-25T11:18:42+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-15T05:41:10+02:00 | N | N |  | Y | Y
73568 | 430_AT_DiscValvesSTVA_Return.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-25T11:18:30+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T11:40:41+02:00 | N | N |  | Y | Y
73569 | 430_AT_DiscValvesSTVZ_Supply.rfa | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-25T11:18:30+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T04:56:13+02:00 | N | N |  | Y | Y
73570 | 430_AT_DisplacementFlowDiffusers_Wall_QLF_Supply.rfa | 2026-06-25 | 2026-07-03 | 7 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-06-25T11:18:19+02:00 ¦¦ END: status→resolved @ 2026-07-03T06:14:36+02:00 | N | N |  | Y | Y
73571 | 430_AT_DisplacementFlowDiffusers_Wall_QLV_Supply.rfa | 2026-06-25 | 2026-07-03 | 7 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-06-25T11:18:19+02:00 ¦¦ END: status→resolved @ 2026-07-03T06:23:25+02:00 | N | N |  | Y | Y
73572 | 430_AT_DoubleSlot_CeilingHorizontal_1ConnectionSymmetrical_Withbox.rfa | 2026-06-25 | 2026-09-11 | 57 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-06-25T11:18:19+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T04:43:01+02:00 | N | N |  | Y | Y
73573 | 430_AT_EggCrateAirGrill_HorizontalCeiling_Rectangular_Return.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-25T11:18:06+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T04:04:13+02:00 | N | N |  | Y | Y
73574 | 430_AT_ExternalRainProtectionGrill_Wall_Round.rfa | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-25T11:18:06+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T02:40:48+02:00 | N | N |  | Y | Y
73575 | 430_AT_Grilles_Wall_Rectangular_TRS_FreshAirIntake.rfa | 2026-06-22 | 2026-07-09 | 14 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-22T03:22:32+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-09T03:23:23+02:00 | N | N |  | Y | Y
73576 | 430_AT_Grilles_Wall_Rectangular_TRS_Return.rfa | 2026-06-22 | 2026-09-23 | 68 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-22T03:22:15+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T07:20:23+02:00 | N | N |  | Y | Y
73577 | 430_AT_Grilles_Wall_Rectangular_TRS_Supply.rfa | 2026-06-22 | 2026-09-21 | 66 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-06-22T03:21:48+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T11:44:09+02:00 | N | N |  | Y | Y
73578 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdividedExhaust.rfa | 2026-06-22 | 2026-07-16 | 19 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-06-22T03:15:10+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T09:35:51+02:00 | N | N |  | Y | Y
73579 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdividedSupply.rfa | 2026-06-22 | 2026-06-25 | 4 | handler_assign | status_resolved | START: handler→d.nguyen @ 2026-06-22T03:15:10+02:00 ¦¦ END: status→resolved @ 2026-06-25T09:31:30+02:00 | N | N |  | Y | N
73580 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Exhaust.rfa | 2026-06-22 | 2026-07-23 | 24 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-22T03:11:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T10:55:03+02:00 | N | N |  | Y | Y
73581 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Supply.rfa | 2026-06-22 | 2026-07-23 | 24 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-06-22T03:11:58+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T10:54:28+02:00 | N | N |  | Y | N
73582 | 410_PA_BackflowPreventer_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-03T03:47:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:56:54+02:00 | N | N |  | Y | Y
73583 | 410_PA_BallValve_Threaded | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-03T03:49:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T06:36:21+02:00 | N | N |  | Y | Y
73584 | 410_PA_CoarseTrap | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-03T03:49:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T06:35:34+02:00 | N | N |  | Y | Y
73585 | 410_PA_CombinationAngleValve_Standard | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-03T03:50:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T10:21:04+02:00 | N | N |  | Y | Y
73586 | 410_PA_DiaphragmValve | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-03T03:50:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:29:28+02:00 | N | N |  | Y | Y
73587 | 410_PA_DoubleInstallationRackWatermeter_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-03T03:51:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:29:13+02:00 | N | N |  | Y | Y
73588 | 410_PA_DrainValve_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-03T03:51:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T06:04:02+02:00 | N | N |  | Y | Y
73589 | 410_PA_FillSetStandardValve_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-03T03:51:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:56:40+02:00 | N | N |  | Y | Y
73590 | 410_PA_FillsoftHousing_Threaded | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-03T03:52:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T03:28:03+02:00 | N | N |  | Y | Y
73591 | 410_PA_Filter_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-03T03:56:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T06:45:54+02:00 | N | N |  | Y | Y
73592 | 410_PA_FittingSpacerForWaterMeter_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-03T03:58:24+02:00 ¦¦ END: hu.dam: tv.huynh This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-05T08:15:17+02:00 | N | N |  | Y | Y
73593 | 410_PA_FlexibleConnection_Flanged | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-03T04:01:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T05:50:22+02:00 | N | N |  | Y | Y
73594 | 410_PA_FloatingValve_Threaded | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-03T04:56:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T04:56:43+02:00 | N | N |  | Y | Y
73595 | 410_PA_FlowSplitterBox_Floor_Threaded_KHS | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-03T04:56:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T06:31:52+02:00 | N | N |  | Y | Y
73596 | 410_PA_FlowSplitterSet_Threaded_KHS | 2026-07-03 | 2026-09-21 | 57 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-03T04:57:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T03:14:00+02:00 | N | N |  | Y | Y
73597 | 410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS | 2026-07-03 | 2026-09-08 | 48 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-03T04:57:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T05:29:07+02:00 | N | N |  | Y | Y
73598 | 410_PA_FlowSplitterUnit_Threaded_DynamicKHS | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-03T04:58:30+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:56:27+02:00 | N | N |  | Y | Y
73599 | 410_PA_FlowTemperatureMeterValve_Threaded | 2026-07-24 | 2026-08-25 | 23 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-24T04:09:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T11:41:32+02:00 | N | N |  | Y | Y
73600 | 410_PA_FlushMountedStopValve_Mapress_UpPlus | 2026-07-03 | 2026-07-10 | 6 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-07-03T05:02:36+02:00 ¦¦ END: status→resolved @ 2026-07-10T11:01:24+02:00 | N | N |  | Y | Y
73603 | 410_PA_FlushMoutedStopValve_Threaded_UpPlus | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-03T05:14:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T11:37:17+02:00 | N | N |  | Y | Y
73604 | 410_PA_FunnelSiphon_Horizontal | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-03T05:14:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:55:48+02:00 | N | N |  | Y | Y
73605 | 410_PA_GateValveSealingDirectionWithDrain_Threaded | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-03T05:25:34+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T11:37:01+02:00 | N | N |  | Y | Y
73606 | 410_PA_GateValveWithDrain_Threaded | 2026-07-03 | 2026-08-25 | 38 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-03T05:26:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T03:23:31+02:00 | N | N |  | Y | Y
73607 | 410_PA_GateValve_Flanged | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-03T05:27:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T09:43:16+02:00 | N | N |  | Y | Y
73608 | 410_PA_GateValve_Threaded | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-03T05:27:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T09:43:04+02:00 | N | N |  | Y | Y
73609 | 410_PA_GlobeValve_Flanged | 2026-07-03 | 2026-08-14 | 31 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-03T05:27:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T10:56:04+02:00 | N | N |  | Y | Y
73610 | 410_PA_GlobeValve_Threaded | 2026-07-03 | 2026-08-03 | 22 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-03T05:28:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-03T04:18:37+02:00 | N | N |  | Y | Y
73611 | 410_PA_KHSFlushPoint_Threaded_230V | 2026-07-03 | 2026-08-03 | 22 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-03T05:28:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-03T05:51:24+02:00 | N | N |  | Y | Y
73612 | 410_PA_KHSFlushPoint_Threaded_24V | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-03T05:29:11+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:51:55+02:00 | N | N |  | Y | Y
73613 | 410_PA_KHSFlushPoint_Threaded_ControlPlus230V | 2026-07-03 | 2026-08-25 | 38 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-03T05:33:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T07:23:00+02:00 | N | N |  | Y | Y
73614 | 410_PA_KHSFlushPoint_Threaded_ControlPlus24V | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-03T05:33:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T04:53:08+02:00 | N | N |  | Y | Y
73615 | 410_PA_KugelSiphon_Standard | 2026-07-09 | 2026-08-24 | 33 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-09T05:27:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T10:37:04+02:00 | N | N |  | Y | Y
73616 | 410_PA_MotorButterflyValve_Flanged | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-09T05:27:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-20T04:51:33+02:00 | N | N |  | Y | Y
73618 | 410_PA_NozzleCheckValve_Flanged | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-10T06:12:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:28:53+02:00 | N | N |  | Y | Y
73620 | 410_PA_OutletValve_Threaded | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-10T06:13:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T09:43:31+02:00 | N | N |  | Y | Y
73621 | 410_PA_OutletValve_Threaded_WithHoseScrewConnection | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-10T06:13:51+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T05:54:15+02:00 | N | N |  | Y | Y
73622 | 410_PA_PoolMainDrain_Threaded | 2026-07-10 | 2026-08-14 | 26 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-10T06:14:16+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T10:55:35+02:00 | N | N |  | Y | Y
73623 | 410_PA_PoolReturnJet_Threaded | 2026-07-10 | 2026-08-14 | 26 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-10T06:15:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T10:56:30+02:00 | N | N |  | Y | Y
73624 | 410_PA_PoolSkimmer_Threaded | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-10T06:16:14+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T11:44:40+02:00 | N | N |  | Y | Y
73631 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Exhaust.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-25T11:17:54+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T03:49:34+02:00 | N | N |  | Y | Y
73632 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Supply.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-25T11:17:54+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T03:45:25+02:00 | N | N |  | Y | Y
73633 | 430_AT_InspectionOpenings_RecDuctHorizontal_Rectangular.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-25T11:17:39+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T11:21:33+02:00 | N | N |  | Y | Y
73634 | 430_AT_InspectionOpenings_RoundDuctHorizontal_Oval.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-25T11:17:39+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-24T03:45:09+02:00 | N | N |  | Y | Y
73635 | 430_AT_JetDiffuser_Round_Standard.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-25T11:17:39+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T11:41:47+02:00 | N | N |  | Y | Y
73636 | 430_AT_LamellarHood_Roof_Rectangular_Exhaust.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-25T11:17:16+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T05:52:54+02:00 | N | N |  | Y | Y
73637 | 430_AT_LamellarHood_Roof_Rectangular_FreshAirIntake.rfa | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-06-25T11:17:16+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T02:41:02+02:00 | N | N |  | Y | Y
73638 | 430_AT_LourveCover_Roof.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-06-25T11:17:39+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T11:37:59+02:00 | N | N |  | Y | Y
73639 | 430_AT_Louvre_Standard.rfa | 2026-06-24 | 2026-08-04 | 30 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-06-24T02:41:06+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-04T11:37:48+02:00 | N | N |  | Y | Y
73640 | 430_AT_NozzlesElectricActuator_DUK_E_Exhaust.rfa | 2026-06-25 | 2026-09-11 | 57 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-25T03:00:53+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T04:43:05+02:00 | N | N |  | Y | Y
73641 | 430_AT_NozzlesElectricActuator_DUK_E_Supply.rfa | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-25T03:00:46+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T11:44:11+02:00 | N | N |  | Y | Y
73644 | 410_PA_BallValve_SocketFusion | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-10T06:16:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T03:08:08+02:00 | N | N |  | Y | Y
73645 | 410_PA_StopValve_SocketFusion | 2026-07-10 | 2026-08-24 | 32 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-10T06:17:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T11:45:11+02:00 | N | N |  | Y | Y
73646 | 410_PA_PressureGauge_WithSiphon | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-10T06:25:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T07:29:16+02:00 | N | N |  | Y | Y
73648 | 410_PA_PressureReducingValveFilterCombination_Threaded | 2026-07-10 | 2026-07-17 | 6 | handler_assign | status_resolved | START: handler→t.luu @ 2026-07-10T06:26:25+02:00 ¦¦ END: status→resolved @ 2026-07-17T11:17:59+02:00 | N | N |  | Y | Y
73649 | 410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded | 2026-07-10 | 2026-09-09 | 44 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-10T06:26:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T05:59:30+02:00 | N | N |  | Y | Y
73650 | 410_PA_PressureReducingValve_Flanged | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-10T06:27:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T10:00:23+02:00 | N | N |  | Y | Y
73652 | 410_PA_PressureReducingValve_Threaded | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-10T06:27:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T11:06:44+02:00 | N | N |  | Y | Y
73653 | 410_PA_PressureRegulator_Thread | 2026-07-10 | 2026-08-25 | 33 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-10T06:28:11+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T11:41:35+02:00 | N | N |  | Y | Y
73654 | 410_PA_SamplingValveForWashBasinAngleValve_Standard_SS | 2026-07-10 | 2026-08-19 | 29 | handler_assign | status_resolved | START: handler→ttc.bui @ 2026-07-10T06:29:00+02:00 ¦¦ END: status→resolved @ 2026-08-19T11:11:13+02:00 | N | N |  | Y | Y
73655 | 410_PA_SamplingValve_Standard_Gunmetal | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-10T06:29:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T11:05:45+02:00 | N | N |  | Y | Y
73656 | 410_PA_SamplingValve_Standard_SS | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-10T06:29:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T11:25:14+02:00 | N | N |  | Y | Y
73657 | 410_PA_ShutoffValve_Flanged | 2026-07-10 | 2026-08-07 | 21 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-10T06:30:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-07T04:11:00+02:00 | N | N |  | Y | Y
73658 | 410_PA_ShutoffValve_Flanged_DrainValve | 2026-07-15 | 2026-08-06 | 17 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-15T09:32:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T09:43:47+02:00 | N | N |  | Y | Y
73659 | 410_PA_ShutoffValve_Threaded | 2026-07-15 | 2026-08-18 | 25 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-15T09:32:45+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-18T11:56:39+02:00 | N | N |  | Y | Y
73660 | 410_PA_ShutoffValve_WithDrainPlug_Threaded | 2026-07-15 | 2026-08-26 | 31 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-15T09:33:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-26T11:38:29+02:00 | N | N |  | Y | Y
73661 | 410_PA_SingleInstallationRackWatermeter_Threaded | 2026-07-15 | 2026-09-21 | 49 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-15T09:33:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T03:14:02+02:00 | N | N |  | Y | Y
73662 | 410_PA_SolenoidControlValve_Flanged | 2026-07-15 | 2026-08-25 | 30 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-15T09:33:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T11:48:26+02:00 | N | N |  | Y | Y
73663 | 410_PA_ShutoffValve_Mapress_WithDrainValve | 2026-07-15 | 2026-08-12 | 21 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-15T09:34:10+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:19:20+02:00 | N | N |  | Y | Y
73664 | 410_PA_StainlessSteel_ShutoffValve_MapressGeberit | 2026-07-16 | 2026-07-17 | 2 | handler_assign | status_resolved | START: handler→ttc.bui @ 2026-07-16T03:37:02+02:00 ¦¦ END: status→resolved @ 2026-07-17T10:40:01+02:00 | N | N |  | Y | Y
73665 | 410_PA_StraightSafetyValve_Threaded | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-16T03:37:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T11:48:22+02:00 | N | N |  | Y | Y
73666 | 410_PA_StaticBalancingValve_Threaded_MultiFixPlus | 2026-07-16 | 2026-09-11 | 42 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-16T03:38:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T07:34:11+02:00 | N | N |  | Y | Y
73667 | 410_PA_StaticBalancingValve_UnionThreaded_MultiFixPlus | 2026-07-16 | 2026-08-12 | 20 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-16T08:39:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:20:11+02:00 | N | N |  | Y | Y
73668 | 410_PA_SwingcheckValve_Flanged | 2026-07-16 | 2026-08-17 | 23 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-16T08:40:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T11:35:42+02:00 | N | N |  | Y | Y
73669 | 410_PA_SwingcheckValve_Threaded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-16T08:40:38+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T03:05:55+02:00 | N | N |  | Y | Y
73670 | 410_PA_SystemSeparator_Flanged | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-16T09:18:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T03:03:06+02:00 | N | N |  | Y | Y
73671 | 410_PA_SystemSeparator_Threaded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-16T09:19:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T02:54:10+02:00 | N | N |  | Y | Y
73672 | 410_PA_TemperatureMeasuringValve_Threaded_KHS | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-16T09:19:24+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-27T04:28:58+02:00 | N | N |  | Y | Y
73673 | 410_PA_THandleBallValve_Threaded | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-16T09:20:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T03:45:52+02:00 | N | N |  | Y | Y
73674 | 410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-16T09:22:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:28:09+02:00 | N | N |  | Y | Y
73675 | 410_PA_ThreePiecesBallValve_Welded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-16T09:23:10+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:36:05+02:00 | N | N |  | Y | Y
73676 | 410_PA_ThreeWayMotorisedControlValve_Flanged | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-16T09:23:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:38:09+02:00 | N | N |  | Y | Y
73677 | 410_PA_ThreeWayMotorisedControlValve_Threaded | 2026-07-16 | 2026-09-18 | 47 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-16T09:23:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:09:21+02:00 | N | N |  | Y | Y
73678 | 410_PA_TwoWayDiaphragmValve_Threaded | 2026-07-16 | 2026-08-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-16T09:24:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-18T11:06:58+02:00 | N | N |  | Y | Y
73679 | 410_PA_TwoWayDiaphragmValve_Flanged | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-16T09:25:10+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-27T04:29:01+02:00 | N | N |  | Y | Y
73680 | 410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-16T09:25:38+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T06:22:10+02:00 | N | N |  | Y | Y
73681 | 410_PA_UpETATHERMThermostaticBalancingValve_Threaded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-16T09:25:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T07:10:17+02:00 | N | N |  | Y | Y
73682 | 410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress | 2026-07-16 | 2026-08-18 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-16T09:26:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-18T03:04:10+02:00 | N | N |  | Y | Y
73683 | 410_PA_UPVSenkrecht | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-16T09:27:04+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-25T03:23:34+02:00 | N | N |  | Y | Y
73684 | 410_PA_UPConcealedShutoffValve | 2026-07-16 | 2026-08-12 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-16T09:27:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:32:50+02:00 | N | N |  | Y | Y
73685 | 410_PA_VAVFullFlowShutOffValve_FemaleThreaded | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-16T09:27:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-27T05:14:59+02:00 | N | N |  | Y | Y
73686 | 410_PA_VentCowl | 2026-07-24 | 2026-08-17 | 17 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-24T03:21:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T11:35:12+02:00 | N | N |  | Y | Y
73687 | 410_PA_WaferButterflyValve_Flanged | 2026-07-24 | 2026-08-27 | 25 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-24T03:22:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-27T05:15:02+02:00 | N | N |  | Y | Y
73688 | 410_PA_WaterHammerArrestor_Threaded | 2026-07-24 | 2026-08-26 | 24 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-24T03:23:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-26T11:38:32+02:00 | N | N |  | Y | Y
73689 | 410_PA_WaterMeterUNI | 2026-07-24 | 2026-08-21 | 21 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-24T03:24:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T10:34:49+02:00 | N | N |  | Y | Y
73690 | 410_PA_WaterMeter_Flanged | 2026-07-24 | 2026-09-09 | 34 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-24T03:26:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T05:59:33+02:00 | N | N |  | Y | Y
73691 | 410_PA_WaterMeter_Threaded | 2026-07-24 | 2026-08-17 | 17 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-24T03:26:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T11:34:42+02:00 | N | N |  | Y | Y
73692 | 445_LF_3FoldPendantLight_CeilingSuspended.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:30:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T03:06:47+02:00 | N | N |  | Y | Y
73693 | 410_PA_YStrainer_Flanged | 2026-07-24 | 2026-09-10 | 35 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-24T03:28:06+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-10T05:08:12+02:00 | N | N |  | Y | Y
73694 | 440_LF_BathroomLuminaire_WallMounted_Rectangular.rfa | 2026-06-22 | 2026-09-10 | 59 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:31:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-10T05:08:15+02:00 | N | N |  | Y | Y
73695 | 410_PA_YStrainer_Threaded | 2026-07-24 | 2026-08-21 | 21 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-24T03:28:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T10:31:33+02:00 | N | N |  | Y | Y
73696 | 410_PA_ZBCapRoof_Standard | 2026-07-24 | 2026-09-18 | 41 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-24T03:28:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:09:24+02:00 | N | N |  | Y | Y
73697 | 445_LF_CoreLineLEDLight_CeilingSuspended.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:33:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:10:27+02:00 | N | N |  | Y | Y
73698 | 445_LF_CoreLineLEDLight_WallSurface.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:35:52+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:40:43+02:00 | N | N |  | Y | Y
73699 | 445_LF_CorelineSlimDownlight_CeilingMounted.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:38:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:40:26+02:00 | N | N |  | Y | Y
73700 | 445_LF_CorelineSlimDownlight_CeilingRecessed.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:41:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:40:14+02:00 | N | N |  | Y | Y
73701 | 445_LF_CorelineSpotlight_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:43:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T05:12:56+02:00 | N | N |  | Y | Y
73702 | 445_LF_DownlightLEDrigid_CeilingRecessed.rfa | 2026-06-22 | 2026-09-07 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:44:19+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-07T03:18:35+02:00 | N | N |  | Y | Y
73703 | 445_LF_DownlightLEDSwivelling_CeilingRecessed.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:45:15+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:38:56+02:00 | N | N |  | Y | Y
73704 | 445_LF_EscapeSign_CeilingMounted.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:46:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:38:27+02:00 | N | N |  | Y | Y
73705 | 445_LF_EscapeSign_CeilingRecessed.rfa | 2026-06-22 | 2026-09-22 | 67 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:54:38+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-22T09:50:10+02:00 | N | N |  | Y | Y
73706 | 445_LF_EscapeSign_WallMounted.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:55:28+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:33:36+02:00 | N | N |  | Y | Y
73707 | 445_LF_ExitCube_Ceiling.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:56:07+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:33:24+02:00 | N | N |  | Y | Y
73708 | 445_LF_FixedOpticSmallBodyIroundOutdoorlight_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:56:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:33:12+02:00 | N | N |  | Y | Y
73709 | 445_LF_GreenSpaceAccentSpotlightRigid_CeilingRecessed.rfa | 2026-06-22 | 2026-08-11 | 37 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T09:57:43+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T02:50:23+02:00 | N | N |  | Y | Y
73710 | 440_LF_InteriorLuminaireBL_CeilingRecessed_Rectangular.rfa | 2026-06-22 | 2026-06-25 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T09:58:21+02:00 ¦¦ END: status→resolved @ 2026-06-25T11:01:08+02:00 | N | N |  | Y | N
73711 | 440_LF_InteriorLuminaireINDMP_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T09:59:21+02:00 ¦¦ END: status→resolved @ 2026-06-29T11:44:49+02:00 | N | N |  | Y | N
73712 | 445_LF_LaserBladeLightXSWallWasher_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:00:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T06:21:41+02:00 | N | N |  | Y | Y
73713 | 445_LF_LaserBladeLightXS_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:00:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T05:28:34+02:00 | N | N |  | Y | Y
73714 | 445_LF_LeadSacidTwinHeadEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-07 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:01:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T11:07:30+02:00 | N | N |  | Y | Y
73715 | 440_LF_LEDAccentGridlight_CeilingRecessed.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_closed | START: handler→h.pham @ 2026-06-22T10:01:56+02:00 ¦¦ END: status→closed @ 2026-06-29T10:35:59+02:00 | N | N |  | Y | N
73716 | 445_LF_LEDAccentRigidlight_CeilingRecessed_Rectangular.rfa | 2026-06-22 | 2026-08-14 | 40 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:02:32+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T10:35:18+02:00 | N | N |  | Y | Y
73717 | 445_LF_LEDBAPPendantLightWithAdjustableRod_CeilingSuspended.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:03:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:33:00+02:00 | N | N |  | Y | Y
73718 | 445_LF_LEDDeckeneinbauMontage_CeilingMounted_LG6E.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:03:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T10:38:53+02:00 | N | N |  | Y | Y
73719 | 445_LF_LEDDoubleHeadEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:04:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:32:47+02:00 | N | N |  | Y | Y
73720 | 445_LF_LEDDownlightForWC_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:04:58+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:32:30+02:00 | N | N |  | Y | Y
73721 | 440_LF_LEDDownlightOP_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T10:05:44+02:00 ¦¦ END: status→resolved @ 2026-06-29T11:31:48+02:00 | N | N |  | Y | N
73722 | 440_LF_LEDDownlightSFNB_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T10:06:17+02:00 ¦¦ END: status→resolved @ 2026-06-29T11:58:14+02:00 | N | N |  | Y | N
73723 | 445_LF_LEDDownlightSM_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:06:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:14+02:00 | N | N |  | Y | Y
73724 | 445_LF_LEDHighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:07:09+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:17+02:00 | N | N |  | Y | Y
73725 | 445_LF_LedinaireHighbayPendantLightWithAdjustableRod_CeilingSuspended.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:07:36+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:32:19+02:00 | N | N |  | Y | Y
73726 | 445_LF_LedinaireSlimDownlight_CeilingSuspended.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:08:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:32:08+02:00 | N | N |  | Y | Y
73727 | 440_LF_LEDLuminaireMP_CeilingMounted_Rectangular.rfa | 2026-06-22 | 2026-07-01 | 8 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T10:08:46+02:00 ¦¦ END: status→resolved @ 2026-07-01T10:38:22+02:00 | N | N |  | Y | N
73728 | 440_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa | 2026-06-22 | 2026-07-01 | 8 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T10:09:23+02:00 ¦¦ END: status→resolved @ 2026-07-01T10:38:22+02:00 | N | N |  | Y | N
73729 | 445_LF_LEDMasterEmergencyLightingLuminaire_WallMounted.rfa | 2026-06-22 | 2026-08-24 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:09:49+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T11:45:14+02:00 | N | N |  | Y | Y
73730 | 445_LF_LEDPanel_CeilingRecessed.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:10:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T04:03:18+02:00 | N | N |  | Y | Y
73731 | 445_LF_LEDPendantLightWithAdjustableRod_CeilingSuspended.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:10:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T04:03:21+02:00 | N | N |  | Y | Y
73732 | 445_LF_LEDPendantRingLight.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:11:19+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T11:25:31+02:00 | N | N |  | Y | Y
73733 | 445_LF_LEDSignalLightForWC_WallMounted.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:11:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:39:01+02:00 | N | N |  | Y | Y
73734 | 445_LF_LEDSpotEmergencyLightingLuminaireInFireResistantCeiling_CeilingRecessed.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:12:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T04:03:24+02:00 | N | N |  | Y | Y
73735 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:12:54+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T04:03:28+02:00 | N | N |  | Y | Y
73736 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square_SQ5D.rfa | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:13:22+02:00 ¦¦ END: hu.dam: h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T08:03:28+02:00 | N | N |  | Y | Y
73737 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:13:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T08:59:20+02:00 | N | N |  | Y | Y
73738 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round_SQ6.rfa | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:14:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T10:04:51+02:00 | N | N |  | Y | Y
73739 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Square_SQ5E.rfa | 2026-06-22 | 2026-06-30 | 7 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T10:14:42+02:00 ¦¦ END: status→resolved @ 2026-06-30T08:41:26+02:00 | N | N |  | Y | N
73740 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Round.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:15:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T04:03:31+02:00 | N | N |  | Y | Y
73741 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Square.rfa | 2026-06-22 | 2026-09-25 | 70 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:15:38+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-25T03:27:16+02:00 | N | N |  | Y | Y
73742 | 445_LF_LEDSpotEmergencyLightingLuminaire_WallMounted_Square_SQ5A.rfa | 2026-06-22 | 2026-08-24 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:16:01+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T11:45:17+02:00 | N | N |  | Y | Y
73743 | 445_LF_LEDStairEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-11 | 37 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:16:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T02:51:40+02:00 | N | N |  | Y | Y
73744 | 445_LF_LEDStripLight_CeilingMounted_Rectangular.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:38:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:08+02:00 | N | N |  | Y | Y
73745 | 445_LF_LEDStripLight_CeilingRecessed_Rectangular.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:39:12+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:11+02:00 | N | N |  | Y | Y
73746 | 445_LF_LEDStripLight_WallSurface_Rectangular.rfa | 2026-06-22 | 2026-09-22 | 67 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:40:28+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-22T03:29:49+02:00 | N | N |  | Y | Y
73747 | 445_LF_LEDTwinHeadsFastChargingIP30EmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-22T10:40:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:15+02:00 | N | N |  | Y | Y
73748 | 445_LF_LEDTwinSpotEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-07-17 | 20 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-22T10:41:34+02:00 ¦¦ END: status→resolved @ 2026-07-17T02:50:56+02:00 | N | N |  | Y | N
73798 | 445_LF_LEDTwoHeadWaterProofIP65EmergencyLight_WallSurface.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:28:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:45:55+02:00 | N | N |  | Y | Y
73799 | 445_LF_LEDUplight_FloorRecessed_Round.rfa | 2026-06-25 | 2026-09-24 | 66 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:28:40+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-24T09:51:03+02:00 | N | N |  | Y | Y
73800 | 445_LF_LED_HighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa | 2026-06-25 | 2026-07-16 | 16 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-25T03:29:27+02:00 ¦¦ END: status→resolved @ 2026-07-16T10:12:53+02:00 | N | N |  | Y | N
73801 | 445_LF_LuxSpaceAccentPerformanceSpotlightSwiveling_CeilingRecessed.rfa | 2026-06-25 | 2026-08-26 | 45 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:30:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:18+02:00 | N | N |  | Y | Y
73802 | 445_LF_LuxSpaceCompactAnbaudownlight_CeilingSuspended.rfa | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:31:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-21T03:27:54+02:00 | N | N |  | Y | Y
73803 | 445_LF_LuxSpaceDownlight_CeilingRecessed_Square.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:32:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:45:58+02:00 | N | N |  | Y | Y
73805 | 445_LF_MoistureProofLuminaire_CeilingSuspended_Rectangular.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:41:11+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T02:51:25+02:00 | N | N |  | Y | Y
73806 | 440_LF_MoistureProofLuminaire_WallSurface_Rectangular.rfa | 2026-06-25 | 2026-07-17 | 17 | handler_assign | status_resolved | START: handler→h.pham @ 2026-06-25T03:42:20+02:00 ¦¦ END: status→resolved @ 2026-07-17T10:32:19+02:00 | N | N |  | Y | N
73807 | 445_LF_OpticalLight_CeilingRecessed_Round_Outdoor.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:45:07+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:39:04+02:00 | N | N |  | Y | Y
73808 | 445_LF_TrackSpot_S_CeilingMounted.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:46:01+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T11:00:24+02:00 | N | N |  | Y | Y
73809 | 445_LF_TruelineLinearLuminaire_CeilingRecessed.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:46:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:39:08+02:00 | N | N |  | Y | Y
73810 | 445_LF_UVCAirDisinfectionLight_WallSurface.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:47:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T11:45:20+02:00 | N | N |  | Y | Y
73811 | 445_LF_InteriorLuminaireBL_CeilingRecessed_Rectangular.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:48:31+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T03:07:38+02:00 | N | N |  | Y | Y
73812 | 445_LF_InteriorLuminaireINDMP_CeilingRecessed_Round.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:49:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T07:23:03+02:00 | N | N |  | Y | Y
73813 | 445_LF_LEDDownlightOP_CeilingRecessed_Round.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:51:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T03:07:41+02:00 | N | N |  | Y | Y
73814 | 445_LF_LEDDownlightSFNB_CeilingRecessed_Round.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:52:30+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T04:08:23+02:00 | N | N |  | Y | Y
73815 | 445_LF_LEDLuminaireMP_CeilingMounted_Rectangular.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:53:15+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T04:08:27+02:00 | N | N |  | Y | Y
73816 | 445_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:54:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-21T10:26:16+02:00 | N | N |  | Y | Y
73817 | 445_LF_MoistureProofLuminaire_WallSurface_Rectangular.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-25T03:55:10+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:46:02+02:00 | N | N |  | Y | Y
73818 | 420_PA_ButterflyValve_Flanged_Handle | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-25T08:54:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-05T05:53:54+02:00 | N | N |  | Y | Y
73819 | 420_PA_BallValve_FullBore | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-25T08:54:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-12T11:55:07+02:00 | N | N |  | Y | Y
73820 | 420_PA_BallValve_Flanged_WheelStandard | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | START: handler→b.tran @ 2026-06-25T08:54:50+02:00 ¦¦ END: status→resolved @ 2026-07-01T10:02:24+02:00 | N | N |  | Y | Y
73821 | 420_PA_BallValve_Flanged_LeverStandard | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | START: handler→b.tran @ 2026-06-25T08:54:47+02:00 ¦¦ END: status→resolved @ 2026-07-01T06:30:03+02:00 | N | N |  | Y | Y
73822 | 420_PA_BallValve_Flanged.rfa | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-25T08:54:44+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T03:27:19+02:00 | N | N |  | Y | Y
73823 | 420_PA_BallValve3Way_TPort.rfa | 2026-06-25 | 2026-10-01 | 71 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-25T08:54:41+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:31:33+02:00 | N | N |  | Y | N
73824 | 420_PA_BallValve3Way_LPort.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-06-25T08:54:39+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-23T09:47:00+02:00 | N | N |  | Y | Y
73825 | 420_PA_BalancingValve_Thread_Standard.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:54:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:29:42+02:00 | N | N |  | Y | Y
73826 | 420_PA_BalancingValve_Thread.rfa | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:53:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-12T08:25:16+02:00 | N | N |  | Y | Y
73827 | 420_PA_BalancingValve_Flanged_Standard.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:53:52+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T12:26:33+02:00 | N | N |  | Y | Y
73828 | 420_PA_BalancingValve_Flanged.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:53:43+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:47:05+02:00 | N | N |  | Y | Y
73829 | 420_PA_AirValve_Thread.rfa | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:53:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-12T08:24:56+02:00 | N | N |  | Y | Y
73830 | 420_PA_AirReleaseValve_Thread_Standard.rfa | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:53:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T06:17:50+02:00 | N | N |  | Y | Y
73831 | 420_PA_AirReleaseValve_Flanged_Standard.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:53:29+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T03:39:49+02:00 | N | N |  | Y | Y
73832 | 420_PA_6WayValve_Thread.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-06-25T08:53:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T12:26:36+02:00 | N | N |  | Y | Y
73833 | 420_ME_WaterHeater_Vertical.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:32+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T04:50:20+02:00 | N | N |  | Y | Y
73834 | 420_ME_SinglePassTubeHeatExchanger_Horizontal.rfa | 2026-06-25 | 2026-09-03 | 51 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:29+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-03T03:20:59+02:00 | N | N |  | Y | Y
73835 | 420_ME_RectangularTubeManifold_8Connection.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-11T11:41:47+02:00 | N | N |  | Y | Y
73836 | 420_ME_Radiator_WallMounted_Standard.rfa | 2026-06-25 | 2026-09-08 | 54 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T12:07:51+02:00 | N | N |  | Y | Y
73837 | 420_ME_RadiatorHeatingWall_WallMounted_Vertical.rfa | 2026-06-25 | 2026-09-03 | 51 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:20+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-09-03T03:16:49+02:00 | N | N |  | Y | Y
73838 | 420_ME_RadiatorHeatingWall_WallMounted_ValveVertical.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:17+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-11T11:55:10+02:00 | N | N |  | Y | Y
73839 | 420_ME_RadiatorHeatingWall_WallMounted_ValveHorizontal.rfa | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-22T11:06:02+02:00 | N | N |  | Y | Y
73840 | 420_ME_RadiatorHeatingWall_WallMounted_Horizontal.rfa | 2026-06-25 | 2026-07-07 | 9 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-06-25T08:52:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-07T05:13:06+02:00 | N | N |  | Y | Y
73841 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileVPlus.rfa | 2026-06-25 | 2026-08-31 | 48 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:51:12+02:00 ¦¦ END: nd.huynh: @n.le On behalf of @hu.dam on vacation leave, this family is now fully completed and securely stored @ 2026-08-31T04:15:57+02:00 | N | N |  | Y | Y
73842 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileV.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:51:07+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T03:46:05+02:00 | N | N |  | Y | Y
73843 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileK.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:51:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T07:23:06+02:00 | N | N |  | Y | Y
73844 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanVPlus.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:50:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T12:26:40+02:00 | N | N |  | Y | Y
73845 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanV.rfa | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:50:52+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T09:16:41+02:00 | N | N |  | Y | Y
73846 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanK.rfa | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:50:48+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T10:25:37+02:00 | N | N |  | Y | Y
73847 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoProfile.rfa | 2026-06-25 | 2026-08-20 | 41 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:50:42+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T10:25:32+02:00 | N | N |  | Y | Y
73848 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoPlan.rfa | 2026-06-25 | 2026-08-20 | 41 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-06-25T08:50:37+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T10:27:32+02:00 | N | N |  | Y | Y
73849 | 434_ME_Pump_Circulator_VeroTwinDPL_DN65.rfa | 2026-07-08 | 2026-09-28 | 59 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-08T03:03:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T12:26:45+02:00 | N | N |  | Y | Y
73850 | 434_ME_Pump_Circulator_VeroTwinDPL_DN50.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:02:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:34+02:00 | N | N |  | Y | Y
73851 | 434_ME_Pump_Circulator_VeroTwinDPL_DN40.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:02:07+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:37+02:00 | N | N |  | Y | Y
73852 | 434_ME_Pump_Circulator_VeroTwinDPL_DN32.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:02:04+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:41+02:00 | N | N |  | Y | Y
73853 | 434_ME_Pump_Circulator_VeroTwinDPL_DN100.rfa | 2026-06-25 | 2026-10-01 | 71 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:02:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:32:51+02:00 | N | N |  | Y | N
73854 | 434_ME_Pump_Circulator_CronoTwin_DL_E.rfa | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:01:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T03:27:23+02:00 | N | N |  | Y | Y
73855 | 434_ME_Pump_CirculatorYonosPICO.rfa | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:01:54+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T03:27:26+02:00 | N | N |  | Y | Y
73856 | 434_ME_Pump_CirculatorYonosMAXO.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:01:51+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-06T11:24:47+02:00 | N | N |  | Y | Y
73857 | 434_ME_Pump_CirculatorVeroLineIPL.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-06-25T09:01:48+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-06T10:06:09+02:00 | N | N |  | Y | Y
73858 | 434_ME_Pump_CirculatorStratosPICO.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-25T09:01:16+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-06T09:18:56+02:00 | N | N |  | Y | Y
73859 | 434_ME_Pump_CirculatorStratosMAXO.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-25T09:01:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T11:41:38+02:00 | N | N |  | Y | Y
73860 | 434_ME_Pump_CirculatorStratosGIGA20&I.rfa | 2026-06-25 | 2026-07-02 | 6 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-06-25T09:01:10+02:00 ¦¦ END: status→resolved @ 2026-07-02T06:24:05+02:00 | N | N |  | Y | Y
73861 | 434_ME_Pump_CirculatorStratosGIGA20&D.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-25T09:01:07+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-24T06:05:16+02:00 | N | N |  | Y | Y
73862 | 434_ME_Pump_CirculatorStratosGIGA.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-25T09:01:04+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-24T06:04:58+02:00 | N | N |  | Y | Y
73863 | 434_ME_Pump_CirculatorStratosGIGA&B.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-25T09:01:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-23T11:02:01+02:00 | N | N |  | Y | Y
73864 | 434_ME_Pump_CirculatorAtmosGIGA&B.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-06-25T09:00:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-07-23T09:46:44+02:00 | N | N |  | Y | Y
73865 | 434_ME_PumpCirculator_FloorStand_Round_CronoLineILE.rfa | 2026-06-25 | 2026-07-10 | 12 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-06-25T09:00:56+02:00 ¦¦ END: status→resolved @ 2026-07-10T11:04:40+02:00 | N | N |  | Y | Y
73866 | 434_ME_PressureMaintenanceMonitoring_PlenoPX.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-25T09:00:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-11T02:52:54+02:00 | N | N |  | Y | Y
73867 | 434_ME_PressureMaintenanceMonitoring_PlenoPIX.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-25T09:00:16+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-11T02:53:55+02:00 | N | N |  | Y | Y
73868 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9F.rfa | 2026-06-25 | 2026-07-09 | 11 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-25T09:00:12+02:00 ¦¦ END: status→resolved @ 2026-07-09T03:03:33+02:00 | N | N |  | Y | N
73869 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9.rfa | 2026-06-25 | 2026-07-07 | 9 | handler_assign | status_closed | START: handler→tm.doan @ 2026-06-25T09:00:09+02:00 ¦¦ END: status→closed @ 2026-07-07T09:26:54+02:00 | N | N |  | Y | N
73870 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9.rfa | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-25T09:00:05+02:00 ¦¦ END: status→resolved @ 2026-07-01T11:26:42+02:00 | N | N |  | Y | Y
73871 | 434_ME_PrecisionPressurisation_CompressoF.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-25T09:00:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T11:41:41+02:00 | N | N |  | Y | Y
73872 | 434_ME_PrecisionPressurisation_CompressoC.rfa | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-06-25T08:59:57+02:00 ¦¦ END: status→resolved @ 2026-07-01T11:26:53+02:00 | N | N |  | Y | Y
73873 | 434_ME_PrecisionPressuremaintenance_TransferoTVI2.rfa | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-06-25T08:59:54+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-05T08:30:45+02:00 | N | N |  | Y | Y
73874 | 434_ME_PrecisionPressureMaintenance_TransferoTVI1.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-25T08:58:48+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T11:41:46+02:00 | N | N |  | Y | Y
73875 | 434_ME_PrecisionPressureMaintenance_TransferoTV2.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-25T08:58:43+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T11:41:49+02:00 | N | N |  | Y | Y
73876 | 434_ME_PrecisionPressureMaintenance_TransferoTV1.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-25T08:58:37+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T11:41:52+02:00 | N | N |  | Y | Y
73877 | 434_ME_PrecisionPressureMaintenance_TransferoTI.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-25T08:58:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T11:45:24+02:00 | N | N |  | Y | Y
73878 | 434_ME_OutDoorUnit_VRV5HeatRecoveryREYA.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-25T08:58:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T11:45:27+02:00 | N | N |  | Y | Y
73879 | 434_ME_Manifold_9Circuits.rfa | 2026-06-25 | 2026-07-10 | 12 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-06-25T08:58:19+02:00 ¦¦ END: status→resolved @ 2026-07-10T10:26:39+02:00 | N | N |  | Y | N
73880 | 434_ME_Manifold_8Circuits.rfa | 2026-06-25 | 2026-08-21 | 42 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-06-25T08:58:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-21T11:37:32+02:00 | N | N |  | Y | Y
73882 | 434_ME_Manifold_7Circuits.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-06-25T08:58:08+02:00 ¦¦ END: status→resolved @ 2026-07-06T09:40:32+02:00 | N | N |  | Y | N
73883 | 434_ME_Manifold_6Circuits.rfa | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | START: handler→t.tran @ 2026-06-25T08:57:30+02:00 ¦¦ END: status→resolved @ 2026-07-01T02:36:20+02:00 | N | N |  | Y | N
73884 | 434_ME_Manifold_5Circuits.rfa | 2026-06-25 | 2026-09-23 | 65 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-25T08:57:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T04:21:27+02:00 | N | N |  | Y | Y
73885 | 434_ME_Manifold_4Circuits.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-25T08:57:20+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T04:50:24+02:00 | N | N |  | Y | Y
73886 | 434_ME_Manifold_3Circuits.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-25T08:57:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-28T04:50:27+02:00 | N | N |  | Y | Y
73887 | 434_ME_Manifold_2Circuits.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-25T08:57:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T08:31:07+02:00 | N | N |  | Y | Y
73888 | 434_ME_Manifold_12Circuits.rfa | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-25T08:57:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T08:18:10+02:00 | N | N |  | Y | Y
73889 | 434_ME_Manifold_11Circuits.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-25T08:56:56+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T04:08:30+02:00 | N | N |  | Y | Y
73890 | 434_ME_Manifold_10Circuits.rfa | 2026-06-25 | 2026-08-26 | 45 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-06-25T08:56:51+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-26T11:38:37+02:00 | N | N |  | Y | Y
73898 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Return.rfa | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-25T11:21:31+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T06:31:08+02:00 | N | N |  | Y | Y
73899 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Supply.rfa | 2026-06-25 | 2026-07-16 | 16 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-06-25T11:22:07+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-16T08:39:18+02:00 | N | N |  | Y | Y
73969 | 2026Q3_DCMvn_Annotation Project_TL & TM Time allocation_Hanh Pham | 2026-06-30 | 2026-10-01 | 68 | handler_assign | status_closed | START: handler→h.pham @ 2026-06-30T06:56:17+02:00 ¦¦ END: status→closed @ 2026-10-01T02:21:41+02:00 | N | N |  | Y | N
73985 | ELT_MSR_Revise and update TIDP | 2026-06-30 |  |  | handler_assign | none | START: handler→h.pham @ 2026-06-30T11:02:30+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
73986 | 456_FA_AspiratingSmokesSystem2Channel_WallMounted.rfa | 2026-06-30 | 2026-09-28 | 65 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:20:04+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T10:32:35+02:00 | N | N |  | Y | Y
73987 | 456_FA_SmokeSamplingHead_Ceiling.rfa | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:20:46+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:08:49+02:00 | N | N |  | Y | Y
73988 | 440_LD_DoubleSwitchSocket_WallMounted.rfa | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:21:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:08:53+02:00 | N | N |  | Y | Y
73989 | 440_LD_SingleSwitchSocket_WallMounted.rfa | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:22:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:08:56+02:00 | N | N |  | Y | Y
73990 | 481_EE_SmartHomeAccessPoint_WLAN.rfa | 2026-06-30 | 2026-09-15 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:23:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:47:09+02:00 | N | N |  | Y | Y
73991 | 457_SD_DomeCamera_Outdoor.rfa | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:24:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T04:46:26+02:00 | N | N |  | Y | Y
73992 | 440_SE_AccessPanel_Ceiling.rfa | 2026-06-30 | 2026-09-28 | 65 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:24:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T10:32:38+02:00 | N | N |  | Y | Y
73993 | 440_SE_Penetration_Curaflex.rfa | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:25:25+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T05:43:26+02:00 | N | N |  | Y | Y
73994 | 455_CD_IndoorAntenna_Ceiling.rfa | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:26:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T05:41:43+02:00 | N | N |  | Y | Y
73995 | 440_CF_AL_eHorizontalElbow_Busway.rfa | 2026-06-30 | 2026-07-31 | 24 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:28:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-07-31T06:32:08+02:00 | N | N |  | Y | Y
73996 | 440_CF_AL_eVerticalElbow90Deg_Busway.rfa | 2026-06-30 | 2026-08-03 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-06-30T11:29:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-03T11:43:05+02:00 | N | N |  | Y | Y
74024 | 440_CF_AL_eVerticalOffsetElbow90Deg_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-07-02T02:26:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T04:23:23+02:00 | N | N |  | Y | Y
74025 | 440_CF_AL_mHorizontalOffsetZShade_Busway.rfa | 2026-07-02 | 2026-08-04 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-07-02T02:27:43+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-04T10:24:49+02:00 | N | N |  | Y | Y
74026 | 440_CF_AL_mVerticalOffsetZShade_Busway.rfa | 2026-07-02 | 2026-08-07 | 27 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-07-02T02:34:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T11:12:25+02:00 | N | N |  | Y | Y
74027 | 440_CF_AL_StraightLength_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-07-02T02:35:28+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T04:23:46+02:00 | N | N |  | Y | Y
74028 | 440_CF_AL_tVerticalTee_Busway.rfa | 2026-07-02 | 2026-07-29 | 20 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-07-02T02:39:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-07-29T04:47:36+02:00 | N | N |  | Y | Y
74029 | 440_CF_AL_uEndFlange_Busway.rfa | 2026-07-02 | 2026-07-31 | 22 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-07-02T02:41:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-07-31T06:32:26+02:00 | N | N |  | Y | Y
74030 | 440_CF_wChannelHorizontalWye_Standard.rfa | 2026-07-02 | 2026-08-21 | 37 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-07-02T02:42:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T10:30:37+02:00 | N | N |  | Y | Y
74031 | 440_CF_CO_eDoubleLeftElbow_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-07-02T02:43:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T04:23:58+02:00 | N | N |  | Y | Y
74032 | 440_CF_CO_eEdgewiseElbowWithAngle_Busway.rfa | 2026-07-02 | 2026-08-13 | 31 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-07-02T02:45:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:26:41+02:00 | N | N |  | Y | Y
74033 | 440_CF_CO_eEdgewiseElbow_Busway.rfa | 2026-07-02 | 2026-08-13 | 31 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-07-02T02:47:51+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-13T11:25:21+02:00 | N | N |  | Y | Y
74034 | 440_CF_CO_eEdgewiseOffet_Standard.rfa | 2026-07-02 | 2026-08-03 | 23 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-07-02T02:49:11+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-03T05:51:43+02:00 | N | N |  | Y | Y
74035 | 440_CF_CO_eFlatwiseOffsetElbow_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-07-02T02:57:59+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-12T04:22:58+02:00 | N | N |  | Y | Y
74064 | PD Tasks_2026Q3 | 2026-07-02 |  |  | handler_assign | none | START: handler→f.imbrogno @ 2026-07-02T09:10:55+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
74067 | 2026Q3_Annotation Project_TL & TM Time allocation_Nhut Minh Le | 2026-07-02 | 2026-09-30 | 65 | handler_assign | status_closed | START: handler→n.le @ 2026-07-02T09:32:22+02:00 ¦¦ END: status→closed @ 2026-09-30T10:58:22+02:00 | N | N |  | Y | N
74077 | 2026Q3_Annotation Project_TL & TM Time allocation_Thuong Van Huynh | 2026-07-02 | 2026-09-30 | 65 | handler_assign | status_closed | START: handler→tv.huynh @ 2026-07-02T11:24:20+02:00 ¦¦ END: status→closed @ 2026-09-30T05:08:47+02:00 | N | N |  | Y | N
74096 | 430_AT_VentilationGrilles_RoundDuct_Standard.rfa | 2026-07-03 | 2026-09-18 | 56 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-07-03T04:38:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:09:27+02:00 | N | N |  | Y | Y
74097 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Supply.rfa | 2026-07-03 | 2026-09-15 | 53 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-07-03T04:39:07+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T11:29:46+02:00 | N | N |  | Y | Y
74098 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Return.rfa | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-07-03T04:39:31+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T04:24:41+02:00 | N | N |  | Y | Y
74099 | 430_AT_VentilationGrilles_Rectangular_Standard.rfa | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-07-03T04:40:08+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T11:06:00+02:00 | N | N |  | Y | Y
74100 | 430_AT_VentilationGrilles_DoorWall_AGS_Supply.rfa | 2026-07-03 | 2026-09-18 | 56 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-07-03T04:40:32+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:09:31+02:00 | N | N |  | Y | Y
74101 | 430_AT_VentilationGrilles_DoorWall_AGS_Exhaust.rfa | 2026-07-03 | 2026-08-17 | 32 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-07-03T04:40:55+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T11:37:50+02:00 | N | N |  | Y | Y
74102 | 430_AT_TextileDiffuser_Supply.rfa | 2026-07-03 | 2026-08-18 | 33 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-07-03T04:41:32+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-18T11:39:21+02:00 | N | N |  | Y | Y
74103 | 430_AT_SwirlDiffuser_VerticalCeiling_Rectangular_Supply.rfa | 2026-07-03 | 2026-07-22 | 14 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-07-03T04:42:05+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T02:39:53+02:00 | N | N |  | Y | Y
74104 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Supply.rfa | 2026-07-03 | 2026-09-29 | 63 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-07-03T04:42:37+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T11:42:24+02:00 | N | N |  | Y | Y
74105 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Return.rfa | 2026-07-03 | 2026-07-22 | 14 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-07-03T04:43:05+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T02:39:28+02:00 | N | N |  | Y | Y
74106 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Supply.rfa | 2026-07-03 | 2026-09-21 | 57 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-07-03T04:43:40+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T11:44:14+02:00 | N | N |  | Y | Y
74107 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Return.rfa | 2026-07-03 | 2026-09-23 | 59 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-07-03T04:44:04+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T11:22:17+02:00 | N | N |  | Y | Y
74119 | 410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron | 2026-07-27 | 2026-08-28 | 25 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-27T03:29:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-28T04:50:30+02:00 | N | N |  | Y | Y
74120 | 410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic | 2026-07-27 | 2026-09-21 | 41 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-27T03:30:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T03:17:47+02:00 | N | N |  | Y | Y
74121 | 410_PX_BasementFloorDrain_Vertical_Coupling_CastIron | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-27T03:31:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T05:15:34+02:00 | N | N |  | Y | Y
74123 | 410_PX_StainlessSteelBoxGutters_Horizontal_Coupling | 2026-08-24 | 2026-08-24 | 1 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-08-24T03:43:02+02:00 ¦¦ END: status→resolved @ 2026-08-24T11:19:16+02:00 | N | N |  | Y | N
74124 | 410_PX_BoxGutters_Vertical_Coupling_StainlessSteel | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-27T03:32:05+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T05:15:37+02:00 | N | N |  | Y | Y
74125 | 410_PX_DoppelPumpStationPowerlift_ACO | 2026-07-27 | 2026-08-28 | 25 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-27T03:54:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-28T08:14:59+02:00 | N | N |  | Y | Y
74126 | 410_PX_DrainageChannel_B125 | 2026-07-27 | 2026-07-30 | 4 | handler_assign | status_resolved | START: handler→ttc.bui @ 2026-07-27T03:55:04+02:00 ¦¦ END: status→resolved @ 2026-07-30T10:52:40+02:00 | N | N |  | Y | Y
74127 | 410_PX_DuofixElementForSinkAGB | 2026-07-27 | 2026-07-30 | 4 | handler_assign | status_resolved | START: handler→y.nguyen @ 2026-07-27T03:59:29+02:00 ¦¦ END: status→resolved @ 2026-07-30T06:05:29+02:00 | N | N |  | Y | Y
74128 | 410_PX_DuofixElementForWallHungWC_BarrierFree | 2026-07-28 | 2026-08-14 | 14 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-28T03:47:36+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T10:54:40+02:00 | N | N |  | Y | Y
74129 | 410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern | 2026-07-28 | 2026-08-14 | 14 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-28T03:48:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T10:55:08+02:00 | N | N |  | Y | Y
74136 | 440_CF_CO_eFlatwise_Standard.rfa | 2026-07-06 | 2026-08-03 | 21 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-07-06T02:18:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-03T11:42:42+02:00 | N | N |  | Y | Y
74137 | 440_CF_CO_mChannelMultiPort_Standard_FeedUnitForDryTransformer.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-07-06T02:20:54+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-06T07:37:11+02:00 | N | N |  | Y | Y
74138 | 440_CF_CO_uFlangedEnd_Busway.rfa | 2026-07-06 | 2026-08-03 | 21 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-07-06T02:22:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-03T04:18:19+02:00 | N | N |  | Y | Y
74139 | 440_CF_CS_eCavityFloorBoxWithHeatResistantRoundFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-07-06T02:23:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T06:15:50+02:00 | N | N |  | Y | Y
74140 | 440_CF_CS_eCavityFloorBoxWithHeatResistantSquareFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-07-06T02:24:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-06T07:36:35+02:00 | N | N |  | Y | Y
74141 | 440_CF_CS_eCavityFloorBoxWithRoundFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-07-06T02:25:20+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-05T05:47:22+02:00 | N | N |  | Y | Y
74142 | 440_CF_CS_eScreedCovered_Standard_ChannelTwoPartVerticalBend.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-07-06T02:26:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-05T05:44:34+02:00 | N | N |  | Y | Y
74143 | 440_CF_CS_tCavityFloorBoxWithHeatResistantRoundFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-07-06T02:27:40+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T04:10:02+02:00 | N | N |  | Y | Y
74144 | 440_CF_CS_tCavityFloorBoxWithHeatResistantSquareFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-07-06T02:28:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T05:57:08+02:00 | N | N |  | Y | Y
74145 | 440_CF_CS_tCavityFloorBoxWithRoundFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-07-06T02:29:52+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T06:28:49+02:00 | N | N |  | Y | Y
74146 | 440_CF_CS_eCavityFloorBoxWithSquareFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-07-06T02:31:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-06T07:37:31+02:00 | N | N |  | Y | Y
74147 | 440_CF_CS_eScreedCovered_Standard_ChannelThreePartVerticalBend.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-07-06T02:32:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-06T07:37:42+02:00 | N | N |  | Y | Y
74148 | 440_CF_CS_tCavityFloorBoxWithSquareFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-07-06T02:36:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-11T05:56:57+02:00 | N | N |  | Y | Y
74149 | 440_CF_CS_uCavityFloorBoxWithHeatResistantRoundFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-07-06T02:37:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-10T05:49:04+02:00 | N | N |  | Y | Y
74150 | 440_CF_CS_uCavityFloorBoxWithHeatResistantSquareFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-07-23 | 14 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-07-06T02:39:12+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-07-23T10:55:56+02:00 | N | N |  | Y | Y
74151 | 440_CF_CS_uCavityFloorBoxWithRoundFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-07-06T02:40:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-10T06:11:57+02:00 | N | N |  | Y | Y
74152 | 440_CF_CS_uCavityFloorBoxWithSquareFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-07-06T02:41:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-10T06:11:44+02:00 | N | N |  | Y | Y
74153 | 440_CF_CS_xCavityFloorBoxWithHeatResistantRoundFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-07-06T02:43:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-05T05:45:51+02:00 | N | N |  | Y | Y
74154 | 440_CF_CS_xCavityFloorBoxWithHeatResistantSquareFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-07-06T02:44:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-05T05:47:03+02:00 | N | N |  | Y | Y
74155 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Supply.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-07-06T02:46:08+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T04:41:20+02:00 | N | N |  | Y | Y
74156 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Return.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-07-06T02:47:10+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T02:53:43+02:00 | N | N |  | Y | Y
74157 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_Return.rfa | 2026-07-06 | 2026-07-27 | 16 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-07-06T02:49:46+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-27T05:18:09+02:00 | N | N |  | Y | Y
74158 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Supply.rfa | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-07-09T05:32:53+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T10:54:27+02:00 | N | N |  | Y | Y
74159 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Return.rfa | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-07-09T05:32:38+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T12:21:39+02:00 | N | N |  | Y | Y
74160 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Supply.rfa | 2026-07-13 | 2026-08-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-07-13T02:52:11+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T12:21:17+02:00 | N | N |  | Y | Y
74161 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Return.rfa | 2026-07-13 | 2026-08-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-07-13T02:51:49+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T08:36:00+02:00 | N | N |  | Y | N
74162 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Supply.rfa | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-07-09T04:33:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T04:55:46+02:00 | N | N |  | Y | Y
74163 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Return.rfa | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-07-09T04:33:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T04:55:31+02:00 | N | N |  | Y | Y
74164 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Supply.rfa | 2026-07-13 | 2026-07-31 | 15 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-13T02:48:26+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T04:55:12+02:00 | N | N |  | Y | Y
74165 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Return.rfa | 2026-07-13 | 2026-07-31 | 15 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-13T02:47:24+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T03:27:45+02:00 | N | N |  | Y | Y
74166 | 430_AT_SmokeExtractionAndVentilationHood_Roof_Rectangular_Exhaust.rfa | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-09T08:20:09+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T03:29:36+02:00 | N | N |  | Y | Y
74167 | 430_AT_SlotDiffuserDSXXXLP2A_Supply.rfa | 2026-07-09 | 2026-08-07 | 22 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-09T04:29:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-07T11:13:10+02:00 | N | N |  | Y | Y
74168 | 430_AT_SlotDiffuserDSXXXLP2A_Return.rfa | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-09T04:29:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T06:12:11+02:00 | N | N |  | Y | Y
74169 | 430_AT_SchakoDisplacementDiffusers_Wall_WQA_Supply.rfa | 2026-07-09 | 2026-07-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-09T04:29:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T06:31:47+02:00 | N | N |  | Y | Y
74170 | 430_AT_Nozzles_Exhaust.rfa | 2026-07-09 | 2026-07-28 | 14 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-07-09T04:28:14+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T05:28:11+02:00 | N | N |  | Y | Y
74171 | 430_AT_Nozzles_Return.rfa | 2026-07-09 | 2026-07-28 | 14 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-07-09T04:28:14+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T05:28:25+02:00 | N | N |  | Y | Y
74172 | 430_AT_Nozzles_Supply.rfa | 2026-07-08 | 2026-07-28 | 15 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-08T09:43:20+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T05:29:38+02:00 | N | N |  | Y | Y
74173 | 430_AT_Nozzle_Standard.rfa | 2026-07-08 | 2026-07-28 | 15 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-08T09:43:20+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T08:15:11+02:00 | N | N |  | Y | Y
74174 | 430_AT_RoofHood.rfa | 2026-07-06 | 2026-07-17 | 10 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-06T03:36:23+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T08:32:24+02:00 | N | N |  | Y | Y
74175 | 430_AT_RoundLouver_Standard.rfa | 2026-07-06 | 2026-07-17 | 10 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-06T03:22:14+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-17T05:37:16+02:00 | N | N |  | Y | Y
74176 | 2026Q3_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-07-06 | 2026-09-07 | 46 | handler_assign | status_closed | START: handler→l.truong @ 2026-07-06T03:23:53+02:00 ¦¦ END: status→closed @ 2026-09-07T02:44:12+02:00 | N | N |  | Y | N
74177 | ELT_Document for proposal of using Fill Region Text Nested to Detail Item | 2026-07-06 | 2026-07-07 | 2 | handler_assign | status_resolved | START: handler→th.le @ 2026-07-06T03:27:13+02:00 ¦¦ END: status→resolved @ 2026-07-07T03:07:00+02:00 | N | N |  | Y | N
74179 | 440_CF_CS_xCavityFloorBoxWithRoundFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-07-06T03:54:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-10T04:24:54+02:00 | N | N |  | Y | Y
74180 | 440_CF_CS_xCavityFloorBoxWithSquareFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-07-06T03:58:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-10T04:25:05+02:00 | N | N |  | Y | Y
74181 | 440_CF_ehFlatwiseElbowFlangeEnd_Busway.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-07-06T04:00:15+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-10T04:25:16+02:00 | N | N |  | Y | Y
74182 | 440_CF_ehFlatwiseElbowWithAngle_Busway.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-07-06T04:02:09+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-06T10:00:39+02:00 | N | N |  | Y | Y
74183 | 440_CF_mFlatwiseTee_Busway.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | START: handler→d.le @ 2026-07-06T04:03:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T11:38:55+02:00 | N | N |  | Y | Y
74184 | 440_CF_mPhaseTransition_Busway.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-07-06T04:04:52+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T05:38:45+02:00 | N | N |  | Y | Y
74185 | 440_CF_mPotentialEqualisationBusbar.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-07-06T04:06:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T05:09:42+02:00 | N | N |  | Y | Y
74187 | 440_CF_mStraightLength_Busway.rfa | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T04:25:09+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T03:05:13+02:00 | N | N |  | Y | Y
74188 | 440_CF_ST_ehChannelHorizontalBend_Standard.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T04:26:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T11:14:24+02:00 | N | N |  | Y | Y
74189 | 440_CF_ST_xChannelHorizontalCross_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T04:31:44+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T08:17:09+02:00 | N | N |  | Y | Y
74190 | 440_CF_ST_ehChannelHorizontalMiteredBend_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T04:32:58+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T11:40:04+02:00 | N | N |  | Y | Y
74199 | 410_PF_PEXA_fRing_QE | 2026-07-16 | 2026-07-16 | 1 | handler_assign | status_resolved | START: handler→tk.pham @ 2026-07-16T02:32:47+02:00 ¦¦ END: status→resolved @ 2026-07-16T08:39:39+02:00 | N | N |  | N | Y
74200 | 410_PF_PEXA_eElbow_QE | 2026-07-16 | 2026-07-16 | 1 | handler_assign | status_resolved | START: handler→n.bui @ 2026-07-16T02:31:49+02:00 ¦¦ END: status→resolved @ 2026-07-16T09:38:44+02:00 | N | N |  | N | Y
74201 | 410_PF_PEXA_fEvolutionRing_QE | 2026-07-16 | 2026-07-16 | 1 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-07-16T02:32:18+02:00 ¦¦ END: status→resolved @ 2026-07-16T09:00:50+02:00 | N | N |  | N | Y
74202 | 410_PX_FloorDrainWithExtensionPieces_Horizontal_Inclination | 2026-07-16 | 2026-07-21 | 4 | handler_assign | status_resolved | START: handler→l.pham @ 2026-07-16T02:36:38+02:00 ¦¦ END: status→resolved @ 2026-07-21T06:45:04+02:00 | N | N |  | N | Y
74203 | 410_SE_PenetrationSealing | 2026-07-16 | 2026-07-22 | 5 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-16T02:33:25+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T08:55:19+02:00 | N | N |  | N | Y
74204 | 410_SE_RainStorageTank | 2026-07-16 | 2026-07-22 | 5 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-07-16T04:16:36+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T11:19:20+02:00 | N | N |  | N | Y
74205 | 410_PX_PressureReliefManhole | 2026-07-16 | 2026-07-23 | 6 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-16T04:18:01+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-23T03:39:22+02:00 | N | N |  | N | Y
74208 | 440_CF_ST_tChannelHorizontalTee_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:50:53+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T11:39:21+02:00 | N | N |  | Y | Y
74209 | 440_CF_ST_rChannelTransition_Standard.rfa | 2026-07-06 | 2026-08-28 | 40 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:52:19+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T10:36:16+02:00 | N | N |  | Y | Y
74210 | 440_CF_ST_uChannelUnion_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:53:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T08:17:12+02:00 | N | N |  | Y | Y
74211 | 440_CF_ST_xvChannelVerticalCross_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:54:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:24:50+02:00 | N | N |  | Y | Y
74212 | 440_CF_ST_tvChannelVerticalDownTee_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:55:44+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T08:19:42+02:00 | N | N |  | Y | Y
74213 | 440_CF_ST_eiChannelVerticalInsideBend_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:57:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T03:17:42+02:00 | N | N |  | Y | Y
74214 | 440_CF_ST_eoChannelVerticalOutsideBend_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:58:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T05:32:23+02:00 | N | N |  | Y | Y
74215 | 440_CF_ST_ehLadderHorizontalBend_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T06:59:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T07:55:58+02:00 | N | N |  | Y | Y
74216 | 440_CF_ST_xLadderHorizontalCross_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:00:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T08:01:20+02:00 | N | N |  | Y | Y
74217 | 440_CF_ST_tLadderHorizontalTee_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:02:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T06:47:53+02:00 | N | N |  | Y | Y
74218 | 440_CF_ST_rLadderTransition_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:03:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T04:47:02+02:00 | N | N |  | Y | Y
74219 | 440_CF_ST_uLadderUnion_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:03:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T04:45:24+02:00 | N | N |  | Y | Y
74220 | 440_CF_ST_tvLadderUTypeVerticalTee_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:04:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T11:54:32+02:00 | N | N |  | Y | Y
74221 | 440_CF_ST_xvLadderVerticalCross_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:06:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T11:53:43+02:00 | N | N |  | Y | N
74222 | 440_CF_ST_eiLadderVerticalInsideBend_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:06:53+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:39:32+02:00 | N | N |  | Y | Y
74223 | 440_CF_ST_eoLadderVerticalOutsideBend_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:07:46+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:39:21+02:00 | N | N |  | Y | Y
74224 | 440_CF_uCableTapBoxCenter_Busway.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:08:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T04:11:48+02:00 | N | N |  | Y | Y
74226 | 440_CF_uCableTapBoxEnd_Busway.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:09:44+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-07T04:10:47+02:00 | N | N |  | Y | Y
74227 | 440_CF_uEndClosure_Busway.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:10:46+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:39:09+02:00 | N | N |  | Y | Y
74228 | 440_CF_uFlexibleLink_Busway.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:11:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T10:37:41+02:00 | N | N |  | Y | Y
74229 | 440_CF_UnfusedReducer_Busway.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:12:38+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T11:39:10+02:00 | N | N |  | Y | Y
74230 | 440_CF_uWallFloorFlange_Busway.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T07:13:25+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T11:39:59+02:00 | N | N |  | Y | Y
74239 | 440_CI_CS_tClamps_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:17:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T07:15:05+02:00 | N | N |  | Y | Y
74240 | 440_CI_CS_tExpansionPiecesRound_Standard.rfa | 2026-07-06 | 2026-08-14 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:18:30+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-14T11:31:39+02:00 | N | N |  | Y | Y
74243 | 440_CI_CS_xClamps_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:20:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-17T11:40:18+02:00 | N | N |  | Y | Y
74246 | 440_CI_CS_xExpansionPiecesRound_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:21:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-19T11:36:16+02:00 | N | N |  | Y | Y
74247 | 440_CI_PC_mJunctionBox_Standard_Weatherproof.rfa | 2026-07-06 | 2026-09-30 | 63 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:23:26+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-30T11:36:18+02:00 | N | N |  | Y | Y
74248 | 440_CI_PVC_e30DegreeElbow_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:24:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:21+02:00 | N | N |  | Y | Y
74249 | 440_CI_PVC_e45DegreeElbow_Standard.rfa | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:25:20+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T05:12:24+02:00 | N | N |  | Y | Y
74251 | 440_CI_PVC_e90DegreeElbow_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:33:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:25+02:00 | N | N |  | Y | Y
74252 | 440_CI_PVC_eAngledTwoWayBox_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:34:09+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T08:17:15+02:00 | N | N |  | Y | Y
74253 | 440_CI_PVC_cMarkerforConnectionLugs.rfa | 2026-07-06 | 2026-09-24 | 59 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:35:01+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-24T07:46:10+02:00 | N | N |  | Y | Y
74254 | 440_CI_PVC_uConduitBodiesTypeC_Standard.rfa | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:35:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-21T05:11:01+02:00 | N | N |  | Y | Y
74255 | 440_CI_PVC_cConduitBodiesTypeE_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:36:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T11:38:13+02:00 | N | N |  | Y | Y
74256 | 440_CI_PVC_eConduitBodiesTypeLB_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:37:26+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T08:17:19+02:00 | N | N |  | Y | Y
74257 | 440_CI_PVC_eConduitBodiesTypeLL_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:38:28+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T11:38:16+02:00 | N | N |  | Y | Y
74258 | 440_CI_PVC_eConduitBodiesTypeLR_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:39:23+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T11:38:19+02:00 | N | N |  | Y | Y
74259 | 440_CI_PVC_tConduitBodiesTypeT_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:40:13+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T11:38:22+02:00 | N | N |  | Y | Y
74260 | 440_CI_PVC_ConduitSleeveCoupling_Standard.rfa | 2026-07-06 | 2026-07-10 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-07-06T10:41:16+02:00 ¦¦ END: status→resolved @ 2026-07-10T11:27:35+02:00 | N | N |  | Y | Y
74263 | 440_CI_PVC_fCoupling_Standard.rfa | 2026-07-06 | 2026-08-25 | 37 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:51:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:23:38+02:00 | N | N |  | Y | Y
74264 | 440_CI_PVC_mHWayJuntionBox_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:51:49+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T04:57:11+02:00 | N | N |  | Y | Y
74265 | 440_CI_PVC_eInspectionBend_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:52:34+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T04:53:01+02:00 | N | N |  | Y | Y
74266 | 440_CI_PVC_e90DegreeInspectionElbow_Standard.rfa | 2026-07-06 | 2026-07-13 | 6 | handler_assign | status_resolved | START: handler→h.pham @ 2026-07-06T10:53:24+02:00 ¦¦ END: status→resolved @ 2026-07-13T11:00:25+02:00 | N | N |  | Y | Y
74267 | 440_CI_PVC_tInspectionTee_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:54:30+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T10:38:57+02:00 | N | N |  | Y | Y
74268 | 440_CI_PVC_xIntersectionFourWayBox_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:55:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T10:39:02+02:00 | N | N |  | Y | Y
74269 | 440_CI_PVC_uJunctionBox_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:56:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T09:33:12+02:00 | N | N |  | Y | Y
74270 | 440_CI_PVC_mJunctionBox_Standard_ThreeWay.rfa | 2026-07-06 | 2026-09-28 | 61 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-06T10:56:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T12:26:50+02:00 | N | N |  | Y | Y
74314 | 440_CI_PVC_rReducer_Standard.rfa | 2026-07-09 | 2026-08-24 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:24:44+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T10:37:07+02:00 | N | N |  | Y | Y
74315 | 440_CI_PVC_tTeeThreeWayBox_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:26:19+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T09:33:15+02:00 | N | N |  | Y | Y
74316 | 440_CI_PVC_cTerminalOneWayBox_Standard.rfa | 2026-07-09 | 2026-09-04 | 42 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:27:37+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam **440_CI_PVC_cTerminalOneWayBox_Standard.rfa** Based on the spreadsheet input, t @ 2026-09-04T09:55:47+02:00 | N | N |  | Y | Y
74317 | 440_CI_PVC_uThroughTwoWayBox_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:28:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T07:16:38+02:00 | N | N |  | Y | Y
74318 | 440_CI_PVC_mUWayBox_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:29:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T05:07:55+02:00 | N | N |  | Y | Y
74319 | 440_CI_PVC_mYWayBox_Standard.rfa | 2026-07-09 | 2026-09-17 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:30:28+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T06:20:14+02:00 | N | N |  | Y | Y
74320 | 440_CI_SS_cDeviceBoxes_Threaded.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:33:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T04:03:34+02:00 | N | N |  | Y | Y
74321 | 440_CI_SS_e45DegreeElbow_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:34:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T11:38:26+02:00 | N | N |  | Y | Y
74322 | 440_CI_SS_e45DegreeElbow_Threaded.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:35:58+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:28+02:00 | N | N |  | Y | Y
74323 | 440_CI_SS_e90DegreeElbow_Standard.rfa | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-07-09T06:37:06+02:00 ¦¦ END: status→resolved @ 2026-07-14T11:30:36+02:00 | N | N |  | Y | Y
74324 | 440_CI_SS_e90DegreeElbow_Threaded.rfa | 2026-07-09 | 2026-08-25 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:38:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:23:41+02:00 | N | N |  | Y | Y
74325 | 440_CI_SS_eConduitBodies_Threaded_TypeLB.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:39:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-26T03:14:31+02:00 | N | N |  | Y | Y
74326 | 440_CI_SS_eConduitBodies_Threaded_TypeLR.rfa | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-07-09T06:41:01+02:00 ¦¦ END: status→resolved @ 2026-07-14T09:30:47+02:00 | N | N |  | Y | Y
74327 | 440_CI_SS_eConduitBodies_Threaded_TypeLU.rfa | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-07-09T06:42:24+02:00 ¦¦ END: status→resolved @ 2026-07-14T09:39:06+02:00 | N | N |  | Y | Y
74328 | 440_CI_SS_eConduitBodies_TypeLL_Threaded.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:44:04+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T10:39:02+02:00 | N | N |  | Y | Y
74329 | 440_CI_SS_eFlatConductorsElbow_Standard.rfa | 2026-07-09 | 2026-09-18 | 52 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:48:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:09:42+02:00 | N | N |  | Y | Y
74330 | 440_CI_SS_eInspectionElbow_Standard.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:49:44+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T10:38:35+02:00 | N | N |  | Y | Y
74331 | 440_CI_SS_FlatStrip_Standard.rfa | 2026-07-09 | 2026-09-18 | 52 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:52:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:09:46+02:00 | N | N |  | Y | Y
74332 | 440_CI_SS_tConduitBodies_Threaded_TypeT.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:53:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T10:37:51+02:00 | N | N |  | Y | Y
74333 | 440_CI_SS_tConduitBodies_Threaded_TypeTB.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:54:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T10:38:24+02:00 | N | N |  | Y | Y
74334 | 440_CI_SS_uCFormConduitUnion_Threaded.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:56:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T10:38:14+02:00 | N | N |  | Y | Y
74335 | 440_CI_SS_xConduitBodies_Threaded_TypeX.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T06:58:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-20T10:38:02+02:00 | N | N |  | Y | Y
74336 | 440_CI_SS_xCrossConductorFlatToRound.rfa | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T07:00:03+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T06:56:48+02:00 | N | N |  | Y | Y
74337 | 440_CI_SS_xFlatConductorCross.rfa | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T07:01:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T05:33:14+02:00 | N | N |  | Y | Y
74338 | 440_CI_ST_mJunctionBox_Explosionproof.rfa | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-09T07:02:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-18T08:15:28+02:00 | N | N |  | Y | Y
74339 | Revise the RFA library for the MSR system. | 2026-07-09 |  |  | handler_assign | none | START: handler→h.pham @ 2026-07-09T07:03:38+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
74371 | 410_PX_DuofixElementForWallHungWC | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-27T03:59:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T05:15:40+02:00 | N | N |  | Y | Y
74373 | 410_PX_DuofixElementForWashbasin | 2026-07-28 | 2026-08-17 | 15 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-28T03:48:42+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-17T11:39:53+02:00 | N | N |  | Y | Y
74374 | 410_PX_DuofixElementForWashBasin_BarrierFree | 2026-07-28 | 2026-09-28 | 45 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-28T03:49:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-28T05:09:18+02:00 | N | N |  | Y | Y
74375 | 410_PX_DuofixElementInsetWashbasin_PillarTap | 2026-07-30 | 2026-07-31 | 2 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-07-30T10:31:49+02:00 ¦¦ END: status→resolved @ 2026-07-31T11:35:36+02:00 | N | N |  | Y | N
74376 | 410_PX_DuofixForShower&Bathtub | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-30T10:32:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T08:28:59+02:00 | N | N |  | Y | Y
74377 | 410_PX_DuofixForShower&Bathtub_WallFittingAP | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-30T10:32:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T10:05:15+02:00 | N | N |  | Y | Y
74378 | 410_PX_DuofixForUrinal | 2026-07-30 | 2026-08-05 | 5 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-07-30T10:33:03+02:00 ¦¦ END: status→resolved @ 2026-08-05T11:27:05+02:00 | N | N |  | Y | N
74379 | 410_PX_DuofixForUrinal_Universal | 2026-07-30 | 2026-09-14 | 33 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-30T10:33:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-14T08:18:13+02:00 | N | N |  | Y | Y
74380 | 410_PX_DuofixSigmaToilet12cm_BarrierFree | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-30T10:34:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T05:08:59+02:00 | N | N |  | Y | Y
74381 | 410_PX_DuofixTraverseForStandaloneFaucetKitchenSink | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-30T10:34:53+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T04:43:49+02:00 | N | N |  | Y | Y
74382 | 410_PX_FaucetWithFlexibleHose | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-30T10:35:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T06:30:59+02:00 | N | N |  | Y | Y
74383 | 410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-30T10:35:38+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T06:30:31+02:00 | N | N |  | Y | Y
74384 | 410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full | START: handler→y.nguyen @ 2026-07-30T10:35:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T09:20:18+02:00 | N | N |  | Y | Y
74385 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-30T10:39:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T06:28:39+02:00 | N | N |  | Y | Y
74386 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel | 2026-07-30 | 2026-08-28 | 22 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-30T10:39:50+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-28T11:24:36+02:00 | N | N |  | Y | Y
74387 | 410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron | 2026-07-30 | 2026-09-28 | 43 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-30T10:40:10+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-28T06:45:12+02:00 | N | N |  | Y | Y
74388 | 410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-30T10:40:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T10:51:59+02:00 | N | N |  | Y | Y
74389 | 410_PX_FloorDrain_Horizontal_Coupling_CastIron | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-07-30T10:40:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T10:52:02+02:00 | N | N |  | Y | Y
74390 | 410_PX_FloorDrain_Horizontal_Coupling_Plastic | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-30T10:41:51+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T10:05:20+02:00 | N | N |  | Y | Y
74391 | 410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-30T10:42:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T10:05:24+02:00 | N | N |  | Y | Y
74392 | 410_PX_FloorDrain_VerticalFinor2PartL15_Coupling_CastIron | 2026-07-30 | 2026-08-05 | 5 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-07-30T10:42:37+02:00 ¦¦ END: status→resolved @ 2026-08-05T11:12:08+02:00 | N | N |  | Y | N
74393 | 410_PX_CastlronFloorDrain_Vertical_Coupling | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-07-30T10:43:06+02:00 ¦¦ END: status→resolved @ 2026-08-06T11:23:20+02:00 | N | N |  | Y | N
74394 | 410_PX_FloorDrain_Vertical_Coupling_Plastic | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-07-30T10:43:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T10:05:28+02:00 | N | N |  | Y | Y
74395 | 410_PX_FloorDrain_Vertical_Coupling_StainlessSteel | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-30T10:44:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T10:52:06+02:00 | N | N |  | Y | Y
74396 | 410_PX_GardenWater_Kemper | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-30T10:44:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T05:09:03+02:00 | N | N |  | Y | Y
74397 | 410_PX_GreaseDisposalPoint | 2026-07-30 | 2026-08-28 | 22 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-30T10:44:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-28T11:42:50+02:00 | N | N |  | Y | Y
74398 | 410_PX_GullyGrating | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-30T10:45:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T10:10:28+02:00 | N | N |  | Y | Y
74399 | 410_PX_HorizontalFloorDrain | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-07-30T10:45:30+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T10:52:09+02:00 | N | N |  | Y | Y
74400 | 410_PX_InspectionShaft_OnePipe_Nosystem | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | START: handler→t.luu @ 2026-07-30T10:46:03+02:00 ¦¦ END: status→resolved @ 2026-08-06T05:36:14+02:00 | N | N |  | Y | Y
74401 | 410_PX_InspectionShaft_TwoPipe_Nosystem | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-30T10:46:30+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T10:39:34+02:00 | N | N |  | Y | Y
74402 | 410_PX_KitchenTap | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-07-30T10:46:49+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T10:52:12+02:00 | N | N |  | Y | Y
74403 | 410_PX_ManholeAdjustingUnits_Round_NoSystem | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | START: handler→t.luu @ 2026-07-30T10:47:10+02:00 ¦¦ END: status→resolved @ 2026-08-06T05:23:50+02:00 | N | N |  | Y | Y
74404 | 410_PX_ManholeBase_CastIn | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | START: handler→t.luu @ 2026-07-30T10:47:35+02:00 ¦¦ END: status→resolved @ 2026-08-06T05:52:26+02:00 | N | N |  | Y | Y
74405 | 480_FA_AddressableManualPullStation.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T08:44:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T09:58:54+02:00 | N | N |  | Y | Y
74406 | 410_PX_ManholeChamberUnits_Round_NoSystem | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-30T10:48:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T10:52:16+02:00 | N | N |  | Y | Y
74407 | 410_PX_ManholeCoverSlabs_Eccentrical_NoSystem | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-30T10:48:56+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T10:52:19+02:00 | N | N |  | Y | Y
74408 | 410_PX_ManholeReducingSlabs_Eccentrical_NoSystem | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→ttc.bui @ 2026-07-30T10:49:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T11:34:36+02:00 | N | N |  | Y | Y
74409 | 410_PX_ManholeTaper_EccentricalCones_NoSystem | 2026-07-30 | 2026-08-05 | 5 | handler_assign | status_resolved | START: handler→ttc.bui @ 2026-07-30T10:49:42+02:00 ¦¦ END: status→resolved @ 2026-08-05T10:36:12+02:00 | N | N |  | Y | N
74410 | 410_PX_Manhole_Round | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-30T10:50:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T05:28:38+02:00 | N | N |  | Y | Y
74411 | 456_FA_AddressableSensor.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T08:48:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T09:58:57+02:00 | N | N |  | Y | Y
74412 | 410_PX_ReusedRainWaterTank | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-30T10:51:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T05:28:41+02:00 | N | N |  | Y | Y
74413 | 410_PX_RoadGully | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-30T10:51:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-19T11:30:20+02:00 | N | N |  | Y | Y
74414 | 480_FA_AnnunciatorPanel.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T08:50:10+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T08:15:03+02:00 | N | N |  | Y | Y
74415 | 410_PX_SumpPit_NoSystem | 2026-07-30 | 2026-09-15 | 34 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-30T10:52:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T04:08:33+02:00 | N | N |  | Y | Y
74416 | 456_FA_AspiratingSmokeDetector_WallMounted.rfa | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T08:51:02+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-22T09:50:13+02:00 | N | N |  | Y | Y
74417 | 410_PX_TapWithMaleHose_Threaded_DN15 | 2026-07-30 | 2026-09-15 | 34 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-30T10:53:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T04:08:36+02:00 | N | N |  | Y | Y
74418 | 456_FA_BeamSensor_WallSurface_Rectangular.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T08:51:51+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T06:28:04+02:00 | N | N |  | Y | Y
74419 | 410_PX_WaterTap | 2026-07-30 | 2026-08-20 | 16 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-07-30T10:53:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-20T04:52:19+02:00 | N | N |  | Y | Y
74420 | 480_FA_Bell.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T08:59:21+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T06:28:08+02:00 | N | N |  | Y | Y
74421 | 456_FA_CouplerUnit.rfa | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:02:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-22T09:50:15+02:00 | N | N |  | Y | Y
74422 | 456_FA_DetectorWithHorn.rfa | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:03:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-22T05:57:37+02:00 | N | N |  | Y | Y
74423 | 456_FA_Detector_CO1224A.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:03:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T05:10:23+02:00 | N | N |  | Y | Y
74424 | 456_FA_Detector_CO1224TR.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:04:33+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T06:20:17+02:00 | N | N |  | Y | Y
74425 | 456_FA_EmegencyDoorRelease_WallMounted.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:26:59+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T06:28:11+02:00 | N | N |  | Y | Y
74426 | 456_FA_FireAlarmCenter.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:28:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T07:19:38+02:00 | N | N |  | Y | Y
74427 | 456_FA_FireAlarmControlPanel.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:29:47+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T06:28:14+02:00 | N | N |  | Y | Y
74428 | 456_FA_FireAlarmZoneModuleControl.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:32:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T05:50:00+02:00 | N | N |  | Y | Y
74429 | 456_FA_FireBrigadeInformationCenter_WallMounted.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:33:32+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T07:19:41+02:00 | N | N |  | Y | Y
74430 | 456_FA_FireDepartmentKeyDepot.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:34:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T07:19:43+02:00 | N | N |  | Y | Y
74431 | 480_FA_FireDoorHolder.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:34:46+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T05:50:03+02:00 | N | N |  | Y | Y
74432 | 456_FA_HeatSensor.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:35:23+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T04:50:34+02:00 | N | N |  | Y | Y
74433 | 480_FA_LEDIndicator_WallMounted.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:36:02+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T04:50:37+02:00 | N | N |  | Y | Y
74434 | 456_FA_LinearHeatDetector.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:36:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:22+02:00 | N | N |  | Y | Y
74435 | 456_FA_MultiSensorDetector_Ceiling.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:37:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T04:24:46+02:00 | N | N |  | Y | Y
74436 | 456_FA_O2TMultisensordetector.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:37:58+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T04:50:40+02:00 | N | N |  | Y | Y
74437 | 456_FA_PhotoelectricSmokeDetector.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:38:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:25+02:00 | N | N |  | Y | Y
74438 | 456_FA_O2TMultisensordetector_BottomSlab.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:39:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:09:49+02:00 | N | N |  | Y | Y
74439 | 456_FA_PhotoThermalSensor_CeilingMouted_Round.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:41:32+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T04:50:44+02:00 | N | N |  | Y | Y
74440 | 456_FA_PresenceDetector24m_Ceiling.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:42:07+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:09:53+02:00 | N | N |  | Y | Y
74441 | 456_FA_PresenceDetectorHTS_Ceiling.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:42:45+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:29+02:00 | N | N |  | Y | Y
74442 | 456_FA_PushButton_WallMounted_RWA.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:43:18+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:09:56+02:00 | N | N |  | Y | Y
74443 | 480_FA_SmokeDectectorOpticalSignal_Ceiling.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:44:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:00+02:00 | N | N |  | Y | Y
74444 | 456_FA_SmokeSensor_BottomSlab.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:44:40+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:32+02:00 | N | N |  | Y | Y
74445 | 456_FA_SmokeSensor_Ceiling.rfa | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:45:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T06:45:15+02:00 | N | N |  | Y | Y
74446 | 456_FA_SmokeSensor_RaiseFloor.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:45:49+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:05+02:00 | N | N |  | Y | Y
74447 | 456_FA_ManualCallPoint_WallMounted_Square.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:46:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T03:24:47+02:00 | N | N |  | Y | Y
74448 | 456_FA_ManualCallPoint_WallMounted_Square_Waterproof.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:47:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T03:07:44+02:00 | N | N |  | Y | Y
74449 | 480_FA_TransferUnit.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:47:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:09+02:00 | N | N |  | Y | Y
74450 | 454_FA_VandalResistantLoudSpeaker.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:48:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T03:07:48+02:00 | N | N |  | Y | Y
74451 | 456_FA_WindandRainDetector_WallMounted_RWA.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:49:25+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:37+02:00 | N | N |  | Y | Y
74452 | 482_EE_ControlDistribution_WallMounted.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:50:23+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:12+02:00 | N | N |  | Y | Y
74453 | 456_EE_ConventionalControlPanel_WallSurface_Rectangular.rfa | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:50:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T09:21:00+02:00 | N | N |  | Y | Y
74454 | 457_EE_DataCabinet.rfa | 2026-07-10 | 2026-09-04 | 41 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:51:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:09:06+02:00 | N | N |  | Y | Y
74455 | 457_EE_DataServerCabinet_FloorStand_Rectangular.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:52:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:42+02:00 | N | N |  | Y | Y
74456 | 482_EE_Distribution_FloorStanding_Indoor.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:52:43+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:15+02:00 | N | N |  | Y | Y
74457 | 482_EE_Distribution_FloorStanding_Outdoor.rfa | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-10T09:53:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T09:21:03+02:00 | N | N |  | Y | Y
74467 | 456_EE_PowerSupplyUnitAccessControl_WallMounted.rfa | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T08:48:52+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T03:07:51+02:00 | N | N |  | Y | Y
74468 | 454_EE_PublicAddressSystemPanel_FloorMounted.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T08:49:33+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T11:12:06+02:00 | N | N |  | Y | Y
74469 | 482_EE_RackCabinet_WallMounted.rfa | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T08:50:12+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:46+02:00 | N | N |  | Y | Y
74470 | 482_EE_SwitchCabinet_FloorStand_Rectangular.rfa | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T08:50:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:18+02:00 | N | N |  | Y | Y
74471 | 480_EE_WallControlPanel_WallMounted.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T08:51:31+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:21+02:00 | N | N |  | Y | Y
74472 | 480_EF_IndividualRoomController.rfa | 2026-07-13 | 2026-08-05 | 18 | handler_assign | status_resolved | START: handler→h.pham @ 2026-07-13T08:52:32+02:00 ¦¦ END: status→resolved @ 2026-08-05T11:21:44+02:00 | N | N |  | Y | N
74475 | 444_CI_ABS_mIndustrialBox.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:47:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T10:32:41+02:00 | N | N |  | Y | Y
74476 | 446_EF_LightningCounterDevice.rfa | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:49:12+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:25+02:00 | N | N |  | Y | Y
74477 | 446_EF_LightningRod_NoSystem.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:50:00+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:26+02:00 | N | N |  | Y | Y
74478 | 443_EF_OvervoltageProtection_WallFlush.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:50:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T10:32:45+02:00 | N | N |  | Y | Y
74479 | 442_EF_SealedBatteries.rfa | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:53:25+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:49+02:00 | N | N |  | Y | Y
74480 | 452_EF_TouchButton_WallMounted.rfa | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:54:30+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:10:28+02:00 | N | N |  | Y | Y
74481 | 484_EF_Transferbox.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:55:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T10:32:48+02:00 | N | N |  | Y | Y
74482 | 454_CD_CabinetLoudspeaker6W_WallMounted_Circular.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:56:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:31+02:00 | N | N |  | Y | Y
74483 | 454_CD_CabinetLoudspeaker6W_WallMounted_Rectangular.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:57:32+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:35+02:00 | N | N |  | Y | Y
74484 | 454_CD_CabinetLoudspeaker6W_WallMounted_Square.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:58:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:40+02:00 | N | N |  | Y | Y
74485 | 452_CD_CallButtonPullCord.rfa | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:58:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:52+02:00 | N | N |  | Y | Y
74486 | 456_CD_DeskIntercomStation.rfa | 2026-07-13 | 2026-09-21 | 51 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:59:15+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-21T11:44:16+02:00 | N | N |  | Y | Y
74487 | 454_CD_FireDepartmentContactPoint_WallMounted.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T10:59:43+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-28T11:00:27+02:00 | N | N |  | Y | Y
74488 | 454_CD_HornLoudspeaker15W_WallMounted.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-13T11:00:13+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T10:24:45+02:00 | N | N |  | Y | Y
74490 | 430_ME_AHUProcess.rfa | 2026-07-14 | 2026-07-14 | 1 | handler_assign | status_resolved | START: handler→h.le @ 2026-07-14T02:38:27+02:00 ¦¦ END: status→resolved @ 2026-07-14T10:28:59+02:00 | N | N |  | Y | N
74491 | 430_ME_AHU_BSF_Standard.rfa | 2026-07-14 | 2026-08-14 | 24 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-14T04:37:54+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T10:11:45+02:00 | N | N |  | Y | Y
74496 | 455_CD_IndoorAntenna_Ceiling.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T08:49:08+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T07:19:45+02:00 | N | N |  | Y | N
74497 | 454_CD_Loudspeaker6W_CeilingRecessed.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T08:49:54+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T08:42:58+02:00 | N | N |  | Y | Y
74498 | 457_CD_Router_Indoor.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T08:50:52+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T11:50:46+02:00 | N | N |  | Y | Y
74499 | 456_CD_Siren.rfa | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T08:52:02+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-29T04:21:43+02:00 | N | N |  | Y | Y
74500 | 456_SD_AnalogCamera.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T08:52:46+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T08:28:07+02:00 | N | N |  | Y | Y
74501 | 456_SD_CameraHub_16Port.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T08:54:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T08:11:44+02:00 | N | N |  | Y | Y
74502 | 456_SD_CameraHub_8Port.rfa | 2026-07-14 | 2026-08-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T08:55:09+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:23:44+02:00 | N | N |  | Y | Y
74503 | 456_SD_CardReader.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:17:31+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T04:21:33+02:00 | N | N |  | Y | Y
74504 | 456_SD_DomeCamera_Indoor.rfa | 2026-07-14 | 2026-08-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:18:03+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-25T03:23:47+02:00 | N | N |  | Y | Y
74505 | 456_SD_DomeCamera_Outdoor.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:18:36+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-27T03:39:11+02:00 | N | N |  | Y | Y
74506 | 456_SD_ElectricalLock_DoorMounted.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:19:14+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T04:21:36+02:00 | N | N |  | Y | Y
74507 | 456_SD_FingerScan.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:19:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:24:52+02:00 | N | N |  | Y | Y
74508 | 456_SD_FingerScanFace_WallMounted.rfa | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:20:23+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:56+02:00 | N | N |  | Y | Y
74509 | 456_SD_FixCameraIP_Indoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:21:10+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:24:54+02:00 | N | N |  | Y | Y
74510 | 456_SD_FixCameraIP_Outdoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:21:43+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:24:57+02:00 | N | N |  | Y | Y
74511 | 456_SD_Monitor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:22:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:24:59+02:00 | N | N |  | Y | Y
74512 | 456_SD_PTZCamera_Indoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:22:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:25:03+02:00 | N | N |  | Y | Y
74513 | 456_SD_PTZCamera_Outdoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:23:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:25:06+02:00 | N | N |  | Y | Y
74514 | 456_SD_SecurityAlarmBell.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:24:01+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T11:50:50+02:00 | N | N |  | Y | Y
74515 | 456_SD_ThermalCamera.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:24:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-24T03:25:08+02:00 | N | N |  | Y | Y
74516 | 442_SD_UPSBattery_FloorStand_Rectangular.rfa | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:25:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-29T04:21:46+02:00 | N | N |  | Y | Y
74517 | 481_DD_BACnetGateway.rfa | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:26:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:11:59+02:00 | N | N |  | Y | Y
74518 | 457_DD_LanAndTelOutlet_WallSurface.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:27:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T11:50:53+02:00 | N | N |  | Y | Y
74519 | 457_DD_LanOutlet_WallMounted_2Gangs.rfa | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:27:53+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-29T04:21:49+02:00 | N | N |  | Y | Y
74520 | 451_DD_TelOutlet_WallMounted_2Gangs.rfa | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:28:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:12:04+02:00 | N | N |  | Y | Y
74521 | 455_DD_TVOutlet_WallMounted_1Gang.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-14T09:29:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T11:50:56+02:00 | N | N |  | Y | Y
74537 | 430_ME_AirHandlingUnit_CeilingMounted_AIR1XC3200L.rfa | 2026-07-15 | 2026-08-28 | 33 | handler_assign | status_resolved | START: handler→l.pham @ 2026-07-15T03:17:22+02:00 ¦¦ END: status→resolved @ 2026-08-28T10:10:44+02:00 | N | N |  | Y | N
74538 | 430_ME_AirCompressors_Standard.rfa | 2026-07-15 | 2026-08-14 | 23 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-07-15T03:23:08+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T05:50:16+02:00 | N | N |  | Y | Y
74539 | 430_ME_AirHandingUnit_RectangularLeftConnection_CeilingStand.rfa | 2026-07-15 | 2026-09-17 | 47 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-15T03:23:48+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T06:20:19+02:00 | N | N |  | Y | Y
74540 | 430_ME_AirHandingUnit_RectangularRightConnection_CeilingStand.rfa | 2026-07-15 | 2026-09-18 | 48 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-15T03:24:14+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:10:31+02:00 | N | N |  | Y | Y
74541 | 440_NC_EmergencyPullCordSwitch_Wall.rfa | 2026-07-15 | 2026-09-04 | 38 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-07-15T03:47:10+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:09:09+02:00 | N | N |  | Y | Y
74552 | 430_ME_AirHandingUnit_RoundConnection_CeilingStand | 2026-07-15 | 2026-09-29 | 55 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-15T06:33:54+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T08:13:51+02:00 | N | N |  | Y | Y
74571 | 410_SE_SoakawayTank | 2026-07-16 | 2026-07-17 | 2 | handler_assign | status_resolved | START: handler→tk.pham @ 2026-07-16T08:42:56+02:00 ¦¦ END: status→resolved @ 2026-07-17T04:25:12+02:00 | N | N |  | N | Y
74577 | 430_ME_AirHandlingUnits_1Layer.rfa | 2026-07-17 | 2026-08-14 | 21 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-07-17T03:41:44+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-14T05:41:27+02:00 | N | N |  | Y | Y
74583 | 410_PF_PEXA_eHotBending_QE | 2026-07-17 | 2026-07-22 | 4 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-07-17T08:02:29+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-22T10:58:59+02:00 | N | N |  | N | Y
74585 | 430_ME_AirHandlingUnits_CF.rfa | 2026-07-17 | 2026-09-07 | 37 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-17T08:49:15+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T06:17:53+02:00 | N | N |  | Y | Y
74586 | 430_ME_AirHandlingUnits_PHE.rfa | 2026-07-17 | 2026-09-16 | 44 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-17T08:49:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T08:30:11+02:00 | N | N |  | Y | Y
74587 | DCMvn_Annotation_Update Families in Existing DCM_SAN_Model | 2026-08-07 | 2026-09-25 | 36 | handler_assign | status_resolved | START: handler→y.nguyen @ 2026-08-07T08:00:23+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:47:12+02:00 | N | N |  | Y | N
74591 | RLT_Test Family | 2026-07-20 | 2026-07-21 | 2 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-07-20T03:26:38+02:00 ¦¦ END: status→resolved @ 2026-07-21T05:54:44+02:00 | N | N |  | Y | N
74592 | 430_ME_AirHandlingUnits_2Layer.rfa | 2026-07-20 | 2026-09-07 | 36 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-07-20T03:27:40+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T06:17:56+02:00 | N | N |  | Y | Y
74603 | RLT_Update RLT Update family to DCM Revit Library Model | 2026-07-21 |  |  | handler_assign | none | START: handler→n.bui @ 2026-07-21T02:10:39+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
74610 | 410_PF_PEXA_uAdapterMaleThread_QE | 2026-07-21 | 2026-07-28 | 6 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-07-21T04:39:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T10:41:35+02:00 | N | N |  | N | Y
74621 | 434_ME_ManifoldWithPump_8Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-21T11:19:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T08:17:22+02:00 | N | N |  | Y | Y
74622 | 434_ME_ManifoldWithPump_7Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-21T11:19:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T08:17:25+02:00 | N | N |  | Y | Y
74623 | 434_ME_ManifoldWithPump_6Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-21T11:19:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T11:45:31+02:00 | N | N |  | Y | Y
74624 | 434_ME_ManifoldWithPump_5Circuits.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-21T11:19:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T03:23:50+02:00 | N | N |  | Y | Y
74625 | 434_ME_ManifoldWithPump_4Circuits.rfa | 2026-07-21 | 2026-08-14 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-21T11:19:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-14T03:13:03+02:00 | N | N |  | Y | Y
74626 | 434_ME_ManifoldWithPump_3Circuits.rfa | 2026-07-21 | 2026-08-14 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-21T11:19:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-14T03:11:48+02:00 | N | N |  | Y | Y
74627 | 434_ME_ManifoldWithPump_2Circuits.rfa | 2026-07-21 | 2026-08-13 | 18 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-21T11:19:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-13T04:00:44+02:00 | N | N |  | Y | Y
74628 | 434_ME_ManifoldWithPump_1Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-21T11:19:10+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T08:17:28+02:00 | N | N |  | Y | Y
74629 | 434_ME_ManifoldWithFlowMeter_9Circuits.rfa | 2026-07-21 | 2026-08-21 | 24 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-21T11:18:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-21T11:37:19+02:00 | N | N |  | Y | Y
74630 | 434_ME_ManifoldWithFlowMeter_8Circuits.rfa | 2026-07-21 | 2026-08-27 | 28 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-21T11:18:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T03:39:14+02:00 | N | N |  | Y | Y
74631 | 434_ME_ManifoldWithFlowMeter_7Circuits.rfa | 2026-07-21 | 2026-08-26 | 27 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-21T11:18:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-26T04:03:37+02:00 | N | N |  | Y | Y
74632 | 434_ME_ManifoldWithFlowMeter_6Circuits.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-21T11:18:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T04:50:02+02:00 | N | N |  | Y | Y
74633 | 434_ME_ManifoldWithFlowMeter_5Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-21T11:18:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T11:45:34+02:00 | N | N |  | Y | Y
74634 | 434_ME_ManifoldWithFlowMeter_4Circuits.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-21T11:18:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:12:08+02:00 | N | N |  | Y | Y
74635 | 434_ME_ManifoldWithFlowMeter_3Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-21T11:18:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:23:46+02:00 | N | N |  | Y | Y
74636 | 434_ME_ManifoldWithFlowMeter_2Circuits.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-21T11:18:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T05:07:51+02:00 | N | N |  | Y | Y
74637 | 434_ME_ManifoldWithFlowMeter_12Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-21T11:18:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:23:49+02:00 | N | N |  | Y | Y
74638 | 434_ME_ManifoldWithFlowMeter_11Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-21T11:18:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:23:51+02:00 | N | N |  | Y | Y
74639 | 434_ME_ManifoldWithFlowMeter_10Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-21T11:18:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:23:53+02:00 | N | N |  | Y | Y
74640 | 434_ME_InLinePump_Standard.rfa | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-21T11:18:38+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-09-04T04:06:31+02:00 | N | N |  | Y | Y
74641 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlusHygiene.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-07-22T02:43:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T10:28:19+02:00 | N | N |  | Y | Y
74642 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlus.rfa | 2026-07-22 | 2026-08-25 | 25 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-07-22T02:43:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T07:23:09+02:00 | N | N |  | Y | Y
74643 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVHygiene.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-07-22T02:43:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T08:19:00+02:00 | N | N |  | Y | Y
74644 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileV.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-07-21T11:17:51+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:23:55+02:00 | N | N |  | Y | Y
74645 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKReplacement.rfa | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:passed_audit | START: handler→d.phan @ 2026-07-21T11:17:51+02:00 ¦¦ END: lk.dang: On behalf of Mr. @hu.dam, the tickets will be assigned directly to @n.le The family has passed the a @ 2026-09-04T10:08:55+02:00 | N | N |  | Y | Y
74646 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKHygiene.rfa | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:passed_audit | START: handler→d.phan @ 2026-07-21T11:17:51+02:00 ¦¦ END: lk.dang: On behalf of Mr. @hu.dam, the tickets will be assigned directly to @n.le The family has passed the a @ 2026-09-04T10:10:18+02:00 | N | N |  | Y | Y
74647 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileK.rfa | 2026-07-21 | 2026-08-20 | 23 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-07-21T11:17:51+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T07:15:40+02:00 | N | N |  | Y | Y
74648 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlusHygiene.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-21T11:17:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-24T11:45:37+02:00 | N | N |  | Y | Y
74649 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlus.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-21T11:17:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T03:13:12+02:00 | N | N |  | Y | Y
74650 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVHygiene.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-21T11:17:38+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T03:46:08+02:00 | N | N |  | Y | Y
74651 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-21T11:17:37+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T03:13:14+02:00 | N | N |  | Y | Y
74652 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKReplacement.rfa | 2026-07-21 | 2026-09-10 | 38 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-21T11:17:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T06:27:26+02:00 | N | N |  | Y | Y
74653 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKHygiene.rfa | 2026-07-21 | 2026-09-09 | 37 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-21T11:17:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-09T05:15:44+02:00 | N | N |  | Y | Y
74654 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanK.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-21T11:17:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:29:50+02:00 | N | N |  | Y | Y
74655 | 420_ME_RadiatorElectricPanel_WallMounted_xThermProfileHorizontal_NoSystem.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-21T11:17:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T03:13:16+02:00 | N | N |  | Y | Y
74656 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanVertical_NoSystem.rfa | 2026-07-21 | 2026-08-10 | 15 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-07-21T11:17:13+02:00 ¦¦ END: status→resolved @ 2026-08-10T09:12:26+02:00 | N | N |  | Y | N
74657 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanHorizontal_NoSystem.rfa | 2026-07-21 | 2026-08-19 | 22 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-21T11:17:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-19T11:37:53+02:00 | N | N |  | Y | Y
74659 | 420_ME_RadiatorBathroom_WallMounted_TabeoV.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-21T11:17:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T07:23:13+02:00 | N | N |  | Y | Y
74660 | 420_ME_RadiatorBathroom_WallMounted_Tabeo.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-21T11:17:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-25T07:23:16+02:00 | N | N |  | Y | Y
74661 | 420_ME_RadiatorBathroom_WallMounted_Signo.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-21T11:17:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T03:13:18+02:00 | N | N |  | Y | Y
74662 | 420_ME_RadiatorBathroom_WallMounted_Rubeo.rfa | 2026-07-21 | 2026-08-20 | 23 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-21T11:17:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T08:15:49+02:00 | N | N |  | Y | Y
74663 | 420_ME_RadiatorBathroom_WallMounted_PioPlus.rfa | 2026-07-21 | 2026-09-11 | 39 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-21T11:17:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T05:55:17+02:00 | N | N |  | Y | Y
74664 | 420_ME_RadiatorBathroom_WallMounted_Pio2layer.rfa | 2026-07-21 | 2026-09-11 | 39 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-21T11:17:02+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T05:55:20+02:00 | N | N |  | Y | Y
74678 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B147SD.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-22T02:45:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T10:23:01+02:00 | N | N |  | Y | Y
74679 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B110.rfa | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-22T02:45:36+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T09:20:21+02:00 | N | N |  | Y | Y
74680 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100SD.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-22T02:45:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:23:57+02:00 | N | N |  | Y | Y
74681 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100.rfa | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-22T02:45:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T09:48:58+02:00 | N | N |  | Y | Y
74682 | 434_ME_HeatedAndChilledPlasterboardCeilings_CeilingMounted_GKHEKDA2Pipes.rfa | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-22T02:45:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:08:16+02:00 | N | N |  | Y | Y
74683 | 434_ME_HeatedAndChilledHybridCeilings_CeilingMounted_DSTAS.rfa | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-22T02:45:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:08:20+02:00 | N | N |  | Y | Y
74684 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E214.rfa | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-07-22T02:45:06+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T09:16:44+02:00 | N | N |  | Y | Y
74685 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E213.rfa | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-22T02:44:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T05:23:00+02:00 | N | N |  | Y | Y
74686 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E210.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-22T02:44:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T10:23:04+02:00 | N | N |  | Y | Y
74687 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E200.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-22T02:44:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:23:59+02:00 | N | N |  | Y | Y
74688 | 434_ME_HeatedAndChilledCorridorCeilings_CeilingMounted_E312.rfa | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-07-22T02:44:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T05:23:03+02:00 | N | N |  | Y | Y
74689 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs78_NoSystem.rfa | 2026-07-22 | 2026-09-23 | 46 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-07-22T02:44:44+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T07:20:28+02:00 | N | N |  | Y | Y
74690 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs125_NoSystem.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-07-22T02:44:44+02:00 ¦¦ END: status→resolved @ 2026-08-12T11:46:34+02:00 | N | N |  | Y | N
74691 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD320.rfa | 2026-07-22 | 2026-08-11 | 15 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-07-22T02:44:44+02:00 ¦¦ END: status→resolved @ 2026-08-11T11:26:40+02:00 | N | N |  | Y | N
74692 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD315.rfa | 2026-07-22 | 2026-08-10 | 14 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-07-22T02:44:44+02:00 ¦¦ END: status→resolved @ 2026-08-10T11:29:05+02:00 | N | N |  | Y | N
74693 | 434_ME_HeatedAndChilledBaffleCeilings_CeilingMounted_L608.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-22T02:44:34+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:24:04+02:00 | N | N |  | Y | Y
74694 | 434_ME_HeatExchanger_Standard.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-22T02:44:34+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T10:29:21+02:00 | N | N |  | Y | Y
74695 | 434_ME_HeatExchanger_Gasketed&Thread.rfa | 2026-07-22 | 2026-08-21 | 23 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-07-22T02:44:34+02:00 ¦¦ END: status→resolved @ 2026-08-21T11:56:46+02:00 | N | N |  | Y | N
74696 | 434_ME_HeatExchanger_Gasketed&Flanged.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-07-22T02:44:34+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:24:06+02:00 | N | N |  | Y | Y
74697 | 434_ME_HeatExchanger_Brazed_SinglePass&Flanged.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-22T02:44:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T10:29:24+02:00 | N | N |  | Y | Y
74698 | 434_ME_HeatExchanger_Brazed_DoublePass.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-22T02:44:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T07:31:57+02:00 | N | N |  | Y | Y
74699 | 434_ME_HeatExchanger_BrazedSinglePass&Thread.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-22T02:44:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T09:31:27+02:00 | N | N |  | Y | Y
74700 | 434_ME_HeatExchanger_Brazed&DoublePass&Flanged.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-22T02:44:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T09:31:31+02:00 | N | N |  | Y | Y
74701 | 434_ME_FlatCompactDryCooler.rfa | 2026-07-22 | 2026-09-10 | 37 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-07-22T02:44:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T08:16:21+02:00 | N | N |  | Y | Y
74702 | 420_ME_RadiatorBathroom_WallMounted_Pio1layer.rfa | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-07-22T02:43:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T07:02:28+02:00 | N | N |  | Y | Y
74703 | 420_ME_RadiatorBathroom_WallMounted_Pateo.rfa | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-22T02:43:44+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T10:24:50+02:00 | N | N |  | Y | Y
74704 | 420_ME_RadiatorBathroom_WallMounted_Leveo.rfa | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-22T02:43:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:29:54+02:00 | N | N |  | Y | Y
74705 | 420_ME_RadiatorBathroom_WallMounted_Ineo.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-22T02:43:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T03:13:20+02:00 | N | N |  | Y | Y
74706 | 420_ME_RadiatorBathroom_WallMounted_Ideos.rfa | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-07-22T02:43:24+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T05:15:06+02:00 | N | N |  | Y | Y
74707 | 420_ME_RadiatorBathroom_WallMounted_Icaro.rfa | 2026-07-22 | 2026-08-13 | 17 | handler_assign | status_resolved | START: handler→b.tran @ 2026-07-22T02:43:24+02:00 ¦¦ END: status→resolved @ 2026-08-13T08:11:00+02:00 | N | N |  | Y | Y
74708 | 420_ME_RadiatorBathroom_WallMounted_Geneoquadris.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-22T02:43:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T12:29:11+02:00 | N | N |  | Y | Y
74709 | 420_ME_RadiatorBathroom_WallMounted_Geneocircle.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-22T02:43:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T12:29:15+02:00 | N | N |  | Y | Y
74710 | 420_ME_RadiatorBathroom_WallMounted_Fineo.rfa | 2026-07-22 | 2026-09-10 | 37 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-07-22T02:43:15+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T10:01:45+02:00 | N | N |  | Y | Y
74711 | 420_ME_RadiatorBathroom_WallMounted_Elveo_NoSystem.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-07-22T02:43:15+02:00 ¦¦ END: status→resolved @ 2026-08-12T09:52:43+02:00 | N | N |  | Y | Y
74712 | 420_ME_RadiatorBathroom_WallMounted_Duett.rfa | 2026-07-22 | 2026-09-23 | 46 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-22T02:43:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T04:21:29+02:00 | N | N |  | Y | Y
74713 | 420_ME_RadiatorBathroom_WallMounted_Diveo.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-22T02:43:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T05:33:29+02:00 | N | N |  | Y | Y
74714 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureVertical.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-22T02:43:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T05:24:21+02:00 | N | N |  | Y | Y
74715 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureHorizontal.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-07-22T02:43:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-20T04:50:58+02:00 | N | N |  | Y | Y
74716 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePlan.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-07-22T02:42:53+02:00 ¦¦ END: status→resolved @ 2026-08-12T10:23:01+02:00 | N | N |  | Y | Y
74717 | 420_ME_RadiatorBathroom_WallMounted_DecorArteLine.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-07-22T02:42:53+02:00 ¦¦ END: status→resolved @ 2026-08-12T10:28:38+02:00 | N | N |  | Y | Y
74718 | 420_ME_RadiatorBathroom_WallMounted_Credoplus.rfa | 2026-07-22 | 2026-09-22 | 45 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-22T02:42:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:15+02:00 | N | N |  | Y | Y
74719 | 420_ME_RadiatorBathroom_WallMounted_Credohalfflat.rfa | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-07-22T02:42:53+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T10:24:53+02:00 | N | N |  | Y | Y
74740 | 410_PX_GutterWithOutLet_Vertical | 2026-07-22 | 2026-07-28 | 5 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-22T10:14:24+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T11:13:42+02:00 | N | N |  | N | Y
74776 | 430_AT_LinearDisplacementDiffuser_FloorStand_LBQ | 2026-07-23 | 2026-07-29 | 5 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-23T05:38:34+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T04:57:50+02:00 | N | N |  | N | Y
74777 | 430_AT_FloorDisplacementDiffuser_QB | 2026-07-23 | 2026-07-28 | 4 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-07-23T05:58:53+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-28T08:14:52+02:00 | N | N |  | N | Y
74839 | 440_NC_PullCordSwitch | 2026-07-27 | 2026-08-06 | 9 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-27T04:02:43+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T12:15:42+02:00 | N | N |  | N | Y
74840 | 440_EE_AnnunciatorPanel | 2026-07-28 | 2026-07-28 | 1 | handler_assign | status_resolved | START: handler→n.bui @ 2026-07-28T03:58:26+02:00 ¦¦ END: status→resolved @ 2026-07-28T10:09:10+02:00 | N | N |  | N | Y
74841 | 440_NC_CancelCallButton | 2026-07-28 | 2026-07-28 | 1 | handler_assign | status_resolved | START: handler→ha.phan @ 2026-07-28T04:32:22+02:00 ¦¦ END: status→resolved @ 2026-07-28T08:24:34+02:00 | N | N |  | N | Y
74842 | 440_EE_MotorizedGlareControl | 2026-07-28 | 2026-07-29 | 2 | handler_assign | status_resolved | START: handler→ha.phan @ 2026-07-28T11:16:42+02:00 ¦¦ END: status→resolved @ 2026-07-29T05:34:16+02:00 | N | N |  | N | Y
74843 | 440_EF_PushButton_Wall | 2026-07-28 | 2026-07-28 | 1 | handler_assign | status_resolved | START: handler→ha.phan @ 2026-07-28T08:25:07+02:00 ¦¦ END: status→resolved @ 2026-07-28T11:14:59+02:00 | N | N |  | N | Y
74844 | 440_LF_RoomSignalLight | 2026-07-27 | 2026-07-29 | 3 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-07-27T11:18:35+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-29T10:42:59+02:00 | N | N |  | N | Y
74845 | 440_EF_UpDownControlSwitch | 2026-07-28 | 2026-07-31 | 4 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-07-28T03:48:31+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-07-31T06:31:31+02:00 | N | N |  | N | Y
74853 | 410_ME_CentrifugalPump | 2026-07-30 | 2026-09-23 | 40 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-30T10:55:25+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T11:22:19+02:00 | N | N |  | Y | Y
74854 | 410_ME_CompactPressureBoostingSystem | 2026-07-30 | 2026-09-09 | 30 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-07-30T10:55:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T11:49:57+02:00 | N | N |  | Y | Y
74855 | 410_ME_CompactPressureBoostingSystem_1MVISE | 2026-08-06 | 2026-09-17 | 31 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-08-06T08:57:00+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:08+02:00 | N | N |  | Y | Y
74856 | 410_ME_CompactWaterHeater_WallMounted | 2026-08-06 | 2026-09-25 | 37 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-08-06T08:57:44+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-25T10:23:07+02:00 | N | N |  | Y | Y
74857 | 410_ME_Desoftening | 2026-08-07 | 2026-09-11 | 26 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-07T05:20:30+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T11:40:10+02:00 | N | N |  | Y | Y
74858 | 410_ME_DoppelHebeanlageSchmutzwasser | 2026-08-07 | 2026-09-14 | 27 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-07T05:21:17+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-14T11:07:38+02:00 | N | N |  | Y | Y
74859 | 410_ME_DoublePressureBoosterSystem | 2026-08-07 | 2026-09-23 | 34 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-07T05:21:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T11:37:34+02:00 | N | N |  | Y | Y
74860 | 410_ME_DrainLiftL_Floor | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-07T05:22:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T07:24:08+02:00 | N | N |  | Y | Y
74861 | 410_ME_DrainLiftM_Floor | 2026-08-07 | 2026-09-24 | 35 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-07T05:22:44+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-24T03:53:29+02:00 | N | N |  | Y | Y
74872 | 410_ME_DrainLiftS_Floor | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-07T05:26:16+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T11:50:01+02:00 | N | N |  | Y | Y
74873 | 410_ME_DrainLiftXL_Floor | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-07T05:27:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:11+02:00 | N | N |  | Y | Y
74874 | 410_ME_DualTank_WaterSofteners | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-07T05:27:27+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:14+02:00 | N | N |  | Y | Y
74875 | 410_ME_DuplexSofteningUnit_RondomatDuo | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-07T05:28:51+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T07:24:10+02:00 | N | N |  | Y | Y
74876 | 410_ME_EKleindurchlauferhitzerCEX | 2026-08-07 | 2026-08-27 | 15 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-07T05:29:23+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-27T11:12:09+02:00 | N | N |  | Y | Y
74877 | 410_ME_EKleindurchlauferhitzer_MCX | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-07T05:30:29+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T11:50:04+02:00 | N | N |  | Y | Y
74878 | 410_ME_ElectricInstantaneousHeater_DLE | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-07T05:34:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T11:50:07+02:00 | N | N |  | Y | Y
74879 | 410_ME_ExpansionVessel | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-07T05:35:09+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T07:24:12+02:00 | N | N |  | Y | Y
74880 | 410_ME_ExpansionVessel_Reflex | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-07T05:35:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T07:24:14+02:00 | N | N |  | Y | Y
74881 | 410_ME_FettabscheiderNG2 | 2026-08-07 | 2026-08-27 | 15 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-07T05:36:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-27T11:12:12+02:00 | N | N |  | Y | Y
74882 | 410_ME_FreshWaterStation | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-07T05:37:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T11:50:11+02:00 | N | N |  | Y | Y
74883 | 410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-07T05:38:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:18+02:00 | N | N |  | Y | Y
74884 | 410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ | 2026-08-07 | 2026-09-16 | 29 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-07T05:39:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:28:26+02:00 | N | N |  | Y | Y
74885 | 410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-07T05:40:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T07:24:16+02:00 | N | N |  | Y | Y
74886 | 410_ME_GreaseSeparatorFreeStandingInstallationNS10 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-07T05:41:47+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T11:50:15+02:00 | N | N |  | Y | Y
74887 | 410_ME_GreaseSeparator_FloorStand | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-07T05:42:16+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T11:50:19+02:00 | N | N |  | Y | Y
74888 | 410_ME_HighPerformanceIndustrialMixers | 2026-08-07 | 2026-09-15 | 28 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-07T05:42:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T11:12:12+02:00 | N | N |  | Y | Y
74889 | 410_ME_HotWaterStorageTank | 2026-08-11 | 2026-08-28 | 14 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-11T10:19:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-28T03:07:54+02:00 | N | N |  | Y | Y
74890 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-13T09:38:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T10:54:29+02:00 | N | N |  | Y | Y
74891 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2 | 2026-08-13 | 2026-08-24 | 8 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-13T09:39:16+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T04:21:39+02:00 | N | N |  | Y | Y
74892 | 410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2 | 2026-08-13 | 2026-08-24 | 8 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-13T09:39:43+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T04:24:39+02:00 | N | N |  | Y | Y
74893 | 410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2 | 2026-08-13 | 2026-08-28 | 12 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-13T09:40:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-28T04:50:47+02:00 | N | N |  | Y | Y
74894 | 410_ME_IBCTank | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | START: handler→n.vo @ 2026-08-13T09:40:46+02:00 ¦¦ END: status→resolved @ 2026-08-20T11:00:48+02:00 | N | N |  | Y | N
74895 | 410_ME_iboxUniversalForShower_WallRecessed | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-13T09:41:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T11:36:24+02:00 | N | N |  | Y | Y
74896 | 410_ME_InstantaneousWaterHeater_Shower | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-13T09:44:50+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T04:02:53+02:00 | N | N |  | Y | Y
74897 | 410_ME_InstantaneousWaterHeater_SinkAGB | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-13T09:45:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T04:02:56+02:00 | N | N |  | Y | Y
74898 | 410_ME_InstantaneousWaterHeater_TeaKitchen | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-13T09:45:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T09:49:01+02:00 | N | N |  | Y | Y
74899 | 410_ME_InstantaneousWaterHeater_WashBasin | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-08-13T09:46:29+02:00 ¦¦ END: status→resolved @ 2026-08-20T11:01:10+02:00 | N | N |  | Y | N
74900 | 410_ME_KHSHygieneFlushBoxLITE_FlowSensorDoublePortwithThreaded | 2026-08-13 | 2026-08-21 | 7 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-08-13T09:47:16+02:00 ¦¦ END: status→resolved @ 2026-08-21T10:55:14+02:00 | N | N |  | Y | N
74901 | 410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-13T09:47:42+02:00 ¦¦ END: hu.dam: tv.huynh This family is now fully completed and securely stored. Thank you for your attention to thi @ 2026-08-21T05:37:28+02:00 | N | N |  | Y | Y
74903 | 410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-13T09:48:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:27:36+02:00 | N | N |  | Y | Y
74904 | 410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-13T09:48:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T11:36:28+02:00 | N | N |  | Y | Y
74905 | 410_ME_KHSHygieneFlushBoxPUREwithFlowSensorSinglePort_Threaded | 2026-08-13 | 2026-08-21 | 7 | handler_assign | status_resolved | START: handler→c.le @ 2026-08-13T09:48:56+02:00 ¦¦ END: status→resolved @ 2026-08-21T03:07:49+02:00 | N | N |  | Y | N
74906 | 410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort | 2026-08-13 | 2026-09-25 | 32 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-13T09:49:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-25T10:23:10+02:00 | N | N |  | Y | Y
74907 | 410_ME_KHSMiniControlSystemSLAVE_WallSurface | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-13T09:51:41+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:27:08+02:00 | N | N |  | Y | Y
74909 | 410_ME_KHSMiniControlSystem_WallSurface_Master | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-13T09:52:13+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-21T05:16:40+02:00 | N | N |  | Y | Y
74910 | 410_ME_KHSTimer_WallSurface | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-13T09:52:54+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T10:54:31+02:00 | N | N |  | Y | Y
74911 | 410_ME_MiniTresorCabinet_InWall | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-13T09:53:30+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T11:36:31+02:00 | N | N |  | Y | Y
74912 | 410_ME_MiniTresorCabinet_WallSurface | 2026-08-13 | 2026-08-21 | 7 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-08-13T09:54:05+02:00 ¦¦ END: status→resolved @ 2026-08-21T11:16:35+02:00 | N | N |  | Y | N
74913 | 410_ME_MixingTank | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | START: handler→k.mai @ 2026-08-13T09:54:57+02:00 ¦¦ END: status→resolved @ 2026-08-18T10:44:10+02:00 | N | N |  | Y | N
74914 | 410_ME_PHController | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-13T09:55:32+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T10:54:34+02:00 | N | N |  | Y | Y
74915 | 410_ME_PlasticInnerTankSeries | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-31T09:24:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T11:44:23+02:00 | N | N |  | Y | Y
74916 | 410_ME_PoolHeatPump | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | START: handler→k.mai @ 2026-08-13T09:56:11+02:00 ¦¦ END: status→resolved @ 2026-08-17T10:52:04+02:00 | N | N |  | Y | N
74917 | 410_ME_PoolSandFilter_FloorStand_Round | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-13T09:56:59+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-28T03:40:01+02:00 | N | N |  | Y | Y
74918 | 410_ME_PressureBoosterPump | 2026-08-20 | 2026-09-16 | 20 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-20T04:41:14+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:28:31+02:00 | N | N |  | Y | Y
74919 | 410_ME_PressurisationUnit_FixedSpeedUnits2Pump | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-20T04:43:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T10:54:37+02:00 | N | N |  | Y | Y
74920 | 410_ME_PressurisationUnit_FixedSpeedUnits3Pump | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-20T04:43:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T10:54:40+02:00 | N | N |  | Y | Y
74921 | 410_ME_PressurisationUnit_VariableSpeedUnits3Pump | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-20T04:43:58+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T05:10:27+02:00 | N | N |  | Y | Y
74922 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith1Pump | 2026-08-20 | 2026-09-18 | 22 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-20T04:44:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T11:10:55+02:00 | N | N |  | Y | Y
74926 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-20T04:47:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:21+02:00 | N | N |  | Y | Y
74929 | 410_ME_Probenahmetopf | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-20T04:47:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T07:13:33+02:00 | N | N |  | Y | Y
74933 | 410_ME_PumpGlandlessCirculator_StarZ | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-20T04:48:02+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-08T10:54:42+02:00 | N | N |  | Y | Y
74934 | 410_ME_PumpGlandlessCirculator_StarZD | 2026-08-20 | 2026-09-15 | 19 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-20T04:48:26+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T11:12:16+02:00 | N | N |  | Y | Y
74935 | 410_ME_PumpGlandlessCirculator_TopZ | 2026-08-20 | 2026-09-30 | 30 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-20T04:49:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T11:36:35+02:00 | N | N |  | Y | Y
74936 | 410_ME_PureWaterTank | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-20T04:50:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T07:13:36+02:00 | N | N |  | Y | Y
74937 | 410_ME_ReverseOsmosisSystem | 2026-08-20 | 2026-09-23 | 25 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-20T04:51:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T11:22:22+02:00 | N | N |  | Y | Y
74938 | 410_ME_SeparationStation | 2026-08-20 | 2026-08-21 | 2 | handler_assign | status_resolved | START: handler→n.vo @ 2026-08-20T04:52:20+02:00 ¦¦ END: status→resolved @ 2026-08-21T08:11:18+02:00 | N | N |  | Y | N
74939 | 410_ME_ServiceStorageTank_Round | 2026-08-20 | 2026-09-11 | 17 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-20T04:52:44+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T07:34:14+02:00 | N | N |  | Y | Y
74940 | 410_ME_Sicherheitstrennstation | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-20T04:53:05+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T07:13:39+02:00 | N | N |  | Y | Y
74941 | 410_ME_SinglePressureBoosterSystem | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-20T04:53:31+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T05:10:30+02:00 | N | N |  | Y | Y
74942 | 410_ME_StratosMAXOZPump_Vertical | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-20T04:55:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T07:13:44+02:00 | N | N |  | Y | Y
74943 | 410_ME_StratosPICOZPump_Vertical | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-20T04:57:12+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T07:13:47+02:00 | N | N |  | Y | Y
74944 | 410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-20T04:57:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T03:50:24+02:00 | N | N |  | Y | Y
74945 | 410_ME_SubmergedPump_Horizontal_SatSeries | 2026-08-20 | 2026-09-24 | 26 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-20T04:58:07+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-24T03:53:32+02:00 | N | N |  | Y | Y
74946 | 410_ME_SubmergedPump_SitaSeries | 2026-08-20 | 2026-09-15 | 19 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-20T04:58:34+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T11:12:19+02:00 | N | N |  | Y | Y
74947 | 410_ME_SubmergedPump_Vertical_SATSeries | 2026-08-24 | 2026-09-04 | 10 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-24T03:48:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-04T05:09:12+02:00 | N | N |  | Y | Y
74948 | 410_ME_SubmergedPump_Vertical_SATVSeries | 2026-08-24 | 2026-09-28 | 26 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-24T03:49:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-28T03:40:05+02:00 | N | N |  | Y | Y
74949 | 410_ME_TresorCabinet_InWall | 2026-08-26 | 2026-09-11 | 13 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-26T05:07:17+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T09:20:24+02:00 | N | N |  | Y | Y
74950 | 410_ME_TresorCabinet_WallSurface | 2026-08-26 | 2026-09-16 | 16 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-26T05:08:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:28:35+02:00 | N | N |  | Y | Y
74951 | 410_ME_TripleSofteningSystem_DeltaP | 2026-08-26 | 2026-09-11 | 13 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-26T05:08:16+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-11T09:20:28+02:00 | N | N |  | Y | Y
74952 | 410_ME_TWPressureBoosterSystem | 2026-08-26 | 2026-09-16 | 16 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-26T05:09:37+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:28:39+02:00 | N | N |  | Y | Y
74953 | 410_ME_VerticaltubeHeatexchanger | 2026-08-26 | 2026-09-15 | 15 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-26T05:10:48+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T11:12:23+02:00 | N | N |  | Y | Y
74954 | 410_ME_WasteWaterLiftingStationPump | 2026-08-26 | 2026-09-23 | 21 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-08-26T05:11:40+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T11:22:24+02:00 | N | N |  | Y | Y
74955 | 410_ME_WastewaterLiftingStation_DouPump | 2026-08-27 | 2026-09-16 | 15 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-27T09:08:22+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:39:36+02:00 | N | N |  | Y | Y
74956 | 410_ME_WasteWaterLiftingStation_KesselPump | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-31T04:06:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:28:43+02:00 | N | N |  | Y | Y
74957 | 410_ME_WastewaterLiftingStation_MuliPES&Mono | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | START: handler→hoa.le @ 2026-08-31T04:06:28+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T03:18:31+02:00 | N | N |  | Y | Y
74958 | 410_ME_WastewaterLiftingStation_MuliProPEKDuo | 2026-08-31 | 2026-09-07 | 6 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-08-31T04:06:56+02:00 ¦¦ END: status→resolved @ 2026-09-07T03:39:34+02:00 | N | N |  | Y | N
74959 | 410_ME_WastewaterLiftingStation_MuliProPEKParallel | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-31T04:09:19+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:39:39+02:00 | N | N |  | Y | Y
74960 | 410_ME_WastewaterLiftingStation_MuliProPENXLDuo | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-31T04:09:34+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T03:14:05+02:00 | N | N |  | Y | Y
74961 | 410_ME_WastewaterLiftingStation_MuliStarDDP | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-31T04:10:01+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:39:44+02:00 | N | N |  | Y | Y
74962 | 410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full | START: handler→c.le @ 2026-08-31T04:10:18+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:30+02:00 | N | N |  | Y | Y
74963 | 410_ME_WastewaterLiftingStation_Sinkamat_HW | 2026-08-31 | 2026-09-24 | 19 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-08-31T09:23:57+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-24T03:53:35+02:00 | N | N |  | Y | Y
74964 | 410_ME_WasteWaterLiftingStation_VerticalPump | 2026-08-31 | 2026-09-08 | 7 | handler_assign | status_resolved | START: handler→hoa.le @ 2026-08-31T09:23:31+02:00 ¦¦ END: status→resolved @ 2026-09-08T11:08:42+02:00 | N | N |  | Y | N
74965 | 410_ME_WasteWaterLift_Floor_C3 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-31T09:22:39+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:37+02:00 | N | N |  | Y | Y
74966 | 410_ME_WasteWaterLift_Floor_CWC3 | 2026-08-31 | 2026-09-22 | 17 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-31T09:22:21+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-22T11:07:40+02:00 | N | N |  | Y | Y
74967 | 410_ME_WasteWaterLift_Floor_D2 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-08-31T09:21:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T11:51:40+02:00 | N | N |  | Y | Y
74968 | 410_ME_WasteWaterLift_Floor_WC1 | 2026-08-31 | 2026-09-24 | 19 | handler_assign | confirm_note:stored_full | START: handler→t.luu @ 2026-08-31T09:21:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-24T12:29:18+02:00 | N | N |  | Y | Y
74969 | 410_ME_WasteWaterLift_Floor_WC3 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-31T09:20:03+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T10:26:23+02:00 | N | N |  | Y | Y
74970 | 410_ME_WaterDispenser_FloorStand | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-31T09:19:46+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T03:14:07+02:00 | N | N |  | Y | Y
74971 | 410_ME_WaterFilterTank | 2026-08-31 | 2026-09-18 | 15 | handler_assign | confirm_note:stored_full | START: handler→k.mai @ 2026-08-31T09:19:33+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T03:06:43+02:00 | N | N |  | Y | Y
74972 | 410_ME_WaterFilterVertical | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-31T09:18:35+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-16T11:28:48+02:00 | N | N |  | Y | Y
74973 | 410_ME_WaterHardnessMeter | 2026-08-31 | 2026-09-14 | 11 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-31T09:18:20+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-14T04:07:28+02:00 | N | N |  | Y | Y
74974 | 410_ME_WaterHeaterWithTap_WallMounted | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-31T09:18:08+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T10:26:28+02:00 | N | N |  | Y | Y
74975 | 410_ME_WaterHeater_WallMounted | 2026-08-31 | 2026-09-18 | 15 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-31T09:17:55+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-18T03:06:46+02:00 | N | N |  | Y | Y
74976 | 410_ME_WaterSofteningTank | 2026-08-31 | 2026-09-09 | 8 | handler_assign | status_resolved | START: handler→dhn.nguyen @ 2026-08-31T09:17:40+02:00 ¦¦ END: status→resolved @ 2026-09-09T11:14:33+02:00 | N | N |  | Y | N
74977 | 410_SE_Conlit150U_NoSystem | 2026-08-04 | 2026-09-09 | 27 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-04T04:59:47+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-09T07:13:50+02:00 | N | N |  | Y | Y
74978 | 410_SE_ConlitFireProtectionSleeve_NoSystem | 2026-08-04 | 2026-09-10 | 28 | handler_assign | confirm_note:stored_full | START: handler→dhn.nguyen @ 2026-08-04T05:00:15+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-10T11:54:10+02:00 | N | N |  | Y | Y
74979 | 410_SE_CoverBox | 2026-08-04 | 2026-09-10 | 28 | handler_assign | confirm_note:stored_full | START: handler→n.vo @ 2026-08-04T05:00:52+02:00 ¦¦ END: hu.dam: @tv.huynh This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-10T11:54:14+02:00 | N | N |  | Y | Y
74980 | 456_SD_DuressAlarmDetector | 2026-07-28 | 2026-08-06 | 8 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-28T09:45:35+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T11:28:06+02:00 | N | N |  | N | Y
74981 | 456_SD_ActiveGlassBreakDetector | 2026-07-28 | 2026-08-05 | 7 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-28T09:45:51+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-05T12:55:15+02:00 | N | N |  | N | Y
74982 | 456_SD_Passive GlassBreakDetector | 2026-07-28 | 2026-08-11 | 11 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-07-28T09:46:07+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T03:16:19+02:00 | N | N |  | N | Y
74983 | 481_EF_DoorBusCoupler | 2026-07-28 | 2026-08-10 | 10 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-28T09:46:25+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-10T12:22:08+02:00 | N | N |  | N | Y
74984 | 456_SD_CombinedOpeningLockingContact | 2026-07-28 | 2026-08-11 | 11 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-07-28T09:46:39+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-11T02:50:55+02:00 | N | N |  | N | Y
75015 | ELT_MSR_High Priority Audit Family List | 2026-07-30 | 2026-07-31 | 2 | handler_assign | status_resolved | START: handler→th.le @ 2026-07-30T10:47:31+02:00 ¦¦ END: status→resolved @ 2026-07-31T10:31:14+02:00 | N | N |  | Y | N
75031 | 440_NC_EmergencyCallButton | 2026-08-03 | 2026-08-06 | 4 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-08-03T06:40:45+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-06T11:06:19+02:00 | N | N |  | N | Y
75059 | 440_EE_FlatRoofSolarModule.rfa | 2026-08-04 | 2026-09-04 | 24 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-08-04T10:53:57+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-04T05:09:16+02:00 | N | N |  | Y | Y
75081 | SPR_Update Pipe Fitting to DCM Revit Library Model | 2026-08-05 |  |  | handler_assign | none | START: handler→s.duong @ 2026-08-05T10:21:05+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
75082 | MED_Update Pipe Fitting to DCM Revit Library Model | 2026-08-05 | 2026-08-31 | 19 | handler_assign | status_resolved | START: handler→s.duong @ 2026-08-05T10:21:33+02:00 ¦¦ END: status→resolved @ 2026-08-31T11:12:52+02:00 | N | N |  | Y | N
75092 | 481_EE_TransmissionDevice | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-08-06T02:22:49+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:47:34+02:00 | N | N |  | N | Y
75093 | 456_SD_KeyCardTransponder_WallMounted | 2026-08-06 | 2026-08-13 | 6 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-08-06T02:23:21+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T05:24:12+02:00 | N | N |  | N | Y
75094 | 456_SD_Keypad_WallMounted | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-08-06T02:23:52+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T10:04:37+02:00 | N | N |  | N | Y
75095 | 456_EF_InfraredMotionDetector_WallMounted | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-08-06T02:24:19+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:55:30+02:00 | N | N |  | N | Y
75096 | 456_SD_LockingElementVertical_DoorMounted | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-08-06T02:24:51+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-12T11:52:50+02:00 | N | N |  | N | Y
75097 | 481_SD_Distributor | 2026-08-06 | 2026-08-13 | 6 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-08-06T02:25:25+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-13T04:01:19+02:00 | N | N |  | N | Y
75126 | 491_SE_ConductorHolders_FloorStand.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-08-11T04:09:24+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-09T07:13:54+02:00 | N | N |  | Y | Y
75127 | Revise the RFA library for the HGR system. | 2026-08-11 |  |  | handler_assign | none | START: handler→h.pham @ 2026-08-11T04:10:02+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
75128 | 491_SE_PillarOnTopAndSingleArmWithThread.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-08-11T04:14:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-09T09:18:44+02:00 | N | N |  | Y | Y
75129 | 491_SE_SingleArmWithPillarOnTop.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-08-11T04:17:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-09T09:18:47+02:00 | N | N |  | Y | Y
75130 | 491_SE_PillarOnTopAndDoubleArmWithThread.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-08-11T04:19:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-09T09:18:51+02:00 | N | N |  | Y | Y
75140 | 430_ME_IndoorUnitsThermoVentI.rfa | 2026-08-12 | 2026-09-14 | 24 | handler_assign | confirm_note:stored_full | START: handler→th.le @ 2026-08-12T02:59:07+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-14T10:54:09+02:00 | N | N |  | Y | Y
75141 | 430_ME_AirHandlingUnit_Single_Abluft.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-08-12T03:28:39+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T06:01:41+02:00 | N | N |  | Y | Y
75142 | 430_ME_JetFanCarPark_FloorSurface_NoSystem.rfa | 2026-08-12 | 2026-09-14 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-08-12T03:44:31+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-14T11:19:43+02:00 | N | N |  | Y | Y
75143 | 430_ME_MixingTank_Becomix.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→t.le @ 2026-08-12T03:47:04+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T07:02:31+02:00 | N | N |  | Y | Y
75144 | 430_ME_SmokeExhaustJetFans_NoSystem.rfa | 2026-08-12 | 2026-09-16 | 26 | handler_assign | confirm_note:stored_full | START: handler→n.chau @ 2026-08-12T03:49:59+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T06:16:54+02:00 | N | N |  | Y | Y
75145 | 430_ME_KitchenExtractorHood.rfa | 2026-08-12 | 2026-09-24 | 32 | handler_assign | confirm_note:stored_full | START: handler→t.do @ 2026-08-12T04:08:49+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-24T10:29:27+02:00 | N | N |  | Y | Y
75146 | 430_ME_VentilationJetFans_GAXO_NoSystem.rfa | 2026-08-12 | 2026-09-17 | 27 | handler_assign | confirm_note:stored_full | START: handler→tu.le @ 2026-08-12T04:18:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T09:12:04+02:00 | N | N |  | Y | Y
75147 | 430_ME_Schleusenventilatoren.rfa | 2026-08-12 | 2026-08-13 | 2 | handler_assign | status_resolved | START: handler→tu.le @ 2026-08-12T04:20:50+02:00 ¦¦ END: status→resolved @ 2026-08-13T11:15:35+02:00 | N | N |  | Y | N
75148 | 430_ME_AirHandlingUnit_Single_Zuluft.rfa | 2026-08-12 | 2026-08-12 | 1 | handler_assign | status_resolved | START: handler→t.doan @ 2026-08-12T04:28:30+02:00 ¦¦ END: status→resolved @ 2026-08-12T11:49:13+02:00 | N | N |  | Y | N
75149 | 430_ME_RoofFanBendDHE_Supply.rfa | 2026-08-12 | 2026-08-12 | 1 | handler_assign | status_resolved | START: handler→d.le @ 2026-08-12T04:40:32+02:00 ¦¦ END: status→resolved @ 2026-08-12T11:32:59+02:00 | N | N |  | Y | N
75150 | 430_ME_InlineCentrifugalFan_FRD.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T04:43:51+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T07:12:36+02:00 | N | N |  | Y | Y
75151 | 430_ME_StartingSolution.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→t.doan @ 2026-08-12T04:51:10+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T09:49:04+02:00 | N | N |  | Y | Y
75154 | 430_ME_KitchenHoodMonoblock_Standard.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T08:51:16+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:12:26+02:00 | N | N |  | Y | Y
75155 | 430_ME_RoofFanDV_Return.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T08:52:54+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T08:13:28+02:00 | N | N |  | Y | Y
75159 | 430_ME_RoofTopUnits_ThermoVentD.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T10:42:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:29:57+02:00 | N | N |  | Y | Y
75160 | 430_ME_RoofVentilationFans_DAX.rfa | 2026-08-12 | 2026-08-14 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-12T10:44:02+02:00 ¦¦ END: status→resolved @ 2026-08-14T04:43:48+02:00 | N | N |  | Y | N
75161 | 430_ME_RoofVentilationFans_DAX_NoSystem.rfa | 2026-08-12 | 2026-09-23 | 31 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T10:46:44+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-23T11:37:37+02:00 | N | N |  | Y | Y
75162 | 430_ME_RoofVentilationFans_DRVFH.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T10:48:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T09:49:08+02:00 | N | N |  | Y | Y
75163 | 430_ME_RoofVentilationFans_DRV_DRH.rfa | 2026-08-12 | 2026-08-14 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-12T10:51:36+02:00 ¦¦ END: status→resolved @ 2026-08-14T11:08:26+02:00 | N | N |  | Y | N
75164 | 430_ME_RoofVentilationFans_DRV_EC.rfa | 2026-08-12 | 2026-08-28 | 13 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T10:53:20+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-08-28T05:50:07+02:00 | N | N |  | Y | Y
75165 | 430_ME_SmokeExhaustAxialFans_BVAXO_F300.rfa | 2026-08-12 | 2026-08-14 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-12T10:55:05+02:00 ¦¦ END: status→resolved @ 2026-08-14T11:20:53+02:00 | N | N |  | Y | N
75166 | 430_ME_SmokeExhaustAxialFans_BVAXO_F400.rfa | 2026-08-12 | 2026-09-16 | 26 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T10:56:54+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:39:47+02:00 | N | N |  | Y | Y
75167 | 430_ME_SmokeExhaustCentrifugalFans_BVRA.rfa | 2026-08-12 | 2026-09-24 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-12T10:59:29+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-24T03:53:38+02:00 | N | N |  | Y | Y
75168 | 430_ME_SmokeExhaustCentrifugalFans_BVREH.rfa | 2026-08-12 | 2026-08-17 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-12T11:01:02+02:00 ¦¦ END: status→resolved @ 2026-08-17T11:23:18+02:00 | N | N |  | Y | N
75174 | 430_ME_SmokeExhaustCentrifugalFans_BVW-B.rfa | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T03:55:28+02:00 ¦¦ END: status→resolved @ 2026-08-17T10:11:55+02:00 | N | N |  | Y | N
75175 | 430_ME_SmokeExhaustFan_WallMounted_BVW_A.rfa | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T03:57:23+02:00 ¦¦ END: status→resolved @ 2026-08-17T10:53:20+02:00 | N | N |  | Y | N
75176 | 430_ME_SmokeExhaustPlugFans_BRERV.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T03:59:06+02:00 ¦¦ END: status→resolved @ 2026-08-19T10:56:36+02:00 | N | N |  | Y | N
75177 | 430_ME_VacuumPump.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:01:06+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T06:16:56+02:00 | N | N |  | Y | Y
75178 | 430_ME_VentilationAxialFans_AXN691256.rfa | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:02:55+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-15T11:12:30+02:00 | N | N |  | Y | Y
75179 | 430_ME_VentilationAxialFans_AXO.rfa | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:04:32+02:00 ¦¦ END: status→resolved @ 2026-08-17T11:06:08+02:00 | N | N |  | Y | N
75180 | 430_ME_VentilationAxialFans_AXO1050.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:05:50+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-09T09:18:54+02:00 | N | N |  | Y | Y
75181 | 430_ME_VentilationAxialFans_AXO927.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:07:18+02:00 ¦¦ END: status→resolved @ 2026-08-18T11:04:22+02:00 | N | N |  | Y | N
75182 | 430_ME_VentilationAxialFans_BVAXN_1256.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:11:03+02:00 ¦¦ END: status→resolved @ 2026-08-18T11:38:48+02:00 | N | N |  | Y | N
75183 | 430_ME_VentilationAxialFans_GLDF.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:12:32+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-09T09:18:57+02:00 | N | N |  | Y | Y
75184 | 430_ME_VentilationAxialFans_ZAXN691256.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:14:11+02:00 ¦¦ END: status→resolved @ 2026-08-19T11:21:49+02:00 | N | N |  | Y | N
75185 | 430_ME_VentilationCentrifugalFans_KFB.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:15:48+02:00 ¦¦ END: status→resolved @ 2026-08-18T11:44:54+02:00 | N | N |  | Y | N
75186 | 430_ME_VentilationCentrifugalFans_REH.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:18:36+02:00 ¦¦ END: status→resolved @ 2026-08-18T11:08:29+02:00 | N | N |  | Y | N
75187 | 430_ME_VentilationCentrifugalFans_RZH.rfa | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:19:58+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-17T05:10:34+02:00 | N | N |  | Y | Y
75188 | 430_ME_VentilationPlugFans_ERV.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:21:36+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T04:02:59+02:00 | N | N |  | Y | Y
75189 | 430_ME_Ventilator_VAM.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:22:54+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T10:46:58+02:00 | N | N |  | Y | Y
75190 | 430_ME_WallMountedVentilator.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T04:24:22+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T11:11:03+02:00 | N | N |  | Y | Y
75191 | 430_ME_WallSmokeExhaustFans.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:25:51+02:00 ¦¦ END: status→resolved @ 2026-08-19T11:22:22+02:00 | N | N |  | Y | N
75192 | 430_ME_WindDrivenRoofVentilator_Standard.rfa | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-13T04:27:18+02:00 ¦¦ END: status→resolved @ 2026-08-20T11:00:31+02:00 | N | N |  | Y | N
75193 | 420_HeatExchangerTank_VerticalPump.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-13T06:16:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T03:53:41+02:00 | N | N |  | Y | Y
75194 | 420_ME_AirCoolHeatPump_MonoBlock.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-13T06:16:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T10:01:50+02:00 | N | N |  | Y | Y
75195 | 420_ME_AirCurtain_StandingType.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-13T06:16:58+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T09:20:31+02:00 | N | N |  | Y | Y
75196 | 420_ME_AirCurtain_WallMounted.rfa | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-13T06:16:39+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T11:47:14+02:00 | N | N |  | Y | Y
75197 | 420_ME_AirCurtain_WallMounted_Standard.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-13T06:16:39+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:55:14+02:00 | N | N |  | Y | Y
75198 | 420_ME_AirHeater_Top.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-13T06:16:39+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-09T07:13:57+02:00 | N | N |  | Y | Y
75199 | 420_ME_AirSoureHeatPump.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-13T06:16:39+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T05:28:44+02:00 | N | N |  | Y | Y
75200 | 420_ME_BufferHeatingTank.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-08-13T06:16:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:44+02:00 | N | N |  | Y | Y
75201 | 420_ME_BufferTank_Custom.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-08-13T06:16:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:55:19+02:00 | N | N |  | Y | Y
75202 | 420_ME_BufferTank_Standard.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-08-13T06:16:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T11:40:18+02:00 | N | N |  | Y | Y
75203 | 420_ME_BufferTank_StorathermHeat&WithInsulation.rfa | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-08-13T06:16:11+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T11:14:41+02:00 | N | N |  | Y | Y
75204 | 420_ME_BufferTank_StorathermHeat1Coil&WithInsulation.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-08-13T06:16:11+02:00 ¦¦ END: status→resolved @ 2026-08-27T09:35:02+02:00 | N | N |  | Y | Y
75205 | 420_ME_BufferTank_StorathermHeat1Coil&WithoutInsulation.rfa | 2026-08-13 | 2026-08-25 | 9 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-08-13T06:15:01+02:00 ¦¦ END: status→resolved @ 2026-08-25T09:03:18+02:00 | N | N |  | Y | N
75206 | 420_ME_BufferTank_StorathermHeat2Coil&WithInsulation.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:15:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T03:18:07+02:00 | N | N |  | Y | Y
75207 | 420_ME_BufferTank_StorathermHeatCombi1Coil&WithInsulation.rfa | 2026-08-13 | 2026-09-04 | 17 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:15:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-04T10:52:22+02:00 | N | N |  | Y | Y
75208 | 420_ME_BufferTank_StorathermHeatCombi2Coil&WithInsulation.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:15:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T03:48:09+02:00 | N | N |  | Y | Y
75209 | 420_ME_BufferTank_StorathermHeatFlange&WithInsulation.rfa | 2026-08-13 | 2026-08-25 | 9 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-08-13T06:15:01+02:00 ¦¦ END: status→resolved @ 2026-08-25T09:02:53+02:00 | N | N |  | Y | N
75210 | 420_ME_BufferTank_StorathermHeatFlange&WithoutInsulation.rfa | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:14:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-17T03:50:28+02:00 | N | N |  | Y | Y
75211 | 420_ME_CeilingPanel_Standard.rfa | 2026-08-13 | 2026-09-23 | 30 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:14:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T11:22:28+02:00 | N | N |  | Y | Y
75212 | 420_ME_CentrifugalPumpWithElectricMotor_Horizontal.rfa | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:14:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T10:32:57+02:00 | N | N |  | Y | Y
75213 | 420_ME_ColdWaterTank.rfa | 2026-08-13 | 2026-09-04 | 17 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:14:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-04T10:52:26+02:00 | N | N |  | Y | Y
75214 | 420_ME_CompressedAirTank.rfa | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:14:12+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-17T03:50:34+02:00 | N | N |  | Y | Y
75215 | 420_ME_ControlValveGroup.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-13T06:03:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:44:28+02:00 | N | N |  | Y | Y
75216 | 420_ME_Convector_FloorSurface.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-13T06:03:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:17+02:00 | N | N |  | Y | Y
75217 | 420_ME_EnergyDistributor_6Pairs.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-13T06:03:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T12:29:20+02:00 | N | N |  | Y | Y
75218 | 420_ME_EnergyDistributor_8Pairs.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | START: handler→d.phan @ 2026-08-13T06:03:45+02:00 ¦¦ END: status→resolved @ 2026-08-19T08:40:37+02:00 | N | N |  | Y | Y
75219 | 420_ME_ExpansionTank_FloorStand.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-13T06:03:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T08:26:14+02:00 | N | N |  | Y | Y
75220 | 420_ME_ExpansionTank_Standard.rfa | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | START: handler→b.tran @ 2026-08-13T06:02:25+02:00 ¦¦ END: status→resolved @ 2026-08-20T08:36:03+02:00 | N | N |  | Y | Y
75221 | 420_ME_FWTransfer.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-13T06:02:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:20+02:00 | N | N |  | Y | Y
75222 | 420_ME_FacadeHeating_Standard.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-13T06:02:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:24:20+02:00 | N | N |  | Y | Y
75223 | 420_ME_Fancoilunit_UnderfloorTrench_KathermNK.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | START: handler→b.tran @ 2026-08-13T06:02:25+02:00 ¦¦ END: status→resolved @ 2026-08-19T09:54:12+02:00 | N | N |  | Y | Y
75224 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQE_NoSystem.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-13T06:02:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T09:47:41+02:00 | N | N |  | Y | Y
75225 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQK.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | START: handler→b.tran @ 2026-08-13T06:02:25+02:00 ¦¦ END: status→resolved @ 2026-08-18T10:09:42+02:00 | N | N |  | Y | Y
75226 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQKnano.rfa | 2026-08-13 | 2026-09-29 | 34 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-29T04:21:53+02:00 | N | N |  | Y | Y
75227 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_1Connector.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T03:14:07+02:00 | N | N |  | Y | Y
75228 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_2Connector.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:23+02:00 | N | N |  | Y | Y
75229 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_3Connector.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T10:54:44+02:00 | N | N |  | Y | Y
75230 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_4Connector.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:28+02:00 | N | N |  | Y | Y
75231 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_5Connector.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T12:07:53+02:00 | N | N |  | Y | Y
75232 | 420_ME_HeatExchangerFreeCooling_Flange.rfa | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: status→resolved @ 2026-08-20T03:15:54+02:00 | N | N |  | Y | Y
75233 | 420_ME_HeatPump_PackageDrooftop_48And50UA&UH.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-13T06:01:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-18T11:11:12+02:00 | N | N |  | Y | Y
75234 | 420_ME_HeatTransferStation_Custom.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:00:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:31+02:00 | N | N |  | Y | Y
75235 | 420_ME_HeatingCoolingSails_Ceiling.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:00:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:44:32+02:00 | N | N |  | Y | Y
75236 | 420_ME_HomeStation_DHK.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:00:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:44:35+02:00 | N | N |  | Y | Y
75237 | 420_ME_HomeStation_GHK.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:00:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:44:37+02:00 | N | N |  | Y | Y
75238 | 420_ME_HomeStation_GHKFBH.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:00:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T05:28:48+02:00 | N | N |  | Y | Y
75239 | 420_ME_HotWaterBoiler.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:00:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T11:44:39+02:00 | N | N |  | Y | Y
75240 | 420_ME_HotWaterStorageTank_Standard.rfa | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-13T06:00:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:18+02:00 | N | N |  | Y | Y
75241 | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:12:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:35+02:00 | N | N |  | Y | N
75242 | 434_ME_AirCooledChillers_30AWH.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:12:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T05:29:09+02:00 | N | N |  | Y | Y
75243 | 434_ME_AirCooledCondensingUnits_38RBS_2Pipes.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:12:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T05:29:11+02:00 | N | N |  | Y | Y
75244 | 434_ME_AirCooledCondensingUnits_38RBS_4Pipes.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:12:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T08:26:16+02:00 | N | N |  | Y | Y
75246 | 434_ME_AirCooledCondensingUnits_38RBS_LeftConnector.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:12:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T09:47:43+02:00 | N | N |  | Y | Y
75247 | 434_ME_AirCooledLiquidChillers_30RB.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:12:59+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T09:47:45+02:00 | N | N |  | Y | Y
75248 | 434_ME_AirCooledLiquidChillers_30RBS.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:12:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T10:54:46+02:00 | N | N |  | Y | Y
75249 | 434_ME_AirCooledLiquidChillers_30XA.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:12:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T04:37:33+02:00 | N | N |  | Y | Y
75250 | 434_ME_AirCooledLiquidChillers_30XAS.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:12:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T06:18:00+02:00 | N | N |  | Y | Y
75251 | 434_ME_AirCooledLiquidChillers_30XAV.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:12:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:24:22+02:00 | N | N |  | Y | Y
75252 | 434_ME_AirCooledLiquidChillers_HeatReclaimUnit30XAS.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:12:28+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T06:49:26+02:00 | N | N |  | Y | Y
75253 | 434_ME_AirCooledScrollChillers_30RBP.rfa | 2026-08-13 | 2026-08-26 | 10 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-08-13T06:11:51+02:00 ¦¦ END: status→resolved @ 2026-08-26T11:28:38+02:00 | N | N |  | Y | N
75254 | 434_ME_CirculatorPump_CronoTwinDL.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-08-13T06:11:51+02:00 ¦¦ END: status→resolved @ 2026-09-10T11:49:00+02:00 | N | N |  | Y | N
75255 | 434_ME_ConvectionElementsCeillings_CeilingMounted_KN.rfa | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:11:51+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T12:26:53+02:00 | N | N |  | Y | Y
75256 | 434_ME_Convector_UnderFloorTrench_Standard.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-08-13T06:11:51+02:00 ¦¦ END: status→resolved @ 2026-08-27T11:48:21+02:00 | N | N |  | Y | N
75257 | 434_ME_CyclonicVacuumDegasser_VentoVEC.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-08-13T06:11:51+02:00 ¦¦ END: status→resolved @ 2026-08-27T11:48:27+02:00 | N | N |  | Y | N
75258 | 434_ME_CyclonicVacuumDegasser_VentoVIEC.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-13T06:11:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T03:53:47+02:00 | N | N |  | Y | Y
75259 | 434_ME_DegassingSystem.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-13T06:11:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T03:53:50+02:00 | N | N |  | Y | Y
75260 | 434_ME_DuctableAirCooledLiquidChillers_30RBY.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-13T06:11:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T08:29:02+02:00 | N | N |  | Y | Y
75261 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY.rfa | 2026-08-13 | 2026-08-25 | 9 | handler_assign | status_closed | START: handler→ht.pham @ 2026-08-13T06:11:18+02:00 ¦¦ END: status→closed @ 2026-08-25T06:01:40+02:00 | N | N |  | Y | N
75262 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY.rfa | 2026-08-13 | 2026-09-25 | 32 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-08-13T06:11:18+02:00 ¦¦ END: status→resolved @ 2026-09-25T09:42:53+02:00 | N | N |  | Y | N
75263 | 434_ME_Ductableaircooledliquidchillers_30RBSY_LeftConnection.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-13T06:10:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-18T11:11:17+02:00 | N | N |  | Y | Y
75264 | 434_ME_EndSuctionPump_Standard.rfa | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-13T06:10:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T02:49:30+02:00 | N | N |  | Y | Y
75265 | 434_ME_ExpansionVessel_IntermediateDD.rfa | 2026-08-13 |  |  | handler_assign | none | START: handler→t.tran @ 2026-08-13T06:10:45+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
75266 | 434_ME_ExpansionVessel_IntermediateDG.rfa | 2026-08-13 | 2026-09-23 | 30 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-13T06:10:45+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T11:37:41+02:00 | N | N |  | Y | Y
75267 | 434_ME_ExpansionVessel_IntermediateDU.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | status_resolved | START: handler→t.tran @ 2026-08-13T06:10:45+02:00 ¦¦ END: status→resolved @ 2026-09-16T03:59:56+02:00 | N | N |  | Y | N
75268 | 434_ME_ExpansionVessel_Standard.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | START: handler→t.tran @ 2026-08-13T06:10:45+02:00 ¦¦ END: status→resolved @ 2026-08-27T11:48:32+02:00 | N | N |  | Y | N
75269 | 434_ME_ExpansionVessel_StaticoSD.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | START: handler→t.tran @ 2026-08-13T06:10:45+02:00 ¦¦ END: status→resolved @ 2026-08-27T11:48:37+02:00 | N | N |  | Y | N
75270 | 434_ME_ExpansionVessel_StaticoSG.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:08:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-09T09:46:04+02:00 | N | N |  | Y | Y
75271 | 434_ME_ExpansionVessel_StaticoSU.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:08:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T06:27:33+02:00 | N | N |  | Y | Y
75272 | 434_ME_FanCoilUnit_AirTreatmentModules42GM2Pipes.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:08:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:44+02:00 | N | N |  | Y | Y
75274 | 434_ME_FanCoilUnit_AirTreatmentModules42GM4Pipes.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:08:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T07:24:24+02:00 | N | N |  | Y | Y
75275 | 434_ME_FanCoilUnit_AirTreatmentModules42GR2Pipes.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-13T06:08:00+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T06:27:36+02:00 | N | N |  | Y | Y
75276 | 434_ME_FanCoilUnit_AirTreatmentModules42GR4Pipes.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:07:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:47+02:00 | N | N |  | Y | Y
75277 | 434_ME_FanCoilUnit_CeilingCassette_2pipes&42GW.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:07:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T08:27:06+02:00 | N | N |  | Y | Y
75278 | 434_ME_FanCoilUnit_CeilingCassette_Standard.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:07:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:50+02:00 | N | N |  | Y | Y
75279 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFBT2Pipes.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:07:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T07:34:18+02:00 | N | N |  | Y | Y
75280 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFCT2Pipes.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-13T06:07:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-08-27T11:25:54+02:00 | N | N |  | Y | Y
75281 | 434_ME_FanCoilUnit_CeilingMounted_CompactChassis42GW4Pipes.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:06:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T07:34:21+02:00 | N | N |  | Y | Y
75282 | 434_ME_FanCoilUnit_CeilingMounted_HybridTerminal36XB.rfa | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:06:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T11:07:41+02:00 | N | N |  | Y | Y
75283 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC2Pipe.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:06:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T09:20:34+02:00 | N | N |  | Y | Y
75284 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC4Pipe.rfa | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:06:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T11:07:44+02:00 | N | N |  | Y | Y
75285 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWD2Pipe.rfa | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:06:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:20+02:00 | N | N |  | Y | Y
75286 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH2Pipe.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:06:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T09:20:38+02:00 | N | N |  | Y | Y
75287 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH4Pipe.rfa | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-13T06:06:25+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T09:50:17+02:00 | N | N |  | Y | Y
75288 | 434_ME_FanCoilUnit_CeilingMounted_LargeChassis42GW4Pipes.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-13T06:05:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T08:29:06+02:00 | N | N |  | Y | Y
75289 | 434_ME_FanCoilUnit_CeilingMounted_Standard.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-13T06:05:09+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T10:05:31+02:00 | N | N |  | Y | Y
75293 | 420_ME_HotWaterStorageTank_StorathermAqua.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | status_resolved | START: handler→b.tran @ 2026-08-14T02:59:29+02:00 ¦¦ END: status→resolved @ 2026-09-07T08:35:34+02:00 | N | N |  | Y | N
75294 | 420_ME_HotWaterStorageTank_StorathermAquaCompact&Electricheater.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | status_resolved | START: handler→b.tran @ 2026-08-14T02:59:29+02:00 ¦¦ END: status→resolved @ 2026-09-07T09:58:40+02:00 | N | N |  | Y | N
75295 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil&Electricheater.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-08-14T02:59:22+02:00 ¦¦ END: status→resolved @ 2026-09-10T08:49:14+02:00 | N | N |  | Y | N
75296 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-14T02:59:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T09:50:20+02:00 | N | N |  | Y | Y
75297 | 420_ME_HotWaterStorageTank_StorathermAquaCompactHorizontal.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-08-14T02:59:22+02:00 ¦¦ END: status→resolved @ 2026-09-10T08:48:44+02:00 | N | N |  | Y | N
75298 | 420_ME_HotWaterStorageTank_StorathermAquaCompactWallHung.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-14T02:59:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:22+02:00 | N | N |  | Y | Y
75299 | 420_ME_HotWaterStorageTank_StorathermAquaEEC.rfa | 2026-08-14 | 2026-09-21 | 27 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-14T02:59:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-21T10:26:39+02:00 | N | N |  | Y | Y
75300 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump1Coil.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-14T02:57:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T03:48:12+02:00 | N | N |  | Y | Y
75301 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump2Coil.rfa | 2026-08-14 | 2026-09-04 | 16 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-14T02:57:50+02:00 ¦¦ END: ht.nguyen: ### Summary @hu.dam - Please review the family report template in comment 0071576:0753425. - Based o @ 2026-09-04T04:32:38+02:00 | N | N |  | Y | Y
75302 | 420_ME_HotWaterStorageTank_StorathermAquaInox.rfa | 2026-08-14 | 2026-08-28 | 11 | handler_assign | status_resolved | START: handler→d.phan @ 2026-08-14T02:57:50+02:00 ¦¦ END: status→resolved @ 2026-08-28T02:48:13+02:00 | N | N |  | Y | N
75303 | 420_ME_HotWaterStorageTank_StorathermAquaLoad1Flange.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-14T02:57:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T03:05:49+02:00 | N | N |  | Y | Y
75304 | 420_ME_HotWaterStorageTank_StorathermAquaLoad2Flange.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-14T02:57:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T03:05:51+02:00 | N | N |  | Y | Y
75305 | 420_ME_HotWaterStorageTank_StorathermAquaLoad3Flange.rfa | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-14T02:57:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-09T09:46:08+02:00 | N | N |  | Y | Y
75306 | 420_ME_HotWaterStorageTank_StorathermAquaLoad4Flange.rfa | 2026-08-14 | 2026-09-04 | 16 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-08-14T02:57:50+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-04T10:52:29+02:00 | N | N |  | Y | Y
75307 | 420_ME_HotWaterStorageTank_StorathermAquaSolar.rfa | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-14T02:56:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-09T09:46:12+02:00 | N | N |  | Y | Y
75308 | 420_ME_HotWaterStorageTank_StorathermAquaSolarEEC.rfa | 2026-08-14 | 2026-08-27 | 10 | handler_assign | status_resolved | START: handler→b.tran @ 2026-08-14T02:56:57+02:00 ¦¦ END: status→resolved @ 2026-08-27T04:29:29+02:00 | N | N |  | Y | N
75309 | 420_ME_HotWaterTank.rfa | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-14T02:56:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-09T11:50:22+02:00 | N | N |  | Y | Y
75310 | 420_ME_HydraulicSeparator_Flanged.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-14T02:56:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T05:08:19+02:00 | N | N |  | Y | Y
75311 | 420_ME_HydraulicSeparator_Threaded.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-14T02:56:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T05:08:22+02:00 | N | N |  | Y | Y
75312 | 420_ME_KTS_ThermoBox.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-08-14T02:56:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T10:54:49+02:00 | N | N |  | Y | Y
75313 | 420_ME_LargeBecomixVessel_Vertical.rfa | 2026-08-14 | 2026-09-17 | 25 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-08-14T02:55:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-17T03:50:38+02:00 | N | N |  | Y | Y
75314 | 420_ME_Manifold12Connection_Custom.rfa | 2026-08-14 | 2026-08-24 | 7 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-08-14T02:55:49+02:00 ¦¦ END: status→resolved @ 2026-08-24T10:33:18+02:00 | N | N |  | Y | N
75315 | 420_ME_ManifoldCabinet_UP110.rfa | 2026-08-14 | 2026-08-24 | 7 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-08-14T02:55:49+02:00 ¦¦ END: status→resolved @ 2026-08-24T10:33:08+02:00 | N | N |  | Y | N
75316 | 420_ME_MixedBecomixVessel_Vertical.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-08-14T02:55:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T10:54:51+02:00 | N | N |  | Y | Y
75317 | 420_ME_MultiOutdoorUnit_SingleFan.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-08-14T02:55:49+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T03:05:54+02:00 | N | N |  | Y | Y
75318 | 420_ME_PlateHeatExchanger.rfa | 2026-08-14 | 2026-08-28 | 11 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-08-14T02:54:14+02:00 ¦¦ END: status→resolved @ 2026-08-28T05:32:59+02:00 | N | N |  | Y | N
75319 | 420_ME_Pump_WaterJetPump_3Way_Flanged.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-14T02:54:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T05:57:51+02:00 | N | N |  | Y | Y
75320 | 420_ME_Pump_WaterJetPump_3Way_Threaded.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-14T02:54:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T05:28:51+02:00 | N | N |  | Y | Y
75321 | 420_ME_QuantumW500_DoubleCapacitor.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-14T02:54:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T05:57:53+02:00 | N | N |  | Y | Y
75322 | 420_ME_RadiatorBathroom_WallMounted_Basic.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-08-14T02:54:14+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T05:28:54+02:00 | N | N |  | Y | Y
75323 | 420_ME_RadiatorBathroom_WallMounted_BasicR.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-14T02:53:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:08:23+02:00 | N | N |  | Y | Y
75324 | 420_ME_RadiatorBathroom_WallMounted_Casteo.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-14T02:53:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:08:26+02:00 | N | N |  | Y | Y
75325 | 420_ME_RadiatorBathroom_WallMounted_Credohalf.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-14T02:53:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T10:54:53+02:00 | N | N |  | Y | Y
75326 | 420_ME_RadiatorBathroom_WallMounted_Credohalfround.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-14T02:53:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:25+02:00 | N | N |  | Y | Y
75327 | 491_SE_ArmFromDoublePerpendicularArm.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-13T10:59:48+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:28:52+02:00 | N | N |  | Y | Y
75328 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJF4pipe.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-14T03:03:34+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:08:29+02:00 | N | N |  | Y | Y
75329 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJT2pipe.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-14T03:03:34+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:38+02:00 | N | N |  | Y | Y
75330 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAF4pipe.rfa | 2026-08-14 | 2026-09-24 | 30 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-14T03:03:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-24T09:51:23+02:00 | N | N |  | Y | Y
75331 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAT2pipe.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-08-14T02:53:22+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T10:05:34+02:00 | N | N |  | Y | Y
75332 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDF4pipe.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-14T03:03:26+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T10:51:26+02:00 | N | N |  | Y | Y
75333 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDT2pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-08-14T03:03:18+02:00 ¦¦ END: status→resolved @ 2026-09-25T09:41:24+02:00 | N | N |  | Y | N
75334 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAF4pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | status_resolved | START: handler→ht.pham @ 2026-08-14T03:03:18+02:00 ¦¦ END: status→resolved @ 2026-09-25T09:39:49+02:00 | N | N |  | Y | N
75335 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAT2pipe.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-14T03:02:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T09:16:47+02:00 | N | N |  | Y | Y
75336 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE2Pipe.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-14T03:02:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T10:54:12+02:00 | N | N |  | Y | Y
75337 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE4Pipe.rfa | 2026-08-14 | 2026-09-17 | 25 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-14T03:02:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-17T03:50:42+02:00 | N | N |  | Y | Y
75339 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS2Pipe.rfa | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-14T03:02:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T04:08:40+02:00 | N | N |  | Y | Y
75340 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS4Pipe.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-14T03:02:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T10:55:23+02:00 | N | N |  | Y | Y
75341 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize0x.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-08-14T03:02:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-11T11:40:22+02:00 | N | N |  | Y | Y
75342 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize1x.rfa | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-14T03:02:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T04:50:05+02:00 | N | N |  | Y | Y
75343 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize0x.rfa | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-14T03:02:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-15T05:07:54+02:00 | N | N |  | Y | Y
75344 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize1x.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-14T03:02:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T06:00:36+02:00 | N | N |  | Y | Y
75345 | 434_ME_FanCoilUnit_CeilingPlenum_Ultra.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-14T03:02:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-10T11:54:41+02:00 | N | N |  | Y | Y
75346 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ2Pipes.rfa | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-08-14T03:02:01+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-16T09:34:11+02:00 | N | N |  | Y | Y
75347 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ4Pipes.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-14T03:01:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T08:18:16+02:00 | N | N |  | Y | Y
75348 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAF4Pipes.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-14T03:01:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-14T09:16:51+02:00 | N | N |  | Y | Y
75349 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAT2Pipes.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-14T03:01:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-22T10:58:27+02:00 | N | N |  | Y | Y
75350 | 434_ME_FanCoilUnit_FloorStanding_FWVDAF4Pipes.rfa | 2026-08-14 | 2026-08-25 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-08-14T03:01:33+02:00 ¦¦ END: status→resolved @ 2026-08-25T11:32:21+02:00 | N | N |  | Y | N
75351 | 434_ME_FanCoilUnit_FloorStanding_FWVDAT2Pipes.rfa | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-08-14T03:01:33+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-16T09:34:14+02:00 | N | N |  | Y | Y
75352 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK2Pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-14T03:00:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T07:32:04+02:00 | N | N |  | Y | Y
75353 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK4Pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-14T03:00:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T07:32:08+02:00 | N | N |  | Y | Y
75354 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHKE.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-14T03:00:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T11:37:44+02:00 | N | N |  | Y | Y
75355 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermID.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-14T03:00:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-25T07:32:12+02:00 | N | N |  | Y | Y
75356 | 434_ME_FanCoilUnit_WallMounted_FWBBT2pipe.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | START: handler→ht.pham @ 2026-08-14T03:00:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-23T11:37:46+02:00 | N | N |  | Y | Y
75357 | 434_ME_FanCoilUnit_WallMounted_Standard.rfa | 2026-08-14 | 2026-08-26 | 9 | handler_assign | status_resolved | START: handler→t.tran @ 2026-08-14T03:00:19+02:00 ¦¦ END: status→resolved @ 2026-08-26T08:47:27+02:00 | N | N |  | Y | N
75358 | 434_ME_Fancoilunit_CeilingMounted_4wayblowcassetteFWFBF4pipes.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-14T03:00:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-07T11:29:33+02:00 | N | N |  | Y | Y
75364 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBF4pipes.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-14T03:00:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T03:13:22+02:00 | N | N |  | Y | Y
75365 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBT2pipes.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-14T03:00:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-08T03:13:25+02:00 | N | N |  | Y | Y
75366 | 434_ME_FillsoftI.rfa | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-08-14T03:00:19+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-16T11:28:56+02:00 | N | N |  | Y | Y
75379 | 491_SE_ArmWithAngleBracket.rfa | 2026-08-17 | 2026-08-20 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-17T02:34:43+02:00 ¦¦ END: status→resolved @ 2026-08-20T11:33:27+02:00 | N | N |  | Y | N
75380 | 491_SE_BracingArmSKOF80.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:37:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:01+02:00 | N | N |  | Y | Y
75381 | 491_SE_CantileverBracketAKF80.rfa | 2026-08-17 | 2026-08-20 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-17T02:39:42+02:00 ¦¦ END: status→resolved @ 2026-08-20T09:56:14+02:00 | N | N |  | Y | N
75382 | 491_SE_ClampDoublePiece.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:41:27+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:05+02:00 | N | N |  | Y | Y
75383 | 491_SE_DoublePillarWithPlate.rfa | 2026-08-17 | 2026-08-20 | 4 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-17T02:43:07+02:00 ¦¦ END: status→resolved @ 2026-08-20T11:17:11+02:00 | N | N |  | Y | N
75384 | 491_SE_DouleClampWithFoundationPlate.rfa | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:44:41+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:15:34+02:00 | N | N |  | Y | Y
75385 | 491_SE_EndSupportSTAF80.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:46:49+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:09+02:00 | N | N |  | Y | Y
75386 | 491_SE_FixedpointsetXS.rfa | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:51:05+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-29T10:53:00+02:00 | N | N |  | Y | Y
75387 | 491_SE_FrameHangerTopBase.rfa | 2026-08-17 | 2026-08-21 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-17T02:53:37+02:00 ¦¦ END: status→resolved @ 2026-08-21T11:29:02+02:00 | N | N |  | Y | N
75388 | 491_SE_GuidingBracketFWF.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:55:36+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:13+02:00 | N | N |  | Y | Y
75389 | 491_SE_PillarWithPlate.rfa | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:57:11+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-29T10:53:04+02:00 | N | N |  | Y | Y
75390 | 491_SE_PipeClampWithRubberRing.rfa | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T02:59:07+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:43:15+02:00 | N | N |  | Y | Y
75391 | 491_SE_PipeClampWithShadeNut.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:01:03+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:17+02:00 | N | N |  | Y | Y
75392 | 491_SE_PipeStrapWithUType.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:02:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:22+02:00 | N | N |  | Y | Y
75393 | 491_SE_PipeSupport_FloorStandingType.rfa | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:04:37+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-29T10:53:07+02:00 | N | N |  | Y | Y
75394 | 491_SE_PipeSupport_RiserType.rfa | 2026-08-17 | 2026-08-24 | 6 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-17T03:06:02+02:00 ¦¦ END: status→resolved @ 2026-08-24T11:30:36+02:00 | N | N |  | Y | N
75395 | 491_SE_PipeSupport_Riser_ClampType.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:07:42+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:26+02:00 | N | N |  | Y | Y
75396 | 491_SE_PipeTrapezeHangerDoubleFrame.rfa | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:16:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-30T04:29:29+02:00 | N | N |  | Y | Y
75397 | 491_SE_PipeTrapezeHangerSingleFrame.rfa | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:17:56+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-18T03:43:18+02:00 | N | N |  | Y | Y
75398 | 491_SE_RectangularDuctHanger_Standard.rfa | 2026-08-17 | 2026-08-21 | 5 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-17T03:22:28+02:00 ¦¦ END: status→resolved @ 2026-08-21T11:24:16+02:00 | N | N |  | Y | N
75399 | 491_SE_RoundDuctHanger_Standard.rfa | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:24:17+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-30T04:29:32+02:00 | N | N |  | Y | Y
75400 | 491_SE_ShouderWithDoubleArm.rfa | 2026-08-17 | 2026-09-21 | 26 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:25:59+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-21T03:45:51+02:00 | N | N |  | Y | Y
75401 | 491_SE_SingleArmWithDoubleBracket.rfa | 2026-08-17 | 2026-08-25 | 7 | handler_assign | status_resolved | START: handler→h.pham @ 2026-08-17T03:27:23+02:00 ¦¦ END: status→resolved @ 2026-08-25T11:15:13+02:00 | N | N |  | Y | N
75402 | 491_SE_SingleArmWithPlate.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:29:20+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-16T11:29:30+02:00 | N | N |  | Y | Y
75403 | 491_SE_SlidesetFS.rfa | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full | START: handler→h.pham @ 2026-08-17T03:31:35+02:00 ¦¦ END: hu.dam: @h.pham This family is now fully completed and securely stored. Thank you for your attention to this @ 2026-09-30T04:29:36+02:00 | N | N |  | Y | Y
75408 | 456_SD_LockIntegratedMonitor | 2026-08-17 | 2026-08-18 | 2 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-08-17T09:47:33+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-18T06:56:37+02:00 | N | N |  | N | Y
75469 | 420_PA_StraightThermostaticValvesForRadiator_Thread | 2026-08-21 | 2026-08-24 | 2 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-08-21T03:07:15+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-08-24T04:24:07+02:00 | N | N |  | N | Y
75492 | DCMvn_Annotation_Update Families in Existing DCM_ELT_Model | 2026-08-24 |  |  | handler_assign | none | START: handler→h.pham @ 2026-08-24T02:32:43+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
75493 | SPR_Update Pipe Accessories to DCM Revit Library Model | 2026-08-24 | 2026-08-31 | 6 | handler_assign | status_resolved | START: handler→s.duong @ 2026-08-24T04:25:36+02:00 ¦¦ END: status→resolved @ 2026-08-31T10:03:54+02:00 | N | N |  | Y | N
75494 | SPR_Update Equipment to DCM Revit Library Model | 2026-08-24 | 2026-08-31 | 6 | handler_assign | status_resolved | START: handler→s.duong @ 2026-08-24T04:25:58+02:00 ¦¦ END: status→resolved @ 2026-08-31T10:05:00+02:00 | N | N |  | Y | N
75516 | 420_PF_SS_eBendByFormedMachine_Mapress | 2026-08-25 | 2026-09-07 | 10 | handler_assign | confirm_note:stored_full | START: handler→t.bui @ 2026-08-25T03:21:10+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-07T07:35:08+02:00 | N | N |  | N | Y
75550 | MED_Update Pipe Accessories to DCM Revit Library Model | 2026-08-27 | 2026-08-31 | 3 | handler_assign | status_resolved | START: handler→s.duong @ 2026-08-27T04:13:36+02:00 ¦¦ END: status→resolved @ 2026-08-31T11:22:50+02:00 | N | N |  | Y | N
75551 | MED_Update Equipment to DCM Revit Library Model | 2026-08-27 | 2026-08-28 | 2 | handler_assign | status_resolved | START: handler→s.duong @ 2026-08-27T04:14:00+02:00 ¦¦ END: status→resolved @ 2026-08-28T08:30:55+02:00 | N | N |  | Y | N
75552 | 420_ME_RoomClimateModule_StandingType | 2026-08-27 | 2026-08-27 | 1 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-08-27T04:47:13+02:00 ¦¦ END: status→resolved @ 2026-08-27T06:36:43+02:00 | N | N |  | N | Y
75605 | LPH5_SAN Discipline Output Checklist Definition | 2026-08-31 | 2026-09-30 | 23 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-08-31T10:08:17+02:00 ¦¦ END: status→resolved @ 2026-09-30T11:37:19+02:00 | N | N |  | Y | N
75616 | 491_NF_GussetPlate90dHexagon.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→dx.quach @ 2026-09-03T06:16:21+02:00 ¦¦ END: status→resolved @ 2026-09-16T09:30:10+02:00 | N | N |  | Y | N
75617 | 491_NF_GussetPlate90dRectangular.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→dx.quach @ 2026-09-03T06:16:21+02:00 ¦¦ END: status→resolved @ 2026-09-17T08:38:42+02:00 | N | N |  | Y | N
75618 | 491_NF_GussetPlate90dTCenter.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-29T08:14:00+02:00 | N | N |  | Y | Y
75619 | 491_NF_GussetPlate90dTSide.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:21+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-29T08:14:04+02:00 | N | N |  | Y | Y
75620 | 491_NF_GussetPlateAngularAxial.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T04:51:02+02:00 | N | N |  | Y | N
75621 | 491_NF_GussetPlateAngularDoubleAdjustableBrace.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-29T10:53:10+02:00 | N | N |  | Y | Y
75622 | 491_NF_GussetPlateAngularRectangular.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-18T03:06:50+02:00 | N | N |  | Y | Y
75623 | 491_NF_GussetPlateAngularSingleAdjustableBrace.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-18T03:15:44+02:00 | N | N |  | Y | Y
75624 | 491_NF_GussetPlateBase.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T04:51:05+02:00 | N | N |  | Y | N
75625 | 491_NF_GussetPlateCantileverBracket.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→dx.quach @ 2026-09-03T06:16:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:32:53+02:00 | N | N |  | Y | N
75626 | 491_NF_GussetPlateFlatHexagon.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-10T11:05:17+02:00 | N | N |  | Y | N
75627 | 491_NF_GussetPlateFlatRectangular.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-10T11:06:45+02:00 | N | N |  | Y | N
75628 | 491_NF_GussetPlateFlatSemiCircle.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-29T10:53:14+02:00 | N | N |  | Y | Y
75629 | 491_NF_GussetPlateFlatT.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-11T06:26:53+02:00 | N | N |  | Y | N
75630 | 491_NF_GussetPlateTrailingArm.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-11T10:36:57+02:00 | N | N |  | Y | N
75631 | 491_NF_GussetPlateTrailingArmBrace.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-17T08:51:16+02:00 | N | N |  | Y | N
75632 | 491_NF_GussetPlateUShape.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-17T08:53:25+02:00 | N | N |  | Y | N
75633 | 491_NF_GussetPlateUShape_2Layers.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-17T08:54:53+02:00 | N | N |  | Y | N
75634 | 491_NF_GussetPlateUShape_Hanger.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:27+02:00 ¦¦ END: status→resolved @ 2026-09-17T08:56:12+02:00 | N | N |  | Y | N
75635 | 491_NF_GussetPlateUShape_Omega.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-09-03T06:15:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:32:56+02:00 | N | N |  | Y | N
75636 | 491_NF_GussetPlateUShape_Side.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-09-03T06:15:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-29T10:53:17+02:00 | N | N |  | Y | Y
75637 | 491_NF_GussetPlateWShape.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-09-03T06:15:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T09:31:56+02:00 | N | N |  | Y | N
75638 | 491_NF_GussetPlateWingShape.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | START: handler→h.huynh @ 2026-09-03T06:15:03+02:00 ¦¦ END: status→resolved @ 2026-09-10T09:47:53+02:00 | N | N |  | Y | N
75639 | 491_NF_GussetPlateZShape.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→h.huynh @ 2026-09-03T06:15:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T09:31:58+02:00 | N | N |  | Y | N
75640 | 491_NF_GussetPlate_StairTreadSupport.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-18T11:23:42+02:00 | N | N |  | Y | N
75641 | 491_NF_PipeClampAccessoriesPunchedAngle.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T04:29:39+02:00 | N | N |  | Y | Y
75642 | 491_NF_PipeClampAccessoriesSquareWasher.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-18T11:23:52+02:00 | N | N |  | Y | N
75643 | 491_NF_PipeClampAccessories_BladeEnd.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-16T11:11:54+02:00 | N | N |  | Y | N
75644 | 491_NF_PipeClampAccessories_Clevis.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-16T11:11:59+02:00 | N | N |  | Y | N
75645 | 491_NF_PipeClampAccessories_EyeNut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-16T03:04:36+02:00 | N | N |  | Y | N
75646 | 491_NF_PipeClampAccessories_HangerStrap.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-16T03:04:42+02:00 | N | N |  | Y | N
75647 | 491_NF_PipeClampAccessories_LinkPlate.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-14T11:30:16+02:00 | N | N |  | Y | N
75648 | 491_NF_PipeClampAccessories_Turnbuckle.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-14T11:30:20+02:00 | N | N |  | Y | N
75649 | 491_NF_PipeClampBeamAttachmentsPurlinClip.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-14T03:15:22+02:00 | N | N |  | Y | N
75650 | 491_NF_PipeClampBeamAttachmentsSwivelFlangeClamp.rfa | 2026-09-03 | 2026-09-09 | 5 | handler_assign | status_resolved | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: status→resolved @ 2026-09-09T11:09:48+02:00 | N | N |  | Y | N
75651 | 491_NF_PipeClampBeamAttachmentsUBracket.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T04:29:42+02:00 | N | N |  | Y | Y
75652 | 491_NF_PipeClampBeamAttachmentsWeldOnBracket.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T04:29:46+02:00 | N | N |  | Y | Y
75653 | 491_NF_PipeClampBeamAttachments_AngleBracket.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→tm.doan @ 2026-09-03T06:14:23+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T04:29:49+02:00 | N | N |  | Y | Y
75654 | 491_NF_PipeClampBeamAttachments_BeamClip.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: status→resolved @ 2026-09-18T08:42:43+02:00 | N | N |  | Y | N
75658 | 491_NF_PipeClampBeamAttachments_FlangeClamp.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-29T08:14:08+02:00 | N | N |  | Y | Y
75659 | 491_NF_PipeClampBeamAttachments_PipeBeamClip.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T04:29:52+02:00 | N | N |  | Y | Y
75660 | 491_NF_PipeClampBeamAttachments_SphericalWasher.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T05:43:09+02:00 | N | N |  | Y | Y
75661 | 491_NF_PipeClampBeamAttachments_SwivelCage.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: status→resolved @ 2026-09-17T05:36:48+02:00 | N | N |  | Y | N
75662 | 491_NF_PipeClampDoubleBoltStrut.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T09:11:31+02:00 | N | N |  | Y | Y
75663 | 491_NF_PipeClampFourBolt.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: status→resolved @ 2026-09-17T08:29:31+02:00 | N | N |  | Y | N
75664 | 491_NF_PipeClampHangedSaddle.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T11:36:38+02:00 | N | N |  | Y | Y
75665 | 491_NF_PipeClampPearHanger.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→t.tran @ 2026-09-03T06:12:55+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T11:36:42+02:00 | N | N |  | Y | Y
75666 | 491_NF_PipeClampSingleBoltStrut.rfa | 2026-09-03 | 2026-09-09 | 5 | handler_assign | status_resolved | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: status→resolved @ 2026-09-09T08:59:18+02:00 | N | N |  | Y | N
75667 | 491_NF_PipeClampThreeBolt.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T09:11:34+02:00 | N | N |  | Y | Y
75668 | 491_NF_PipeClampTwistClip.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T09:11:39+02:00 | N | N |  | Y | Y
75669 | 491_NF_PipeClampTwoPiece.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T11:00:40+02:00 | N | N |  | Y | Y
75670 | 491_NF_PipeClampTwoPieceWithYoke.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T11:00:44+02:00 | N | N |  | Y | Y
75671 | 491_NF_PipeClampUBolt.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T11:00:49+02:00 | N | N |  | Y | Y
75672 | 491_NF_PipeClamp_OnePiece.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T11:36:45+02:00 | N | N |  | Y | N
75673 | 491_NF_PipeClamp_StandOffBracket.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | START: handler→d.phan @ 2026-09-03T06:12:03+02:00 ¦¦ END: status→resolved @ 2026-09-14T09:33:40+02:00 | N | N |  | Y | N
75674 | 491_NF_Steel_A1000_Unistrut.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | START: handler→b.tran @ 2026-09-03T06:11:13+02:00 ¦¦ END: status→resolved @ 2026-09-10T08:56:05+02:00 | N | N |  | Y | N
75675 | 491_NF_Steel_AnchorScrew.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-09-03T06:11:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T11:36:48+02:00 | N | N |  | Y | N
75676 | 491_NF_Steel_CantileverBrackets_Triangle.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | START: handler→b.tran @ 2026-09-03T06:11:13+02:00 ¦¦ END: status→resolved @ 2026-09-11T08:25:16+02:00 | N | N |  | Y | N
75677 | 491_NF_Steel_FlatWashers.rfa | 2026-09-03 | 2026-09-09 | 5 | handler_assign | status_resolved | START: handler→b.tran @ 2026-09-03T06:11:13+02:00 ¦¦ END: status→resolved @ 2026-09-09T08:13:54+02:00 | N | N |  | Y | N
75678 | 491_NF_Steel_HexagonHeadScrew.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→b.tran @ 2026-09-03T06:11:13+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T05:43:12+02:00 | N | N |  | Y | Y
75679 | 491_NF_Steel_HexagonNut_Threaded.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: status→resolved @ 2026-09-16T05:20:20+02:00 | N | N |  | Y | N
75680 | 491_NF_Steel_P1000B_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:32:59+02:00 | N | N |  | Y | N
75681 | 491_NF_Steel_P1000C41_Unistrut.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: status→resolved @ 2026-09-18T05:51:57+02:00 | N | N |  | Y | N
75682 | 491_NF_Steel_P1000C_Unistrut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: status→resolved @ 2026-09-16T08:49:12+02:00 | N | N |  | Y | N
75683 | 491_NF_Steel_P1000_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T04:51:10+02:00 | N | N |  | Y | N
75684 | 491_NF_Steel_P10013_Unistrut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: status→resolved @ 2026-09-16T05:41:20+02:00 | N | N |  | Y | N
75685 | 491_NF_Steel_P1001A_Unistrut.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T05:43:15+02:00 | N | N |  | Y | Y
75686 | 491_NF_Steel_P1001C3_Unistrut.rfa | 2026-09-03 | 2026-09-15 | 9 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: status→resolved @ 2026-09-15T09:49:00+02:00 | N | N |  | Y | N
75687 | 491_NF_Steel_P1001D3_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:33:01+02:00 | N | N |  | Y | N
75688 | 491_NF_Steel_P1001_Unistrut.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | START: handler→ht.tran @ 2026-09-03T06:09:57+02:00 ¦¦ END: status→resolved @ 2026-09-18T08:42:46+02:00 | N | N |  | Y | N
75689 | 491_NF_Steel_P1003_Unistrut.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | START: handler→l.nguyen @ 2026-09-03T06:09:05+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-30T09:11:43+02:00 | N | N |  | Y | Y
75690 | 491_NF_Steel_P1004A_Unistrut.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-09-03T06:09:05+02:00 ¦¦ END: status→resolved @ 2026-09-11T08:04:31+02:00 | N | N |  | Y | N
75691 | 491_NF_Steel_P2001A_Unistrut.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-09-03T06:09:05+02:00 ¦¦ END: status→resolved @ 2026-09-11T08:05:30+02:00 | N | N |  | Y | N
75692 | 491_NF_Steel_P2001B_Unistrut.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-09-03T06:09:05+02:00 ¦¦ END: status→resolved @ 2026-09-11T08:04:57+02:00 | N | N |  | Y | N
75693 | 491_NF_Steel_P2001C3_Unistrut.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: status→resolved @ 2026-09-14T11:13:50+02:00 | N | N |  | Y | N
75694 | 491_NF_Steel_P3300_Unistrut.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-09-28T11:00:52+02:00 | N | N |  | Y | Y
75695 | 491_NF_Steel_P4000_Unistrut.rfa | 2026-09-03 | 2026-09-15 | 9 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: status→resolved @ 2026-09-15T11:05:16+02:00 | N | N |  | Y | N
75696 | 491_NF_Steel_P40021_Unistrut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: status→resolved @ 2026-09-16T09:51:37+02:00 | N | N |  | Y | N
75697 | 491_NF_Steel_P4003_Unistrut.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: status→resolved @ 2026-09-17T11:24:10+02:00 | N | N |  | Y | N
75698 | 491_NF_Steel_P5500_Unistrut.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: status→resolved @ 2026-09-18T10:45:36+02:00 | N | N |  | Y | N
75699 | 491_NF_Steel_P5501_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:46:57+02:00 | N | N |  | Y | N
75700 | 491_NF_Steel_UnirodThreadedRod.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | START: handler→th.nguyen @ 2026-09-03T06:08:18+02:00 ¦¦ END: hu.dam: @n.le This family is now fully completed and securely stored. Thank you for your attention to this m @ 2026-10-01T06:33:04+02:00 | N | N |  | Y | N
75704 | SPR_Producing layouts for LPH3 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-09-03T08:30:14+02:00 ¦¦ END: status→resolved @ 2026-09-30T10:08:38+02:00 | N | N |  | Y | N
75705 | SPR_Producing layouts for LPH5 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-09-03T08:31:05+02:00 ¦¦ END: status→resolved @ 2026-09-30T10:10:37+02:00 | N | N |  | Y | N
75706 | SPR_Producing layouts for LPH8 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-09-03T08:31:59+02:00 ¦¦ END: status→resolved @ 2026-09-30T09:52:12+02:00 | N | N |  | Y | N
75707 | MED_Producing layouts for LPH3 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-09-03T08:35:51+02:00 ¦¦ END: status→resolved @ 2026-09-30T11:05:37+02:00 | N | N |  | Y | N
75708 | MED_Producing layouts for LPH5 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-09-03T08:36:40+02:00 ¦¦ END: status→resolved @ 2026-09-30T11:04:42+02:00 | N | N |  | Y | N
75709 | LPH3_SAN Existing Layout and Section Drawings Review and Update in DCM_SAN Model | 2026-09-03 | 2026-09-25 | 17 | handler_assign | status_resolved | START: handler→tv.huynh @ 2026-09-03T08:37:46+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:38:15+02:00 | N | N |  | Y | N
75710 | MED_Producing layouts for LPH8 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | START: handler→s.duong @ 2026-09-03T08:37:18+02:00 ¦¦ END: status→resolved @ 2026-09-30T10:59:12+02:00 | N | N |  | Y | N
75711 | LPH5_SAN Existing Layout and Section Drawings Review and Update in DCM_SAN Model | 2026-09-04 | 2026-09-25 | 16 | handler_assign | status_resolved | START: handler→t.luu @ 2026-09-04T06:09:50+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:38:10+02:00 | N | N |  | Y | N
75712 | SAN Existing Schematic Diagrams Review and Update_ LPH3 and LPH5 in DCM_SAN Model | 2026-09-04 | 2026-09-25 | 16 | handler_assign | status_resolved | START: handler→k.mai @ 2026-09-04T08:23:22+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:04:02+02:00 | N | N |  | Y | N
75746 | 2026Q4_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-09-07 |  |  | handler_assign | none | START: handler→l.truong @ 2026-09-07T02:44:01+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
75747 | 430_ME_AirHandlingUnit_Single_Fortluft.rfa | 2026-09-07 | 2026-09-25 | 15 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-09-07T03:02:55+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-25T07:32:15+02:00 | N | N |  | Y | Y
75748 | 430_ME_AirHandlingUnit_Floor_Single_Aubenluft.rfa | 2026-09-07 | 2026-09-25 | 15 | handler_assign | confirm_note:stored_full | START: handler→ha.phan @ 2026-09-07T03:05:05+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-25T07:32:19+02:00 | N | N |  | Y | Y
75778 | 430_ME_AirHandlingUnit_1LayerFlachSeries_CeilingStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-09T09:17:06+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T11:42:49+02:00 | N | N |  | Y | Y
75779 | 430_ME_AirHandlingUnit_2LayerBowl_RoofStand.rfa | 2026-09-09 | 2026-09-11 | 3 | handler_assign | status_resolved | START: handler→da.nguyen @ 2026-09-09T09:16:51+02:00 ¦¦ END: status→resolved @ 2026-09-11T11:10:43+02:00 | N | N |  | Y | N
75780 | 430_ME_AirHandlingUnit_2LayerCompactSeries_FloorStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-09-09T09:16:41+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T04:21:57+02:00 | N | N |  | Y | Y
75781 | 430_ME_AirHandlingUnit_2LayerForKitchen_FloorStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-09T09:10:08+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T10:53:25+02:00 | N | N |  | Y | Y
75782 | 430_ME_AirHandlingUnit_FloorStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-09T09:10:08+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T04:22:05+02:00 | N | N |  | Y | Y
75783 | 430_ME_AirHandlingUnit_Geniox29H.rfa | 2026-09-09 | 2026-09-17 | 7 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-09T05:59:04+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-17T06:20:21+02:00 | N | N |  | Y | Y
75784 | 430_ME_AxialWindowFan_Rectangular.rfa | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-09T09:10:07+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T11:36:52+02:00 | N | N |  | Y | Y
75785 | 430_ME_CentrifugalDuctMountedFan.rfa | 2026-09-09 | 2026-09-24 | 12 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-09-09T09:09:03+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-24T10:29:30+02:00 | N | N |  | Y | Y
75786 | 430_ME_ChemicalMachine.rfa | 2026-09-09 | 2026-09-22 | 10 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-09-09T09:09:03+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-22T10:58:29+02:00 | N | N |  | Y | Y
75787 | 430_ME_CrossFlowFans_NoSystem.rfa | 2026-09-09 | 2026-09-21 | 9 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-09-09T09:09:03+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T11:44:50+02:00 | N | N |  | Y | Y
75788 | 430_ME_DiesselTank_Becomix.rfa | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full | START: handler→tn.nguyen @ 2026-09-09T09:09:03+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T04:21:34+02:00 | N | N |  | Y | Y
75789 | 430_ME_Ductfans_Round_DF.rfa | 2026-09-09 | 2026-09-22 | 10 | handler_assign | status_resolved | START: handler→h.le @ 2026-09-09T09:08:08+02:00 ¦¦ END: status→resolved @ 2026-09-22T12:04:51+02:00 | N | N |  | Y | N
75790 | 430_ME_Ductfans_WallMounted_Round.rfa | 2026-09-09 | 2026-09-22 | 10 | handler_assign | status_resolved | START: handler→h.le @ 2026-09-09T09:08:08+02:00 ¦¦ END: status→resolved @ 2026-09-22T09:16:42+02:00 | N | N |  | Y | N
75791 | 430_ME_ExpansionTank_BottomConnection.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-09-09T09:08:08+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T11:42:53+02:00 | N | N |  | Y | Y
75792 | 430_ME_FansForAggressiveAir.rfa | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-09T09:07:26+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T11:36:55+02:00 | N | N |  | Y | Y
75793 | 430_ME_Fan_Axial.rfa | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-09T09:07:26+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T07:20:38+02:00 | N | N |  | Y | Y
75794 | 430_ME_Fan_Roof_Exhaust.rfa | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-09T09:07:26+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T07:20:41+02:00 | N | N |  | Y | Y
75795 | 430_ME_Fan_Roof_SmokeExtraction_NoSystem.rfa | 2026-09-09 | 2026-09-21 | 9 | handler_assign | status_resolved | START: handler→d.nguyen @ 2026-09-09T09:06:50+02:00 ¦¦ END: status→resolved @ 2026-09-21T05:56:26+02:00 | N | N |  | Y | N
75796 | 430_ME_Fan_WallMounted.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-09-09T09:06:50+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T11:42:56+02:00 | N | N |  | Y | Y
75798 | 430_ME_FilterFanCoilUnit.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→d.nguyen @ 2026-09-09T09:06:50+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T11:43:01+02:00 | N | N |  | Y | Y
75799 | 430_ME_FlushMountedFan_BackConnection_SilentECO.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-09T02:18:40+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T11:43:06+02:00 | N | N |  | Y | Y
75800 | 430_ME_FlushMountedFan_TopConnection_SilentECO.rfa | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-09T02:18:26+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T11:36:58+02:00 | N | N |  | Y | Y
75801 | 430_ME_GloveBox.rfa | 2026-09-08 | 2026-09-21 | 10 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-08T08:30:53+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-21T11:44:52+02:00 | N | N |  | Y | Y
75802 | 430_ME_HeatExchangersAndAirHeaters_EL.rfa | 2026-09-08 | 2026-09-23 | 12 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-08T08:30:45+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T11:23:06+02:00 | N | N |  | Y | Y
75803 | 430_ME_HeatExchangersAndAirHeaters_WL.rfa | 2026-09-08 | 2026-09-22 | 11 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-08T08:27:09+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-22T10:58:32+02:00 | N | N |  | Y | Y
75804 | 430_ME_HeatExchangersAndAirHeaters_WT.rfa | 2026-09-08 | 2026-09-24 | 13 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-09-08T04:58:10+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-24T03:53:56+02:00 | N | N |  | Y | Y
75805 | 430_ME_HeatExchangers_KTH_NoSystem.rfa | 2026-09-08 | 2026-09-23 | 12 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-08T08:27:05+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T11:23:09+02:00 | N | N |  | Y | Y
75806 | 430_ME_HeatReclaimVentilator_VAMFC.rfa | 2026-09-08 | 2026-09-23 | 12 | handler_assign | status_resolved | START: handler→h.le @ 2026-09-08T08:25:53+02:00 ¦¦ END: status→resolved @ 2026-09-23T09:16:43+02:00 | N | N |  | Y | N
75807 | 430_ME_HeatRecoveryWheelPrimaryAirUnits_Standard.rfa | 2026-09-08 | 2026-09-15 | 6 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-08T02:20:52+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-15T11:12:33+02:00 | N | N |  | Y | Y
75909 | RLT_Creation RVT Template | 2026-09-11 | 2026-10-01 | 15 | handler_assign | status_resolved | START: handler→n.bui @ 2026-09-11T03:14:46+02:00 ¦¦ END: status→resolved @ 2026-10-01T02:31:03+02:00 | N | N |  | Y | N
75910 | RLT_Output Check List | 2026-09-11 | 2026-09-30 | 14 | handler_assign | status_resolved | START: handler→n.bui @ 2026-09-11T03:15:53+02:00 ¦¦ END: status→resolved @ 2026-09-30T10:27:44+02:00 | N | N |  | Y | N
75911 | RLT_Sample layout_LPH3_5_8 | 2026-09-11 |  |  | handler_assign | none | START: handler→n.bui @ 2026-09-11T03:17:46+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
75935 | HKT_Update family to DCM Revit Library Model_Sample Zone | 2026-09-14 | 2026-09-28 | 11 | handler_assign | status_resolved | START: handler→t.tran @ 2026-09-14T06:10:21+02:00 ¦¦ END: status→resolved @ 2026-09-28T04:10:54+02:00 | N | N |  | Y | N
75936 | HKT_Creation RVT Template | 2026-09-14 | 2026-09-23 | 8 | handler_assign | status_resolved | START: handler→t.tran @ 2026-09-14T06:10:13+02:00 ¦¦ END: status→resolved @ 2026-09-23T03:05:08+02:00 | N | N |  | Y | N
75937 | HKT_Output Check List | 2026-09-14 | 2026-09-22 | 7 | handler_assign | status_resolved | START: handler→t.tran @ 2026-09-14T06:10:08+02:00 ¦¦ END: status→resolved @ 2026-09-22T03:13:09+02:00 | N | N |  | Y | N
75938 | HKT_Sample layout_LPH8 | 2026-09-14 |  |  | handler_assign | none | START: handler→t.tran @ 2026-09-14T06:10:01+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
75948 | 430_DA_PlenumBoxRectoRec_Standard.rfa | 2026-09-15 | 2026-09-25 | 9 | handler_assign | status_resolved | START: handler→t.bui @ 2026-09-15T04:42:15+02:00 ¦¦ END: status→resolved @ 2026-09-25T03:41:13+02:00 | N | N |  | Y | N
75949 | 430_DA_PlenumBoxRoutoRec_Standard.rfa | 2026-09-15 | 2026-09-25 | 9 | handler_assign | status_resolved | START: handler→t.bui @ 2026-09-15T04:42:15+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:03:51+02:00 | N | N |  | Y | N
76095 | 430_AT_SchakoDisplacementDiffusers_Wall_WQARU_Supply | 2026-09-17 | 2026-09-22 | 4 | handler_assign | confirm_note:stored_full | START: handler→da.nguyen @ 2026-09-17T05:34:58+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-22T06:03:08+02:00 | N | N |  | N | Y
76100 | 430_AT_NodeFlushChannelPlenumOpposedHorizontalFlow_Supply | 2026-09-18 | 2026-09-22 | 3 | handler_assign | confirm_note:stored_full | START: handler→l.pham @ 2026-09-18T03:40:38+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-22T11:06:22+02:00 | N | N |  | N | Y
76104 | Digital_Research_Upgrade the DCMvn Tool | 2026-09-18 |  |  | handler_assign | none | START: handler→nd.huynh @ 2026-09-18T08:36:38+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76117 | HKT_Sample layout_LPH5 | 2026-09-21 |  |  | handler_assign | none | START: handler→b.tran @ 2026-09-21T04:09:02+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76118 | HKT_Sample layout_LPH3 | 2026-09-21 |  |  | handler_assign | none | START: handler→th.nguyen @ 2026-09-21T04:11:35+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76120 | HKT_Overview_Sample layout_LPH3 + LPH5 + LPH8 | 2026-09-21 |  |  | handler_assign | none | START: handler→t.tran @ 2026-09-21T04:18:07+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76121 | HKT_Updating Schematic_LPH3 | 2026-09-21 |  |  | handler_assign | none | START: handler→tm.doan @ 2026-09-21T04:39:11+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76123 | HKT_Updating Schematic_LPH5 | 2026-09-21 |  |  | handler_assign | none | START: handler→dx.quach @ 2026-09-21T04:40:14+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76124 | HKT_Updating Schematic_LPH8 | 2026-09-21 |  |  | handler_assign | none | START: handler→ht.pham @ 2026-09-21T04:41:55+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76125 | HKT_Overview_Updating Schematic | 2026-09-21 |  |  | handler_assign | none | START: handler→ht.pham @ 2026-09-21T04:42:33+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76127 | HKT_Producing BOM | 2026-09-21 |  |  | handler_assign | none | START: handler→ht.tran @ 2026-09-21T05:14:27+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76128 | HKT_Updating LOIN | 2026-09-21 | 2026-09-29 | 7 | handler_assign | status_resolved | START: handler→l.nguyen @ 2026-09-21T05:17:27+02:00 ¦¦ END: status→resolved @ 2026-09-29T08:11:09+02:00 | N | N |  | Y | N
76129 | HKT_Uploading the 2D document to Revizto platform and set up 3D overlay | 2026-09-21 |  |  | handler_assign | none | START: handler→th.nguyen @ 2026-09-21T05:23:44+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76131 | HKT_Publishing Revizto + Exporting Ifc model | 2026-09-21 |  |  | handler_assign | none | START: handler→h.huynh @ 2026-09-21T05:35:39+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76138 | 420_SE_PenetrationSealing_Outside | 2026-09-21 | 2026-09-23 | 3 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-09-21T09:13:11+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T09:58:48+02:00 | N | N |  | N | Y
76139 | 420_SE_DistrictHeatingTransferStation | 2026-09-21 | 2026-09-23 | 3 | handler_assign | confirm_note:stored_full | START: handler→h.le @ 2026-09-21T09:13:31+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-23T06:13:04+02:00 | N | N |  | N | Y
76169 | Revit Template for ELT in LPH3 | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | START: handler→th.le @ 2026-09-24T04:18:52+02:00 ¦¦ END: status→resolved @ 2026-09-28T12:52:17+02:00 | N | N |  | Y | N
76170 | Revit Template for ELT in LPH5 | 2026-09-24 | 2026-09-29 | 4 | handler_assign | status_resolved | START: handler→n.chau @ 2026-09-24T04:19:34+02:00 ¦¦ END: status→resolved @ 2026-09-29T11:05:32+02:00 | N | N |  | Y | N
76171 | Revit Template for ELT in LPH8 | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | START: handler→d.le @ 2026-09-24T04:21:23+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:24:21+02:00 | N | N |  | Y | N
76172 | Revit Template for MSR in LPH3 | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | START: handler→t.le @ 2026-09-24T04:23:54+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:15:23+02:00 | N | N |  | Y | N
76173 | Revit Template for MSR in LPH5 | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | START: handler→tu.le @ 2026-09-24T04:25:24+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:17:46+02:00 | N | N |  | Y | N
76174 | Revit Template for MSR in LPH8 | 2026-09-24 | 2026-09-24 | 1 | handler_assign | status_resolved | START: handler→t.do @ 2026-09-24T04:26:50+02:00 ¦¦ END: status→resolved @ 2026-09-24T11:00:35+02:00 | N | N |  | Y | N
76175 | LPH3 Check list for ELT discipline | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | START: handler→t.doan @ 2026-09-24T04:32:21+02:00 ¦¦ END: status→resolved @ 2026-09-25T11:06:22+02:00 | N | N |  | Y | N
76176 | LPH5 Check list for ELT discipline | 2026-09-24 | 2026-09-29 | 4 | handler_assign | status_resolved | START: handler→th.le @ 2026-09-24T04:34:40+02:00 ¦¦ END: status→resolved @ 2026-09-29T12:22:59+02:00 | N | N |  | Y | N
76177 | LPH8 Check list for ELT discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | START: handler→t.do @ 2026-09-24T04:36:07+02:00 ¦¦ END: status→resolved @ 2026-09-28T11:26:27+02:00 | N | N |  | Y | N
76178 | LPH3 Check list for MSR discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | START: handler→t.le @ 2026-09-24T04:38:35+02:00 ¦¦ END: status→resolved @ 2026-09-28T11:18:29+02:00 | N | N |  | Y | N
76179 | LPH5 Check list for MSR discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | START: handler→tu.le @ 2026-09-24T04:39:27+02:00 ¦¦ END: status→resolved @ 2026-09-28T11:10:01+02:00 | N | N |  | Y | N
76180 | LPH8 Check list for MSR discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | START: handler→d.le @ 2026-09-24T04:40:23+02:00 ¦¦ END: status→resolved @ 2026-09-28T11:08:09+02:00 | N | N |  | Y | N
76206 | 420_PA_MotorizedGloboBallValve_Thread.rfa | 2026-09-25 | 2026-09-30 | 4 | handler_assign | confirm_note:stored_full | START: handler→n.bui @ 2026-09-25T08:16:20+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-30T07:31:59+02:00 | N | N |  | N | Y
76212 | Revit Template for SAN in LPH3 | 2026-09-25 |  |  | handler_assign | none | START: handler→y.nguyen @ 2026-09-25T11:29:15+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76213 | Revit Template for SAN in LPH5 | 2026-09-25 |  |  | handler_assign | none | START: handler→k.mai @ 2026-09-25T11:27:53+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76219 | 434_PA_DewPointMonitor.rfa | 2026-09-28 | 2026-09-29 | 2 | handler_assign | confirm_note:stored_full | START: handler→tk.pham @ 2026-09-28T02:16:30+02:00 ¦¦ END: hu.dam: @l.truong This family is now fully completed and securely stored. Thank you for your attention to th @ 2026-09-29T11:46:58+02:00 | N | N |  | N | Y
76220 | Produce Sample layout for ELT LPH3 | 2026-09-28 |  |  | handler_assign | none | START: handler→t.doan @ 2026-09-28T03:06:49+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76221 | Produce Sample layout for ELT LPH5 | 2026-09-28 |  |  | handler_assign | none | START: handler→h.pham @ 2026-09-28T03:10:52+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76222 | Produce Sample layout for ELT LPH8 | 2026-09-28 |  |  | handler_assign | none | START: handler→th.le @ 2026-09-28T03:13:59+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76227 | DCMvn_Annotation_Update Pump Room in Existing DCM_SAN_Model | 2026-09-28 |  |  | handler_assign | none | START: handler→n.vo @ 2026-09-28T10:46:58+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76253 | Produce Schematic Drawing Sample for ELT LPH3 | 2026-09-29 |  |  | handler_assign | none | START: handler→t.do @ 2026-09-29T03:01:09+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76254 | Produce Schematic Drawing Sample for ELT LPH5 | 2026-09-29 |  |  | handler_assign | none | START: handler→t.le @ 2026-09-29T03:03:17+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76255 | Produce Schematic Drawing Sample for ELT LPH8 | 2026-09-29 |  |  | handler_assign | none | START: handler→d.le @ 2026-09-29T03:07:28+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76256 | DCMvn Annotation_Practice_SAN Discipline | 2026-09-29 |  |  | handler_assign | none | START: handler→ttc.bui @ 2026-09-29T04:14:15+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76258 | Produce Sample layout for MSR LPH3 | 2026-09-29 |  |  | handler_assign | none | START: handler→tu.le @ 2026-09-29T04:27:39+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76259 | Produce Sample layout for MSR LPH5 | 2026-09-29 |  |  | handler_assign | none | START: handler→h.pham @ 2026-09-29T04:29:07+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76260 | Produce Sample layout for MSR LPH8 | 2026-09-29 |  |  | handler_assign | none | START: handler→h.pham @ 2026-09-29T04:31:17+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76273 | DCMvn Annotation_Practice_RLT Discipline |  |  |  | none | none | START: no handler-assign or status→assigned in history ¦¦ END: no confirm note and no status→resolved/closed | Y | Y | missing_start,missing_end | Y | N
76283 | DCMvn_Annotation_SAN_Upload 2D Layout to Revizto and Set Up 3D Overlay | 2026-09-29 |  |  | handler_assign | none | START: handler→ttc.bui @ 2026-09-29T11:35:36+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N
76286 | DCMvn_Annotation_SAN_Export BOM Based on Template | 2026-09-29 |  |  | handler_assign | none | START: handler→c.le @ 2026-09-29T11:16:52+02:00 ¦¦ END: no confirm note and no status→resolved/closed | N | Y | missing_end | Y | N

## Family_Preview
Family Name | Ticket_IDs | Primary_Ticket_ID | Start Date | End Date | Duration | Start_Method | End_Method | Flag
400_NF_GussetPlateAngularRectangular | 75622 | 75622 | 2026-09-03 | 2026-09-18 | 12 | handler_assign | confirm_note:stored_full
400_NF_GussetPlateAngularSingleAdjustableBrace | 75623 | 75623 | 2026-09-03 | 2026-09-18 | 12 | handler_assign | confirm_note:stored_full
410_ME_CentrifugalPump | 74853 | 74853 | 2026-07-30 | 2026-09-23 | 40 | handler_assign | confirm_note:stored_full
410_ME_CompactPressureBoostingSystem | 74854 | 74854 | 2026-07-30 | 2026-09-09 | 30 | handler_assign | confirm_note:stored_full
410_ME_CompactPressureBoostingSystem_1MVISE | 74855 | 74855 | 2026-08-06 | 2026-09-17 | 31 | handler_assign | confirm_note:stored_full
410_ME_CompactWaterHeater_WallMounted | 74856 | 74856 | 2026-08-06 | 2026-09-25 | 37 | handler_assign | confirm_note:stored_full
410_ME_Desoftening | 74857 | 74857 | 2026-08-07 | 2026-09-11 | 26 | handler_assign | confirm_note:stored_full
410_ME_DoppelHebeanlageSchmutzwasser | 74858 | 74858 | 2026-08-07 | 2026-09-14 | 27 | handler_assign | confirm_note:stored_full
410_ME_DoublePressureBoosterSystem | 74859 | 74859 | 2026-08-07 | 2026-09-23 | 34 | handler_assign | confirm_note:stored_full
410_ME_DrainLiftL_Floor | 74860 | 74860 | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full
410_ME_DrainLiftM_Floor | 74861 | 74861 | 2026-08-07 | 2026-09-24 | 35 | handler_assign | confirm_note:stored_full
410_ME_DrainLiftS_Floor | 74872 | 74872 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full
410_ME_DrainLiftXL_Floor | 74873 | 74873 | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full
410_ME_DualTank_WaterSofteners | 74874 | 74874 | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full
410_ME_DuplexSofteningUnit_RondomatDuo | 74875 | 74875 | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full
410_ME_EKleindurchlauferhitzerCEX | 74876 | 74876 | 2026-08-07 | 2026-08-27 | 15 | handler_assign | confirm_note:stored_full
410_ME_EKleindurchlauferhitzer_MCX | 74877 | 74877 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full
410_ME_ElectricInstantaneousHeater_DLE | 74878 | 74878 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full
410_ME_ExpansionVessel | 74879 | 74879 | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full
410_ME_ExpansionVessel_Reflex | 74880 | 74880 | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full
410_ME_FettabscheiderNG2 | 74881 | 74881 | 2026-08-07 | 2026-08-27 | 15 | handler_assign | confirm_note:stored_full
410_ME_FreshWaterStation | 74882 | 74882 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full
410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ | 74883 | 74883 | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full
410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ | 74884 | 74884 | 2026-08-07 | 2026-09-16 | 29 | handler_assign | confirm_note:stored_full
410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ | 74885 | 74885 | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full
410_ME_GreaseSeparator_FloorStand | 74887 | 74887 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full
410_ME_GreaseSeparatorFreeStandingInstallationNS10 | 74886 | 74886 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full
410_ME_HighPerformanceIndustrialMixers | 74888 | 74888 | 2026-08-07 | 2026-09-15 | 28 | handler_assign | confirm_note:stored_full
410_ME_HotWaterStorageTank | 74889 | 74889 | 2026-08-11 | 2026-08-28 | 14 | handler_assign | confirm_note:stored_full
410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2 | 74892 | 74892 | 2026-08-13 | 2026-08-24 | 8 | handler_assign | confirm_note:stored_full
410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2 | 74890 | 74890 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2 | 74891 | 74891 | 2026-08-13 | 2026-08-24 | 8 | handler_assign | confirm_note:stored_full
410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2 | 74893 | 74893 | 2026-08-13 | 2026-08-28 | 12 | handler_assign | confirm_note:stored_full
410_ME_iboxUniversalForShower_WallRecessed | 74895 | 74895 | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full
410_ME_InstantaneousWaterHeater_Shower | 74896 | 74896 | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full
410_ME_InstantaneousWaterHeater_SinkAGB | 74897 | 74897 | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full
410_ME_InstantaneousWaterHeater_TeaKitchen | 74898 | 74898 | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full
410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort | 74901 | 74901 | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full
410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort | 74904 | 74904 | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full
410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded | 74903 | 74903 | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full
410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort | 74906 | 74906 | 2026-08-13 | 2026-09-25 | 32 | handler_assign | confirm_note:stored_full
410_ME_KHSMiniControlSystemSLAVE_WallSurface | 74907 | 74907 | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full
410_ME_KHSMiniControlSystem_WallSurface_Master | 74909 | 74909 | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full
410_ME_KHSTimer_WallSurface | 74910 | 74910 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
410_ME_MiniTresorCabinet_InWall | 74911 | 74911 | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full
410_ME_PHController | 74914 | 74914 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
410_ME_PlasticInnerTankSeries | 74915 | 74915 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full
410_ME_PoolSandFilter_FloorStand_Round | 74917 | 74917 | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full
410_ME_PressureBoosterPump | 74918 | 74918 | 2026-08-20 | 2026-09-16 | 20 | handler_assign | confirm_note:stored_full
410_ME_PressurisationUnit_FixedSpeedUnits2Pump | 74919 | 74919 | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full
410_ME_PressurisationUnit_FixedSpeedUnits3Pump | 74920 | 74920 | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full
410_ME_PressurisationUnit_VariableSpeedUnits3Pump | 74921 | 74921 | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full
410_ME_PressurisationUnit_VariableSpeedUnitsWith1Pump | 74922 | 74922 | 2026-08-20 | 2026-09-18 | 22 | handler_assign | confirm_note:stored_full
410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP | 74926 | 74926 | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full
410_ME_Probenahmetopf | 74929 | 74929 | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full
410_ME_PumpGlandlessCirculator_StarZ | 74933 | 74933 | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full
410_ME_PumpGlandlessCirculator_StarZD | 74934 | 74934 | 2026-08-20 | 2026-09-15 | 19 | handler_assign | confirm_note:stored_full
410_ME_PumpGlandlessCirculator_TopZ | 74935 | 74935 | 2026-08-20 | 2026-09-30 | 30 | handler_assign | confirm_note:stored_full
410_ME_PureWaterTank | 74936 | 74936 | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full
410_ME_ReverseOsmosisSystem | 74937 | 74937 | 2026-08-20 | 2026-09-23 | 25 | handler_assign | confirm_note:stored_full
410_ME_ServiceStorageTank_Round | 74939 | 74939 | 2026-08-20 | 2026-09-11 | 17 | handler_assign | confirm_note:stored_full
410_ME_Sicherheitstrennstation | 74940 | 74940 | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full
410_ME_SinglePressureBoosterSystem | 74941 | 74941 | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full
410_ME_StratosMAXOZPump_Vertical | 74942 | 74942 | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full
410_ME_StratosPICOZPump_Vertical | 74943 | 74943 | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full
410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono | 74944 | 74944 | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full
410_ME_SubmergedPump_Horizontal_SatSeries | 74945 | 74945 | 2026-08-20 | 2026-09-24 | 26 | handler_assign | confirm_note:stored_full
410_ME_SubmergedPump_SitaSeries | 74946 | 74946 | 2026-08-20 | 2026-09-15 | 19 | handler_assign | confirm_note:stored_full
410_ME_SubmergedPump_Vertical_SATSeries | 74947 | 74947 | 2026-08-24 | 2026-09-04 | 10 | handler_assign | confirm_note:stored_full
410_ME_SubmergedPump_Vertical_SATVSeries | 74948 | 74948 | 2026-08-24 | 2026-09-28 | 26 | handler_assign | confirm_note:stored_full
410_ME_TresorCabinet_InWall | 74949 | 74949 | 2026-08-26 | 2026-09-11 | 13 | handler_assign | confirm_note:stored_full
410_ME_TresorCabinet_WallSurface | 74950 | 74950 | 2026-08-26 | 2026-09-16 | 16 | handler_assign | confirm_note:stored_full
410_ME_TripleSofteningSystem_DeltaP | 74951 | 74951 | 2026-08-26 | 2026-09-11 | 13 | handler_assign | confirm_note:stored_full
410_ME_TWPressureBoosterSystem | 74952 | 74952 | 2026-08-26 | 2026-09-16 | 16 | handler_assign | confirm_note:stored_full
410_ME_VerticaltubeHeatexchanger | 74953 | 74953 | 2026-08-26 | 2026-09-15 | 15 | handler_assign | confirm_note:stored_full
410_ME_WasteWaterLift_Floor_C3 | 74965 | 74965 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full
410_ME_WasteWaterLift_Floor_CWC3 | 74966 | 74966 | 2026-08-31 | 2026-09-22 | 17 | handler_assign | confirm_note:stored_full
410_ME_WasteWaterLift_Floor_D2 | 74967 | 74967 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full
410_ME_WasteWaterLift_Floor_WC1 | 74968 | 74968 | 2026-08-31 | 2026-09-24 | 19 | handler_assign | confirm_note:stored_full
410_ME_WasteWaterLift_Floor_WC3 | 74969 | 74969 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full
410_ME_WastewaterLiftingStation_DouPump | 74955 | 74955 | 2026-08-27 | 2026-09-16 | 15 | handler_assign | confirm_note:stored_full
410_ME_WasteWaterLiftingStation_KesselPump | 74956 | 74956 | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full
410_ME_WastewaterLiftingStation_MuliPES&Mono | 74957 | 74957 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full
410_ME_WastewaterLiftingStation_MuliProPEKParallel | 74959 | 74959 | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full
410_ME_WastewaterLiftingStation_MuliProPENXLDuo | 74960 | 74960 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full
410_ME_WastewaterLiftingStation_MuliStarDDP | 74961 | 74961 | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full
410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1 | 74962 | 74962 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full
410_ME_WasteWaterLiftingStationPump | 74954 | 74954 | 2026-08-26 | 2026-09-23 | 21 | handler_assign | confirm_note:stored_full
410_ME_WastewaterLiftingStation_Sinkamat_HW | 74963 | 74963 | 2026-08-31 | 2026-09-24 | 19 | handler_assign | confirm_note:stored_full
410_ME_WaterDispenser_FloorStand | 74970 | 74970 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full
410_ME_WaterFilterTank | 74971 | 74971 | 2026-08-31 | 2026-09-18 | 15 | handler_assign | confirm_note:stored_full
410_ME_WaterFilterVertical | 74972 | 74972 | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full
410_ME_WaterHardnessMeter | 74973 | 74973 | 2026-08-31 | 2026-09-14 | 11 | handler_assign | confirm_note:stored_full
410_ME_WaterHeater_WallMounted | 74975 | 74975 | 2026-08-31 | 2026-09-18 | 15 | handler_assign | confirm_note:stored_full
410_ME_WaterHeaterWithTap_WallMounted | 74974 | 74974 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full
410_PA_AirReleaseValve_Threaded | 73518 | 73518 | 2026-07-02 | 2026-08-20 | 36 | handler_assign | confirm_note:stored_full
410_PA_AngleSafetyValve_Threaded | 73519 | 73519 | 2026-07-02 | 2026-08-03 | 23 | handler_assign | confirm_note:stored_full
410_PA_AngleSeatPistonValve_Flanged | 73523 | 73523 | 2026-07-02 | 2026-08-20 | 36 | handler_assign | confirm_note:stored_full
410_PA_AngleSeatPistonValve_Threaded | 73554 | 73554 | 2026-07-02 | 2026-07-08 | 5 | handler_assign | confirm_note:stored_full
410_PA_AngleValve_Threaded_WithRegulatingFunction | 73555 | 73555 | 2026-07-03 | 2026-08-20 | 35 | handler_assign | confirm_note:stored_full
410_PA_AutomaticBackwashFilter_Flanged | 73556 | 73556 | 2026-07-03 | 2026-07-10 | 6 | handler_assign | status_resolved
410_PA_AutomaticCirculationRegulatingValve | 73557 | 73557 | 2026-07-03 | 2026-07-09 | 5 | handler_assign | status_resolved
410_PA_AutomaticHygieneFlushingStationHS10_Geberit | 73558 | 73558 | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full
410_PA_BackflowPreventer_Threaded | 73582 | 73582 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_BackflowPreventerValve_Threaded | 73559 | 73559 | 2026-07-03 | 2026-07-30 | 20 | handler_assign | confirm_note:stored_full
410_PA_BallValve_Flanged | 73561 | 73561 | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full
410_PA_BallValve_SocketFusion | 73644 | 73644 | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full
410_PA_BallValve_Threaded | 73583 | 73583 | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full
410_PA_CoarseTrap | 73584 | 73584 | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full
410_PA_CombinationAngleValve_Standard | 73585 | 73585 | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full
410_PA_DiaphragmValve | 73586 | 73586 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_DoubleInstallationRackWatermeter_Threaded | 73587 | 73587 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_DrainValve_Threaded | 73588 | 73588 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_FillSetStandardValve_Threaded | 73589 | 73589 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_FillsoftHousing_Threaded | 73590 | 73590 | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full
410_PA_Filter_Threaded | 73591 | 73591 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_FittingSpacerForWaterMeter_Threaded | 73592 | 73592 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_FlexibleConnection_Flanged | 73593 | 73593 | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full
410_PA_FloatingValve_Threaded | 73594 | 73594 | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full
410_PA_FlowSplitterBox_Floor_Threaded_KHS | 73595 | 73595 | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full
410_PA_FlowSplitterSet_Threaded_KHS | 73596 | 73596 | 2026-07-03 | 2026-09-21 | 57 | handler_assign | confirm_note:stored_full
410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS | 73597 | 73597 | 2026-07-03 | 2026-09-08 | 48 | handler_assign | confirm_note:stored_full
410_PA_FlowSplitterUnit_Threaded_DynamicKHS | 73598 | 73598 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_FlowTemperatureMeterValve_Threaded | 73599 | 73599 | 2026-07-24 | 2026-08-25 | 23 | handler_assign | confirm_note:stored_full
410_PA_FlushMountedStopValve_Mapress_UpPlus | 73600 | 73600 | 2026-07-03 | 2026-07-10 | 6 | handler_assign | status_resolved
410_PA_FlushMoutedStopValve_Threaded_UpPlus | 73603 | 73603 | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full
410_PA_FunnelSiphon_Horizontal | 73604 | 73604 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_GateValve_Flanged | 73607 | 73607 | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full
410_PA_GateValveSealingDirectionWithDrain_Threaded | 73605 | 73605 | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full
410_PA_GateValve_Threaded | 73608 | 73608 | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full
410_PA_GateValveWithDrain_Threaded | 73606 | 73606 | 2026-07-03 | 2026-08-25 | 38 | handler_assign | confirm_note:stored_full
410_PA_GlobeValve_Flanged | 73609 | 73609 | 2026-07-03 | 2026-08-14 | 31 | handler_assign | confirm_note:stored_full
410_PA_GlobeValve_Threaded | 73610 | 73610 | 2026-07-03 | 2026-08-03 | 22 | handler_assign | confirm_note:stored_full
410_PA_KHSFlushPoint_Threaded_230V | 73611 | 73611 | 2026-07-03 | 2026-08-03 | 22 | handler_assign | confirm_note:stored_full
410_PA_KHSFlushPoint_Threaded_24V | 73612 | 73612 | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full
410_PA_KHSFlushPoint_Threaded_ControlPlus230V | 73613 | 73613 | 2026-07-03 | 2026-08-25 | 38 | handler_assign | confirm_note:stored_full
410_PA_KHSFlushPoint_Threaded_ControlPlus24V | 73614 | 73614 | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full
410_PA_KugelSiphon_Standard | 73615 | 73615 | 2026-07-09 | 2026-08-24 | 33 | handler_assign | confirm_note:stored_full
410_PA_MotorButterflyValve_Flanged | 73616 | 73616 | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full
410_PA_NozzleCheckValve_Flanged | 73618 | 73618 | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full
410_PA_OutletValve_Threaded | 73620 | 73620 | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full
410_PA_OutletValve_Threaded_WithHoseScrewConnection | 73621 | 73621 | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full
410_PA_PoolMainDrain_Threaded | 73622 | 73622 | 2026-07-10 | 2026-08-14 | 26 | handler_assign | confirm_note:stored_full
410_PA_PoolReturnJet_Threaded | 73623 | 73623 | 2026-07-10 | 2026-08-14 | 26 | handler_assign | confirm_note:stored_full
410_PA_PoolSkimmer_Threaded | 73624 | 73624 | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full
410_PA_PressureGauge_withSiphon | 73646 | 73646 | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full
410_PA_PressureReducingValveFilterCombination_Threaded | 73648 | 73648 | 2026-07-10 | 2026-07-17 | 6 | handler_assign | status_resolved
410_PA_PressureReducingValve_Flanged | 73650 | 73650 | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full
410_PA_PressureReducingValve_Threaded | 73652 | 73652 | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full
410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded | 73649 | 73649 | 2026-07-10 | 2026-09-09 | 44 | handler_assign | confirm_note:stored_full
410_PA_PressureRegulator_Thread | 73653 | 73653 | 2026-07-10 | 2026-08-25 | 33 | handler_assign | confirm_note:stored_full
410_PA_SamplingValveForWashBasinAngleValve_Standard_SS | 73654 | 73654 | 2026-07-10 | 2026-08-19 | 29 | handler_assign | status_resolved
410_PA_SamplingValve_Standard_Gunmetal | 73655 | 73655 | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full
410_PA_SamplingValve_Standard_SS | 73656 | 73656 | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full
410_PA_ShutoffValve_Flanged | 73657 | 73657 | 2026-07-10 | 2026-08-07 | 21 | handler_assign | confirm_note:stored_full
410_PA_ShutoffValve_Flanged_DrainValve | 73658 | 73658 | 2026-07-15 | 2026-08-06 | 17 | handler_assign | confirm_note:stored_full
410_PA_ShutoffValve_MapressGeberit | 73664 | 73664 | 2026-07-16 | 2026-07-17 | 2 | handler_assign | status_resolved
410_PA_ShutoffValve_Mapress_WithDrainValve | 73663 | 73663 | 2026-07-15 | 2026-08-12 | 21 | handler_assign | confirm_note:stored_full
410_PA_ShutoffValve_Threaded | 73659 | 73659 | 2026-07-15 | 2026-08-18 | 25 | handler_assign | confirm_note:stored_full
410_PA_ShutoffValve_WithDrainPlug_Threaded | 73660 | 73660 | 2026-07-15 | 2026-08-26 | 31 | handler_assign | confirm_note:stored_full
410_PA_SingleInstallationRackWatermeter_Threaded | 73661 | 73661 | 2026-07-15 | 2026-09-21 | 49 | handler_assign | confirm_note:stored_full
410_PA_SolenoidControlValve_Flanged | 73662 | 73662 | 2026-07-15 | 2026-08-25 | 30 | handler_assign | confirm_note:stored_full
410_PA_StaticBalancingValve_Threaded_MultiFixPlus | 73666 | 73666 | 2026-07-16 | 2026-09-11 | 42 | handler_assign | confirm_note:stored_full
410_PA_StaticBalancingValve_UnionThreaded_MultiFixPlus | 73667 | 73667 | 2026-07-16 | 2026-08-12 | 20 | handler_assign | confirm_note:stored_full
410_PA_StopValve_SocketFusion | 73645 | 73645 | 2026-07-10 | 2026-08-24 | 32 | handler_assign | confirm_note:stored_full
410_PA_StraightSafetyValve_Threaded | 73665 | 73665 | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full
410_PA_SwingcheckValve_Flanged | 73668 | 73668 | 2026-07-16 | 2026-08-17 | 23 | handler_assign | confirm_note:stored_full
410_PA_SwingcheckValve_Threaded | 73669 | 73669 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_SystemSeparator_Flanged | 73670 | 73670 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_SystemSeparator_Threaded | 73671 | 73671 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_TemperatureMeasuringValve_Threaded_KHS | 73672 | 73672 | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full
410_PA_THandleBallValve_Threaded | 73673 | 73673 | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full
410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm | 73674 | 73674 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_ThreePiecesBallValve_Welded | 73675 | 73675 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_ThreeWayMotorisedControlValve_Flanged | 73676 | 73676 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_ThreeWayMotorisedControlValve_Threaded | 73677 | 73677 | 2026-07-16 | 2026-09-18 | 47 | handler_assign | confirm_note:stored_full
410_PA_TwoWayDiaphragmValve_Flanged | 73679 | 73679 | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full
410_PA_TwoWayDiaphragmValve_Threaded | 73678 | 73678 | 2026-07-16 | 2026-08-18 | 24 | handler_assign | confirm_note:stored_full
410_PA_UPConcealedShutoffValve | 73684 | 73684 | 2026-07-16 | 2026-08-12 | 20 | handler_assign | confirm_note:stored_full
410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress | 73680 | 73680 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_UpETATHERMThermostaticBalancingValve_Threaded | 73681 | 73681 | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full
410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress | 73682 | 73682 | 2026-07-16 | 2026-08-18 | 24 | handler_assign | confirm_note:stored_full
410_PA_UPVSenkrecht | 73683 | 73683 | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full
410_PA_VAVFullFlowShutOffValve_FemaleThreaded | 73685 | 73685 | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full
410_PA_VentCowl | 73686 | 73686 | 2026-07-24 | 2026-08-17 | 17 | handler_assign | confirm_note:stored_full
410_PA_WaferButterflyValve_Flanged | 73687 | 73687 | 2026-07-24 | 2026-08-27 | 25 | handler_assign | confirm_note:stored_full
410_PA_WaterHammerArrestor_Threaded | 73688 | 73688 | 2026-07-24 | 2026-08-26 | 24 | handler_assign | confirm_note:stored_full
410_PA_WaterMeter_Flanged | 73690 | 73690 | 2026-07-24 | 2026-09-09 | 34 | handler_assign | confirm_note:stored_full
410_PA_WaterMeter_Threaded | 73691 | 73691 | 2026-07-24 | 2026-08-17 | 17 | handler_assign | confirm_note:stored_full
410_PA_WaterMeterUNI | 73689 | 73689 | 2026-07-24 | 2026-08-21 | 21 | handler_assign | confirm_note:stored_full
410_PA_YStrainer_Flanged | 73693 | 73693 | 2026-07-24 | 2026-09-10 | 35 | handler_assign | confirm_note:stored_full
410_PA_YStrainer_Threaded | 73695 | 73695 | 2026-07-24 | 2026-08-21 | 21 | handler_assign | confirm_note:stored_full
410_PA_ZBCapRoof_Standard | 73696 | 73696 | 2026-07-24 | 2026-09-18 | 41 | handler_assign | confirm_note:stored_full
410_PF_cHDPE_BlindFlange_Flanged | 71686 | 71686 | 2026-05-18 | 2026-06-16 | 22 | handler_assign | confirm_note:stored_full
410_PF_CI_cGutterCap_ExternalStopEnd | 71828 | 71828 | 2026-05-25 | 2026-06-17 | 18 | handler_assign | confirm_note:stored_full
410_PF_CI_cGutterCap_InternalStopEnd | 71830 | 71830 | 2026-05-25 | 2026-06-17 | 18 | handler_assign | confirm_note:stored_full
410_PF_CI_cPlug_Coupling | 71683 | 71683 | 2026-05-15 | 2026-05-21 | 5 | handler_assign | status_resolved
410_PF_CI_cPushinPlug_Clamp | 71692 | 71692 | 2026-05-19 | 2026-05-22 | 4 | handler_assign | status_resolved
410_PF_CI_eAccessBendLong_Clamp | 71694 | 71694 | 2026-05-19 | 2026-06-18 | 23 | handler_assign | confirm_note:stored_full
410_PF_CI_eAccessBendShort_Clamp | 71695 | 71695 | 2026-05-19 | 2026-06-10 | 17 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend15Degrees_Standard_Clamp | 71696 | 71696 | 2026-05-19 | 2026-06-03 | 12 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend30Degrees_Standard_Clamp | 71697 | 71697 | 2026-05-19 | 2026-05-29 | 9 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend68Degree_Clamp | 71698 | 71698 | 2026-05-19 | 2026-06-03 | 12 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend88Deg_Clamp | 71700 | 71700 | 2026-05-19 | 2026-05-29 | 9 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend88Degree_SpigotAndClamp | 71699 | 71699 | 2026-05-19 | 2026-05-28 | 8 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend_Clamp | 71702 | 71702 | 2026-05-19 | 2026-06-02 | 11 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend_Coupling | 71703 | 71703 | 2026-05-19 | 2026-06-01 | 10 | handler_assign | confirm_note:stored_full
410_PF_CI_eBend_Coupling_HOST | 71704 | 71704 | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved
410_PF_CI_eBendWC_Clamp_Standard | 71701 | 71701 | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved
410_PF_CI_eConectionBend_Clamp | 71705 | 71705 | 2026-05-19 | 2026-05-22 | 4 | handler_assign | status_resolved
410_PF_CI_eDoubleBend45Deg_Coupling_HOST | 71706 | 71706 | 2026-05-21 | 2026-05-29 | 7 | handler_assign | confirm_note:stored_full
410_PF_CI_eDoubleBend88Deg_Coupling | 71806 | 71806 | 2026-05-21 | 2026-06-05 | 12 | handler_assign | confirm_note:stored_full
410_PF_CI_eGutterAngleUniversal | 71826 | 71826 | 2026-05-22 | 2026-06-10 | 14 | handler_assign | confirm_note:stored_full
410_PF_CI_eGutterElbow_ExternalDropEndOutlet | 71831 | 71831 | 2026-05-25 | 2026-06-19 | 20 | handler_assign | confirm_note:stored_full
410_PF_CI_eGutterElbow_InternalDropEndOutlet | 71832 | 71832 | 2026-05-25 | 2026-06-18 | 19 | handler_assign | confirm_note:stored_full
410_PF_CI_eOffsetBend130_Clamp | 71807 | 71807 | 2026-05-22 | 2026-06-04 | 10 | handler_assign | confirm_note:stored_full
410_PF_CI_eOffsetBend200_Clamp | 71808 | 71808 | 2026-05-22 | 2026-05-25 | 2 | handler_assign | status_resolved
410_PF_CI_eOffsetBend65_Clamp | 71820 | 71820 | 2026-05-22 | 2026-06-01 | 7 | handler_assign | confirm_note:stored_full
410_PF_CI_ePlainTrap_Clamp | 71821 | 71821 | 2026-05-22 | 2026-06-01 | 7 | handler_assign | confirm_note:stored_full
410_PF_CI_eRainwaterSiphon_Coupling | 71684 | 71684 | 2026-05-18 | 2026-06-02 | 12 | handler_assign | confirm_note:stored_full
410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp | 71822 | 71822 | 2026-05-22 | 2026-06-05 | 11 | handler_assign | confirm_note:stored_full
410_PF_CI_eRestBend88_Clamp | 71823 | 71823 | 2026-05-22 | 2026-05-26 | 3 | handler_assign | status_resolved
410_PF_CI_eVentilationBend88Axial_Clamp | 71824 | 71824 | 2026-05-22 | 2026-05-29 | 6 | handler_assign | status_resolved
410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp | 71825 | 71825 | 2026-05-22 | 2026-06-18 | 20 | handler_assign | confirm_note:stored_full
410_PF_CI_fAngleDoubleBranch88Degree_Coupling | 71687 | 71687 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
410_PF_CI_mGutterHalfRound | 71833 | 71833 | 2026-05-25 | 2026-06-18 | 19 | handler_assign | confirm_note:stored_full
410_PF_CI_mShortPipeRectangularAccessDoor_Standard | 71843 | 71843 | 2026-05-26 | 2026-06-09 | 11 | handler_assign | confirm_note:stored_full
410_PF_CI_mVerticalTrap_Standard | 71846 | 71846 | 2026-05-26 | 2026-06-09 | 11 | handler_assign | confirm_note:stored_full
410_PF_CI_rEccentricReducer_Coupling | 71682 | 71682 | 2026-05-15 | 2026-05-18 | 2 | handler_assign | status_resolved
410_PF_CI_rEccentricReducer_Coupling_HOST | 71918 | 71918 | 2026-05-26 | 2026-06-08 | 10 | handler_assign | confirm_note:stored_full
410_PF_CI_rEccentricReducer_WithoutCoupling | 71847 | 71847 | 2026-05-26 | 2026-08-12 | 57 | handler_assign | confirm_note:stored_full
410_PF_CI_rReducingEccentric_Clamp | 71919 | 71919 | 2026-05-26 | 2026-05-27 | 2 | handler_assign | status_resolved
410_PF_CI_tBranch45_Clamp | 71920 | 71920 | 2026-05-26 | 2026-06-05 | 9 | handler_assign | confirm_note:stored_full
410_PF_CI_tBranch45Deg_Coupling | 71689 | 71689 | 2026-05-18 | 2026-06-09 | 17 | handler_assign | confirm_note:stored_full
410_PF_CI_tBranch45Deg_Coupling_HOST | 71691 | 71691 | 2026-05-18 | 2026-06-09 | 17 | handler_assign | confirm_note:stored_full
410_PF_CI_tBranch68Deg_Coupling | 71598 | 71598 | 2026-05-15 | 2026-05-26 | 8 | handler_assign | confirm_note:stored_full
410_PF_CI_tBranch70_Clamp | 71921 | 71921 | 2026-05-26 | 2026-06-04 | 8 | handler_assign | confirm_note:stored_full
410_PF_CI_tBranch88Deg_Coupling | 71922 | 71922 | 2026-05-26 | 2026-05-29 | 4 | handler_assign | status_resolved
410_PF_CI_tBranch88Deg_Coupling_HOST | 71923 | 71923 | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full
410_PF_CI_tBranch88Long_Spigot_Clamp | 71924 | 71924 | 2026-05-28 | 2026-06-04 | 6 | handler_assign | confirm_note:stored_full
410_PF_CI_tBranch88_Spigot_Clamp | 71925 | 71925 | 2026-05-28 | 2026-05-29 | 2 | handler_assign | status_resolved
410_PF_CI_tCombinationBranch90_Standard | 71926 | 71926 | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full
410_PF_CI_tCornerBranch88_Clamp | 71927 | 71927 | 2026-05-29 | 2026-07-01 | 24 | handler_assign | confirm_note:stored_full
410_PF_CI_tGutterTee_RunningOutlet | 71834 | 71834 | 2026-05-26 | 2026-08-13 | 58 | handler_assign | confirm_note:stored_full
410_PF_CI_tSweptEntryBranch88_Spigot_Clamp | 71928 | 71928 | 2026-05-29 | 2026-06-01 | 2 | handler_assign | status_resolved
410_PF_CI_uBearing | 71688 | 71688 | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved
410_PF_CI_uCleaningPipeWithRoundCover_Coupling | 71679 | 71679 | 2026-05-15 | 2026-05-28 | 10 | handler_assign | confirm_note:stored_full
410_PF_CI_uDownPipeBracket_Coupling | 71850 | 71850 | 2026-05-15 | 2026-06-17 | 24 | handler_assign | confirm_note:stored_full
410_PF_CI_uGutterUnionConnector | 71842 | 71842 | 2026-05-26 | 2026-06-19 | 19 | handler_assign | confirm_note:stored_full
410_PF_CI_uShortPipeRoundAccessDoor_Clamp | 71929 | 71929 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_CI_uSMLRainwaterSiphonVertical_Coupling | 71685 | 71685 | 2026-05-18 | 2026-06-01 | 11 | handler_assign | confirm_note:stored_full
410_PF_CI_uTrapHorizontal_Clamp | 71930 | 71930 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_CI_xCombinationBranch88Degree_Coupling | 71680 | 71680 | 2026-05-15 | 2026-06-17 | 24 | handler_assign | confirm_note:stored_full
410_PF_CI_xDoubleBend88Degrees_Standard_Clamp | 71805 | 71805 | 2026-05-21 | 2026-05-26 | 4 | handler_assign | status_resolved
410_PF_CI_xDoubleBranch45_Clamp | 71931 | 71931 | 2026-05-29 | 2026-06-02 | 3 | handler_assign | confirm_note:stored_full
410_PF_CI_xDoubleBranch70Deg_Clamp | 71988 | 71988 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_CI_xDoubleBranch_Coupling | 71693 | 71693 | 2026-05-19 | 2026-05-28 | 8 | handler_assign | confirm_note:stored_full
410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress | 71989 | 71989 | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full
410_PF_CS_cEndCaps_Welded | 71990 | 71990 | 2026-05-29 | 2026-06-01 | 2 | handler_assign | status_resolved
410_PF_CS_eLongRadiusElbows_Welded | 71991 | 71991 | 2026-06-17 | 2026-08-25 | 50 | handler_assign | confirm_note:stored_full
410_PF_CS_eLongRadiusReturnBends_Welded | 71992 | 71992 | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full
410_PF_CS_eRadiusElbows_Welded | 71994 | 71994 | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full
410_PF_CS_eRadiusReturnBends_Welded | 73481 | 73481 | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full
410_PF_CS_fPlaneFlange_Flanged | 71996 | 71996 | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full
410_PF_CS_rConcentricReducers_Welded | 71997 | 71997 | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full
410_PF_CS_rConnector_MapressAndFemaleThread | 71998 | 71998 | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full
410_PF_CS_tTee_Welded | 73482 | 73482 | 2026-06-19 | 2026-09-16 | 64 | handler_assign | confirm_note:stored_full
410_PF_CS_uConnector_MapressAndFemaleThread | 71999 | 71999 | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full
410_PF_DI_cBellmouth_Flanged | 72000 | 72000 | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full
410_PF_DI_cBlind_Flanged | 72001 | 72001 | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full
410_PF_DI_cCap_KType | 72002 | 72002 | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full
410_PF_DI_cPlug_TType | 72003 | 72003 | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full
410_PF_DI_eBend_Flange | 72005 | 72005 | 2026-05-29 | 2026-06-17 | 14 | handler_assign | confirm_note:stored_full
410_PF_DI_eBend_Socket | 72006 | 72006 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_DI_eDuckfoodBend90Deg_Flanged | 72007 | 72007 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_DI_fFlange_RFType | 72008 | 72008 | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full
410_PF_DI_rFlangedCover | 72009 | 72009 | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full
410_PF_DI_rTapper_Flanged | 72012 | 72012 | 2026-05-29 | 2026-07-28 | 43 | handler_assign | confirm_note:stored_full
410_PF_DI_rTapper_Socket | 72013 | 72013 | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full
410_PF_DI_tDoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch | 72023 | 72023 | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full
410_PF_DI_tLevelInvertTee_Flanged | 72014 | 72014 | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full
410_PF_DI_tTee_Flanged | 72017 | 72017 | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full
410_PF_DI_tTee_Socket | 72018 | 72018 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_DI_tTee_SocketAndFlangedBranch | 72015 | 72015 | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full
410_PF_DI_tTeeSocketWithLevelInvertFlangedBranch | 72016 | 72016 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_DI_uAdaptorRestrained_Flanged | 72019 | 72019 | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full
410_PF_DI_uFlangeAdaptor | 72020 | 72020 | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full
410_PF_DI_uUnion_Socket | 72022 | 72022 | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full
410_PF_EPDM_mKonfixConnector_PushOnJoint | 72024 | 72024 | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full
410_PF_eSweptBendLong_Medium_Clamp | 72025 | 72025 | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full
410_PF_GA_mPTrapGMX_Standard | 72612 | 72612 | 2026-06-10 | 2026-07-29 | 36 | handler_assign | confirm_note:stored_full
410_PF_GS_cFrogFlap_Socket_GMX | 72035 | 72035 | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full
410_PF_GS_cSealingPlugsWithVentilationSlots_PushOnJoint | 72040 | 72040 | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full
410_PF_GS_eAngleBend_1PushShortSocket_GMX | 72041 | 72041 | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full
410_PF_GS_eAngleBend_1PushSocket_GMX | 72464 | 72464 | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full
410_PF_GS_eBasinConnector_1PushSocket_GMX | 72042 | 72042 | 2026-05-29 | 2026-06-04 | 5 | handler_assign | confirm_note:stored_full
410_PF_GS_eBend_1PushSocket_GMX | 72046 | 72046 | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full
410_PF_GS_eBend_NoSocket_GMX | 72048 | 72048 | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full
410_PF_GS_eBendWithCalm_1PushSocket_GMX | 72043 | 72043 | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full
410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX | 72049 | 72049 | 2026-06-17 | 2026-08-03 | 34 | handler_assign | confirm_note:stored_full
410_PF_GS_eReductionAngleBend_1PushSocket_GMX | 72051 | 72051 | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full
410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX | 72050 | 72050 | 2026-06-17 | 2026-07-08 | 16 | handler_assign | confirm_note:stored_full
410_PF_GS_mOptimisationPart_1PushSocket | 72053 | 72053 | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full
410_PF_GS_rAdapterConcentric_1PushSocket_GMX | 72077 | 72077 | 2026-05-29 | 2026-06-10 | 9 | handler_assign | confirm_note:stored_full
410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX | 72076 | 72076 | 2026-05-29 | 2026-08-19 | 59 | handler_assign | confirm_note:task_completed_closed
410_PF_GS_rAdapterEccentric_1PushSocket_GMX | 72078 | 72078 | 2026-05-29 | 2026-09-30 | 89 | handler_assign | confirm_note:stored_full
410_PF_GS_rConcentricOptimiser_1PushSocket_GMX | 72079 | 72079 | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full
410_PF_GS_rTransitiontoCastIron_PushSocket_GMX | 72080 | 72080 | 2026-05-29 | 2026-08-17 | 57 | handler_assign | confirm_note:stored_full
410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX | 72081 | 72081 | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full
410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX | 72083 | 72083 | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full
410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX | 72082 | 72082 | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full
410_PF_GS_tTeeBranches_2PushSocket_GMX | 72084 | 72084 | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full
410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX | 72085 | 72085 | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full
410_PF_GS_uBends_1PushSocket_GMX | 72086 | 72086 | 2026-06-01 | 2026-06-15 | 11 | handler_assign | confirm_note:stored_full
410_PF_GS_uGutterPipes_1PushSocket_GMX | 72087 | 72087 | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full
410_PF_GS_uGutterRound_SocketAndStandard | 72052 | 72052 | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full
410_PF_GS_uLongCleaningOpening_1PushSocket_GMX | 72088 | 72088 | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full
410_PF_GS_uLongCleaningOpening_NoSocket_GMX | 72090 | 72090 | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full
410_PF_GS_uLongUnion_1PushSocket_GMX | 72089 | 72089 | 2026-05-29 | 2026-07-07 | 28 | handler_assign | confirm_note:stored_full
410_PF_GS_uSpigottoPlastic_1PushSocket_GMX | 72091 | 72091 | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full
410_PF_GS_uTransitionSMLtoGMX_1PushSocket | 72092 | 72092 | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full
410_PF_GS_uTranstiontoCastIron_GMX | 72093 | 72093 | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full
410_PF_GS_uUnion_2PushSocket_GMX | 72095 | 72095 | 2026-05-29 | 2026-07-27 | 42 | handler_assign | confirm_note:stored_full
410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX | 72100 | 72100 | 2026-05-29 | 2026-07-27 | 42 | handler_assign | confirm_note:stored_full
410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX | 72101 | 72101 | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full
410_PF_HDPE_cProtectionCap | 72102 | 72102 | 2026-05-29 | 2026-07-14 | 33 | handler_assign | confirm_note:stored_full
410_PF_HDPE_cProtectionCapForPipeEnd_Standard | 72103 | 72103 | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full
410_PF_HDPE_cThreadedConnectorWithScrewCap | 72104 | 72104 | 2026-05-29 | 2026-07-14 | 33 | handler_assign | confirm_note:stored_full
410_PF_HDPE_eBend90Deg_Reducer_Welded | 72105 | 72105 | 2026-05-29 | 2026-07-15 | 34 | handler_assign | confirm_note:stored_full
410_PF_HDPE_eBend_Welded | 72106 | 72106 | 2026-06-02 | 2026-08-14 | 54 | handler_assign | confirm_note:stored_full
410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC | 72521 | 72521 | 2026-06-02 | 2026-07-15 | 32 | handler_assign | confirm_note:stored_full
410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC | 72524 | 72524 | 2026-06-02 | 2026-09-15 | 76 | handler_assign | confirm_note:stored_full
410_PF_HDPE_eScrewCap | 72526 | 72526 | 2026-06-16 | 2026-07-14 | 21 | handler_assign | confirm_note:stored_full
410_PF_HDPE_eSegmentBend_Welded | 72527 | 72527 | 2026-06-02 | 2026-08-14 | 54 | handler_assign | confirm_note:stored_full
410_PF_HDPE_fLooseFlange_Flanged | 72032 | 72032 | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC | 72529 | 72529 | 2026-06-02 | 2026-06-16 | 11 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mPTrap | 72614 | 72614 | 2026-06-10 | 2026-08-04 | 40 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded | 72531 | 72531 | 2026-06-03 | 2026-08-14 | 53 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mReducedRingSealSocket_Socket | 72547 | 72547 | 2026-06-03 | 2026-09-17 | 77 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mRunningTrap_Standard | 72532 | 72532 | 2026-06-03 | 2026-08-14 | 53 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mSoventFitting_Welded | 72533 | 72533 | 2026-06-03 | 2026-07-14 | 30 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mSTrap_Standard | 72537 | 72537 | 2026-06-03 | 2026-06-22 | 14 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mUniversalTrap_WithFlangeBushing | 72539 | 72539 | 2026-06-03 | 2026-06-19 | 13 | handler_assign | confirm_note:stored_full
410_PF_HDPE_mWasteManifold | 72541 | 72541 | 2026-06-03 | 2026-07-15 | 31 | handler_assign | confirm_note:stored_full
410_PF_HDPE_rAdaptorSocket_DN90xDN100 | 72542 | 72542 | 2026-06-03 | 2026-07-03 | 23 | handler_assign | confirm_note:stored_full
410_PF_HDPE_rCompressionJoint_MechanicalJoint | 72544 | 72544 | 2026-06-03 | 2026-09-17 | 77 | handler_assign | confirm_note:stored_full
410_PF_HDPE_rReducerAdaptor_MaleThreaded | 72557 | 72557 | 2026-06-10 | 2026-08-21 | 53 | handler_assign | confirm_note:stored_full
410_PF_HDPE_rReducer_Welded | 72546 | 72546 | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full
410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC | 72548 | 72548 | 2026-06-03 | 2026-07-03 | 23 | handler_assign | confirm_note:stored_full
410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded | 72549 | 72549 | 2026-06-03 | 2026-06-19 | 13 | handler_assign | confirm_note:stored_full
410_PF_HDPE_tDoubleConnectionBend90Deg_ForSleeve | 72528 | 72528 | 2026-06-02 | 2026-09-21 | 80 | handler_assign | confirm_note:stored_full
410_PF_HDPE_tDoubleConnectionBend90Deg_SlipJoint_VerticalForWallHungWC | 72530 | 72530 | 2026-06-02 | 2026-09-17 | 78 | handler_assign | confirm_note:stored_full
410_PF_HDPE_tLateralTee_Welded | 72550 | 72550 | 2026-06-10 | 2026-07-15 | 26 | handler_assign | confirm_note:stored_full
410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded | 72551 | 72551 | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded | 72552 | 72552 | 2026-06-03 | 2026-07-06 | 24 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded | 72553 | 72553 | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded | 72554 | 72554 | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint | 72556 | 72556 | 2026-06-03 | 2026-07-08 | 26 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uAdapterUnion_FemaleThreaded | 72555 | 72555 | 2026-06-03 | 2026-08-21 | 58 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uClampingConnector | 72558 | 72558 | 2026-06-10 | 2026-06-30 | 15 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uExpansion_Socket | 72559 | 72559 | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uFlangeAdapter_Standard | 72560 | 72560 | 2026-06-09 | 2026-09-17 | 73 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uFlangeBushing_Standard | 72561 | 72561 | 2026-06-09 | 2026-09-17 | 73 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uStraightAdapter_CompressionAndSpigot | 72605 | 72605 | 2026-06-10 | 2026-08-11 | 45 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uStraightAdapterHDPEToPVC_ButtFusionAndPushOnJoint | 72601 | 72601 | 2026-06-10 | 2026-07-28 | 35 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uStraightAdapterToCastIronPipe | 72596 | 72596 | 2026-06-09 | 2026-07-07 | 21 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard | 72606 | 72606 | 2026-06-10 | 2026-08-03 | 39 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uStraightConnector_ForFloorStandingWC | 72608 | 72608 | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uStraightConnectorForWC_ButtFusionAndPushOnJoint | 72607 | 72607 | 2026-06-10 | 2026-07-27 | 34 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uUnionConnection_WeldingJoints | 72610 | 72610 | 2026-06-10 | 2026-07-29 | 36 | handler_assign | confirm_note:stored_full
410_PF_HDPE_uUnion_FemaleThreadAndCompression | 72609 | 72609 | 2026-06-10 | 2026-08-12 | 46 | handler_assign | confirm_note:stored_full
410_PF_HDPE_xDoubleBrandFitting45Deg_Welded | 72611 | 72611 | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full
410_PF_PE_eBendForWandWC | 72618 | 72618 | 2026-06-10 | 2026-08-04 | 40 | handler_assign | confirm_note:stored_full
410_PF_PEXA_eElbow_QE | 74200 | 74200 | 2026-07-16 | 2026-07-16 | 1 | handler_assign | status_resolved
410_PF_PEXA_eHotBending_QE | 74583 | 74583 | 2026-07-17 | 2026-07-22 | 4 | handler_assign | confirm_note:stored_full
410_PF_PEXA_fEvolutionRing_QE | 74201 | 74201 | 2026-07-16 | 2026-07-16 | 1 | handler_assign | status_resolved
410_PF_PEXA_fRing_QE | 74199 | 74199 | 2026-07-16 | 2026-07-16 | 1 | handler_assign | status_resolved
410_PF_PEXA_rReducerAdaptor_MaleThreadedAndQE | 74610 | 74610 | 2026-07-21 | 2026-07-28 | 6 | handler_assign | confirm_note:stored_full
410_PF_PPMD_eBend_SocketAndSpigot_Silent | 72678 | 72678 | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full
410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_Silent | 72681 | 72681 | 2026-06-12 | 2026-08-13 | 45 | handler_assign | confirm_note:stored_full
410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_SilentPro | 72721 | 72721 | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full
410_PF_PPMD_mCornerBranch88Deg_SocketAndSpigot_SilentPro | 72723 | 72723 | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full
410_PF_PPMD_rReducerEccentric_SocketAndSpigot_Silent | 72700 | 72700 | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full
410_PF_PPMD_tBranchSweptEntry88Deg_SocketAndSpigot_Silent | 72672 | 72672 | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full
410_PF_PPMD_tDoubleConnectionBend90Deg_Extended_Silent | 72673 | 72673 | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full
410_PF_PPMD_uAccessPipe90DegWithRoundServiceOpening_SocketAndSpigot_SilentPro | 72730 | 72730 | 2026-06-17 | 2026-08-24 | 49 | handler_assign | confirm_note:stored_full
410_PF_PPMD_xDuctBranchSweptEntry88DegLeft_SocketAndSpigot_Silent | 72671 | 72671 | 2026-06-12 | 2026-07-29 | 34 | handler_assign | confirm_note:passed_audit
410_PF_PP_mOdorTrapForSinkHorizontal_Standard | 72692 | 72692 | 2026-06-12 | 2026-06-16 | 3 | handler_assign | status_resolved
410_PF_PP_mOdorTrapForSinkVerticalAndHorizontal_Standard | 72697 | 72697 | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full
410_PF_PP_mOdorTrapForSinkVertical_Standard | 72696 | 72696 | 2026-06-12 | 2026-06-17 | 4 | handler_assign | status_resolved
410_PF_PPMX_eElbow_SocketAndSpigot_SilentPro | 72720 | 72720 | 2026-06-16 | 2026-08-17 | 45 | handler_assign | confirm_note:stored_full
410_PF_PPMX_rReducerEccentric_SocketAndSpigot_SilentPro | 72725 | 72725 | 2026-06-17 | 2026-08-07 | 38 | handler_assign | confirm_note:stored_full
410_PF_PPMX_uSlipCoupling_PushOnJoint_SilentPro | 72731 | 72731 | 2026-06-17 | 2026-08-17 | 44 | handler_assign | confirm_note:stored_full
410_PF_PPMX_wParallelBrand45Deg_SocketAndSpigot_SilentPro | 72732 | 72732 | 2026-06-17 | 2026-08-24 | 49 | handler_assign | confirm_note:stored_full
410_PF_PPR_cEndCap_SocketFusion | 72638 | 72638 | 2026-06-10 | 2026-07-02 | 17 | handler_assign | confirm_note:stored_full
410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion | 72641 | 72641 | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full
410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion | 72645 | 72645 | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full
410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion | 72646 | 72646 | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full
410_PF_PPR_eElbow90Deg_MaleThreadAndSocketFusion | 72651 | 72651 | 2026-06-10 | 2026-07-30 | 37 | handler_assign | confirm_note:stored_full
410_PF_PPR_eElbow_SocketFusion | 72647 | 72647 | 2026-06-10 | 2026-07-28 | 35 | handler_assign | confirm_note:stored_full
410_PF_PPR_mCoupling_FemaleThreadAndSocketFusion | 72648 | 72648 | 2026-06-10 | 2026-08-21 | 53 | handler_assign | confirm_note:stored_full
410_PF_PPR_rReducing_SocketFusion | 72656 | 72656 | 2026-06-10 | 2026-07-02 | 17 | handler_assign | confirm_note:stored_full
410_PF_PPR_tTee_FemaleThreadedAndSocketFusion | 72661 | 72661 | 2026-06-10 | 2026-06-24 | 11 | handler_assign | confirm_note:stored_full
410_PF_PPR_tTee_MaleThreadedAndSocketFusion | 72664 | 72664 | 2026-06-10 | 2026-06-25 | 12 | handler_assign | confirm_note:stored_full
410_PF_PPR_tTee_SocketFusion | 72665 | 72665 | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full
410_PF_PPR_uCoupling_FemaleThreadAndSocketFusion | 72666 | 72666 | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full
410_PF_PPR_uCoupling_MaleThreadAndSocketFusion | 72667 | 72667 | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full
410_PF_PPR_uUnion_BushSocketFusion | 72668 | 72668 | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full
410_PF_PPR_uUnion_SocketFusion | 72669 | 72669 | 2026-06-25 | 2026-06-30 | 4 | handler_assign | status_resolved
410_PF_PP_tBranch_SocketSpigot_Silent | 72679 | 72679 | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full
410_PF_PP_uAccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent | 72674 | 72674 | 2026-06-12 | 2026-07-14 | 23 | handler_assign | confirm_note:stored_full
410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_Silent | 72682 | 72682 | 2026-06-12 | 2026-08-13 | 45 | handler_assign | confirm_note:stored_full
410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent | 72689 | 72689 | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full
410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg | 72726 | 72726 | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full
410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot | 72728 | 72728 | 2026-06-17 | 2026-07-28 | 30 | handler_assign | confirm_note:stored_full
410_PF_SilentPro_tTeeBranch_SocketSpigot | 72729 | 72729 | 2026-06-25 | 2026-07-27 | 23 | handler_assign | confirm_note:stored_full
410_PF_SilentPro_xCrossDoubleBranchFitting88DegSweptEntry_SocketAndSpigot | 72733 | 72733 | 2026-06-17 | 2026-07-13 | 19 | handler_assign | confirm_note:stored_full
410_PF_SS_cCap_Mapress | 72737 | 72737 | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full
410_PF_SS_cDrainplugWithScrewedPlug | 72739 | 72739 | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full
410_PF_SS_cSocketPlug | 72740 | 72740 | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full
410_PF_SS_cSocketPlugWithClamp | 72742 | 72742 | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full
410_PF_SS_cVentCowl_Standard | 72744 | 72744 | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full
410_PF_SS_eBend_15_1Socket | 72755 | 72755 | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full
410_PF_SS_eBend_30_1Socket | 72757 | 72757 | 2026-06-17 | 2026-08-10 | 39 | handler_assign | confirm_note:stored_full
410_PF_SS_eBend45Degrees_SocketAndStandard | 72747 | 72747 | 2026-06-17 | 2026-07-22 | 26 | handler_assign | confirm_note:stored_full
410_PF_SS_eBend87_Socket | 72750 | 72750 | 2026-06-17 | 2026-08-14 | 43 | handler_assign | confirm_note:stored_full
410_PF_SS_eBendWith250mmOblong_Clamp | 72754 | 72754 | 2026-06-17 | 2026-08-17 | 44 | handler_assign | confirm_note:stored_full
410_PF_SS_eElbow90DegAdaptor_FemaleThreadedAndPlainEndAndMapress | 72759 | 72759 | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full
410_PF_SS_eElbow90DegAdaptor_MaleThreadAndMapress | 72761 | 72761 | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full
410_PF_SS_eElbow90Deg_FemaleThreadAndMapress | 72763 | 72763 | 2026-06-17 | 2026-06-23 | 5 | handler_assign | status_resolved
410_PF_SS_eElbow90DegTapConnector_Mapress | 72762 | 72762 | 2026-06-17 | 2026-07-22 | 26 | handler_assign | confirm_note:stored_full
410_PF_SS_eElbow_Mapress | 72766 | 72766 | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full
410_PF_SS_eElbowTapConector90Degree_Mapress | 72764 | 72764 | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full
410_PF_SS_eLongBend_1Socket | 72767 | 72767 | 2026-06-17 | 2026-07-03 | 13 | handler_assign | confirm_note:stored_full
410_PF_SS_ePTrap_SocketAndSpigot | 72768 | 72768 | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full
410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset | 72776 | 72776 | 2026-06-17 | 2026-08-14 | 43 | handler_assign | confirm_note:stored_full
410_PF_SS_mCornerElbow90Deg_Mapress | 72777 | 72777 | 2026-06-17 | 2026-06-23 | 5 | handler_assign | status_resolved
410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress | 72779 | 72779 | 2026-06-17 | 2026-08-04 | 35 | handler_assign | confirm_note:task_completed_closed
410_PF_SS_rConcentricIncreaserCoupling_Standard | 72782 | 72782 | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full
410_PF_SS_rConnectorExternalThreadSpigot | 72783 | 72783 | 2026-06-17 | 2026-07-28 | 30 | handler_assign | confirm_note:stored_full
410_PF_SS_rConnectorInternal_ThreadSpigot | 72784 | 72784 | 2026-06-17 | 2026-07-01 | 11 | handler_assign | confirm_note:stored_full
410_PF_SS_rConnector_Socket | 72798 | 72798 | 2026-06-17 | 2026-07-30 | 32 | handler_assign | confirm_note:stored_full
410_PF_SS_rConnector_SocketAndThreaded | 72800 | 72800 | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full
410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot | 72802 | 72802 | 2026-06-17 | 2026-09-25 | 73 | handler_assign | confirm_note:stored_full
410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong | 72807 | 72807 | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full
410_PF_SS_rReducerWithPlainEnd_Mapress | 72808 | 72808 | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full
410_PF_SS_rTransition_SocketAndFemaleThreaded | 72811 | 72811 | 2026-06-17 | 2026-07-03 | 13 | handler_assign | confirm_note:stored_full
410_PF_SS_rTransition_SocketAndFlanged | 72797 | 72797 | 2026-06-17 | 2026-09-30 | 76 | handler_assign | confirm_note:stored_full
410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot | 72813 | 72813 | 2026-06-18 | 2026-07-03 | 12 | handler_assign | confirm_note:stored_full
410_PF_SS_tPieceReducer_Mapress | 72829 | 72829 | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full
410_PF_SS_tReducingDoubleBranch45_Socket | 72821 | 72821 | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full
410_PF_SS_tReducingSingleBranch45Degree_Socket | 72822 | 72822 | 2026-06-23 | 2026-08-24 | 45 | handler_assign | confirm_note:stored_full
410_PF_SS_tReducingSingleBranch87Deg_Socket | 72823 | 72823 | 2026-06-23 | 2026-08-24 | 45 | handler_assign | confirm_note:stored_full
410_PF_SS_tSingleBranch45_SocketAndSpigot | 72824 | 72824 | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full
410_PF_SS_tSweptBranch87Deg_SocketAndSpigot | 72825 | 72825 | 2026-06-23 | 2026-08-07 | 34 | handler_assign | confirm_note:stored_full
410_PF_SS_tTeePiece_FemaleThreadedAndMapress | 72826 | 72826 | 2026-06-23 | 2026-08-21 | 44 | handler_assign | confirm_note:stored_full
410_PF_SS_tTeePiece_MaleThreadedAndMapress | 72827 | 72827 | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full
410_PF_SS_tTeePiece_Mapress | 72828 | 72828 | 2026-06-23 | 2026-07-27 | 25 | handler_assign | confirm_note:stored_full
410_PF_SS_tTPiece_Mapress_Equal | 72820 | 72820 | 2026-06-23 | 2026-08-06 | 33 | handler_assign | confirm_note:stored_full
410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress | 72830 | 72830 | 2026-06-23 | 2026-07-27 | 25 | handler_assign | confirm_note:stored_full
410_PF_SS_uAdaptorUnion_MaleThreadAndMapress | 72831 | 72831 | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full
410_PF_SS_uAdaptor_WithFemaleThreadAndMapress | 72833 | 72833 | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full
410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress | 72834 | 72834 | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full
410_PF_SS_uAdaptor_WithMaleThreadAndMapress | 72835 | 72835 | 2026-06-23 | 2026-07-17 | 19 | handler_assign | confirm_note:stored_full
410_PF_SS_uAdaptorWithPlainEnd_MaleThreadAndMapress | 72836 | 72836 | 2026-06-23 | 2026-08-18 | 41 | handler_assign | confirm_note:stored_full
410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress | 72832 | 72832 | 2026-06-23 | 2026-09-21 | 65 | handler_assign | confirm_note:stored_full
410_PF_SS_uAxialExpansion_PressingSockets | 72837 | 72837 | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full
410_PF_SS_uBulkhead_Welded | 72838 | 72838 | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full
410_PF_SS_uConnectionWithPlainEnd_FlangedAndMapress | 72840 | 72840 | 2026-06-23 | 2026-08-13 | 38 | handler_assign | confirm_note:stored_full
410_PF_SS_uConnectionWithPlainEnd_FlangedAndWelded | 72839 | 72839 | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full
410_PF_SS_uConnector_FlangedAndSpigot | 72841 | 72841 | 2026-06-23 | 2026-08-13 | 38 | handler_assign | confirm_note:stored_full
410_PF_SS_uConnector_SocketAndThreaded | 72855 | 72855 | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full
410_PF_SS_uCoupling_Mapress | 72856 | 72856 | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full
410_PF_SS_uExpansionSocket | 72857 | 72857 | 2026-06-23 | 2026-07-22 | 22 | handler_assign | confirm_note:stored_full
410_PF_SS_uPeakPressure_Standard | 72858 | 72858 | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full
410_PF_SS_uRapid_Coupling | 72781 | 72781 | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full
410_PF_SS_uRatStop_SocketAndSpigot | 72859 | 72859 | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full
410_PF_SS_uRepairCoupling_Socket | 72860 | 72860 | 2026-06-23 | 2026-08-03 | 30 | handler_assign | confirm_note:stored_full
410_PF_SS_uSocketClamp_Special | 72861 | 72861 | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full
410_PF_SS_uSocketClamp_Twopiece | 72863 | 72863 | 2026-06-23 | 2026-07-15 | 17 | handler_assign | confirm_note:stored_full
410_PF_SS_uStraightCoupling_Socket | 72864 | 72864 | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full
410_PF_SS_uUnion_Coupling | 72735 | 72735 | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full
410_PF_SS_uUnion_Mapress | 72865 | 72865 | 2026-06-23 | 2026-06-30 | 6 | handler_assign | status_resolved
410_PF_SS_wCleaningPipes | 72867 | 72867 | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full
410_PF_SS_xCornerBranch87Deg_SocketAndSpigot | 72868 | 72868 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full
410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot | 72869 | 72869 | 2026-06-25 | 2026-07-14 | 14 | handler_assign | confirm_note:stored_full
410_PF_SS_xDoubleBranch87_Socket | 72870 | 72870 | 2026-06-25 | 2026-07-15 | 15 | handler_assign | confirm_note:stored_full
410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot | 72871 | 72871 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full
410_PF_ST_SanpressDoubleWallPane_Threaded_DN15 | 72872 | 72872 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full
410_PF_UPVC_cCap_FemaleThreaded | 72875 | 72875 | 2026-06-25 | 2026-07-30 | 26 | handler_assign | confirm_note:stored_full
410_PF_UPVC_cCap_Socket | 72878 | 72878 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full
410_PF_UPVC_eBend90Deg_Socket | 72879 | 72879 | 2026-06-25 | 2026-07-30 | 26 | handler_assign | confirm_note:stored_full
410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded | 72880 | 72880 | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full
410_PF_UPVC_eElbow90Deg_FemaleThreaded | 72881 | 72881 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full
410_PF_UPVC_eElbow_Socket | 72882 | 72882 | 2026-06-25 | 2026-08-10 | 33 | handler_assign | confirm_note:stored_full
410_PF_UPVC_eReducerElbow_Socket | 72883 | 72883 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full
410_PF_UPVC_eShortBend90Deg_Socket | 72884 | 72884 | 2026-06-25 | 2026-08-10 | 33 | handler_assign | confirm_note:stored_full
410_PF_UPVC_rBushReducing_Socket | 72885 | 72885 | 2026-06-30 | 2026-08-07 | 29 | handler_assign | confirm_note:stored_full
410_PF_UPVC_rLongBushReducing_Socket | 72886 | 72886 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full
410_PF_UPVC_rShortBushReducing_Socket | 72887 | 72887 | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full
410_PF_UPVC_tLateralTee90Deg_Socket | 72888 | 72888 | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full
410_PF_UPVC_tTee90Deg_FemaleThreaded | 72889 | 72889 | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full
410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded | 72890 | 72890 | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full
410_PF_UPVC_tTee_Socket | 72891 | 72891 | 2026-06-23 | 2026-07-30 | 28 | handler_assign | confirm_note:stored_full
410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded | 72892 | 72892 | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full
410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced | 72893 | 72893 | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full
410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded | 72894 | 72894 | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full
410_PF_UPVC_uCoupling_Socket | 72895 | 72895 | 2026-06-17 | 2026-07-02 | 12 | handler_assign | confirm_note:stored_full
410_PF_UPVC_uInspectionPort_Glue | 72896 | 72896 | 2026-06-23 | 2026-07-13 | 15 | handler_assign | confirm_note:stored_full
410_PF_UPVC_uSiphon_Socket | 72897 | 72897 | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full
410_PF_UPVC_xCross_Socket | 72898 | 72898 | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full
410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron | 74119 | 74119 | 2026-07-27 | 2026-08-28 | 25 | handler_assign | confirm_note:stored_full
410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic | 74120 | 74120 | 2026-07-27 | 2026-09-21 | 41 | handler_assign | confirm_note:stored_full
410_PX_BasementFloorDrain_Vertical_Coupling_CastIron | 74121 | 74121 | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full
410_PX_BoxGutters_Vertical_Coupling_StainlessSteel | 74124 | 74124 | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full
410_PX_DoppelPumpStationPowerlift_ACO | 74125 | 74125 | 2026-07-27 | 2026-08-28 | 25 | handler_assign | confirm_note:stored_full
410_PX_DrainageChannel_B125 | 74126 | 74126 | 2026-07-27 | 2026-07-30 | 4 | handler_assign | status_resolved
410_PX_DuofixElementForSinkAGB | 74127 | 74127 | 2026-07-27 | 2026-07-30 | 4 | handler_assign | status_resolved
410_PX_DuofixElementForWallHungWC | 74371 | 74371 | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full
410_PX_DuofixElementForWallHungWC_BarrierFree | 74128 | 74128 | 2026-07-28 | 2026-08-14 | 14 | handler_assign | confirm_note:stored_full
410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern | 74129 | 74129 | 2026-07-28 | 2026-08-14 | 14 | handler_assign | confirm_note:stored_full
410_PX_DuofixElementForWashbasin | 74373 | 74373 | 2026-07-28 | 2026-08-17 | 15 | handler_assign | confirm_note:stored_full
410_PX_DuofixElementForWashBasin_BarrierFree | 74374 | 74374 | 2026-07-28 | 2026-09-28 | 45 | handler_assign | confirm_note:stored_full
410_PX_DuofixForShower&Bathtub | 74376 | 74376 | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full
410_PX_DuofixForShower&Bathtub_WallFittingAP | 74377 | 74377 | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full
410_PX_DuofixForUrinal_Universal | 74379 | 74379 | 2026-07-30 | 2026-09-14 | 33 | handler_assign | confirm_note:stored_full
410_PX_DuofixSigmaToilet12cm_BarrierFree | 74380 | 74380 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_DuofixTraverseForStandaloneFaucetKitchenSink | 74381 | 74381 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_FaucetWithFlexibleHose | 74382 | 74382 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel | 74383 | 74383 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel | 74384 | 74384 | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full
410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron | 74385 | 74385 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel | 74386 | 74386 | 2026-07-30 | 2026-08-28 | 22 | handler_assign | confirm_note:stored_full
410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron | 74387 | 74387 | 2026-07-30 | 2026-09-28 | 43 | handler_assign | confirm_note:stored_full
410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard | 74388 | 74388 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_FloorDrain_Horizontal_Coupling_CastIron | 74389 | 74389 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_FloorDrain_Horizontal_Coupling_Plastic | 74390 | 74390 | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full
410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel | 74391 | 74391 | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full
410_PX_FloorDrain_Vertical_Coupling_Plastic | 74394 | 74394 | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full
410_PX_FloorDrain_Vertical_Coupling_StainlessSteel | 74395 | 74395 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_FloorDrainWithExtensionPieces_Horizontal_Inclination | 74202 | 74202 | 2026-07-16 | 2026-07-21 | 4 | handler_assign | status_resolved
410_PX_GardenWater_Kemper | 74396 | 74396 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_GreaseDisposalPoint | 74397 | 74397 | 2026-07-30 | 2026-08-28 | 22 | handler_assign | confirm_note:stored_full
410_PX_GullyGrating | 74398 | 74398 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_GutterWithOutLet_Vertical | 74740 | 74740 | 2026-07-22 | 2026-07-28 | 5 | handler_assign | confirm_note:stored_full
410_PX_HorizontalFloorDrain | 74399 | 74399 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_InspectionShaft_OnePipe_Nosystem | 74400 | 74400 | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved
410_PX_InspectionShaft_TwoPipe_Nosystem | 74401 | 74401 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_KitchenTap | 74402 | 74402 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_ManholeAdjustingUnits_Round_NoSystem | 74403 | 74403 | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved
410_PX_ManholeBase_CastIn | 74404 | 74404 | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved
410_PX_ManholeChamberUnits_Round_NoSystem | 74406 | 74406 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_ManholeCoverSlabs_Eccentrical_NoSystem | 74407 | 74407 | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full
410_PX_ManholeReducingSlabs_Eccentrical_NoSystem | 74408 | 74408 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_Manhole_Round | 74410 | 74410 | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full
410_PX_PressureReliefManhole | 74205 | 74205 | 2026-07-16 | 2026-07-23 | 6 | handler_assign | confirm_note:stored_full
410_PX_ReusedRainWaterTank | 74412 | 74412 | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full
410_PX_RoadGully | 74413 | 74413 | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full
410_PX_SumpPit_NoSystem | 74415 | 74415 | 2026-07-30 | 2026-09-15 | 34 | handler_assign | confirm_note:stored_full
410_PX_TapWithMaleHose_Threaded_DN15 | 74417 | 74417 | 2026-07-30 | 2026-09-15 | 34 | handler_assign | confirm_note:stored_full
410_PX_WaterTap | 74419 | 74419 | 2026-07-30 | 2026-08-20 | 16 | handler_assign | confirm_note:stored_full
410_SE_Conlit150U_NoSystem | 74977 | 74977 | 2026-08-04 | 2026-09-09 | 27 | handler_assign | confirm_note:stored_full
410_SE_ConlitFireProtectionSleeve_NoSystem | 74978 | 74978 | 2026-08-04 | 2026-09-10 | 28 | handler_assign | confirm_note:stored_full
410_SE_CoverBox | 74979 | 74979 | 2026-08-04 | 2026-09-10 | 28 | handler_assign | confirm_note:stored_full
410_SE_FireCollar_Horizontal | 72037 | 72037 | 2026-05-29 | 2026-09-15 | 78 | handler_assign | confirm_note:stored_full
410_SE_PenetrationSealing | 74203 | 74203 | 2026-07-16 | 2026-07-22 | 5 | handler_assign | confirm_note:stored_full
410_SE_RainStorageTank | 74204 | 74204 | 2026-07-16 | 2026-07-22 | 5 | handler_assign | confirm_note:stored_full
410_SE_SoakawayTank | 74571 | 74571 | 2026-07-16 | 2026-07-17 | 2 | handler_assign | status_resolved
420_ME_AirCoolHeatPump_MonoBlock | 75194 | 75194 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_AirCurtain_StandingType | 75195 | 75195 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_AirCurtain_WallMounted | 75196 | 75196 | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full
420_ME_AirCurtain_WallMounted_Standard | 75197 | 75197 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_AirHeater_Top | 75198 | 75198 | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full
420_ME_AirSoureHeatPump | 75199 | 75199 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_BufferHeatingTank | 75200 | 75200 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_BufferTank_Custom | 75201 | 75201 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_BufferTank_Standard | 75202 | 75202 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_BufferTank_StorathermHeat1Coil&WithInsulation | 75204 | 75204 | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved
420_ME_BufferTank_StorathermHeat2Coil&WithInsulation | 75206 | 75206 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_BufferTank_StorathermHeatCombi1Coil&WithInsulation | 75207 | 75207 | 2026-08-13 | 2026-09-04 | 17 | handler_assign | confirm_note:stored_full
420_ME_BufferTank_StorathermHeatCombi2Coil&WithInsulation | 75208 | 75208 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_BufferTank_StorathermHeatFlange&WithoutInsulation | 75210 | 75210 | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full
420_ME_BufferTank_StorathermHeat&WithInsulation | 75203 | 75203 | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full
420_ME_CeilingPanel_Standard | 75211 | 75211 | 2026-08-13 | 2026-09-23 | 30 | handler_assign | confirm_note:stored_full
420_ME_CentrifugalPumpWithElectricMotor_Horizontal | 75212 | 75212 | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full
420_ME_ColdWaterTank | 75213 | 75213 | 2026-08-13 | 2026-09-04 | 17 | handler_assign | confirm_note:stored_full
420_ME_CompressedAirTank | 75214 | 75214 | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full
420_ME_ControlValveGroup | 75215 | 75215 | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full
420_ME_Convector_FloorSurface | 75216 | 75216 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_EnergyDistributor_6Pairs | 75217 | 75217 | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full
420_ME_EnergyDistributor_8Pairs | 75218 | 75218 | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved
420_ME_ExpansionTank_FloorStand | 75219 | 75219 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
420_ME_ExpansionTank_Standard | 75220 | 75220 | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved
420_ME_FacadeHeating_Standard | 75222 | 75222 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
420_ME_Fancoilunit_UnderfloorTrench_KathermNK | 75223 | 75223 | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved
420_ME_Fancoilunit_UnderfloorTrench_KathermQE_NoSystem | 75224 | 75224 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
420_ME_Fancoilunit_UnderfloorTrench_KathermQK | 75225 | 75225 | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved
420_ME_Fancoilunit_UnderfloorTrench_KathermQKnano | 75226 | 75226 | 2026-08-13 | 2026-09-29 | 34 | handler_assign | confirm_note:stored_full
420_ME_Fancoilunit_UnderfloorTrench_KathermQL_1Connector | 75227 | 75227 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_Fancoilunit_UnderfloorTrench_KathermQL_2Connector | 75228 | 75228 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_Fancoilunit_UnderfloorTrench_KathermQL_3Connector | 75229 | 75229 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
420_ME_Fancoilunit_UnderfloorTrench_KathermQL_4Connector | 75230 | 75230 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_Fancoilunit_UnderfloorTrench_KathermQL_5Connector | 75231 | 75231 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
420_ME_FWTransfer | 75221 | 75221 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_HeatExchangerFreeCooling_Flange | 75232 | 75232 | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved
420_ME_HeatExchangerTank_VerticalPump | 75193 | 75193 | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full
420_ME_HeatingCoolingSails_Ceiling | 75235 | 75235 | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full
420_ME_HeatPump_PackageDrooftop_48And50UA&UH | 75233 | 75233 | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full
420_ME_HeatTransferStation_Custom | 75234 | 75234 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
420_ME_HomeStation_DHK | 75236 | 75236 | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full
420_ME_HomeStation_GHK | 75237 | 75237 | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full
420_ME_HomeStation_GHKFBH | 75238 | 75238 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
420_ME_HotWaterBoiler | 75239 | 75239 | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_Standard | 75240 | 75240 | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil | 75296 | 75296 | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaCompactWallHung | 75298 | 75298 | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaEEC | 75299 | 75299 | 2026-08-14 | 2026-09-21 | 27 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaHeatPump1Coil | 75300 | 75300 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaHeatPump2Coil | 75301 | 75301 | 2026-08-14 | 2026-09-04 | 16 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaLoad1Flange | 75303 | 75303 | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaLoad2Flange | 75304 | 75304 | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaLoad3Flange | 75305 | 75305 | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaLoad4Flange | 75306 | 75306 | 2026-08-14 | 2026-09-04 | 16 | handler_assign | confirm_note:stored_full
420_ME_HotWaterStorageTank_StorathermAquaSolar | 75307 | 75307 | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full
420_ME_HotWaterTank | 75309 | 75309 | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full
420_ME_HydraulicSeparator_Flanged | 75310 | 75310 | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full
420_ME_HydraulicSeparator_Threaded | 75311 | 75311 | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full
420_ME_KTS_ThermoBox | 75312 | 75312 | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full
420_ME_LargeBecomixVessel_Vertical | 75313 | 75313 | 2026-08-14 | 2026-09-17 | 25 | handler_assign | confirm_note:stored_full
420_ME_MixedBecomixVessel_Vertical | 75316 | 75316 | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full
420_ME_MultiOutdoorUnit_SingleFan | 75317 | 75317 | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full
420_ME_Pump_WaterJetPump_3Way_Flanged | 75319 | 75319 | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full
420_ME_Pump_WaterJetPump_3Way_Threaded | 75320 | 75320 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
420_ME_QuantumW500_DoubleCapacitor | 75321 | 75321 | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Basic | 75322 | 75322 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_BasicR | 75323 | 75323 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Casteo | 75324 | 75324 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Credohalf | 75325 | 75325 | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Credohalfflat | 74719 | 74719 | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Credohalfround | 75326 | 75326 | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Credoplus | 74718 | 74718 | 2026-07-22 | 2026-09-22 | 45 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_DecorArteLine | 74717 | 74717 | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved
420_ME_RadiatorBathroom_WallMounted_DecorArtePlan | 74716 | 74716 | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved
420_ME_RadiatorBathroom_WallMounted_DecorArtePureHorizontal | 74715 | 74715 | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_DecorArtePureVertical | 74714 | 74714 | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Diveo | 74713 | 74713 | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Duett | 74712 | 74712 | 2026-07-22 | 2026-09-23 | 46 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Elveo_NoSystem | 74711 | 74711 | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved
420_ME_RadiatorBathroom_WallMounted_Fineo | 74710 | 74710 | 2026-07-22 | 2026-09-10 | 37 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Geneocircle | 74709 | 74709 | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Geneoquadris | 74708 | 74708 | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Icaro | 74707 | 74707 | 2026-07-22 | 2026-08-13 | 17 | handler_assign | status_resolved
420_ME_RadiatorBathroom_WallMounted_Ideos | 74706 | 74706 | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Ineo | 74705 | 74705 | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Leveo | 74704 | 74704 | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Pateo | 74703 | 74703 | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Pio1layer | 74702 | 74702 | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Pio2layer | 74664 | 74664 | 2026-07-21 | 2026-09-11 | 39 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_PioPlus | 74663 | 74663 | 2026-07-21 | 2026-09-11 | 39 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Rubeo | 74662 | 74662 | 2026-07-21 | 2026-08-20 | 23 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Signo | 74661 | 74661 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_Tabeo | 74660 | 74660 | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full
420_ME_RadiatorBathroom_WallMounted_TabeoV | 74659 | 74659 | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full
420_ME_RadiatorElectricPanel_WallMounted_xThermPlanHorizontal_NoSystem | 74657 | 74657 | 2026-07-21 | 2026-08-19 | 22 | handler_assign | confirm_note:stored_full
420_ME_RadiatorElectricPanel_WallMounted_xThermProfileHorizontal_NoSystem | 74655 | 74655 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanK | 74654 | 74654 | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKHygiene | 74653 | 74653 | 2026-07-21 | 2026-09-09 | 37 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKReplacement | 74652 | 74652 | 2026-07-21 | 2026-09-10 | 38 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV | 74651 | 74651 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVHygiene | 74650 | 74650 | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlus | 74649 | 74649 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlusHygiene | 74648 | 74648 | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileK | 74647 | 74647 | 2026-07-21 | 2026-08-20 | 23 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKHygiene | 74646 | 74646 | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:passed_audit
420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKReplacement | 74645 | 74645 | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:passed_audit
420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileV | 74644 | 74644 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVHygiene | 74643 | 74643 | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlus | 74642 | 74642 | 2026-07-22 | 2026-08-25 | 25 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlusHygiene | 74641 | 74641 | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_VerteoPlan | 73848 | 73848 | 2026-06-25 | 2026-08-20 | 41 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_VerteoProfile | 73847 | 73847 | 2026-06-25 | 2026-08-20 | 41 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanK | 73846 | 73846 | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanV | 73845 | 73845 | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanVPlus | 73844 | 73844 | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileK | 73843 | 73843 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileV | 73842 | 73842 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileVPlus | 73841 | 73841 | 2026-06-25 | 2026-08-31 | 48 | handler_assign | confirm_note:stored_full
420_ME_RadiatorHeatingWall_WallMounted_Horizontal | 73840 | 73840 | 2026-06-25 | 2026-07-07 | 9 | handler_assign | confirm_note:stored_full
420_ME_RadiatorHeatingWall_WallMounted_ValveHorizontal | 73839 | 73839 | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full
420_ME_RadiatorHeatingWall_WallMounted_ValveVertical | 73838 | 73838 | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full
420_ME_RadiatorHeatingWall_WallMounted_Vertical | 73837 | 73837 | 2026-06-25 | 2026-09-03 | 51 | handler_assign | confirm_note:stored_full
420_ME_Radiator_WallMounted_Standard | 73836 | 73836 | 2026-06-25 | 2026-09-08 | 54 | handler_assign | confirm_note:stored_full
420_ME_RectangularTubeManifold_8Connection | 73835 | 73835 | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full
420_ME_RoomClimateModule_StandingType | 75552 | 75552 | 2026-08-27 | 2026-08-27 | 1 | handler_assign | status_resolved
420_ME_SinglePassTubeHeatExchanger_Horizontal | 73834 | 73834 | 2026-06-25 | 2026-09-03 | 51 | handler_assign | confirm_note:stored_full
420_ME_WaterHeater_Vertical | 73833 | 73833 | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full
420_PA_6WayValve_Thread | 73832 | 73832 | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full
420_PA_AirReleaseValve_Flanged_Standard | 73831 | 73831 | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full
420_PA_AirReleaseValve_Thread_Standard | 73830 | 73830 | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full
420_PA_AirValve_Thread | 73829 | 73829 | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full
420_PA_BalancingValve_Flanged | 73828 | 73828 | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full
420_PA_BalancingValve_Flanged_Standard | 73827 | 73827 | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full
420_PA_BalancingValve_Thread | 73826 | 73826 | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full
420_PA_BalancingValve_Thread_Standard | 73825 | 73825 | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full
420_PA_BallValve3Way_LPort | 73824 | 73824 | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full
420_PA_BallValve_Flanged | 73822 | 73822 | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full
420_PA_BallValve_Flanged_LeverStandard | 73821 | 73821 | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved
420_PA_BallValve_Flanged_WheelStandard | 73820 | 73820 | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved
420_PA_BallValve_FullBore | 73819 | 73819 | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full
420_PA_BallValve_Threaded | 73551 | 73551 | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full
420_PA_BallValve_Thread_LeverStandard | 73553 | 73553 | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full
420_PA_BallValve_Thread_WheelStandard | 73552 | 73552 | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full
420_PA_BasketStrainerValve_Thread_Standard | 73549 | 73549 | 2026-06-19 | 2026-06-24 | 4 | handler_assign | status_resolved
420_PA_ButterflyValve_Flanged_GearStandard | 73547 | 73547 | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full
420_PA_ButterflyValve_Flanged_Handle | 73818 | 73818 | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full
420_PA_ButterflyValve_Flanged_LeverStandard | 73546 | 73546 | 2026-06-19 | 2026-08-05 | 34 | handler_assign | confirm_note:stored_full
420_PA_ButterflyValveHandwheel_Flanged | 73548 | 73548 | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full
420_PA_ButterflyvalveMotor_Flanged | 73543 | 73543 | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full
420_PA_ButterflyValve_Thread_LeverStandard | 73544 | 73544 | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full
420_PA_CapValve_Thread | 73542 | 73542 | 2026-06-19 | 2026-07-10 | 16 | handler_assign | confirm_note:stored_full
420_PA_CheckValveWithThermometer_Thread | 73541 | 73541 | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full
420_PA_DifferentialPressureControlValve_Thread | 73540 | 73540 | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full
420_PA_DifferentialPressureGauge_Standard | 73539 | 73539 | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full
420_PA_DifferentialPressureSensor | 73537 | 73537 | 2026-06-19 | 2026-09-11 | 61 | handler_assign | confirm_note:stored_full
420_PA_DifferentialPressureSensor_Standard | 73536 | 73536 | 2026-06-19 | 2026-08-14 | 41 | handler_assign | confirm_note:stored_full
420_PA_DiscCheckValve_Flanged_Standard | 73535 | 73535 | 2026-06-19 | 2026-09-07 | 57 | handler_assign | confirm_note:stored_full
420_PA_DrainValve_Thread_Standard | 73534 | 73534 | 2026-06-19 | 2026-09-28 | 72 | handler_assign | confirm_note:stored_full
420_PA_ExpansionJoint_Flanged | 73532 | 73532 | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full
420_PA_ExpansionJoint_Threaded | 73531 | 73531 | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full
420_PA_ExpansionJoint_Weld | 73530 | 73530 | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full
420_PA_FillAndDrainBallValve_Threaded | 73529 | 73529 | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full
420_PA_FilterValve_Flanged | 73528 | 73528 | 2026-06-19 | 2026-09-21 | 67 | handler_assign | confirm_note:stored_full
420_PA_FilterValve_Thread | 73527 | 73527 | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full
420_PA_FlexibleConnection_Flanged_Standard | 73526 | 73526 | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full
420_PA_FlexibleConnection_Thread_Standard | 73146 | 73146 | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full
420_PA_FlowSensor | 73145 | 73145 | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full
420_PA_FlowSensor_Flanged_Standard | 73144 | 73144 | 2026-06-08 | 2026-08-10 | 46 | handler_assign | confirm_note:stored_full
420_PA_FlowSensor_Thread_Standard | 73143 | 73143 | 2026-06-08 | 2026-09-10 | 69 | handler_assign | confirm_note:stored_full
420_PA_GateValve_Flanged_Standard | 73141 | 73141 | 2026-06-08 | 2026-09-14 | 71 | handler_assign | confirm_note:stored_full
420_PA_GateValve_Thread | 73140 | 73140 | 2026-06-08 | 2026-09-08 | 67 | handler_assign | confirm_note:stored_full
420_PA_GateValve_Thread_Standard | 73139 | 73139 | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full
420_PA_GlobeValve_Flanged_Standard | 73136 | 73136 | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full
420_PA_GlobeValve_Thread | 73135 | 73135 | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full
420_PA_GlobeValve_Thread_Standard | 73134 | 73134 | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full
420_PA_HeatingBallValve_Thread | 73130 | 73130 | 2026-06-08 | 2026-09-03 | 64 | handler_assign | confirm_note:stored_full
420_PA_HeatMeter_Flanged | 73133 | 73133 | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full
420_PA_LiftCheckValve_Flanged_Standard | 73129 | 73129 | 2026-06-08 | 2026-09-21 | 76 | handler_assign | confirm_note:stored_full
420_PA_LiftCheckValve_Thread_Standard | 73128 | 73128 | 2026-06-08 | 2026-09-11 | 70 | handler_assign | confirm_note:stored_full
420_PA_ManifoldConnection_Thread | 73525 | 73525 | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full
420_PA_MotorizedBallValve_Flanged_Standard | 73127 | 73127 | 2026-06-08 | 2026-08-25 | 57 | handler_assign | confirm_note:stored_full
420_PA_MotorizedButterflyValve_Flanged_Standard | 73125 | 73125 | 2026-06-08 | 2026-07-17 | 30 | handler_assign | confirm_note:stored_full
420_PA_MotorizedGateValve_Flanged_Standard | 73124 | 73124 | 2026-06-08 | 2026-07-29 | 38 | handler_assign | confirm_note:stored_full
420_PA_MotorizedGateValve_Thread_Standard | 73123 | 73123 | 2026-06-08 | 2026-07-31 | 40 | handler_assign | confirm_note:stored_full
420_PA_MotorizedGlobeValve_Flanged_Standard | 73122 | 73122 | 2026-06-08 | 2026-07-31 | 40 | handler_assign | confirm_note:stored_full
420_PA_MotorizedGlobeValve_Thread_Standard | 73121 | 73121 | 2026-06-08 | 2026-07-24 | 35 | handler_assign | confirm_note:stored_full
420_PA_MotorizedGloboBallValve_Thread | 76206 | 76206 | 2026-09-25 | 2026-09-30 | 4 | handler_assign | confirm_note:stored_full
420_PA_MotorizedThreeWayValve_Flanged_Standard | 73120 | 73120 | 2026-06-08 | 2026-09-16 | 73 | handler_assign | confirm_note:stored_full
420_PA_MotorizedThreeWayvalve_Thread_Standard | 73119 | 73119 | 2026-06-12 | 2026-09-21 | 72 | handler_assign | confirm_note:stored_full
420_PA_PICCV2WayValve_Thread | 73117 | 73117 | 2026-06-12 | 2026-07-24 | 31 | handler_assign | confirm_note:stored_full
420_PA_PICCV3WayValve_Thread | 73116 | 73116 | 2026-06-12 | 2026-07-24 | 31 | handler_assign | confirm_note:stored_full
420_PA_PICVValve_Thread | 73524 | 73524 | 2026-06-19 | 2026-08-07 | 36 | handler_assign | confirm_note:stored_full
420_PA_PneumaticGlobeControlValve_Flanged | 73113 | 73113 | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full
420_PA_PneumaticGlobeControlValve_Thread | 73112 | 73112 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
420_PA_PressureGauge | 73111 | 73111 | 2026-07-13 | 2026-09-07 | 41 | handler_assign | confirm_note:stored_full
420_PA_PressureGauge_2Connection | 73110 | 73110 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
420_PA_PressureGauge_Standard | 73109 | 73109 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
420_PA_PressureIndependentControlValveCompact_Threaded | 73108 | 73108 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
420_PA_PressureIndependentControlValve_Flanged | 73107 | 73107 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
420_PA_PressureIndependentControlValve_Threaded | 73106 | 73106 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
420_PA_PressureReducingValveWithGauge_Thread | 73105 | 73105 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
420_PA_PressureSensor_Standard | 72694 | 72694 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
420_PA_RadiatorLockshield_Thread | 72693 | 72693 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
420_PA_RadiatorShutOffValveAngle_Thread | 72691 | 72691 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
420_PA_RadiatorShutOffValveStraight_Thread | 72690 | 72690 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
420_PA_RadiatorThermostatic2PointAngleValve_Thread | 72688 | 72688 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
420_PA_RadiatorThermostaticAngleValve_Thread | 72687 | 72687 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
420_PA_RegulatingValve_Threaded | 72662 | 72662 | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full
420_PA_RegulatingValve_Thread_Standard | 72663 | 72663 | 2026-06-01 | 2026-08-11 | 52 | handler_assign | confirm_note:stored_full
420_PA_SafetyReliefValveConer_Thread | 72660 | 72660 | 2026-06-01 | 2026-08-11 | 52 | handler_assign | confirm_note:stored_full
420_PA_SafetyReliefValveCorner_Flanged | 72659 | 72659 | 2026-06-01 | 2026-08-12 | 53 | handler_assign | confirm_note:stored_full
420_PA_SafetyReliefValveStraight_Flanged | 72658 | 72658 | 2026-06-01 | 2026-09-15 | 77 | handler_assign | confirm_note:stored_full
420_PA_SafetyValveCorner_Flanged_Standard | 72657 | 72657 | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full
420_PA_SafetyValveCorner_Thread_Standard | 72655 | 72655 | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full
420_PA_ShutOffValveWithSafetyFunction_Flanged | 73521 | 73521 | 2026-06-25 | 2026-07-16 | 16 | handler_assign | confirm_note:stored_full
420_PA_SixWayMotorisedControlValve_Threaded | 73517 | 73517 | 2026-06-25 | 2026-08-13 | 36 | handler_assign | confirm_note:stored_full
420_PA_SmartForEnergyManagement_Flanged | 73516 | 73516 | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full
420_PA_SmartForEnergyManagement_Thread | 73515 | 73515 | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full
420_PA_SpringCheckValve_Flanged_Standard | 72654 | 72654 | 2026-06-01 | 2026-07-13 | 31 | handler_assign | confirm_note:stored_full
420_PA_StraightThermostaticValvesForRadiator_Thread | 75469 | 75469 | 2026-08-21 | 2026-08-24 | 2 | handler_assign | confirm_note:stored_full
420_PA_SwingcheckValve_Flanged | 72650 | 72650 | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full
420_PA_SwingcheckValve_Threaded | 72604 | 72604 | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full
420_PA_SwingCheckValve_Thread_Standard | 72652 | 72652 | 2026-06-01 | 2026-06-16 | 12 | handler_assign | confirm_note:stored_full
420_PA_TemperatureGauge_Standard | 72603 | 72603 | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full
420_PA_TemperatureRegulatorValve_SelfOperated | 73514 | 73514 | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full
420_PA_TemperatureSensor | 72602 | 72602 | 2026-06-01 | 2026-07-03 | 25 | handler_assign | confirm_note:stored_full
420_PA_Thermometer | 72600 | 72600 | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full
420_PA_Thermometergauge | 72599 | 72599 | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full
420_PA_ThreeWayMotorisedControlValve_Flanged | 73513 | 73513 | 2026-06-25 | 2026-07-27 | 23 | handler_assign | confirm_note:stored_full
420_PA_ThreeWayvalve_Flanged_Standard | 72598 | 72598 | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full
420_PA_ThreeWayValve_Threaded | 72597 | 72597 | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full
420_PA_WaferCheckValve_Flanged_Standard | 72595 | 72595 | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full
420_PA_WaterMeter_Flanged | 72594 | 72594 | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full
420_PA_WaterMeter_Flanged_Standard | 72593 | 72593 | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full
420_PA_WaterMeter_Threaded | 72591 | 72591 | 2026-06-01 | 2026-06-19 | 15 | handler_assign | confirm_note:stored_full
420_PA_WaterMeter_Threaded_Standard | 73511 | 73511 | 2026-07-08 | 2026-08-17 | 29 | handler_assign | confirm_note:stored_full
420_PA_YStrainer_Flanged | 72588 | 72588 | 2026-06-01 | 2026-08-12 | 53 | handler_assign | confirm_note:stored_full
420_PA_YStrainer_Thread | 72587 | 72587 | 2026-06-01 | 2026-07-27 | 41 | handler_assign | confirm_note:stored_full
420_PA_YStrainerValve_Flanged_Standard | 72590 | 72590 | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full
420_PA_YStrainerValve_Thread_Standard | 72589 | 72589 | 2026-06-01 | 2026-07-27 | 41 | handler_assign | confirm_note:stored_full
420_PF_Brass_tThreeWayEqualTee_Compression | 72195 | 72195 | 2026-05-28 | 2026-06-19 | 17 | handler_assign | confirm_note:stored_full
420_PF_CO_cCap_Soldered | 72196 | 72196 | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full
420_PF_CO_eElbow | 72177 | 72177 | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full
420_PF_CO_eElbow_Soldered | 72198 | 72198 | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full
420_PF_CO_rReducer_Soldered | 73509 | 73509 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
420_PF_CO_tTee_Soldered | 72586 | 72586 | 2026-06-01 | 2026-07-15 | 33 | handler_assign | confirm_note:stored_full
420_PF_CO_uUnion_Soldered | 72585 | 72585 | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full
420_PF_CO_xCross_Soldered | 72584 | 72584 | 2026-06-01 | 2026-07-08 | 28 | handler_assign | confirm_note:stored_full
420_PF_CS_cCap_Mapress | 72176 | 72176 | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full
420_PF_CS_cCap_Welded | 72583 | 72583 | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full
420_PF_CS_eElbow_SlipJoinAndMapress | 72174 | 72174 | 2026-05-28 | 2026-09-10 | 76 | handler_assign | confirm_note:stored_full
420_PF_CS_eElbow_Welded | 72582 | 72582 | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full
420_PF_CS_fConnectionFlanged_Welded | 72204 | 72204 | 2026-05-28 | 2026-06-04 | 6 | handler_assign | confirm_note:stored_full
420_PF_CS_rReducer_Welded | 72203 | 72203 | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full
420_PF_CS_rTransition_MapressAndSlipJoin | 72169 | 72169 | 2026-05-28 | 2026-07-17 | 37 | handler_assign | confirm_note:stored_full
420_PF_CS_sTap_Welded | 72202 | 72202 | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full
420_PF_CS_tTee_MapressAndSlipJoin | 72170 | 72170 | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full
420_PF_CS_tTee_Welded | 72201 | 72201 | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full
420_PF_CS_uSocketAdaptor_MapressAndSlipJoin | 72172 | 72172 | 2026-05-28 | 2026-07-23 | 41 | handler_assign | confirm_note:stored_full
420_PF_CS_uSocketFlangeAdaptor_SlipJoinAndMapress | 72171 | 72171 | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full
420_PF_CS_uUnion_MapressAndSlipJoin | 72168 | 72168 | 2026-05-28 | 2026-07-22 | 40 | handler_assign | confirm_note:stored_full
420_PF_CS_uUnion_Welded | 72200 | 72200 | 2026-05-28 | 2026-06-01 | 3 | handler_assign | status_resolved
420_PF_CS_xCross_Mapress | 72175 | 72175 | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full
420_PF_CS_xCross_Welded | 72199 | 72199 | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full
420_PF_PE_eElbow_Welded | 72167 | 72167 | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full
420_PF_SS_eBendByFormedMachine_Mapress | 75516 | 75516 | 2026-08-25 | 2026-09-07 | 10 | handler_assign | confirm_note:stored_full
420_SE_DistrictHeatingTransferStation | 76139 | 76139 | 2026-09-21 | 2026-09-23 | 3 | handler_assign | confirm_note:stored_full
420_SE_PenetrationSealing_Outside | 76138 | 76138 | 2026-09-21 | 2026-09-23 | 3 | handler_assign | confirm_note:stored_full
430_AT_AirDiffuser_Standard | 73173 | 73173 | 2026-06-10 | 2026-07-30 | 37 | handler_assign | confirm_note:stored_full
430_AT_CircularDiscValves_LVS_Return | 73174 | 73174 | 2026-06-10 | 2026-08-13 | 47 | handler_assign | confirm_note:stored_full
430_AT_CircularDiscValves_ZLVS_Supply | 73329 | 73329 | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full
430_AT_CrossflowCFE_TPP_NoSystem | 73241 | 73241 | 2026-06-12 | 2026-07-08 | 19 | handler_assign | confirm_note:stored_full
430_AT_DeflectorHood_Roof_Rectangular_Exhaust | 73243 | 73243 | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full
430_AT_DeflectorHood_Roof_Rectangular_FreshAirIntake | 73330 | 73330 | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full
430_AT_DeflectorHood_Roof_Round_Exhaust | 73331 | 73331 | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Return | 73337 | 73337 | 2026-06-15 | 2026-07-29 | 33 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Supply | 73338 | 73338 | 2026-06-15 | 2026-07-10 | 20 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Return | 73340 | 73340 | 2026-06-15 | 2026-07-29 | 33 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Supply | 73339 | 73339 | 2026-06-15 | 2026-09-28 | 76 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Return | 73341 | 73341 | 2026-06-15 | 2026-08-04 | 37 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Supply | 73342 | 73342 | 2026-06-15 | 2026-08-03 | 36 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Return | 73343 | 73343 | 2026-06-15 | 2026-09-23 | 73 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Supply | 73345 | 73345 | 2026-06-15 | 2026-09-18 | 70 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Return | 73562 | 73562 | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Supply | 73563 | 73563 | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Exhaust | 73564 | 73564 | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Supply | 73565 | 73565 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Return | 73346 | 73346 | 2026-06-15 | 2026-07-09 | 19 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Supply | 73347 | 73347 | 2026-06-15 | 2026-07-09 | 19 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Return | 73348 | 73348 | 2026-06-15 | 2026-08-13 | 44 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Supply | 73349 | 73349 | 2026-06-15 | 2026-07-03 | 15 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Return | 73566 | 73566 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Supply | 73567 | 73567 | 2026-06-25 | 2026-07-15 | 15 | handler_assign | confirm_note:stored_full
430_AT_Diffusers_Floor_FBK_Return | 73333 | 73333 | 2026-06-15 | 2026-08-10 | 41 | handler_assign | confirm_note:stored_full
430_AT_Diffusers_Floor_FBK_Supply | 73334 | 73334 | 2026-06-15 | 2026-08-24 | 51 | handler_assign | confirm_note:stored_full
430_AT_Diffusers_Wall_CHM_Supply | 73335 | 73335 | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full
430_AT_Diffusers_Wall_CHS_Supply | 73336 | 73336 | 2026-06-15 | 2026-07-10 | 20 | handler_assign | confirm_note:stored_full
430_AT_DiscValvesSTVA_Return | 73568 | 73568 | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full
430_AT_DiscValvesSTVZ_Supply | 73569 | 73569 | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full
430_AT_DisplacementFlowDiffusers_Wall_QLF_Supply | 73570 | 73570 | 2026-06-25 | 2026-07-03 | 7 | handler_assign | status_resolved
430_AT_DisplacementFlowDiffusers_Wall_QLV_Supply | 73571 | 73571 | 2026-06-25 | 2026-07-03 | 7 | handler_assign | status_resolved
430_AT_DoubleSlot_CeilingHorizontal_1ConnectionSymmetrical_Withbox | 73572 | 73572 | 2026-06-25 | 2026-09-11 | 57 | handler_assign | confirm_note:stored_full
430_AT_EggCrateAirGrill_HorizontalCeiling_Rectangular_Return | 73573 | 73573 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
430_AT_ExternalRainProtectionGrill_Wall_Round | 73574 | 73574 | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full
430_AT_FloorDisplacementDiffuser_QB | 74777 | 74777 | 2026-07-23 | 2026-07-28 | 4 | handler_assign | confirm_note:stored_full
430_AT_Grilles_Wall_Rectangular_TRS_FreshAirIntake | 73575 | 73575 | 2026-06-22 | 2026-07-09 | 14 | handler_assign | confirm_note:stored_full
430_AT_Grilles_Wall_Rectangular_TRS_Return | 73576 | 73576 | 2026-06-22 | 2026-09-23 | 68 | handler_assign | confirm_note:stored_full
430_AT_Grilles_Wall_Rectangular_TRS_Supply | 73577 | 73577 | 2026-06-22 | 2026-09-21 | 66 | handler_assign | confirm_note:stored_full
430_AT_GrilleWeatherProtectionExhaust_Wall_Rectangular_WGALWidthSubdivided | 73580 | 73580 | 2026-06-22 | 2026-07-23 | 24 | handler_assign | confirm_note:stored_full
430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Exhaust | 73631 | 73631 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdividedExhaust | 73578 | 73578 | 2026-06-22 | 2026-07-16 | 19 | handler_assign | confirm_note:stored_full
430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Supply | 73632 | 73632 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
430_AT_InspectionOpenings_RecDuctHorizontal_Rectangular | 73633 | 73633 | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full
430_AT_InspectionOpenings_RoundDuctHorizontal_Oval | 73634 | 73634 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
430_AT_JetDiffuser_Round_Standard | 73635 | 73635 | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full
430_AT_LamellarHood_Roof_Rectangular_Exhaust | 73636 | 73636 | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full
430_AT_LamellarHood_Roof_Rectangular_FreshAirIntake | 73637 | 73637 | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full
430_AT_LinearDisplacementDiffuser_FloorStand_LBQ | 74776 | 74776 | 2026-07-23 | 2026-07-29 | 5 | handler_assign | confirm_note:stored_full
430_AT_LourveCover_Roof | 73638 | 73638 | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full
430_AT_Louvre_Standard | 73639 | 73639 | 2026-06-24 | 2026-08-04 | 30 | handler_assign | confirm_note:stored_full
430_AT_NodeFlushChannelPlenumOpposedHorizontalFlow_Supply | 76100 | 76100 | 2026-09-18 | 2026-09-22 | 3 | handler_assign | confirm_note:stored_full
430_AT_NozzlesElectricActuator_DUK_E_Exhaust | 73640 | 73640 | 2026-06-25 | 2026-09-11 | 57 | handler_assign | confirm_note:stored_full
430_AT_NozzlesElectricActuator_DUK_E_Supply | 73641 | 73641 | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full
430_AT_Nozzles_Exhaust | 74170 | 74170 | 2026-07-09 | 2026-07-28 | 14 | handler_assign | confirm_note:stored_full
430_AT_Nozzles_Return | 74171 | 74171 | 2026-07-09 | 2026-07-28 | 14 | handler_assign | confirm_note:stored_full
430_AT_Nozzles_Supply | 74172 | 74172 | 2026-07-08 | 2026-07-28 | 15 | handler_assign | confirm_note:stored_full
430_AT_Nozzle_Standard | 74173 | 74173 | 2026-07-08 | 2026-07-28 | 15 | handler_assign | confirm_note:stored_full
430_AT_RoofHood | 74174 | 74174 | 2026-07-06 | 2026-07-17 | 10 | handler_assign | confirm_note:stored_full
430_AT_RoundLouver_Standard | 74175 | 74175 | 2026-07-06 | 2026-07-17 | 10 | handler_assign | confirm_note:stored_full
430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Return | 73898 | 73898 | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full
430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Supply | 73899 | 73899 | 2026-06-25 | 2026-07-16 | 16 | handler_assign | confirm_note:stored_full
430_AT_SchakoDisplacementDiffusersSupply_FloorMounted_WQARU | 76095 | 76095 | 2026-09-17 | 2026-09-22 | 4 | handler_assign | confirm_note:stored_full
430_AT_SchakoDisplacementDiffusers_Wall_WQA_Supply | 74169 | 74169 | 2026-07-09 | 2026-07-29 | 15 | handler_assign | confirm_note:stored_full
430_AT_SlotDiffuserDSXXXLP2A_Return | 74168 | 74168 | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full
430_AT_SlotDiffuserDSXXXLP2A_Supply | 74167 | 74167 | 2026-07-09 | 2026-08-07 | 22 | handler_assign | confirm_note:stored_full
430_AT_SmokeExtractionAndVentilationHood_Roof_Rectangular_Exhaust | 74166 | 74166 | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Return | 74156 | 74156 | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Supply | 74155 | 74155 | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Return | 74163 | 74163 | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Supply | 74162 | 74162 | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingHorizontal_Round_Supply | 74160 | 74160 | 2026-07-13 | 2026-08-10 | 21 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Return | 74159 | 74159 | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Supply | 74158 | 74158 | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingVertical_Rectangular_Return | 74157 | 74157 | 2026-07-06 | 2026-07-27 | 16 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingVertical_Round_Return | 74107 | 74107 | 2026-07-03 | 2026-09-23 | 59 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_CeilingVertical_Round_Supply | 74106 | 74106 | 2026-07-03 | 2026-09-21 | 57 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Return | 74105 | 74105 | 2026-07-03 | 2026-07-22 | 14 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Supply | 74104 | 74104 | 2026-07-03 | 2026-09-29 | 63 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Return | 74165 | 74165 | 2026-07-13 | 2026-07-31 | 15 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Supply | 74164 | 74164 | 2026-07-13 | 2026-07-31 | 15 | handler_assign | confirm_note:stored_full
430_AT_SwirlDiffuser_VerticalCeiling_Rectangular_Supply | 74103 | 74103 | 2026-07-03 | 2026-07-22 | 14 | handler_assign | confirm_note:stored_full
430_AT_TextileDiffuser_Supply | 74102 | 74102 | 2026-07-03 | 2026-08-18 | 33 | handler_assign | confirm_note:stored_full
430_AT_VentilationGrilles_DoorWall_AGS_Exhaust | 74101 | 74101 | 2026-07-03 | 2026-08-17 | 32 | handler_assign | confirm_note:stored_full
430_AT_VentilationGrilles_DoorWall_AGS_Supply | 74100 | 74100 | 2026-07-03 | 2026-09-18 | 56 | handler_assign | confirm_note:stored_full
430_AT_VentilationGrilles_Rectangular_Standard | 74099 | 74099 | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full
430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Return | 74098 | 74098 | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full
430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Supply | 74097 | 74097 | 2026-07-03 | 2026-09-15 | 53 | handler_assign | confirm_note:stored_full
430_AT_VentilationGrilles_RoundDuct_Standard | 74096 | 74096 | 2026-07-03 | 2026-09-18 | 56 | handler_assign | confirm_note:stored_full
430_DA_AirtightLouverDamper | 72055 | 72055 | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full
430_DA_CircularSilencers_CA_050 | 72056 | 72056 | 2026-05-25 | 2026-07-10 | 35 | handler_assign | confirm_note:stored_full
430_DA_CircularSilencers_CA_100 | 72057 | 72057 | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full
430_DA_CircularSilencers_CB | 72058 | 72058 | 2026-05-25 | 2026-07-13 | 36 | handler_assign | confirm_note:stored_full
430_DA_CircularSilencers_CS | 72060 | 72060 | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full
430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowEN | 72061 | 72061 | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full
430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowENEx | 72062 | 72062 | 2026-05-25 | 2026-07-06 | 31 | handler_assign | confirm_note:stored_full
430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRN | 72063 | 72063 | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full
430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRNEx | 72064 | 72064 | 2026-05-25 | 2026-07-09 | 34 | handler_assign | confirm_note:stored_full
430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFC | 72066 | 72066 | 2026-05-25 | 2026-09-18 | 85 | handler_assign | confirm_note:stored_full
430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFL | 72065 | 72065 | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full
430_DA_FireDampers_CommercialKitchens_KA_EU | 72069 | 72069 | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full
430_DA_FireDampers_FireProtectionValve_FV_EU | 72070 | 72070 | 2026-05-25 | 2026-07-23 | 44 | handler_assign | confirm_note:stored_full
430_DA_FireDampersForCeiling_KU_K30 | 72068 | 72068 | 2026-05-25 | 2026-07-08 | 33 | handler_assign | confirm_note:stored_full
430_DA_FireInsulationSheets_Fitting_Promat_L90 | 72071 | 72071 | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full
430_DA_FireInsulationSheets_Promat_L90 | 72072 | 72072 | 2026-05-26 | 2026-06-19 | 19 | handler_assign | confirm_note:stored_full
430_DA_FireProtectionDamper_Round_FLIVE | 72073 | 72073 | 2026-05-26 | 2026-07-13 | 35 | handler_assign | confirm_note:stored_full
430_DA_FlexibleConnection_Rectangular | 72074 | 72074 | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full
430_DA_FlexibleConnection_Round | 73071 | 73071 | 2026-06-08 | 2026-06-30 | 17 | handler_assign | confirm_note:stored_full
430_DA_FlowAdjustmentDampers | 72751 | 72751 | 2026-06-02 | 2026-07-07 | 26 | handler_assign | confirm_note:stored_full
430_DA_IntumescentDamper_OverflowGrill_NoSystem | 72753 | 72753 | 2026-06-02 | 2026-07-15 | 32 | handler_assign | confirm_note:stored_full
430_DA_MultileafDamperRec_LowLeakage | 72819 | 72819 | 2026-06-02 | 2026-07-02 | 23 | handler_assign | confirm_note:stored_full
430_DA_NonReturnValves | 72851 | 72851 | 2026-06-03 | 2026-07-08 | 26 | handler_assign | confirm_note:stored_full
430_DA_PressureOverflowElements | 72067 | 72067 | 2026-05-26 | 2026-08-31 | 70 | handler_assign | confirm_note:stored_full
430_DA_PressureReliefDamper_Rectangular_Standard_NoSystem | 72853 | 72853 | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full
430_DA_RecFireDamperMechanism_FK2EU | 73076 | 73076 | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full
430_DA_RecFireDampers_FKEU | 72854 | 72854 | 2026-06-03 | 2026-09-16 | 76 | handler_assign | confirm_note:stored_full
430_DA_RoundFireDampers_FKREU | 72876 | 72876 | 2026-06-03 | 2026-07-27 | 39 | handler_assign | confirm_note:stored_full
430_DA_RoundFireDampers_FKRS_EU | 72877 | 72877 | 2026-06-03 | 2026-09-14 | 74 | handler_assign | confirm_note:stored_full
430_DA_SchakoConstantVolumeFlowControl_Round_ConstantFlowVLV | 72760 | 72760 | 2026-06-02 | 2026-07-03 | 24 | handler_assign | confirm_note:stored_full
430_DA_SchakoSilencer_Round_RS | 72745 | 72745 | 2026-06-02 | 2026-07-07 | 26 | handler_assign | confirm_note:stored_full
430_DA_ShutOffDevices_AK | 72734 | 72734 | 2026-06-02 | 2026-09-25 | 84 | handler_assign | confirm_note:stored_full
430_DA_ShutOffDevices_AKEx | 72736 | 72736 | 2026-06-02 | 2026-07-01 | 22 | handler_assign | confirm_note:stored_full
430_DA_ShutOffDevices_AKK | 72738 | 72738 | 2026-06-02 | 2026-09-16 | 77 | handler_assign | confirm_note:stored_full
430_DA_Silencer_Rectangular_Standard | 72743 | 72743 | 2026-06-02 | 2026-09-03 | 68 | handler_assign | confirm_note:stored_full
430_DA_Silencer_Round_Standard | 72741 | 72741 | 2026-06-02 | 2026-07-03 | 24 | handler_assign | confirm_note:stored_full
430_DA_SilencersVAV_Rectangular_TS | 72746 | 72746 | 2026-06-02 | 2026-06-03 | 2 | handler_assign | status_resolved
430_DA_SilencersVAV_Rectangular_TX | 72748 | 72748 | 2026-06-02 | 2026-07-27 | 40 | handler_assign | confirm_note:stored_full
430_DA_SmokeControlDamper_EKEU | 72756 | 72756 | 2026-06-02 | 2026-06-23 | 16 | handler_assign | confirm_note:stored_full
430_DA_SmokeControlDamper_EKJZ | 72758 | 72758 | 2026-06-02 | 2026-07-27 | 40 | handler_assign | confirm_note:stored_full
430_DA_SmokeDetectorinDucts_RMO3D | 72803 | 72803 | 2026-06-02 | 2026-09-25 | 84 | handler_assign | confirm_note:stored_full
430_DA_SmokeDetectorinDucts_RMOVSD | 72804 | 72804 | 2026-06-02 | 2026-09-14 | 75 | handler_assign | confirm_note:stored_full
430_DA_SmokeProtectionDamper_JZRS | 72899 | 72899 | 2026-06-03 | 2026-08-21 | 58 | handler_assign | confirm_note:stored_full
430_DA_TunnelDampers_JF | 72917 | 72917 | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full
430_DA_VariableAirVolume_Rectangular_MQTH | 72919 | 72919 | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full
430_DA_VariableAirVolume_Round_MQTH | 72920 | 72920 | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTASilenzio | 72931 | 72931 | 2026-06-04 | 2026-09-14 | 73 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVA | 72932 | 72932 | 2026-06-04 | 2026-07-08 | 25 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVJ | 72933 | 72933 | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVM | 72934 | 72934 | 2026-06-04 | 2026-08-05 | 45 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVT | 72935 | 72935 | 2026-06-04 | 2026-06-30 | 19 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVZ | 72937 | 72937 | 2026-06-04 | 2026-09-24 | 81 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTZSilenzio | 72938 | 72938 | 2026-06-04 | 2026-09-16 | 75 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Round_VarycontrolTVLK | 72939 | 72939 | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Round_VaryControlTVREX | 72940 | 72940 | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_VaryControl_Round_LVC | 73069 | 73069 | 2026-06-08 | 2026-09-09 | 68 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_VaryControl_Round_TVR | 73070 | 73070 | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full
430_DA_VariableVolumeFlowControl_Varycontrol_Round_TVRK | 73072 | 73072 | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full
430_DA_VolumeFlowRateMeasuringUnits_VME | 73073 | 73073 | 2026-06-08 | 2026-07-22 | 33 | handler_assign | confirm_note:stored_full
430_DA_VolumeFlowRateMeasuringUnits_VMLK | 73074 | 73074 | 2026-06-08 | 2026-06-23 | 12 | handler_assign | confirm_note:stored_full
430_DA_VolumeFlowRateMeasuringUnits_VMR | 73075 | 73075 | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full
430_DA_VolumeFlowRateMeasuringUnits_VMRK | 73077 | 73077 | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full
430_DF_GS_cBoden_Flanged | 71867 | 71867 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
430_DF_GS_cCapEnd_Spigot_Round | 71868 | 71868 | 2026-05-18 | 2026-06-02 | 12 | handler_assign | confirm_note:stored_full
430_DF_GS_eBogen_Flanged | 71869 | 71869 | 2026-05-18 | 2026-09-18 | 90 | handler_assign | confirm_note:stored_full
430_DF_GS_eEckbogen_Flanged | 71870 | 71870 | 2026-05-18 | 2026-07-09 | 39 | handler_assign | confirm_note:stored_full
430_DF_GS_eRoundElbow_Spigot | 71871 | 71871 | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved
430_DF_GS_eTransitionElbow_Flanged | 71872 | 71872 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
430_DF_GS_rEtage_Flanged | 71873 | 71873 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
430_DF_GS_rReducer_Spigot_Round | 71874 | 71874 | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved
430_DF_GS_rUbergang_Flanged | 71875 | 71875 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
430_DF_GS_rUbergangRechteckRund_Flanged_SlipJoint | 71876 | 71876 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
430_DF_GS_sRoundTaps_Spigot | 71877 | 71877 | 2026-05-18 | 2026-06-04 | 14 | handler_assign | confirm_note:stored_full
430_DF_GS_sUbergangsstutzen_Flanged | 71866 | 71866 | 2026-05-18 | 2026-09-18 | 90 | handler_assign | confirm_note:stored_full
430_DF_GS_tTee_Spigot_Round | 71860 | 71860 | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved
430_DF_GS_tTStuck_Flanged | 71861 | 71861 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
430_DF_GS_uCoupling_Spigot_Round | 71862 | 71862 | 2026-05-18 | 2026-06-05 | 15 | handler_assign | confirm_note:stored_full
430_DF_GS_uUnion_Flanged | 71863 | 71863 | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full
430_DF_GS_wHosenStuck_Flanged | 71864 | 71864 | 2026-05-18 | 2026-06-19 | 25 | handler_assign | confirm_note:stored_full
430_DF_GS_xKreuzstuck_Flanged | 71865 | 71865 | 2026-05-18 | 2026-06-19 | 25 | handler_assign | confirm_note:stored_full
430_ME_AHU_BSF_Standard | 74491 | 74491 | 2026-07-14 | 2026-08-14 | 24 | handler_assign | confirm_note:stored_full
430_ME_AirCompressors_Standard | 74538 | 74538 | 2026-07-15 | 2026-08-14 | 23 | handler_assign | confirm_note:stored_full
430_ME_AirHandingUnit_RectangularLeftConnection_CeilingStand | 74539 | 74539 | 2026-07-15 | 2026-09-17 | 47 | handler_assign | confirm_note:stored_full
430_ME_AirHandingUnit_RectangularRightConnection_CeilingStand | 74540 | 74540 | 2026-07-15 | 2026-09-18 | 48 | handler_assign | confirm_note:stored_full
430_ME_AirHandingUnit_RoundConnection_CeilingStand | 74552 | 74552 | 2026-07-15 | 2026-09-29 | 55 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_2LayerForKitchen_FloorStand | 75781 | 75781 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_CeilingStand_1LayerFlachSeries | 75778 | 75778 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_Floor_Single_Aubenluft | 75748 | 75748 | 2026-09-07 | 2026-09-25 | 15 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_FloorStand | 75782 | 75782 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_FloorStand_2LayerCompactSeries | 75780 | 75780 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_Geniox29H | 75783 | 75783 | 2026-09-09 | 2026-09-17 | 7 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnits_1Layer | 74577 | 74577 | 2026-07-17 | 2026-08-14 | 21 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnits_2Layer | 74592 | 74592 | 2026-07-20 | 2026-09-07 | 36 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnits_CF | 74585 | 74585 | 2026-07-17 | 2026-09-07 | 37 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_Single_Abluft | 75141 | 75141 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnit_Single_Fortluft | 75747 | 75747 | 2026-09-07 | 2026-09-25 | 15 | handler_assign | confirm_note:stored_full
430_ME_AirHandlingUnits_PHE | 74586 | 74586 | 2026-07-17 | 2026-09-16 | 44 | handler_assign | confirm_note:stored_full
430_ME_AxialWindowFan_Rectangular | 75784 | 75784 | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full
430_ME_CentrifugalDuctMountedFan | 75785 | 75785 | 2026-09-09 | 2026-09-24 | 12 | handler_assign | confirm_note:stored_full
430_ME_ChemicalMachine | 75786 | 75786 | 2026-09-09 | 2026-09-22 | 10 | handler_assign | confirm_note:stored_full
430_ME_CrossFlowFans_NoSystem | 75787 | 75787 | 2026-09-09 | 2026-09-21 | 9 | handler_assign | confirm_note:stored_full
430_ME_DiesselTank_Becomix | 75788 | 75788 | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full
430_ME_ExpansionTank_BottomConnection | 75791 | 75791 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_Fan_Axial | 75793 | 75793 | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full
430_ME_Fan_Roof_Exhaust | 75794 | 75794 | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full
430_ME_FansForAggressiveAir | 75792 | 75792 | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full
430_ME_Fan_WallMounted | 75796 | 75796 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_FilterFanCoilUnit | 75798 | 75798 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_FlushMountedFan_BackConnection_SilentECO | 75799 | 75799 | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full
430_ME_FlushMountedFan_TopConnection_SilentECO | 75800 | 75800 | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full
430_ME_GloveBox | 75801 | 75801 | 2026-09-08 | 2026-09-21 | 10 | handler_assign | confirm_note:stored_full
430_ME_HeatExchangersAndAirHeaters_EL | 75802 | 75802 | 2026-09-08 | 2026-09-23 | 12 | handler_assign | confirm_note:stored_full
430_ME_HeatExchangersAndAirHeaters_WL | 75803 | 75803 | 2026-09-08 | 2026-09-22 | 11 | handler_assign | confirm_note:stored_full
430_ME_HeatExchangersAndAirHeaters_WT | 75804 | 75804 | 2026-09-08 | 2026-09-24 | 13 | handler_assign | confirm_note:stored_full
430_ME_HeatExchangers_KTH_NoSystem | 75805 | 75805 | 2026-09-08 | 2026-09-23 | 12 | handler_assign | confirm_note:stored_full
430_ME_HeatRecoveryWheelPrimaryAirUnits_Standard | 75807 | 75807 | 2026-09-08 | 2026-09-15 | 6 | handler_assign | confirm_note:stored_full
430_ME_IndoorUnitsThermoVentI | 75140 | 75140 | 2026-08-12 | 2026-09-14 | 24 | handler_assign | confirm_note:stored_full
430_ME_InlineCentrifugalFan_FRD | 75150 | 75150 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_JetFanCarPark_FloorSurface_NoSystem | 75142 | 75142 | 2026-08-12 | 2026-09-14 | 24 | handler_assign | confirm_note:stored_full
430_ME_KitchenExtractorHood | 75145 | 75145 | 2026-08-12 | 2026-09-24 | 32 | handler_assign | confirm_note:stored_full
430_ME_KitchenHoodMonoblock_Standard | 75154 | 75154 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_MixingTank_Becomix | 75143 | 75143 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_RoofFanDV_Return | 75155 | 75155 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_RoofTopUnits_ThermoVentD | 75159 | 75159 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_RoofVentilationFans_DAX_NoSystem | 75161 | 75161 | 2026-08-12 | 2026-09-23 | 31 | handler_assign | confirm_note:stored_full
430_ME_RoofVentilationFans_DRV_EC | 75164 | 75164 | 2026-08-12 | 2026-08-28 | 13 | handler_assign | confirm_note:stored_full
430_ME_RoofVentilationFans_DRVFH | 75162 | 75162 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_SmokeExhaustAxialFans_BVAXO_F400 | 75166 | 75166 | 2026-08-12 | 2026-09-16 | 26 | handler_assign | confirm_note:stored_full
430_ME_SmokeExhaustCentrifugalFans_BVRA | 75167 | 75167 | 2026-08-12 | 2026-09-24 | 32 | handler_assign | confirm_note:stored_full
430_ME_SmokeExhaustJetFans_NoSystem | 75144 | 75144 | 2026-08-12 | 2026-09-16 | 26 | handler_assign | confirm_note:stored_full
430_ME_StartingSolution | 75151 | 75151 | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full
430_ME_VacuumPump | 75177 | 75177 | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full
430_ME_VentilationAxialFans_AXN691256 | 75178 | 75178 | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full
430_ME_VentilationAxialFans_AXO1050 | 75180 | 75180 | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full
430_ME_VentilationAxialFans_GLDF | 75183 | 75183 | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full
430_ME_VentilationCentrifugalFans_RZH | 75187 | 75187 | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full
430_ME_VentilationJetFans_GAXO_NoSystem | 75146 | 75146 | 2026-08-12 | 2026-09-17 | 27 | handler_assign | confirm_note:stored_full
430_ME_VentilationPlugFans_ERV | 75188 | 75188 | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full
430_ME_Ventilator_VAM | 75189 | 75189 | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full
430_ME_WallMountedVentilator | 75190 | 75190 | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full
434_ME_AirCooledChillers_30AWH | 75242 | 75242 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_AirCooledCondensingUnits_38RBS_2Pipes | 75243 | 75243 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_AirCooledCondensingUnits_38RBS_4Pipes | 75244 | 75244 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_AirCooledCondensingUnits_38RBS_LeftConnector | 75246 | 75246 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_AirCooledLiquidChillers_30RB | 75247 | 75247 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_AirCooledLiquidChillers_30RBS | 75248 | 75248 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_AirCooledLiquidChillers_30XA | 75249 | 75249 | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full
434_ME_AirCooledLiquidChillers_30XAS | 75250 | 75250 | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full
434_ME_AirCooledLiquidChillers_30XAV | 75251 | 75251 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_AirCooledLiquidChillers_HeatReclaimUnit30XAS | 75252 | 75252 | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full
434_ME_ConvectionElementsCeillings_CeilingMounted_KN | 75255 | 75255 | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full
434_ME_CyclonicVacuumDegasser_VentoVIEC | 75258 | 75258 | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full
434_ME_DegassingSystem | 75259 | 75259 | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full
434_ME_Ductableaircooledliquidchillers_30RBSY_LeftConnection | 75263 | 75263 | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full
434_ME_DuctableAirCooledLiquidChillers_30RBY | 75260 | 75260 | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full
434_ME_EndSuctionPump_Standard | 75264 | 75264 | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full
434_ME_ExpansionVessel_IntermediateDG | 75266 | 75266 | 2026-08-13 | 2026-09-23 | 30 | handler_assign | confirm_note:stored_full
434_ME_ExpansionVessel_StaticoSG | 75270 | 75270 | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full
434_ME_ExpansionVessel_StaticoSU | 75271 | 75271 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_AirTreatmentModules42GM2Pipes | 75272 | 75272 | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_AirTreatmentModules42GM4Pipes | 75274 | 75274 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_AirTreatmentModules42GR2Pipes | 75275 | 75275 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_AirTreatmentModules42GR4Pipes | 75276 | 75276 | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingCassette_2pipes&42GW | 75277 | 75277 | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingCassette_Standard | 75278 | 75278 | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full
434_ME_Fancoilunit_CeilingMounted_4wayblowcassetteFWFBF4pipes | 75358 | 75358 | 2026-08-14 | 2026-09-07 | 17 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFBT2Pipes | 75279 | 75279 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFCT2Pipes | 75280 | 75280 | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_CompactChassis42GW4Pipes | 75281 | 75281 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_HybridTerminal36XB | 75282 | 75282 | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC2Pipe | 75283 | 75283 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC4Pipe | 75284 | 75284 | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWD2Pipe | 75285 | 75285 | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH2Pipe | 75286 | 75286 | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH4Pipe | 75287 | 75287 | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_LargeChassis42GW4Pipes | 75288 | 75288 | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full
434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBF4pipes | 75364 | 75364 | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full
434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBT2pipes | 75365 | 75365 | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingMounted_Standard | 75289 | 75289 | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_FWBJF4pipe | 75328 | 75328 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_FWBJT2pipe | 75329 | 75329 | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_FWDAF4pipe | 75330 | 75330 | 2026-08-14 | 2026-09-24 | 30 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_FWDAT2pipe | 75331 | 75331 | 2026-08-14 | 2026-09-07 | 17 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_FWMDF4pipe | 75332 | 75332 | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_FWSAT2pipe | 75335 | 75335 | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE2Pipe | 75336 | 75336 | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE4Pipe | 75337 | 75337 | 2026-08-14 | 2026-09-17 | 25 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS2Pipe | 75339 | 75339 | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS4Pipe | 75340 | 75340 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize0x | 75341 | 75341 | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize1x | 75342 | 75342 | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize0x | 75343 | 75343 | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize1x | 75344 | 75344 | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_CeilingPlenum_Ultra | 75345 | 75345 | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_ConcealedCeiling_42BJ2Pipes | 75346 | 75346 | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_ConcealedCeiling_42BJ4Pipes | 75347 | 75347 | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_FlexiTypeUnitFWLDAF4Pipes | 75348 | 75348 | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_FlexiTypeUnitFWLDAT2Pipes | 75349 | 75349 | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_FloorStanding_FWVDAT2Pipes | 75351 | 75351 | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_UnderFloorTrench_KathermHK2Pipe | 75352 | 75352 | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_UnderFloorTrench_KathermHK4Pipe | 75353 | 75353 | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_UnderFloorTrench_KathermHKE | 75354 | 75354 | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_UnderFloorTrench_KathermID | 75355 | 75355 | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full
434_ME_FanCoilUnit_WallMounted_FWBBT2pipe | 75356 | 75356 | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full
434_ME_FillsoftI | 75366 | 75366 | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full
434_ME_FlatCompactDryCooler | 74701 | 74701 | 2026-07-22 | 2026-09-10 | 37 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledBaffleCeilings_CeilingMounted_L608 | 74693 | 74693 | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs78_NoSystem | 74689 | 74689 | 2026-07-22 | 2026-09-23 | 46 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledCorridorCeilings_CeilingMounted_E312 | 74688 | 74688 | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E200 | 74687 | 74687 | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E210 | 74686 | 74686 | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E213 | 74685 | 74685 | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E214 | 74684 | 74684 | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledHybridCeilings_CeilingMounted_DSTAS | 74683 | 74683 | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledPlasterboardCeilings_CeilingMounted_GKHEKDA2Pipes | 74682 | 74682 | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100 | 74681 | 74681 | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100SD | 74680 | 74680 | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B110 | 74679 | 74679 | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full
434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B147SD | 74678 | 74678 | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full
434_ME_HeatExchanger_Brazed_DoublePass | 74698 | 74698 | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full
434_ME_HeatExchanger_Brazed&DoublePass&Flanged | 74700 | 74700 | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full
434_ME_HeatExchanger_Brazed_SinglePass&Flanged | 74697 | 74697 | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full
434_ME_HeatExchanger_BrazedSinglePass&Thread | 74699 | 74699 | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full
434_ME_HeatExchanger_Gasketed&Flanged | 74696 | 74696 | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full
434_ME_HeatExchanger_Standard | 74694 | 74694 | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full
434_ME_InLinePump_Standard | 74640 | 74640 | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:stored_full
434_ME_Manifold_10Circuits | 73890 | 73890 | 2026-06-25 | 2026-08-26 | 45 | handler_assign | confirm_note:stored_full
434_ME_Manifold_11Circuits | 73889 | 73889 | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full
434_ME_Manifold_12Circuits | 73888 | 73888 | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full
434_ME_Manifold_2Circuits | 73887 | 73887 | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full
434_ME_Manifold_3Circuits | 73886 | 73886 | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full
434_ME_Manifold_4Circuits | 73885 | 73885 | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full
434_ME_Manifold_5Circuits | 73884 | 73884 | 2026-06-25 | 2026-09-23 | 65 | handler_assign | confirm_note:stored_full
434_ME_Manifold_8Circuits | 73880 | 73880 | 2026-06-25 | 2026-08-21 | 42 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_10Circuits | 74639 | 74639 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_11Circuits | 74638 | 74638 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_12Circuits | 74637 | 74637 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_2Circuits | 74636 | 74636 | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_3Circuits | 74635 | 74635 | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_4Circuits | 74634 | 74634 | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_5Circuits | 74633 | 74633 | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_6Circuits | 74632 | 74632 | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_7Circuits | 74631 | 74631 | 2026-07-21 | 2026-08-26 | 27 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_8Circuits | 74630 | 74630 | 2026-07-21 | 2026-08-27 | 28 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithFlowMeter_9Circuits | 74629 | 74629 | 2026-07-21 | 2026-08-21 | 24 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_1Circuits | 74628 | 74628 | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_2Circuits | 74627 | 74627 | 2026-07-21 | 2026-08-13 | 18 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_3Circuits | 74626 | 74626 | 2026-07-21 | 2026-08-14 | 19 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_4Circuits | 74625 | 74625 | 2026-07-21 | 2026-08-14 | 19 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_5Circuits | 74624 | 74624 | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_6Circuits | 74623 | 74623 | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_7Circuits | 74622 | 74622 | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full
434_ME_ManifoldWithPump_8Circuits | 74621 | 74621 | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full
434_ME_OutDoorUnit_VRV5HeatRecoveryREYA | 73878 | 73878 | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full
434_ME_PrecisionPressureMaintenance_TransferoTI | 73877 | 73877 | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full
434_ME_PrecisionPressureMaintenance_TransferoTV1 | 73876 | 73876 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
434_ME_PrecisionPressureMaintenance_TransferoTV2 | 73875 | 73875 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
434_ME_PrecisionPressureMaintenance_TransferoTVI1 | 73874 | 73874 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
434_ME_PrecisionPressuremaintenance_TransferoTVI2 | 73873 | 73873 | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full
434_ME_PrecisionPressurisation_CompressoC | 73872 | 73872 | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved
434_ME_PrecisionPressurisation_CompressoF | 73871 | 73871 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
434_ME_PressureMaintenanceMonitoring_PlenoPI9 | 73870 | 73870 | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved
434_ME_PressureMaintenanceMonitoring_PlenoPIX | 73867 | 73867 | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full
434_ME_PressureMaintenanceMonitoring_PlenoPX | 73866 | 73866 | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorAtmosGIGA&B | 73864 | 73864 | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full
434_ME_Pump_Circulator_CronoTwin_DL_E | 73854 | 73854 | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full
434_ME_PumpCirculator_FloorStand_Round_CronoLineILE | 73865 | 73865 | 2026-06-25 | 2026-07-10 | 12 | handler_assign | status_resolved
434_ME_Pump_CirculatorStratosGIGA | 73862 | 73862 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorStratosGIGA20&D | 73861 | 73861 | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorStratosGIGA20&I | 73860 | 73860 | 2026-06-25 | 2026-07-02 | 6 | handler_assign | status_resolved
434_ME_Pump_CirculatorStratosGIGA&B | 73863 | 73863 | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorStratosMAXO | 73859 | 73859 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorStratosPICO | 73858 | 73858 | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorVeroLineIPL | 73857 | 73857 | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full
434_ME_Pump_Circulator_VeroTwinDPL_DN32 | 73852 | 73852 | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full
434_ME_Pump_Circulator_VeroTwinDPL_DN40 | 73851 | 73851 | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full
434_ME_Pump_Circulator_VeroTwinDPL_DN50 | 73850 | 73850 | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full
434_ME_Pump_Circulator_VeroTwinDPL_DN65 | 73849 | 73849 | 2026-07-08 | 2026-09-28 | 59 | handler_assign | confirm_note:stored_full
434_ME_Pump_Circulator_YonosGIGA20D | 73508 | 73508 | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full
434_ME_Pump_Circulator_YonosGIGA20_I | 73104 | 73104 | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorYonosMAXO | 73856 | 73856 | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full
434_ME_Pump_CirculatorYonosPICO | 73855 | 73855 | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full
434_ME_Pump_SingleStageGlandedBM | 73507 | 73507 | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full
434_ME_Pump_SingleStageLowPressureBAC | 73506 | 73506 | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full
434_ME_Pump_SingleStageLowPressureBAC65 | 73103 | 73103 | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyAtmosGIGA&N | 73505 | 73505 | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyAtmosI | 73504 | 73504 | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyAtmosTERA&SCH | 73503 | 73503 | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyCronoBlocBLE | 73502 | 73502 | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyCronoNorm&NLG | 73501 | 73501 | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyVeroLineIPE | 73499 | 73499 | 2026-06-19 | 2026-08-27 | 50 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyVeroTwinDPE | 73498 | 73498 | 2026-06-19 | 2026-08-17 | 42 | handler_assign | confirm_note:stored_full
434_ME_Pump_WaterSupplyYonosGIGA&N | 73497 | 73497 | 2026-06-19 | 2026-08-27 | 50 | handler_assign | confirm_note:stored_full
434_ME_SplitCasePump_Standard | 73102 | 73102 | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full
434_ME_TwoOutletPump_Flanged | 73101 | 73101 | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full
434_ME_VariableSpeedWaterCooledLiquidChiller_SingleCompressor30XW&V | 73495 | 73495 | 2026-06-19 | 2026-09-25 | 71 | handler_assign | confirm_note:stored_full
434_ME_VRVInDoorUnit_CeilingMouted_FXFA&A | 73100 | 73100 | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full
434_ME_VRVInDoorUnit_CeilingMouted_FXZA&A | 73099 | 73099 | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full
434_ME_VRVInDoorUnit_CeilingSuspended_FXHA&A | 73098 | 73098 | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full
434_ME_VRVInDoorUnit_CeilingSuspended_FXUA&A | 73097 | 73097 | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full
434_ME_VRVInDoorUnit_WallMounted_FXAA&A | 73092 | 73092 | 2026-06-08 | 2026-09-22 | 77 | handler_assign | confirm_note:stored_full
434_ME_VRVMultiBranchSelector_BS&10A14AV1B | 73091 | 73091 | 2026-06-08 | 2026-09-21 | 76 | handler_assign | confirm_note:stored_full
434_ME_VRVMultiBranchSelector_BS&8A14AV1B | 73087 | 73087 | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full
434_ME_VRVOutDoorUnit_HeatPumpRXYA14&20A | 73086 | 73086 | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full
434_ME_VRVOutDoorUnit_HeatPumpRXYA8&12A | 73085 | 73085 | 2026-06-08 | 2026-08-28 | 60 | handler_assign | confirm_note:stored_full
434_ME_VRVOutDoorUnit_HeatPumpRXYSA&AV1&AY1 | 73084 | 73084 | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full
434_ME_VRVShutOffValveBox_SV1A25AJV1B | 73083 | 73083 | 2026-06-08 | 2026-09-11 | 70 | handler_assign | confirm_note:stored_full
434_ME_VRVShutOffValveBox_SV4A14AJV1B | 73082 | 73082 | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full
434_ME_VRVShutOffValveBox_SV6A14AJV1B | 73081 | 73081 | 2026-06-08 | 2026-07-03 | 20 | handler_assign | confirm_note:stored_full
434_ME_VRVShutOffValveBox_SV8A14AJV1B | 73080 | 73080 | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full
434_ME_WateCooledCondenserlessLiquidChillers_WithHydraulicModule_30RW | 73494 | 73494 | 2026-06-19 | 2026-08-28 | 51 | handler_assign | confirm_note:stored_full
434_ME_Watercooled_Condenserlessliquidchillers_30RW_30RWA_VerticalConnection | 72644 | 72644 | 2026-06-01 | 2026-09-22 | 82 | handler_assign | confirm_note:stored_full
434_ME_WaterCooledLiquidChillers_30XW | 73079 | 73079 | 2026-06-08 | 2026-08-25 | 57 | handler_assign | confirm_note:stored_full
434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC4Pipes | 73491 | 73491 | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full
434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC5Pipes | 73078 | 73078 | 2026-06-08 | 2026-08-24 | 56 | handler_assign | confirm_note:stored_full
434_PA_BranchProviderBox_BPMKS2Port | 72643 | 72643 | 2026-06-01 | 2026-06-30 | 22 | handler_assign | confirm_note:stored_full
434_PA_BranchProviderBox_BPMKS3Port | 72642 | 72642 | 2026-06-01 | 2026-06-30 | 22 | handler_assign | confirm_note:stored_full
434_PA_DewPointMonitor | 76219 | 76219 | 2026-09-28 | 2026-09-29 | 2 | handler_assign | confirm_note:stored_full
434_PA_MultiConnectionPipingKit1_BHFPGas | 72640 | 72640 | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full
434_PA_MultiConnectionPipingKit1_BHFPLiquid | 72639 | 72639 | 2026-06-01 | 2026-07-01 | 23 | handler_assign | confirm_note:stored_full
434_PA_MultiConnectionPipingKit2_BHFPGas | 72637 | 72637 | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full
434_PA_MultiConnectionPipingKit2_BHFPLiquid | 72636 | 72636 | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full
434_PA_RefnetHeader_KHRPGas4Branches | 72635 | 72635 | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full
434_PA_RefnetHeader_KHRPGas8Branches | 72634 | 72634 | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full
434_PA_RefnetHeader_KHRPHP&LPGas | 72633 | 72633 | 2026-06-01 | 2026-09-10 | 74 | handler_assign | confirm_note:stored_full
434_PA_RefnetHeader_KHRPLiquid4Branches | 72632 | 72632 | 2026-06-01 | 2026-07-02 | 24 | handler_assign | confirm_note:stored_full
434_PA_RefnetHeader_KHRPLiquid8Branches | 72631 | 72631 | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full
434_PF_CO_cCap_Mapress | 72579,72578 | 72579 | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full
434_PF_CO_cCap_MapressGas | 72577 | 72577 | 2026-06-01 | 2026-06-09 | 7 | handler_assign | confirm_note:stored_full
434_PF_CO_e90Elbow_ThreadAndMeplaFix | 73489 | 73489 | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full
434_PF_CO_eAdaptorBend_MapressAndFemaleThread_WithNut | 73488 | 73488 | 2026-06-19 | 2026-08-11 | 38 | handler_assign | confirm_note:stored_full
434_PF_CO_eAdaptorBend_MapressAndMeplaFix | 73487 | 73487 | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full
434_PF_CO_eAdaptorBend_MapressAndThread | 72484 | 72484 | 2026-05-28 | 2026-06-09 | 9 | handler_assign | confirm_note:stored_full
434_PF_CO_eAdaptorBend_MapressAndThreadFKMBlue | 72483 | 72483 | 2026-05-28 | 2026-07-29 | 45 | handler_assign | confirm_note:stored_full
434_PF_CO_eAdaptorBend_MapressAndThreadGas | 72482 | 72482 | 2026-05-28 | 2026-06-24 | 20 | handler_assign | confirm_note:stored_full
434_PF_CO_eBend_Mapress | 72622 | 72622 | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full
434_PF_CO_eBend_MapressFKMBlue | 72621 | 72621 | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full
434_PF_CO_eBend_MapressGas | 72581 | 72581 | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full
434_PF_CO_eDouble90ElbowMultiPort_Mapress | 73486 | 73486 | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full
434_PF_CO_eElbow90Deg_MaleThread_MeplaFixAndPremounted | 73485 | 73485 | 2026-06-19 | 2026-07-29 | 29 | handler_assign | confirm_note:stored_full
434_PF_CO_eElbowDouble90Deg_MaleThread_MeplaFixAndPremounted | 73484 | 73484 | 2026-06-19 | 2026-07-29 | 29 | handler_assign | confirm_note:stored_full
434_PF_CO_fFlange_Mapress | 73483 | 73483 | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full
434_PF_CO_mAdaptorMultiPort_MapressAndNut | 72626 | 72626 | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full
434_PF_CO_mBridgeBend_Mapress | 73314 | 73314 | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full
434_PF_CO_mElbow_MapressAndFemaleThread | 73311 | 73311 | 2026-06-12 | 2026-09-14 | 67 | handler_assign | confirm_note:stored_full
434_PF_CO_mElbowOffset_MapressAndFemaleThread | 73312 | 73312 | 2026-06-12 | 2026-07-22 | 29 | handler_assign | confirm_note:stored_full
434_PF_CO_mTeeCrossing_Mapress | 73310 | 73310 | 2026-06-12 | 2026-09-07 | 62 | handler_assign | confirm_note:stored_full
434_PF_CO_mTeeInletReturn_Mapress | 73308 | 73308 | 2026-06-12 | 2026-07-28 | 33 | handler_assign | confirm_note:stored_full
434_PF_CO_mTeeInletReturnUnion_Mapress | 73309 | 73309 | 2026-06-12 | 2026-09-11 | 66 | handler_assign | confirm_note:stored_full
434_PF_CO_mTeeReturn_Mapress | 73307 | 73307 | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptorForGas_MapressAndThread | 73299 | 73299 | 2026-06-19 | 2026-07-17 | 21 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptorForGas_PlainEndAndThread | 73296 | 73296 | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_MaleThread_MeplaFix | 73306 | 73306 | 2026-06-12 | 2026-07-28 | 33 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_MapressAndFemaleThreadFKMBlue_WithNut | 73305 | 73305 | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_MapressAndFemaleThread_WithNut | 73304 | 73304 | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_MapressAndMaleThreadFKMBlue_WithNut | 73303 | 73303 | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_MapressAndMaleThread_WithNut | 73302 | 73302 | 2026-06-19 | 2026-08-04 | 33 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_MapressAndThread | 73301 | 73301 | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_MapressAndThreadFKMBlue | 73300 | 73300 | 2026-06-19 | 2026-08-20 | 45 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFix | 73298 | 73298 | 2026-06-19 | 2026-07-17 | 21 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFixAdaptor | 72481 | 72481 | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_PlainEndAndClampingRing | 72576 | 72576 | 2026-06-01 | 2026-06-09 | 7 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_PlainEndAndThread | 73297 | 73297 | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full
434_PF_CO_rReducerAdaptor_PlainEnd_WithMeplaFixAdaptor | 72480 | 72480 | 2026-05-28 | 2026-06-09 | 9 | handler_assign | confirm_note:stored_full
434_PF_CO_rTransitionForGas_Mapress | 72567 | 72567 | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full
434_PF_CO_rTransition_MapressFKMBlue | 72568 | 72568 | 2026-06-01 | 2026-07-30 | 44 | handler_assign | confirm_note:stored_full
434_PF_CO_tTee_Mapress | 72574 | 72574 | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full
434_PF_CO_tTee_Mapress&FemaleThread | 72575 | 72575 | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full
434_PF_CO_tTee_MapressFKMBlue | 72572 | 72572 | 2026-06-01 | 2026-06-15 | 11 | handler_assign | confirm_note:stored_full
434_PF_CO_tTee_MapressFKMBlue&FemaleThread | 72573 | 72573 | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full
434_PF_CO_tTee_MapressGas | 72570 | 72570 | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full
434_PF_CO_tTee_MapressGas&FemaleThread | 72571 | 72571 | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full
434_PF_CO_tTransition_Mapress | 72569 | 72569 | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_FemaleThreadAndMeplaFix | 72625 | 72625 | 2026-06-01 | 2026-07-01 | 23 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MaleThreadAndMeplaFix | 73295 | 73295 | 2026-07-08 | 2026-08-05 | 21 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MaleThread_MeplaFix | 73294 | 73294 | 2026-07-09 | 2026-07-29 | 15 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_Mapress | 72479 | 72479 | 2026-05-28 | 2026-08-20 | 61 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MapressAndFemaleThreadFKMBlue_WithNut | 72478 | 72478 | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MapressAndFemaleThread_WithNut | 73293 | 73293 | 2026-07-09 | 2026-08-06 | 21 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MapressAndFlangeGas | 72624 | 72624 | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MapressAndThread | 72471 | 72471 | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MapressAndThreadFKMBlue | 72468 | 72468 | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_MapressAndThreadGas | 72467 | 72467 | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_PlainEndAndClampingRing | 73290 | 73290 | 2026-07-13 | 2026-09-07 | 41 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_PlainEndAndFlange | 72623 | 72623 | 2026-06-01 | 2026-06-19 | 15 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_PlainEndAndThread | 73289 | 73289 | 2026-07-13 | 2026-09-21 | 51 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_PlainEndAndThreadGas | 72466 | 72466 | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full
434_PF_CO_uAdaptorUnion_PlainEnd_WithMeplaFix | 72465 | 72465 | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full
434_PF_CO_uTap_Thread | 73288 | 73288 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
434_PF_CO_uUnion_Mapress | 72566 | 72566 | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full
434_PF_CO_uUnion_MapressFKMBlue | 72565 | 72565 | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full
434_PF_CO_uUnion_MapressGas | 72485 | 72485 | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full
434_PF_CO_x30Cross_Mapress | 72627 | 72627 | 2026-06-01 | 2026-07-06 | 26 | handler_assign | confirm_note:stored_full
434_PF_CO_xOffsetCross_Mapress | 73287 | 73287 | 2026-07-13 | 2026-09-14 | 46 | handler_assign | confirm_note:stored_full
440_CF_AL_eHorizontalElbow_Busway | 73995 | 73995 | 2026-06-30 | 2026-07-31 | 24 | handler_assign | confirm_note:stored_full
440_CF_AL_eVerticalElbow90Deg_Busway | 73996 | 73996 | 2026-06-30 | 2026-08-03 | 25 | handler_assign | confirm_note:stored_full
440_CF_AL_eVerticalOffsetElbow90Deg_Busway | 74024 | 74024 | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full
440_CF_AL_mHorizontalOffsetZShade_Busway | 74025 | 74025 | 2026-07-02 | 2026-08-04 | 24 | handler_assign | confirm_note:stored_full
440_CF_AL_mVerticalOffsetZShade_Busway | 74026 | 74026 | 2026-07-02 | 2026-08-07 | 27 | handler_assign | confirm_note:stored_full
440_CF_AL_StraightLength_Busway | 74027 | 74027 | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full
440_CF_AL_tVerticalTee_Busway | 74028 | 74028 | 2026-07-02 | 2026-07-29 | 20 | handler_assign | confirm_note:stored_full
440_CF_AL_uEndFlange_Busway | 74029 | 74029 | 2026-07-02 | 2026-07-31 | 22 | handler_assign | confirm_note:stored_full
440_CF_CO_eDoubleLeftElbow_Busway | 74031 | 74031 | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full
440_CF_CO_eEdgewiseElbow_Busway | 74033 | 74033 | 2026-07-02 | 2026-08-13 | 31 | handler_assign | confirm_note:stored_full
440_CF_CO_eEdgewiseElbowWithAngle_Busway | 74032 | 74032 | 2026-07-02 | 2026-08-13 | 31 | handler_assign | confirm_note:stored_full
440_CF_CO_eEdgewiseOffet_Standard | 74034 | 74034 | 2026-07-02 | 2026-08-03 | 23 | handler_assign | confirm_note:stored_full
440_CF_CO_eFlatwiseOffsetElbow_Busway | 74035 | 74035 | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full
440_CF_CO_eFlatwise_Standard | 74136 | 74136 | 2026-07-06 | 2026-08-03 | 21 | handler_assign | confirm_note:stored_full
440_CF_CO_mChannelMultiPort_Standard_FeedUnitForDryTransformer | 74137 | 74137 | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full
440_CF_CO_uFlangedEnd_Busway | 74138 | 74138 | 2026-07-06 | 2026-08-03 | 21 | handler_assign | confirm_note:stored_full
440_CF_CS_eCavityFloorBoxWithHeatResistantRoundFormworkBodyElbow_Standard | 74139 | 74139 | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full
440_CF_CS_eCavityFloorBoxWithHeatResistantSquareFormworkBodyElbow_Standard | 74140 | 74140 | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full
440_CF_CS_eCavityFloorBoxWithRoundFormworkBodyElbow_Standard | 74141 | 74141 | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full
440_CF_CS_eCavityFloorBoxWithSquareFormworkBodyElbow_Standard | 74146 | 74146 | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full
440_CF_CS_eScreedCovered_Standard_ChannelThreePartVerticalBend | 74147 | 74147 | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full
440_CF_CS_eScreedCovered_Standard_ChannelTwoPartVerticalBend | 74142 | 74142 | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full
440_CF_CS_tCavityFloorBoxWithHeatResistantRoundFormworkBodyTee_Standard | 74143 | 74143 | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full
440_CF_CS_tCavityFloorBoxWithHeatResistantSquareFormworkBodyTee_Standard | 74144 | 74144 | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full
440_CF_CS_tCavityFloorBoxWithRoundFormworkBodyTee_Standard | 74145 | 74145 | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full
440_CF_CS_tCavityFloorBoxWithSquareFormworkBodyTee_Standard | 74148 | 74148 | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full
440_CF_CS_uCavityFloorBoxWithHeatResistantRoundFormworkBodyEnd_Standard | 74149 | 74149 | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full
440_CF_CS_uCavityFloorBoxWithHeatResistantSquareFormworkBodyEnd_Standard | 74150 | 74150 | 2026-07-06 | 2026-07-23 | 14 | handler_assign | confirm_note:stored_full
440_CF_CS_uCavityFloorBoxWithRoundFormworkBodyEnd_Standard | 74151 | 74151 | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full
440_CF_CS_uCavityFloorBoxWithSquareFormworkBodyEnd_Standard | 74152 | 74152 | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full
440_CF_CS_xCavityFloorBoxWithHeatResistantRoundFormworkBodyCross_Standard | 74153 | 74153 | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full
440_CF_CS_xCavityFloorBoxWithHeatResistantSquareFormworkBodyCross_Standard | 74154 | 74154 | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full
440_CF_CS_xCavityFloorBoxWithRoundFormworkBodyCross_Standard | 74179 | 74179 | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full
440_CF_CS_xCavityFloorBoxWithSquareFormworkBodyCross_Standard | 74180 | 74180 | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full
440_CF_ehFlatwiseElbowFlangeEnd_Busway | 74181 | 74181 | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full
440_CF_ehFlatwiseElbowWithAngle_Busway | 74182 | 74182 | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full
440_CF_mFlatwiseTee_Busway | 74183 | 74183 | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full
440_CF_mPhaseTransition_Busway | 74184 | 74184 | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full
440_CF_mPotentialEqualisationBusbar | 74185 | 74185 | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full
440_CF_mStraightLength_Busway | 74187 | 74187 | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full
440_CF_ST_ehChannelHorizontalBend_Standard | 74188 | 74188 | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full
440_CF_ST_ehChannelHorizontalMiteredBend_Standard | 74190 | 74190 | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full
440_CF_ST_ehLadderHorizontalBend_Standard | 74215 | 74215 | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full
440_CF_ST_eiChannelVerticalInsideBend_Standard | 74213 | 74213 | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full
440_CF_ST_eiLadderVerticalInsideBend_Standard | 74222 | 74222 | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full
440_CF_ST_eoChannelVerticalOutsideBend_Standard | 74214 | 74214 | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full
440_CF_ST_eoLadderVerticalOutsideBend_Standard | 74223 | 74223 | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full
440_CF_ST_rChannelTransition_Standard | 74209 | 74209 | 2026-07-06 | 2026-08-28 | 40 | handler_assign | confirm_note:stored_full
440_CF_ST_rLadderTransition_Standard | 74218 | 74218 | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full
440_CF_ST_tChannelHorizontalTee_Standard | 74208 | 74208 | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full
440_CF_ST_tLadderHorizontalTee_Standard | 74217 | 74217 | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full
440_CF_ST_tvChannelVerticalDownTee_Standard | 74212 | 74212 | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full
440_CF_ST_tvLadderUTypeVerticalTee_Standard | 74220 | 74220 | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full
440_CF_ST_uChannelUnion_Standard | 74210 | 74210 | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full
440_CF_ST_uLadderUnion_Standard | 74219 | 74219 | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full
440_CF_ST_xChannelHorizontalCross_Standard | 74189 | 74189 | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full
440_CF_ST_xLadderHorizontalCross_Standard | 74216 | 74216 | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full
440_CF_ST_xvChannelVerticalCross_Standard | 74211 | 74211 | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full
440_CF_uCableTapBoxCenter_Busway | 74224 | 74224 | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full
440_CF_uCableTapBoxEnd_Busway | 74226 | 74226 | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full
440_CF_uEndClosure_Busway | 74227 | 74227 | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full
440_CF_uFlexibleLink_Busway | 74228 | 74228 | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full
440_CF_UnfusedReducer_Busway | 74229 | 74229 | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full
440_CF_uWallFloorFlange_Busway | 74230 | 74230 | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full
440_CF_wChannelHorizontalWye_Standard | 74030 | 74030 | 2026-07-02 | 2026-08-21 | 37 | handler_assign | confirm_note:stored_full
440_CI_CS_tClamps_Standard | 74239 | 74239 | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full
440_CI_CS_tExpansionPiecesRound_Standard | 74240 | 74240 | 2026-07-06 | 2026-08-14 | 30 | handler_assign | confirm_note:stored_full
440_CI_CS_xClamps_Standard | 74243 | 74243 | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full
440_CI_CS_xExpansionPiecesRound_Standard | 74246 | 74246 | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full
440_CI_PC_mJunctionBox_Standard_Weatherproof | 74247 | 74247 | 2026-07-06 | 2026-09-30 | 63 | handler_assign | confirm_note:stored_full
440_CI_PVC_cConduitBodiesTypeE_Standard | 74255 | 74255 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_cMarkerforConnectionLugs | 74253 | 74253 | 2026-07-06 | 2026-09-24 | 59 | handler_assign | confirm_note:stored_full
440_CI_PVC_ConduitSleeveCoupling_Standard | 74260 | 74260 | 2026-07-06 | 2026-07-10 | 5 | handler_assign | status_resolved
440_CI_PVC_cTerminalOneWayBox_Standard | 74316 | 74316 | 2026-07-09 | 2026-09-04 | 42 | handler_assign | confirm_note:stored_full
440_CI_PVC_e30DegreeElbow_Standard | 74248 | 74248 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_e45DegreeElbow_Standard | 74249 | 74249 | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full
440_CI_PVC_e90DegreeElbow_Standard | 74251 | 74251 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_e90DegreeInspectionElbow_Standard | 74266 | 74266 | 2026-07-06 | 2026-07-13 | 6 | handler_assign | status_resolved
440_CI_PVC_eAngledTwoWayBox_Standard | 74252 | 74252 | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full
440_CI_PVC_eConduitBodiesTypeLB_Standard | 74256 | 74256 | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full
440_CI_PVC_eConduitBodiesTypeLL_Standard | 74257 | 74257 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_eConduitBodiesTypeLR_Standard | 74258 | 74258 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_eInspectionBend_Standard | 74265 | 74265 | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full
440_CI_PVC_fCoupling_Standard | 74263 | 74263 | 2026-07-06 | 2026-08-25 | 37 | handler_assign | confirm_note:stored_full
440_CI_PVC_mHWayJuntionBox_Standard | 74264 | 74264 | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full
440_CI_PVC_mJunctionBox_Standard_ThreeWay | 74270 | 74270 | 2026-07-06 | 2026-09-28 | 61 | handler_assign | confirm_note:stored_full
440_CI_PVC_mUWayBox_Standard | 74318 | 74318 | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full
440_CI_PVC_mYWayBox_Standard | 74319 | 74319 | 2026-07-09 | 2026-09-17 | 51 | handler_assign | confirm_note:stored_full
440_CI_PVC_rReducer_Standard | 74314 | 74314 | 2026-07-09 | 2026-08-24 | 33 | handler_assign | confirm_note:stored_full
440_CI_PVC_tConduitBodiesTypeT_Standard | 74259 | 74259 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_tInspectionTee_Standard | 74267 | 74267 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_tTeeThreeWayBox_Standard | 74315 | 74315 | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full
440_CI_PVC_uConduitBodiesTypeC_Standard | 74254 | 74254 | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full
440_CI_PVC_uJunctionBox_Standard | 74269 | 74269 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_PVC_uThroughTwoWayBox_Standard | 74317 | 74317 | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full
440_CI_PVC_xIntersectionFourWayBox_Standard | 74268 | 74268 | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full
440_CI_SS_cDeviceBoxes_Threaded | 74320 | 74320 | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full
440_CI_SS_e45DegreeElbow_Standard | 74321 | 74321 | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full
440_CI_SS_e45DegreeElbow_Threaded | 74322 | 74322 | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full
440_CI_SS_e90DegreeElbow_Standard | 74323 | 74323 | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved
440_CI_SS_e90DegreeElbow_Threaded | 74324 | 74324 | 2026-07-09 | 2026-08-25 | 34 | handler_assign | confirm_note:stored_full
440_CI_SS_eConduitBodies_Threaded_TypeLB | 74325 | 74325 | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full
440_CI_SS_eConduitBodies_Threaded_TypeLR | 74326 | 74326 | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved
440_CI_SS_eConduitBodies_Threaded_TypeLU | 74327 | 74327 | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved
440_CI_SS_eConduitBodies_TypeLL_Threaded | 74328 | 74328 | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full
440_CI_SS_eFlatConductorsElbow_Standard | 74329 | 74329 | 2026-07-09 | 2026-09-18 | 52 | handler_assign | confirm_note:stored_full
440_CI_SS_eInspectionElbow_Standard | 74330 | 74330 | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full
440_CI_SS_FlatStrip_Standard | 74331 | 74331 | 2026-07-09 | 2026-09-18 | 52 | handler_assign | confirm_note:stored_full
440_CI_SS_tConduitBodies_Threaded_TypeT | 74332 | 74332 | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full
440_CI_SS_tConduitBodies_Threaded_TypeTB | 74333 | 74333 | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full
440_CI_SS_uCFormConduitUnion_Threaded | 74334 | 74334 | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full
440_CI_SS_xConduitBodies_Threaded_TypeX | 74335 | 74335 | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full
440_CI_SS_xCrossConductorFlatToRound | 74336 | 74336 | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full
440_CI_SS_xFlatConductorCross | 74337 | 74337 | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full
440_CI_ST_mJunctionBox_Explosionproof | 74338 | 74338 | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full
440_EE_AnnunciatorPanel | 74840 | 74840 | 2026-07-28 | 2026-07-28 | 1 | handler_assign | status_resolved
440_EE_AutomaticTranferSwitchPanel | 72534 | 72534 | 2026-05-29 | 2026-08-18 | 58 | handler_assign | confirm_note:stored_full
440_EE_BatteryStorage | 72535 | 72535 | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full
440_EE_CircuitBreakerEnclosure | 72538 | 72538 | 2026-05-29 | 2026-09-18 | 81 | handler_assign | confirm_note:stored_full
440_EE_DCtoAC_Inverter | 72540 | 72540 | 2026-05-29 | 2026-08-14 | 56 | handler_assign | confirm_note:stored_full
440_EE_DieselGenerator | 72543 | 72543 | 2026-05-29 | 2026-09-18 | 81 | handler_assign | confirm_note:stored_full
440_EE_DieselTankGenerator | 72545 | 72545 | 2026-05-29 | 2026-08-17 | 57 | handler_assign | confirm_note:stored_full
440_EE_DistributionBox_DALI | 72715 | 72715 | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full
440_EE_DryTransformer | 72716 | 72716 | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full
440_EE_ElectricalCabinet_Standard | 72717 | 72717 | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full
440_EE_FlatRoofSolar | 72718 | 72718 | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full
440_EE_FlatRoofSolarFrame_NoSystem | 72769 | 72769 | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full
440_EE_FlatRoofSolarFrameWithRoot_NoSystem | 72719 | 72719 | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full
440_EE_GasInsulatedMediumVoltageSwitchgear_MSEVU | 72805 | 72805 | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full
440_EE_GasInsulatedMediumVoltageSwitchgear_MSKälte | 72806 | 72806 | 2026-06-02 | 2026-09-22 | 81 | handler_assign | confirm_note:stored_full
440_EE_GasInsulatedMediumVoltageSwitchgear_MSNord | 72809 | 72809 | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full
440_EE_GasInsulatedMediumVoltageSwitchgear_MSSud | 72814 | 72814 | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full
440_EE_Generator_Standard | 72815 | 72815 | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full
440_EE_IndoorTransformer | 72816 | 72816 | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full
440_EE_kwhMeter_3Phases | 72817 | 72817 | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full
440_EE_LowVoltagePanel | 72818 | 72818 | 2026-06-02 | 2026-06-04 | 3 | handler_assign | status_resolved
440_EE_LowVoltageSwitchboard_GHVNord_HOST | 72999 | 72999 | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full
440_EE_LowVoltageSwitchboard_NshvKälte_HOST | 73001 | 73001 | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full
440_EE_LowVoltageSwitchboard_NshvPV_HOST | 73002 | 73002 | 2026-06-05 | 2026-07-22 | 34 | handler_assign | confirm_note:stored_full
440_EE_MainDistributionBoard_WallMounted | 73003 | 73003 | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full
440_EE_MainSupply_GEVBnetwork | 73004 | 73004 | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full
440_EE_MainSupply_UPSmains | 73005 | 73005 | 2026-06-05 | 2026-08-17 | 52 | handler_assign | confirm_note:stored_full
440_EE_MainSwitchBoard | 73006 | 73006 | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full
440_EE_Manhole_Standard | 73007 | 73007 | 2026-06-05 | 2026-09-18 | 76 | handler_assign | confirm_note:stored_full
440_EE_MediumVoltageSwitchgear | 73009 | 73009 | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full
440_EE_MotorControlCenter_SwitchBoard | 73011 | 73011 | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full
440_EE_MotorizedGlareControl | 74842 | 74842 | 2026-07-28 | 2026-07-29 | 2 | handler_assign | status_resolved
440_EE_OilTransformer | 73012 | 73012 | 2026-06-05 | 2026-06-24 | 14 | handler_assign | confirm_note:stored_full
440_EE_OutdoorTransformer | 73014 | 73014 | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full
440_EE_PanelBoard | 73015 | 73015 | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full
440_EE_SilentDieselGenerator | 73016 | 73016 | 2026-06-05 | 2026-06-05 | 1 | handler_assign | status_resolved
440_EE_SpringVibration | 73018 | 73018 | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full
440_EE_SubmainSwitchBoard | 73019 | 73019 | 2026-06-05 | 2026-08-25 | 58 | handler_assign | confirm_note:stored_full
440_EE_SwitchCabinet_OutgoingPanel | 73020 | 73020 | 2026-06-05 | 2026-08-19 | 54 | handler_assign | confirm_note:stored_full
440_EE_SwitchCabinet_SupplyPanel | 73021 | 73021 | 2026-06-05 | 2026-08-24 | 57 | handler_assign | confirm_note:stored_full
440_EE_SynchronizationPanel | 73022 | 73022 | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full
440_EE_TransferDistributor | 73023 | 73023 | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full
440_EF_360DegreeRadiusMotionDetector_CeilingMounted | 73162 | 73162 | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full
440_EF_AL_SideFeedingUnitForTransformer_Busway | 73165 | 73165 | 2026-06-09 | 2026-08-24 | 55 | handler_assign | confirm_note:stored_full
440_EF_AL_TakeOffUnitWithFuseSwitch_Busway | 73166 | 73166 | 2026-06-09 | 2026-08-24 | 55 | handler_assign | confirm_note:stored_full
440_EF_AL_TopFeedingUnitForTransformer_Busway | 73167 | 73167 | 2026-06-09 | 2026-08-11 | 46 | handler_assign | confirm_note:stored_full
440_EF_BasementVentilationControl | 73366 | 73366 | 2026-06-15 | 2026-08-13 | 44 | handler_assign | confirm_note:stored_full
440_EF_CableConnection_PluginSystem | 73182 | 73182 | 2026-06-10 | 2026-08-13 | 47 | handler_assign | confirm_note:stored_full
440_EF_ConnectionBrackets | 73183 | 73183 | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full
440_EF_DALIPresenceDetector_CeilingSurface | 73185 | 73185 | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full
440_EF_DALIPresenceDetectorCombineLightingSensor_CeilingSurface | 73184 | 73184 | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full
440_EF_DataConnectionSocket_Audio_Out_HDMI | 73186 | 73186 | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full
440_EF_DataConnectionSocket_Ceiling | 73187 | 73187 | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full
440_EF_DataConnectionSocket_Floor | 73189 | 73189 | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full
440_EF_DataConnectionSocket_Wall | 73190 | 73190 | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full
440_EF_DaylightSensor_Ceiling | 73191 | 73191 | 2026-06-10 | 2026-09-28 | 79 | handler_assign | confirm_note:stored_full
440_EF_DaylightSensor_Wall | 73192 | 73192 | 2026-06-10 | 2026-08-31 | 59 | handler_assign | confirm_note:stored_full
440_EF_DimmerSwitch_WallRecessed | 73193 | 73193 | 2026-06-10 | 2026-08-31 | 59 | handler_assign | confirm_note:stored_full
440_EF_DoorbellPushButton_WallMounted | 73200 | 73200 | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full
440_EF_DoubleSocketOutlet_Ceiling | 73205 | 73205 | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full
440_EF_DoubleSocketOutlet_Floor | 73206 | 73206 | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full
440_EF_DoubleSocketOutletHorizontal_Wall | 73201 | 73201 | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full
440_EF_DoubleSocketOutletUSBTypeAC_WallSurface | 73202 | 73202 | 2026-06-11 | 2026-08-11 | 44 | handler_assign | confirm_note:stored_full
440_EF_DoubleSocketOutletVertical_Wall | 73203 | 73203 | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full
440_EF_DoubleSocketOutletVertical_WallFlush | 73204 | 73204 | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full
440_EF_DoubleSocketOutlet_Wall | 73207 | 73207 | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full
440_EF_EarthPit | 73221 | 73221 | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full
440_EF_EarthRod | 73350 | 73350 | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full
440_EF_EmergencyStopPushButtons | 73352 | 73352 | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full
440_EF_EnergyBollard | 73353 | 73353 | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full
440_EF_FixedConnection_1Pole | 73356 | 73356 | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full
440_EF_FixedConnection_400V | 73357 | 73357 | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full
440_EF_Isolator_3Phases | 73362 | 73362 | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full
440_EF_Isolator_SinglePhase | 73363 | 73363 | 2026-06-15 | 2026-08-11 | 42 | handler_assign | confirm_note:stored_full
440_EF_JunctionBox_Ceiling_3Pole | 73364 | 73364 | 2026-06-15 | 2026-09-28 | 76 | handler_assign | confirm_note:stored_full
440_EF_JunctionBox_Floor_3Pole | 73365 | 73365 | 2026-06-15 | 2026-09-04 | 60 | handler_assign | confirm_note:stored_full
440_EF_KeySwitch_WallRecessed | 73367 | 73367 | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full
440_EF_KNXPresenceDetection_Ceiling | 73368 | 73368 | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full
440_EF_KNX_PushButtonSensor_2gang | 73369 | 73369 | 2026-06-15 | 2026-09-18 | 70 | handler_assign | confirm_note:stored_full
440_EF_MainEquipotentialBondingBar | 73370 | 73370 | 2026-06-15 | 2026-08-07 | 40 | handler_assign | confirm_note:stored_full
440_EF_PanelBoard | 73372 | 73372 | 2026-06-15 | 2026-09-04 | 60 | handler_assign | confirm_note:stored_full
440_EF_PresenceDetector_Ceiling | 73373 | 73373 | 2026-06-15 | 2026-08-19 | 48 | handler_assign | confirm_note:stored_full
440_EF_PresenceDetector_Wall | 73374 | 73374 | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full
440_EF_PushButtonSensorKNX_4gang | 73375 | 73375 | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full
440_EF_PushButton_Wall | 74843 | 74843 | 2026-07-28 | 2026-07-28 | 1 | handler_assign | status_resolved
440_EF_Raumluftfühler | 73435 | 73435 | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full
440_EF_RoomSignallight | 73436 | 73436 | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full
440_EF_RotaryDimmer | 73437 | 73437 | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full
440_EF_ShaverSocketOutlet_Wall | 73438 | 73438 | 2026-06-18 | 2026-08-12 | 40 | handler_assign | confirm_note:stored_full
440_EF_SocketDistributionBox_Ceiling | 73439 | 73439 | 2026-06-18 | 2026-09-23 | 70 | handler_assign | confirm_note:stored_full
440_EF_SocketDistributionBox_Wall | 73440 | 73440 | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full
440_EF_SocketOutletCombination_Ceiling | 73441 | 73441 | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full
440_EF_SocketOutlet_FloorRecessed_Round | 73443 | 73443 | 2026-06-18 | 2026-08-11 | 39 | handler_assign | confirm_note:stored_full
440_EF_SocketOutlet_Horizontal_4Gangs_Wall | 73444 | 73444 | 2026-06-18 | 2026-08-11 | 39 | handler_assign | confirm_note:stored_full
440_EF_SocketOutletRound_Floor | 73442 | 73442 | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full
440_EF_SocketOutlet_Wall | 73448 | 73448 | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full
440_EF_SocketOutlet_Wall_3Phase | 73450 | 73450 | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full
440_EF_SocketOutlet_Wall_4Gangs | 73451 | 73451 | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full
440_EF_SocketOutlet_Wall_Combination | 73452 | 73452 | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full
440_EF_SocketOutlet_WallMounted_WaterProof | 73449 | 73449 | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full
440_EF_Switch_1Gang | 73457 | 73457 | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full
440_EF_Switch_2Gang | 73458 | 73458 | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full
440_EF_Switch_2Gang2Way | 73459 | 73459 | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full
440_EF_Switch_3Gang | 73460 | 73460 | 2026-06-18 | 2026-08-20 | 46 | handler_assign | confirm_note:stored_full
440_EF_SwitchableSocketOutlet_Ceiling | 73453 | 73453 | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full
440_EF_SwitchableSocketOutlet_Floor | 73454 | 73454 | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full
440_EF_SwitchPushButton_FlushMounted | 73456 | 73456 | 2026-06-18 | 2026-08-20 | 46 | handler_assign | confirm_note:stored_full
440_EF_Thermosat | 73462 | 73462 | 2026-06-18 | 2026-08-26 | 50 | handler_assign | confirm_note:stored_full
440_EF_TouchPanelRoomOperating_WallMounted | 73463 | 73463 | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full
440_EF_TripleSocketOutlet_Ceiling | 73464 | 73464 | 2026-06-18 | 2026-08-07 | 37 | handler_assign | confirm_note:stored_full
440_EF_TripleSocketOutlet_Floor | 73465 | 73465 | 2026-06-18 | 2026-08-25 | 49 | handler_assign | confirm_note:stored_full
440_EF_TripleSocketOutlet_Wall | 73466 | 73466 | 2026-06-18 | 2026-08-12 | 40 | handler_assign | confirm_note:stored_full
440_EF_UpDownControlSwitch | 74845 | 74845 | 2026-07-28 | 2026-07-31 | 4 | handler_assign | confirm_note:stored_full
440_EF_WindowMotor_WallMounted | 73467 | 73467 | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full
440_LD_DoubleSwitchSocket_WallMounted | 73988 | 73988 | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full
440_LD_SingleSwitchSocket_WallMounted | 73989 | 73989 | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full
440_LF_BathroomLuminaire_WallMounted_Rectangular | 73694 | 73694 | 2026-06-22 | 2026-09-10 | 59 | handler_assign | confirm_note:stored_full
440_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square_SQ5D | 73736 | 73736 | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full
440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round | 73737 | 73737 | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full
440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round_SQ6 | 73738 | 73738 | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full
440_LF_RoomSignalLight | 74844 | 74844 | 2026-07-27 | 2026-07-29 | 3 | handler_assign | confirm_note:stored_full
440_NC_CancelCallButton | 74841 | 74841 | 2026-07-28 | 2026-07-28 | 1 | handler_assign | status_resolved
440_NC_EmergencyCallButton | 75031 | 75031 | 2026-08-03 | 2026-08-06 | 4 | handler_assign | confirm_note:stored_full
440_NC_EmergencyPullCordSwitch_Wall | 74541 | 74541 | 2026-07-15 | 2026-09-04 | 38 | handler_assign | confirm_note:stored_full
440_NC_PullCordSwitch_WallMounted | 74839 | 74839 | 2026-07-27 | 2026-08-06 | 9 | handler_assign | confirm_note:stored_full
440_SE_AccessPanel_Ceiling | 73992 | 73992 | 2026-06-30 | 2026-09-28 | 65 | handler_assign | confirm_note:stored_full
440_SE_Penetration_Curaflex | 73993 | 73993 | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full
442_EE_ChargeController | 72536 | 72536 | 2026-05-29 | 2026-09-15 | 78 | handler_assign | confirm_note:stored_full
442_EE_FlatRoofSolarModule | 75059 | 75059 | 2026-08-04 | 2026-09-04 | 24 | handler_assign | confirm_note:stored_full
442_EF_SealedBatteries | 74479 | 74479 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
442_SD_UPSBattery_FloorStand_Rectangular | 74516 | 74516 | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full
443_EE_LowVoltageSwitchboard_GHVSüd_HOST | 73000 | 73000 | 2026-06-05 | 2026-09-22 | 78 | handler_assign | confirm_note:stored_full
443_EF_OvervoltageProtection_WallFlush | 74478 | 74478 | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full
444_CI_ABS_mIndustrialBox | 74475 | 74475 | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full
444_EE_SinglePhase_Panel | 73017 | 73017 | 2026-06-05 | 2026-09-18 | 76 | handler_assign | confirm_note:stored_full
444_EF_GooseneckBushing_NoSystem | 73359 | 73359 | 2026-06-15 | 2026-08-28 | 55 | handler_assign | confirm_note:stored_full
444_EF_InstallationTrunking | 73361 | 73361 | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full
444_EF_SocketOutlet_Rec_Floor | 73445 | 73445 | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full
444_EF_SocketOutlet_VerticalWallSurface_4Gangs | 73447 | 73447 | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full
444_EF_SwitchableSocketOutlet_WallSurface | 73455 | 73455 | 2026-06-18 | 2026-08-21 | 47 | handler_assign | confirm_note:stored_full
444_EF_USBSocketOutlet_WallFlush | 73446 | 73446 | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full
445_LF_3FoldPendantLight_CeilingSuspended | 73692 | 73692 | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full
445_LF_CoreLineLEDLight_CeilingSuspended | 73697 | 73697 | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full
445_LF_CoreLineLEDLight_WallSurface | 73698 | 73698 | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full
445_LF_CorelineSlimDownlight_CeilingMounted | 73699 | 73699 | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full
445_LF_CorelineSlimDownlight_CeilingRecessed | 73700 | 73700 | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full
445_LF_CorelineSpotlight_CeilingRecessed | 73701 | 73701 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_DownlightLEDrigid_CeilingRecessed | 73702 | 73702 | 2026-06-22 | 2026-09-07 | 56 | handler_assign | confirm_note:stored_full
445_LF_DownlightLEDSwivelling_CeilingRecessed | 73703 | 73703 | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full
445_LF_EscapeSign_CeilingMounted | 73704 | 73704 | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full
445_LF_EscapeSign_CeilingRecessed | 73705 | 73705 | 2026-06-22 | 2026-09-22 | 67 | handler_assign | confirm_note:stored_full
445_LF_EscapeSign_WallMounted | 73706 | 73706 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_ExitCube_Ceiling | 73707 | 73707 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_FixedOpticSmallBodyIroundOutdoorlight_CeilingRecessed | 73708 | 73708 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_GreenSpaceAccentSpotlightRigid_CeilingRecessed | 73709 | 73709 | 2026-06-22 | 2026-08-11 | 37 | handler_assign | confirm_note:stored_full
445_LF_InteriorLuminaireBL_CeilingRecessed_Rectangular | 73811 | 73811 | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full
445_LF_InteriorLuminaireINDMP_CeilingRecessed_Round | 73812 | 73812 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
445_LF_LaserBladeLightXS_CeilingRecessed | 73713 | 73713 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_LaserBladeLightXSWallWasher_CeilingRecessed | 73712 | 73712 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_LeadSacidTwinHeadEmergencyLight_WallSurface | 73714 | 73714 | 2026-06-22 | 2026-08-07 | 35 | handler_assign | confirm_note:stored_full
445_LF_LEDAccentRigidlight_CeilingRecessed_Rectangular | 73716 | 73716 | 2026-06-22 | 2026-08-14 | 40 | handler_assign | confirm_note:stored_full
445_LF_LEDBAPPendantLightWithAdjustableRod_CeilingSuspended | 73717 | 73717 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_LEDDeckeneinbauMontage_CeilingMounted_LG6E | 73718 | 73718 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDDoubleHeadEmergencyLight_WallSurface | 73719 | 73719 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_LEDDownlightForWC_CeilingRecessed | 73720 | 73720 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_LEDDownlightOP_CeilingRecessed_Round | 73813 | 73813 | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full
445_LF_LEDDownlightSFNB_CeilingRecessed_Round | 73814 | 73814 | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full
445_LF_LEDDownlightSM_CeilingRecessed_Round | 73723 | 73723 | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full
445_LF_LEDHighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod | 73724 | 73724 | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full
445_LF_LedinaireHighbayPendantLightWithAdjustableRod_CeilingSuspended | 73725 | 73725 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_LedinaireSlimDownlight_CeilingSuspended | 73726 | 73726 | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full
445_LF_LEDLuminaireMP_CeilingMounted_Rectangular | 73815 | 73815 | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full
445_LF_LEDLuminaireOP_CeilingMounted_Rectangular | 73816 | 73816 | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full
445_LF_LEDMasterEmergencyLightingLuminaire_WallMounted | 73729 | 73729 | 2026-06-22 | 2026-08-24 | 46 | handler_assign | confirm_note:stored_full
445_LF_LEDPanel_CeilingRecessed | 73730 | 73730 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDPendantLightWithAdjustableRod_CeilingSuspended | 73731 | 73731 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDPendantRingLight | 73732 | 73732 | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full
445_LF_LEDSignalLightForWC_WallMounted | 73733 | 73733 | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full
445_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square | 73735 | 73735 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Round | 73740 | 73740 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Square | 73741 | 73741 | 2026-06-22 | 2026-09-25 | 70 | handler_assign | confirm_note:stored_full
445_LF_LEDSpotEmergencyLightingLuminaireInFireResistantCeiling_CeilingRecessed | 73734 | 73734 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDSpotEmergencyLightingLuminaire_WallMounted_Square_SQ5A | 73742 | 73742 | 2026-06-22 | 2026-08-24 | 46 | handler_assign | confirm_note:stored_full
445_LF_LEDStairEmergencyLight_WallSurface | 73743 | 73743 | 2026-06-22 | 2026-08-11 | 37 | handler_assign | confirm_note:stored_full
445_LF_LEDStripLight_CeilingMounted_Rectangular | 73744 | 73744 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDStripLight_CeilingRecessed_Rectangular | 73745 | 73745 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDStripLight_WallSurface_Rectangular | 73746 | 73746 | 2026-06-22 | 2026-09-22 | 67 | handler_assign | confirm_note:stored_full
445_LF_LEDTwinHeadsFastChargingIP30EmergencyLight_WallSurface | 73747 | 73747 | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full
445_LF_LEDTwoHeadWaterProofIP65EmergencyLight_WallSurface | 73798 | 73798 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
445_LF_LEDUplight_FloorRecessed_Round | 73799 | 73799 | 2026-06-25 | 2026-09-24 | 66 | handler_assign | confirm_note:stored_full
445_LF_LuxSpaceAccentPerformanceSpotlightSwiveling_CeilingRecessed | 73801 | 73801 | 2026-06-25 | 2026-08-26 | 45 | handler_assign | confirm_note:stored_full
445_LF_LuxSpaceCompactAnbaudownlight_CeilingSuspended | 73802 | 73802 | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full
445_LF_LuxSpaceDownlight_CeilingRecessed_Square | 73803 | 73803 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
445_LF_MoistureProofLuminaire_CeilingSuspended_Rectangular | 73805 | 73805 | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full
445_LF_MoistureProofLuminaire_WallSurface_Rectangular | 73817 | 73817 | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full
445_LF_OpticalLight_CeilingRecessed_Round_Outdoor | 73807 | 73807 | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full
445_LF_TrackSpot_S_CeilingMounted | 73808 | 73808 | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full
445_LF_TruelineLinearLuminaire_CeilingRecessed | 73809 | 73809 | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full
445_LF_UVCAirDisinfectionLight_WallSurface | 73810 | 73810 | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full
446_EF_AirTerminationRods_FloorStand | 73164 | 73164 | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full
446_EF_AirTerminationRodsForMetalRoofs | 73163 | 73163 | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full
446_EF_EarthingFixedPoint_WallSurface | 73208 | 73208 | 2026-06-11 | 2026-09-16 | 70 | handler_assign | confirm_note:stored_full
446_EF_Earthing_WallSurface | 73209 | 73209 | 2026-06-11 | 2026-08-11 | 44 | handler_assign | confirm_note:stored_full
446_EF_EarthTestBox | 73351 | 73351 | 2026-06-15 | 2026-08-19 | 48 | handler_assign | confirm_note:stored_full
446_EF_EquipotentialBondingBusbars_WallMounted | 73355 | 73355 | 2026-06-15 | 2026-08-21 | 50 | handler_assign | confirm_note:stored_full
446_EF_LightningCounterDevice | 74476 | 74476 | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full
446_EF_LightningRod_NoSystem | 74477 | 74477 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
451_DD_TelOutlet_WallMounted_2Gangs | 74520 | 74520 | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full
451_EF_TelephoneOutlet_Single | 73461 | 73461 | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full
452_CD_CallButtonPullCord | 74485 | 74485 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
452_EF_TouchButton_WallMounted | 74480 | 74480 | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full
454_CD_CabinetLoudspeaker6W_WallMounted_Circular | 74482 | 74482 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
454_CD_CabinetLoudspeaker6W_WallMounted_Rectangular | 74483 | 74483 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
454_CD_CabinetLoudspeaker6W_WallMounted_Square | 74484 | 74484 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
454_CD_FireDepartmentContactPoint_WallMounted | 74487 | 74487 | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full
454_CD_HornLoudspeaker15W_WallMounted | 74488 | 74488 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
454_CD_Loudspeaker6W_CeilingRecessed | 74497 | 74497 | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full
454_EE_PublicAddressSystemPanel_FloorMounted | 74468 | 74468 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
454_FA_VandalResistantLoudSpeaker | 74450 | 74450 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
455_CD_IndoorAntenna_Ceiling | 73994 | 73994 | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full
455_DD_TVOutlet_WallMounted_1Gang | 74521 | 74521 | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full
456_CD_DeskIntercomStation | 74486 | 74486 | 2026-07-13 | 2026-09-21 | 51 | handler_assign | confirm_note:stored_full
456_CD_Siren | 74499 | 74499 | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full
456_EE_BMABusCoupler | 73024 | 73024 | 2026-06-05 | 2026-08-26 | 59 | handler_assign | confirm_note:stored_full
456_EE_ConventionalControlPanel_WallSurface_Rectangular | 74453 | 74453 | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full
456_EE_PowerSupplyUnitAccessControl_WallMounted | 74467 | 74467 | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full
456_EF_InfraredMotionDetector_WallMounted | 75095 | 75095 | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full
456_FA_AddressableSensor | 74411 | 74411 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_AspiratingSmokeDetector_WallMounted | 74416 | 74416 | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full
456_FA_AspiratingSmokesSystem2Channel_WallMounted | 73986 | 73986 | 2026-06-30 | 2026-09-28 | 65 | handler_assign | confirm_note:stored_full
456_FA_BeamSensor_WallSurface_Rectangular | 74418 | 74418 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_CouplerUnit | 74421 | 74421 | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full
456_FA_Detector_CO1224A | 74423 | 74423 | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full
456_FA_Detector_CO1224TR | 74424 | 74424 | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full
456_FA_DetectorWithHorn | 74422 | 74422 | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full
456_FA_EmegencyDoorRelease_WallMounted | 74425 | 74425 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_FireAlarmCenter | 74426 | 74426 | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full
456_FA_FireAlarmControlPanel | 74427 | 74427 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_FireAlarmZoneModuleControl | 74428 | 74428 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_FireBrigadeInformationCenter_WallMounted | 74429 | 74429 | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full
456_FA_FireDepartmentKeyDepot | 74430 | 74430 | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full
456_FA_HeatSensor | 74432 | 74432 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_LinearHeatDetector | 74434 | 74434 | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full
456_FA_ManualCallPoint_WallMounted_Square | 74447 | 74447 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_ManualCallPoint_WallMounted_Square_Waterproof | 74448 | 74448 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_MultiSensorDetector_Ceiling | 74435 | 74435 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
456_FA_O2TMultisensordetector | 74436 | 74436 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_O2TMultisensordetector_BottomSlab | 74438 | 74438 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
456_FA_PhotoelectricSmokeDetector | 74437 | 74437 | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full
456_FA_PhotoThermalSensor_CeilingMouted_Round | 74439 | 74439 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
456_FA_PresenceDetector24m_Ceiling | 74440 | 74440 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
456_FA_PresenceDetectorHTS_Ceiling | 74441 | 74441 | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full
456_FA_PushButton_WallMounted_RWA | 74442 | 74442 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
456_FA_SmokeSamplingHead_Ceiling | 73987 | 73987 | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full
456_FA_SmokeSensor_BottomSlab | 74444 | 74444 | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full
456_FA_SmokeSensor_Ceiling | 74445 | 74445 | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full
456_FA_SmokeSensor_RaiseFloor | 74446 | 74446 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
456_FA_WindandRainDetector_WallMounted_RWA | 74451 | 74451 | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full
456_SD_ActiveGlassBreakDetector | 74981 | 74981 | 2026-07-28 | 2026-08-05 | 7 | handler_assign | confirm_note:stored_full
456_SD_AnalogCamera | 74500 | 74500 | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full
456_SD_CameraHub_16Port | 74501 | 74501 | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full
456_SD_CameraHub_8Port | 74502 | 74502 | 2026-07-14 | 2026-08-25 | 31 | handler_assign | confirm_note:stored_full
456_SD_CardReader | 74503 | 74503 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_CombinedOpeningLockingContact | 74984 | 74984 | 2026-07-28 | 2026-08-11 | 11 | handler_assign | confirm_note:stored_full
456_SD_DomeCamera_Indoor | 74504 | 74504 | 2026-07-14 | 2026-08-25 | 31 | handler_assign | confirm_note:stored_full
456_SD_DomeCamera_Outdoor | 74505 | 74505 | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full
456_SD_DuressAlarmDetector | 74980 | 74980 | 2026-07-28 | 2026-08-06 | 8 | handler_assign | confirm_note:stored_full
456_SD_ElectricalLock_DoorMounted | 74506 | 74506 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_FingerScan | 74507 | 74507 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_FingerScanFace_WallMounted | 74508 | 74508 | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full
456_SD_FixCameraIP_Indoor | 74509 | 74509 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_FixCameraIP_Outdoor | 74510 | 74510 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_KeyCardTransponder_WallMounted | 75093 | 75093 | 2026-08-06 | 2026-08-13 | 6 | handler_assign | confirm_note:stored_full
456_SD_Keypad_WallMounted | 75094 | 75094 | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full
456_SD_LockingElementVertical_DoorMounted | 75096 | 75096 | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full
456_SD_LockIntegratedMonitor | 75408 | 75408 | 2026-08-17 | 2026-08-18 | 2 | handler_assign | confirm_note:stored_full
456_SD_Monitor | 74511 | 74511 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_PassiveGlassBreakDetector | 74982 | 74982 | 2026-07-28 | 2026-08-11 | 11 | handler_assign | confirm_note:stored_full
456_SD_PTZCamera_Indoor | 74512 | 74512 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_PTZCamera_Outdoor | 74513 | 74513 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
456_SD_SecurityAlarmBell | 74514 | 74514 | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full
456_SD_ThermalCamera | 74515 | 74515 | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full
457_CD_Router_Indoor | 74498 | 74498 | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full
457_DD_LanAndTelOutlet_WallSurface | 74518 | 74518 | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full
457_DD_LanOutlet_WallMounted_2Gangs | 74519 | 74519 | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full
457_EE_DataCabinet | 74454 | 74454 | 2026-07-10 | 2026-09-04 | 41 | handler_assign | confirm_note:stored_full
457_EE_DataServerCabinet_FloorStand_Rectangular | 74455 | 74455 | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full
457_EF_DataConnectionSocket_CeilingMounted_WaterProof | 73188 | 73188 | 2026-06-10 | 2026-09-16 | 71 | handler_assign | confirm_note:stored_full
457_EF_VideoModul | 73468 | 73468 | 2026-06-18 | 2026-08-07 | 37 | handler_assign | confirm_note:stored_full
457_SD_DomeCamera_Outdoor | 73991 | 73991 | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full
473_EF_BathroomCallUnit_PullCord | 72345 | 72345 | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full
473_EF_BathroomCallUnit_PushButton | 72346 | 72346 | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full
473_EF_DoorUnit | 72350 | 72350 | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full
473_EF_ElectronicBuzzer_WallSurface | 72351 | 72351 | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full
473_EF_RemoteControlModules | 72352 | 72352 | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full
473_EF_SocketForCordedPushButton_WallSurface | 72353 | 72353 | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full
473_EF_SocketforHandPushButton | 72354 | 72354 | 2026-05-28 | 2026-08-28 | 67 | handler_assign | confirm_note:stored_full
473_ME_ActivatedCarbonTower | 72356 | 72356 | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full
473_ME_AirDryer | 72357 | 72357 | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full
473_ME_AirDryer_Vertical | 72358 | 72358 | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full
473_ME_AirPurifiers | 72359 | 72359 | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full
473_ME_AirReceiverTank | 72360 | 72360 | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full
473_ME_BHU_HY2017D | 72366 | 72366 | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full
473_ME_BHU_HY2017DS | 72367 | 72367 | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full
473_ME_BHU_SC2015 | 72368 | 72368 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full
473_ME_BHU_Vertical | 72369 | 72369 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full
473_ME_BottleFillingPlant | 72370 | 72370 | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full
473_ME_CompactH2O2DecontaminationAirlock | 72371 | 72371 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full
473_ME_CylinderTank_NoSystem | 72372 | 72372 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full
473_ME_DesiccantAdsorptionCompressedAirDryers | 72373 | 72373 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full
473_ME_DryVacuumPump | 72374 | 72374 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
473_ME_ExternalHeatRecoveryUnits | 72375 | 72375 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
473_ME_HeatlessRegenerationAdsorptionDryers | 72376 | 72376 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
473_ME_HeatlessRegenerationAdsorptionDryers_ActivatedCarbonTower | 72377 | 72377 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
473_ME_HeatRegenerationAdsorptionDryers | 72378 | 72378 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
473_ME_ICU_Eurocare | 72379 | 72379 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
473_ME_ICU_EurocareD | 72380 | 72380 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_ME_MedicalAirCompressors_FloorMounted | 72385 | 72385 | 2026-05-28 | 2026-08-14 | 57 | handler_assign | confirm_note:stored_full
473_ME_VacuumPump | 72391 | 72391 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_ME_ZoneWallUnit_CZ200 | 72392 | 72392 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_ME_ZoneWallUnit_HST100 | 72393 | 72393 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_ME_ZoneWallUnit_HST200 | 72394 | 72394 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PA_3WayMotorControlValve_Threaded | 72395 | 72395 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full
473_PA_3WayValveDN15toDN50_Threaded | 72410 | 72410 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_AGSSOutletType1L | 72396 | 72396 | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full
473_PA_AirHeader_10Connection | 72398 | 72398 | 2026-05-28 | 2026-08-17 | 58 | handler_assign | confirm_note:stored_full
473_PA_AirHeader_12Connection | 72399 | 72399 | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full
473_PA_AirHeader_14Connection | 72400 | 72400 | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full
473_PA_AirHeader_16Connection | 72401 | 72401 | 2026-05-28 | 2026-07-31 | 47 | handler_assign | confirm_note:will_be_closed
473_PA_AirHeader_18Connection | 72402 | 72402 | 2026-05-28 | 2026-07-31 | 47 | handler_assign | confirm_note:will_be_closed
473_PA_AirHeader_8Connection | 72397 | 72397 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PA_AirPressureRegulator_Mapress | 72403 | 72403 | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full
473_PA_AirRegulatorValve_Threaded | 72404 | 72404 | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full
473_PA_AirReliefValve_Threaded | 72411 | 72411 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_AirVentingFilters_Standard | 72405 | 72405 | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full
473_PA_AutoDrainValve_FloatType_Threaded | 72406 | 72406 | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full
473_PA_AutomaticMechanicalCondensateDrain | 72407 | 72407 | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full
473_PA_BallValve_Threaded | 72408 | 72408 | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full
473_PA_CheckValve_Threaded | 72412 | 72412 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_ClampedStraightSightGlass | 72413 | 72413 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PA_CompressedAirFilters_DDp | 72414 | 72414 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_CompressedAirFilters_QDT | 72416 | 72416 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_CondensateDistributor12Branch_WOSCD | 72420 | 72420 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_CondensateDistributor2Branch_WOSCD | 72417 | 72417 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_CondensateDistributor4Branch_WOSCD | 72418 | 72418 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_CondensateDistributor8Branch_WOSCD | 72419 | 72419 | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full
473_PA_CS_PressureReducingValve_Flanged | 72421 | 72421 | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full
473_PA_CycloneSeparator_Standard | 72422 | 72422 | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full
473_PA_ElectronicCondensateDrain | 72424 | 72424 | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full
473_PA_ElectronicMotorizedValve | 72425 | 72425 | 2026-05-28 | 2026-08-14 | 57 | handler_assign | confirm_note:stored_full
473_PA_Filters_Flanged | 72426 | 72426 | 2026-05-28 | 2026-08-17 | 58 | handler_assign | confirm_note:stored_full
473_PA_GasO2Outlet | 72429 | 72429 | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full
473_PA_LineBallValve_LV10_V | 72430 | 72430 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PA_LineBallValve_LV10VF | 72431 | 72431 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PA_MembraneAirDryers | 72435 | 72435 | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full
473_PA_MotorizedPneumaticDiaphragmValve_Welded | 72436 | 72436 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PA_N2OOutlet | 72438 | 72438 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PA_NRVValve | 72439 | 72439 | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full
473_PA_PlasticBox_Air | 72440 | 72440 | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full
473_PA_PneumaticButterflyValve_Welded | 72441 | 72441 | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full
473_PA_PneumaticDiaphragmValveWithAlarm | 72442 | 72442 | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full
473_PA_PneumaticManualDiaphragmValve | 72443 | 72443 | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full
473_PA_PressureGauge_ElectricalContactCodeA | 72444 | 72444 | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full
473_PA_RectangularPressureRegulator | 72445 | 72445 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_SafetyValve | 72446 | 72446 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_ShutOffValveBox_MultiConnection | 72447 | 72447 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_SingleZone_ValveBox | 72448 | 72448 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_SS_CouplingsFemale_Threaded | 72451 | 72451 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_SS_HighPressureProcessFilters_Welded | 72452 | 72452 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_SS_PressureGauge_AnalogueType | 72453 | 72453 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_SS_PressureReducingValve_Flanged | 72454 | 72454 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_StainlessSteel1WayValve | 72456 | 72456 | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full
473_PA_StainlessSteelFlexibleConnection | 72457 | 72457 | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full
473_PA_SterileFilters_SFSeries_Flanged | 72458 | 72458 | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full
473_PA_VAC_Outlet | 72459 | 72459 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_WaterOilSeparators_WOS | 72460 | 72460 | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full
473_PA_WaterOilSeparators_WOSm | 72461 | 72461 | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full
473_PA_WeldedCondensateSeparators | 72455 | 72455 | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full
473_PF_CO_cEndCap_Soldered | 72486 | 72486 | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:stored_full
473_PF_CO_eElbow180_Soldered | 72490 | 72490 | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:will_be_closed
473_PF_CO_eElbow45_FemaleAndFemaleSoldered | 72488 | 72488 | 2026-05-28 | 2026-07-16 | 36 | handler_assign | confirm_note:stored_full
473_PF_CO_eElbow45_MaleAndFemaleSoldered | 72489 | 72489 | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full
473_PF_CO_eElbowLongRadiusFF_Soldered | 72491 | 72491 | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:stored_full
473_PF_CO_eElbowShortRadiusMF_Soldered | 72492 | 72492 | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full
473_PF_CO_eLongRadius_MFSoldered | 72493 | 72493 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PF_CO_eLongRadius_Soldered | 72494 | 72494 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full
473_PF_CO_eOffset_Soldered | 72495 | 72495 | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full
473_PF_CO_eShortRadiusFF_Soldered | 72496 | 72496 | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full
473_PF_CO_rReducer_FemaleSoldered | 72336 | 72336 | 2026-05-28 | 2026-06-29 | 23 | handler_assign | status_resolved
473_PF_CO_rReducerMF_Soldered | 72337 | 72337 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
473_PF_CO_tEqualTee_FemaleSoldered | 72338 | 72338 | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full
473_PF_CO_tTee_Reducing_FemaleSoldered | 72339 | 72339 | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full
473_PF_CO_uOffsetFF_Soldered | 72341 | 72341 | 2026-05-28 | 2026-07-14 | 34 | handler_assign | confirm_note:stored_full
473_PF_SS_tTee_Welded | 72342 | 72342 | 2026-05-28 | 2026-07-29 | 45 | handler_assign | confirm_note:stored_full
474_ME_AirSamplingPump | 71761 | 71761 | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:stored_full
474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC1kg | 71714 | 71714 | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full
474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC6kg | 71716 | 71716 | 2026-05-14 | 2026-06-29 | 33 | handler_assign | confirm_note:stored_full
474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC8kg | 71719 | 71719 | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full
474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve | 71762 | 71762 | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full
474_ME_Cabinet_FlushMountedWall | 71763 | 71763 | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full
474_ME_Compressor | 71764 | 71764 | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full
474_ME_ControlBox_CO2 | 71765 | 71765 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full
474_ME_CylinderAssemblies_CO2 | 71722 | 71722 | 2026-05-14 | 2026-05-19 | 4 | handler_assign | status_resolved
474_ME_CylinderTank_FM200 | 71743 | 71743 | 2026-05-14 | 2026-07-09 | 41 | handler_assign | confirm_note:stored_full
474_ME_EndSuctionFirePump | 71726 | 71726 | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full
474_ME_FE_AutomaticDryPowerCeiling_HFC17_NoSystem | 71727 | 71727 | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full
474_ME_FireExtinguisherCarbonDioxide | 71749 | 71749 | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full
474_ME_FireExtinguisherPortable_Foam | 71751 | 71751 | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full
474_ME_FireExtinguisherPortable_Powder | 71728 | 71728 | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full
474_ME_FireHoseReel_WallSurface | 71729 | 71729 | 2026-05-14 | 2026-07-13 | 43 | handler_assign | confirm_note:stored_full
474_ME_FirePump_Horizontal_SplitCase | 71732 | 71732 | 2026-05-14 | 2026-08-18 | 69 | handler_assign | confirm_note:stored_full
474_ME_FireValveBox | 71733 | 71733 | 2026-05-14 | 2026-08-12 | 65 | handler_assign | confirm_note:stored_full
474_ME_FoamBladderTank_HorizontalType | 71735 | 71735 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full
474_ME_FoamPump | 71737 | 71737 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full
474_ME_HorizontalPresssureTank | 71738 | 71738 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full
474_ME_JockeyPump | 71739 | 71739 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full
474_ME_MasterCylinderWithTopValveOfActuator_CO2 | 71767 | 71767 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full
474_PA_3WayBronzeGlobeValve | 71770 | 71770 | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full
474_PA_AerationVentilationValve | 71771 | 71771 | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full
474_PA_AirMaintenanceCompressorAssembly | 71748 | 71748 | 2026-05-14 | 2026-07-09 | 41 | handler_assign | confirm_note:stored_full
474_PA_AirVentValve | 71750 | 71750 | 2026-05-14 | 2026-07-01 | 35 | handler_assign | confirm_note:stored_full
474_PA_AlarmCheckValve_European | 72245 | 72245 | 2026-05-27 | 2026-08-21 | 63 | handler_assign | confirm_note:stored_full
474_PA_AlarmCheckValve_Preaction | 72246 | 72246 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_AlarmPressureSwitch | 71752 | 71752 | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full
474_PA_AlarmTestModuleGrooveEnd | 72247 | 72247 | 2026-05-27 | 2026-07-24 | 43 | handler_assign | confirm_note:stored_full
474_PA_AlarmTestModulePressureReliefValve_ThreadEnd | 71754 | 71754 | 2026-05-14 | 2026-08-20 | 71 | handler_assign | confirm_note:stored_full
474_PA_AlarmTestModuleThreadEnd | 71755 | 71755 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full
474_PA_AngleHoseValve | 71756 | 71756 | 2026-05-14 | 2026-07-02 | 36 | handler_assign | confirm_note:stored_full
474_PA_AutoConvertAssembly | 71757 | 71757 | 2026-05-14 | 2026-08-20 | 71 | handler_assign | confirm_note:stored_full
474_PA_AutoDrainValve_FloatType_Threaded | 71758 | 71758 | 2026-05-14 | 2026-07-27 | 53 | handler_assign | confirm_note:stored_full
474_PA_AutomaticConcentrateControlValve_Foam | 72248 | 72248 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_BallValve | 72249 | 72249 | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full
474_PA_BallValves_GrooveAndGroove | 72250 | 72250 | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full
474_PA_BallValvesThreadandThread | 72251 | 72251 | 2026-05-27 | 2026-07-31 | 48 | handler_assign | confirm_note:stored_full
474_PA_BrassBodyBallValves_Threaded | 72252 | 72252 | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full
474_PA_ButterflyValve | 72253 | 72253 | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full
474_PA_ButterflyValveSupervisedOpen | 71760 | 71760 | 2026-05-14 | 2026-08-04 | 59 | handler_assign | confirm_note:stored_full
474_PA_CheckValve | 72254 | 72254 | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full
474_PA_CheckValveAlternateWetDrySystem | 72255 | 72255 | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full
474_PA_CylinderValve_CO2 | 71723 | 71723 | 2026-05-14 | 2026-08-19 | 70 | handler_assign | confirm_note:stored_full
474_PA_DelugeValve | 71724 | 71724 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full
474_PA_DiaphragmValves | 71768 | 71768 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full
474_PA_DischargeValve | 71597 | 71597 | 2026-05-11 | 2026-09-04 | 85 | handler_assign | confirm_note:stored_full
474_PA_DoubleDoorCheckValve | 72261 | 72261 | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full
474_PA_DryAccelerator | 72262 | 72262 | 2026-05-27 | 2026-07-22 | 41 | handler_assign | confirm_note:stored_full
474_PA_DryPilotActuator | 72263 | 72263 | 2026-05-27 | 2026-07-28 | 45 | handler_assign | confirm_note:stored_full
474_PA_DuplexPressureGauges | 71769 | 71769 | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full
474_PA_FireHoseAngleValveWithCap | 72260 | 72260 | 2026-05-27 | 2026-08-13 | 57 | handler_assign | confirm_note:stored_full
474_PA_FireLockAlarmCheckValve | 72265 | 72265 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_FireLockBallValve | 72264 | 72264 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_FlexibleMetalHose | 71772 | 71772 | 2026-05-14 | 2026-07-27 | 53 | handler_assign | confirm_note:stored_full
474_PA_FlowTestMeter_Flange | 71773 | 71773 | 2026-05-14 | 2026-08-21 | 72 | handler_assign | confirm_note:stored_full
474_PA_Flushing_Connection | 71774 | 71774 | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full
474_PA_FM200_ActuatorBox | 71777 | 71777 | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full
474_PA_FM200_DischagePressureSwitch | 72266 | 72266 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_FM200_SectorValve_Flanged | 71781 | 71781 | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full
474_PA_FM200_SectorValve_Threaded | 71782 | 71782 | 2026-05-14 | 2026-08-14 | 67 | handler_assign | confirm_note:stored_full
474_PA_FM200_SolenoidValve | 71783 | 71783 | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full
474_PA_Foam_AutomaticControlValve_Flanged | 71785 | 71785 | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full
474_PA_Foam_DuctileIron_DelugeValve_AngleStype | 71786 | 71786 | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full
474_PA_Foam_InLineBalancedPressureProportioners | 71787 | 71787 | 2026-05-14 | 2026-08-03 | 58 | handler_assign | confirm_note:stored_full
474_PA_GateValve | 71594 | 71594 | 2026-05-11 | 2026-08-14 | 70 | handler_assign | confirm_note:stored_full
474_PA_GateValveWithElectricActuator | 72257 | 72257 | 2026-05-27 | 2026-08-21 | 63 | handler_assign | confirm_note:stored_full
474_PA_InlineCheckValve_CO2 | 71789 | 71789 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full
474_PA_LevelControlValves_Flange | 72272 | 72272 | 2026-05-27 | 2026-07-17 | 38 | handler_assign | confirm_note:stored_full
474_PA_LevelControlValves_Grooved | 72273 | 72273 | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:will_be_closed
474_PA_MaintenanceUnit | 71596 | 71596 | 2026-05-11 | 2026-08-21 | 75 | handler_assign | confirm_note:stored_full
474_PA_ManifoldCheckValve_Grooved | 71791 | 71791 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full
474_PA_ManifoldCheckValve_Threaded | 71792 | 71792 | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full
474_PA_ManualPneumaticActuator_FM200 | 72276 | 72276 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_NRSOS&YGateValves_GrooveAndFlange | 72277 | 72277 | 2026-05-27 | 2026-09-11 | 78 | handler_assign | confirm_note:stored_full
474_PA_NRSOS&YGateValves_GrooveAndGroove | 71794 | 71794 | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full
474_PA_OS&YGateValves_GrooveAndFlange | 72279 | 72279 | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full
474_PA_OS&YGateValves_GrooveAndGroove | 71796 | 71796 | 2026-05-14 | 2026-07-08 | 40 | handler_assign | confirm_note:stored_full
474_PA_PressureGauge_withBallValve | 72280 | 72280 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_PressureMeter | 72281 | 72281 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full
474_PA_PressureOperatedDirectionalValve_CO2 | 72282 | 72282 | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full
474_PA_PressureReducingControlValve_Groove | 72283 | 72283 | 2026-05-27 | 2026-08-13 | 57 | handler_assign | confirm_note:stored_full
474_PA_PressureReducingControlValveThread | 71798 | 71798 | 2026-05-14 | 2026-08-14 | 67 | handler_assign | confirm_note:stored_full
474_PA_PressureSwitch_FM200 | 72287 | 72287 | 2026-05-27 | 2026-08-05 | 51 | handler_assign | confirm_note:stored_full
474_PA_RiserCheckValve | 72288 | 72288 | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full
474_PA_RubberExpansionJoint_Flanged | 72289 | 72289 | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full
474_PA_RubberExpansionJoint_Threaded | 72290 | 72290 | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full
474_PA_SafertyReliefValve_CO2 | 72292 | 72292 | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full
474_PA_SafetyValve | 72293 | 72293 | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full
474_PA_ShutoffValve_Motorized | 72295 | 72295 | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full
474_PA_SightGlasses | 72296 | 72296 | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full
474_PA_SolenoidValve | 72297 | 72297 | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full
474_PA_SS_CompoundPressureGauge | 72298 | 72298 | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full
474_PA_StoneCatcher | 72299 | 72299 | 2026-05-27 | 2026-08-17 | 59 | handler_assign | confirm_note:stored_full
474_PA_WaterFlowDetector_ZoneCheck | 72259 | 72259 | 2026-05-27 | 2026-08-12 | 56 | handler_assign | confirm_note:stored_full
474_PA_WaterflowSwitches | 72301 | 72301 | 2026-05-27 | 2026-09-11 | 78 | handler_assign | confirm_note:stored_full
474_PA_ZoneControlRiserModule_Residential | 71731 | 71731 | 2026-05-14 | 2026-08-21 | 72 | handler_assign | confirm_note:stored_full
474_PF_CI_cCap_Threaded | 72214 | 72214 | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full
474_PF_CI_eShortBend_Threaded | 72216 | 72216 | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full
474_PF_CI_rReducer_Threaded | 72218 | 72218 | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full
474_PF_CI_tEqualTee_Thread | 72220 | 72220 | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full
474_PF_CI_tTeeReducing_Thread | 72221 | 72221 | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full
474_PF_CI_uHexNipple | 72217 | 72217 | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full
474_PF_CI_uUnion_Threaded | 72222 | 72222 | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full
474_PF_CI_xCross_Thread | 72215 | 72215 | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full
474_PF_CI_xSocketUnion_Threaded | 72219 | 72219 | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full
474_PF_CS_cCap_Grooved | 72223 | 72223 | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full
474_PF_CS_eElbowEndOfRun_Grooved | 72225 | 72225 | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full
474_PF_CS_eElbow_Grooved | 72224 | 72224 | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full
474_PF_CS_fConnection_Coupling_FireLockEZRigid | 72226 | 72226 | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full
474_PF_CS_fConnection_Coupling_FireLockRigid | 72227 | 72227 | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full
474_PF_CS_rConcentricReducer_Grooved | 72228 | 72228 | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full
474_PF_CS_rEccentricReducer_Grooved | 72229 | 72229 | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full
474_PF_CS_tEndTee_Grooved | 72212 | 72212 | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full
474_PF_CS_tLateralTee_Grooved | 72207 | 72207 | 2026-05-27 | 2026-07-23 | 42 | handler_assign | confirm_note:stored_full
474_PF_CS_tLateralThread_Standard | 72208 | 72208 | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full
474_PF_CS_tLowProfileSprinklerTee_Threaded | 72205 | 72205 | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full
474_PF_CS_tOutletReducingCouplingTee_Grooved | 72231 | 72231 | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full
474_PF_CS_tOutletReducingTee_Threaded | 72210 | 72210 | 2026-05-27 | 2026-06-23 | 20 | handler_assign | confirm_note:stored_full
474_PF_CS_tOutletTeeReducing_Coupling | 72209 | 72209 | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full
474_PF_CS_tReducingLateralTee_Grooved | 72211 | 72211 | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full
474_PF_CS_tReducingTee_Grooved | 72213 | 72213 | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full
474_PF_CS_uAdapterNipple_Flanged | 72206 | 72206 | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full
474_PF_CS_uAdaptorNipple_Grooved | 72234 | 72234 | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full
474_PF_CS_wTrueWye_Grooved | 72235 | 72235 | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full
474_PF_CS_xCross_Grooved | 72236 | 72236 | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full
474_PF_SS_eUnionElbow_Threaded | 72241 | 72241 | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full
474_PROMAT_Horizontal_Vertical_WallMount | 72317 | 72317 | 2026-05-28 | 2026-08-31 | 68 | handler_assign | confirm_note:stored_full
474_SP_FM200_180RadialNozzle_2Port | 72321 | 72321 | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full
474_SP_FM200_360RadialNozzle_1Port | 72322 | 72322 | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full
474_SP_FM200_360RadialNozzle_4Port | 72323 | 72323 | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full
474_SP_FM200_DischargeNozzle | 72324 | 72324 | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full
474_SP_FoamNozzle_Pendent | 72325 | 72325 | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full
474_SP_FoamNozzle_Upright | 72326 | 72326 | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full
474_SP_GE_DoubleSprinkler | 72327 | 72327 | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full
474_SP_GE_HorizontalSideWall | 72328 | 72328 | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full
474_SP_GE_HVSprayNozzles | 72329 | 72329 | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full
474_SP_GE_Pendent | 72330 | 72330 | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full
474_SP_GE_PendentCover | 72331 | 72331 | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full
474_SP_GE_SprayNozzles | 72332 | 72332 | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full
474_SP_GE_Upright | 72333 | 72333 | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full
474_SP_GE_UprightCover | 72334 | 72334 | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full
474_SP_GE_WindowOpenNozzle | 71759 | 71759 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full
480_EE_WallControlPanel_WallMounted | 74471 | 74471 | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full
480_FA_AddressableManualPullStation | 74405 | 74405 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
480_FA_AnnunciatorPanel | 74414 | 74414 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
480_FA_Bell | 74420 | 74420 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
480_FA_FireDoorHolder | 74431 | 74431 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
480_FA_LEDIndicator_WallMounted | 74433 | 74433 | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full
480_FA_SmokeDectectorOpticalSignal_Ceiling | 74443 | 74443 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
480_FA_TransferUnit | 74449 | 74449 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
481_DD_BACnetGateway | 74517 | 74517 | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full
481_EE_SmartHomeAccessPoint_WLAN | 73990 | 73990 | 2026-06-30 | 2026-09-15 | 56 | handler_assign | confirm_note:stored_full
481_EE_TransmissionDevice | 75092 | 75092 | 2026-08-06 | 2026-08-12 | 5 | handler_assign | confirm_note:stored_full
481_EF_DoorBusCoupler | 74983 | 74983 | 2026-07-28 | 2026-08-10 | 10 | handler_assign | confirm_note:stored_full
481_EF_Hygrostat | 73360 | 73360 | 2026-06-15 | 2026-08-27 | 54 | handler_assign | confirm_note:stored_full
481_EF_OutdoorAirTemperatureSensor | 73168 | 73168 | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full
481_SD_Distributor | 75097 | 75097 | 2026-08-06 | 2026-08-13 | 6 | handler_assign | confirm_note:stored_full
482_EE_ControlDistribution_WallMounted | 74452 | 74452 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
482_EE_Distribution_FloorStanding_Indoor | 74456 | 74456 | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full
482_EE_Distribution_FloorStanding_Outdoor | 74457 | 74457 | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full
482_EE_RackCabinet_WallMounted | 74469 | 74469 | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full
482_EE_SwitchCabinet_FloorStand_Rectangular | 74470 | 74470 | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full
484_EF_Transferbox | 74481 | 74481 | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full
491_NF_GussetPlateAngularDoubleAdjustableBrace | 75621 | 75621 | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full
491_NF_GussetPlateFlatSemiCircle | 75628 | 75628 | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full
491_NF_GussetPlateUShape_Side | 75636 | 75636 | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full
491_NF_PipeClampAccessoriesPunchedAngle | 75641 | 75641 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampBeamAttachments_AngleBracket | 75653 | 75653 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampBeamAttachments_PipeBeamClip | 75659 | 75659 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampBeamAttachments_SphericalWasher | 75660 | 75660 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampBeamAttachmentsUBracket | 75651 | 75651 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampBeamAttachmentsWeldOnBracket | 75652 | 75652 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampDoubleBoltStrut | 75662 | 75662 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampThreeBolt | 75667 | 75667 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_PipeClampTwistClip | 75668 | 75668 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_Steel_HexagonHeadScrew | 75678 | 75678 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_Steel_P1001A_Unistrut | 75685 | 75685 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_NF_Steel_P1003_Unistrut | 75689 | 75689 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_SE_ArmFromDoublePerpendicularArm | 75327 | 75327 | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full
491_SE_BracingArmSKOF80 | 75380 | 75380 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_ClampDoublePiece | 75382 | 75382 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_ConductorHolders_FloorStand | 75126 | 75126 | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full
491_SE_DouleClampWithFoundationPlate | 75384 | 75384 | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full
491_SE_EndSupportSTAF80 | 75385 | 75385 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_FixedpointsetXS | 75386 | 75386 | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full
491_SE_GuidingBracketFWF | 75388 | 75388 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_GussetPlate90dTCenter | 75618 | 75618 | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full
491_SE_GussetPlate90dTSide | 75619 | 75619 | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full
491_SE_PillarOnTopAndDoubleArmWithThread | 75130 | 75130 | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full
491_SE_PillarOnTopAndSingleArmWithThread | 75128 | 75128 | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full
491_SE_PillarWithPlate | 75389 | 75389 | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full
491_SE_PipeClampBeamAttachments_FlangeClamp | 75658 | 75658 | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full
491_SE_PipeClampHangedSaddle | 75664 | 75664 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_SE_PipeClampPearHanger | 75665 | 75665 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full
491_SE_PipeClampTwoPiece | 75669 | 75669 | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full
491_SE_PipeClampTwoPieceWithYoke | 75670 | 75670 | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full
491_SE_PipeClampUBolt | 75671 | 75671 | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full
491_SE_PipeClampWithRubberRing | 75390 | 75390 | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full
491_SE_PipeClampWithShadeNut | 75391 | 75391 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_PipeStrapWithUType | 75392 | 75392 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_PipeSupport_FloorStandingType | 75393 | 75393 | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full
491_SE_PipeSupport_Riser_ClampType | 75395 | 75395 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_PipeTrapezeHangerDoubleFrame | 75396 | 75396 | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full
491_SE_PipeTrapezeHangerSingleFrame | 75397 | 75397 | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full
491_SE_RoundDuctHanger_Standard | 75399 | 75399 | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full
491_SE_ShouderWithDoubleArm | 75400 | 75400 | 2026-08-17 | 2026-09-21 | 26 | handler_assign | confirm_note:stored_full
491_SE_SingleArmWithPillarOnTop | 75129 | 75129 | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full
491_SE_SingleArmWithPlate | 75402 | 75402 | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full
491_SE_SlidesetFS | 75403 | 75403 | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full
491_SE_ST_P3300_Unistrut | 75694 | 75694 | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full

## Matrix_Preview
Ticket ID | Summary | Start Date | End Date | Duration | Start_Method | End_Method | Missing_Start | Missing_End | Flag
76286 | DCMvn_Annotation_SAN_Export BOM Based on Template | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76283 | DCMvn_Annotation_SAN_Upload 2D Layout to Revizto and Set Up 3D Overlay | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76273 | DCMvn Annotation_Practice_RLT Discipline |  |  |  | none | none | Y | Y | missing_start,missing_end
76260 | Produce Sample layout for MSR LPH8 | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76259 | Produce Sample layout for MSR LPH5 | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76258 | Produce Sample layout for MSR LPH3 | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76256 | DCMvn Annotation_Practice_SAN Discipline | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76255 | Produce Schematic Drawing Sample for ELT LPH8 | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76254 | Produce Schematic Drawing Sample for ELT LPH5 | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76253 | Produce Schematic Drawing Sample for ELT LPH3 | 2026-09-29 |  |  | handler_assign | none | N | Y | missing_end
76227 | DCMvn_Annotation_Update Pump Room in Existing DCM_SAN_Model | 2026-09-28 |  |  | handler_assign | none | N | Y | missing_end
76222 | Produce Sample layout for ELT LPH8 | 2026-09-28 |  |  | handler_assign | none | N | Y | missing_end
76221 | Produce Sample layout for ELT LPH5 | 2026-09-28 |  |  | handler_assign | none | N | Y | missing_end
76220 | Produce Sample layout for ELT LPH3 | 2026-09-28 |  |  | handler_assign | none | N | Y | missing_end
76213 | Revit Template for SAN in LPH5 | 2026-09-25 |  |  | handler_assign | none | N | Y | missing_end
76212 | Revit Template for SAN in LPH3 | 2026-09-25 |  |  | handler_assign | none | N | Y | missing_end
76180 | LPH8 Check list for MSR discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | N | N
76179 | LPH5 Check list for MSR discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | N | N
76178 | LPH3 Check list for MSR discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | N | N
76177 | LPH8 Check list for ELT discipline | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | N | N
76176 | LPH5 Check list for ELT discipline | 2026-09-24 | 2026-09-29 | 4 | handler_assign | status_resolved | N | N
76175 | LPH3 Check list for ELT discipline | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | N | N
76174 | Revit Template for MSR in LPH8 | 2026-09-24 | 2026-09-24 | 1 | handler_assign | status_resolved | N | N
76173 | Revit Template for MSR in LPH5 | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | N | N
76172 | Revit Template for MSR in LPH3 | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | N | N
76171 | Revit Template for ELT in LPH8 | 2026-09-24 | 2026-09-25 | 2 | handler_assign | status_resolved | N | N
76170 | Revit Template for ELT in LPH5 | 2026-09-24 | 2026-09-29 | 4 | handler_assign | status_resolved | N | N
76169 | Revit Template for ELT in LPH3 | 2026-09-24 | 2026-09-28 | 3 | handler_assign | status_resolved | N | N
76131 | HKT_Publishing Revizto + Exporting Ifc model | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76129 | HKT_Uploading the 2D document to Revizto platform and set up 3D overlay | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76128 | HKT_Updating LOIN | 2026-09-21 | 2026-09-29 | 7 | handler_assign | status_resolved | N | N
76127 | HKT_Producing BOM | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76125 | HKT_Overview_Updating Schematic | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76124 | HKT_Updating Schematic_LPH8 | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76123 | HKT_Updating Schematic_LPH5 | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76121 | HKT_Updating Schematic_LPH3 | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76120 | HKT_Overview_Sample layout_LPH3 + LPH5 + LPH8 | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76118 | HKT_Sample layout_LPH3 | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76117 | HKT_Sample layout_LPH5 | 2026-09-21 |  |  | handler_assign | none | N | Y | missing_end
76104 | Digital_Research_Upgrade the DCMvn Tool | 2026-09-18 |  |  | handler_assign | none | N | Y | missing_end
75949 | 430_DA_PlenumBoxRoutoRec_Standard.rfa | 2026-09-15 | 2026-09-25 | 9 | handler_assign | status_resolved | N | N
75948 | 430_DA_PlenumBoxRectoRec_Standard.rfa | 2026-09-15 | 2026-09-25 | 9 | handler_assign | status_resolved | N | N
75938 | HKT_Sample layout_LPH8 | 2026-09-14 |  |  | handler_assign | none | N | Y | missing_end
75937 | HKT_Output Check List | 2026-09-14 | 2026-09-22 | 7 | handler_assign | status_resolved | N | N
75936 | HKT_Creation RVT Template | 2026-09-14 | 2026-09-23 | 8 | handler_assign | status_resolved | N | N
75935 | HKT_Update family to DCM Revit Library Model_Sample Zone | 2026-09-14 | 2026-09-28 | 11 | handler_assign | status_resolved | N | N
75911 | RLT_Sample layout_LPH3_5_8 | 2026-09-11 |  |  | handler_assign | none | N | Y | missing_end
75910 | RLT_Output Check List | 2026-09-11 | 2026-09-30 | 14 | handler_assign | status_resolved | N | N
75909 | RLT_Creation RVT Template | 2026-09-11 | 2026-10-01 | 15 | handler_assign | status_resolved | N | N
75807 | 430_ME_HeatRecoveryWheelPrimaryAirUnits_Standard.rfa | 2026-09-08 | 2026-09-15 | 6 | handler_assign | confirm_note:stored_full | N | N
75806 | 430_ME_HeatReclaimVentilator_VAMFC.rfa | 2026-09-08 | 2026-09-23 | 12 | handler_assign | status_resolved | N | N
75805 | 430_ME_HeatExchangers_KTH_NoSystem.rfa | 2026-09-08 | 2026-09-23 | 12 | handler_assign | confirm_note:stored_full | N | N
75804 | 430_ME_HeatExchangersAndAirHeaters_WT.rfa | 2026-09-08 | 2026-09-24 | 13 | handler_assign | confirm_note:stored_full | N | N
75803 | 430_ME_HeatExchangersAndAirHeaters_WL.rfa | 2026-09-08 | 2026-09-22 | 11 | handler_assign | confirm_note:stored_full | N | N
75802 | 430_ME_HeatExchangersAndAirHeaters_EL.rfa | 2026-09-08 | 2026-09-23 | 12 | handler_assign | confirm_note:stored_full | N | N
75801 | 430_ME_GloveBox.rfa | 2026-09-08 | 2026-09-21 | 10 | handler_assign | confirm_note:stored_full | N | N
75800 | 430_ME_FlushMountedFan_TopConnection_SilentECO.rfa | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full | N | N
75799 | 430_ME_FlushMountedFan_BackConnection_SilentECO.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75798 | 430_ME_FilterFanCoilUnit.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75796 | 430_ME_Fan_WallMounted.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75795 | 430_ME_Fan_Roof_SmokeExtraction_NoSystem.rfa | 2026-09-09 | 2026-09-21 | 9 | handler_assign | status_resolved | N | N
75794 | 430_ME_Fan_Roof_Exhaust.rfa | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full | N | N
75793 | 430_ME_Fan_Axial.rfa | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full | N | N
75792 | 430_ME_FansForAggressiveAir.rfa | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full | N | N
75791 | 430_ME_ExpansionTank_BottomConnection.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75790 | 430_ME_Ductfans_WallMounted_Round.rfa | 2026-09-09 | 2026-09-22 | 10 | handler_assign | status_resolved | N | N
75789 | 430_ME_Ductfans_Round_DF.rfa | 2026-09-09 | 2026-09-22 | 10 | handler_assign | status_resolved | N | N
75788 | 430_ME_DiesselTank_Becomix.rfa | 2026-09-09 | 2026-09-23 | 11 | handler_assign | confirm_note:stored_full | N | N
75787 | 430_ME_CrossFlowFans_NoSystem.rfa | 2026-09-09 | 2026-09-21 | 9 | handler_assign | confirm_note:stored_full | N | N
75786 | 430_ME_ChemicalMachine.rfa | 2026-09-09 | 2026-09-22 | 10 | handler_assign | confirm_note:stored_full | N | N
75785 | 430_ME_CentrifugalDuctMountedFan.rfa | 2026-09-09 | 2026-09-24 | 12 | handler_assign | confirm_note:stored_full | N | N
75784 | 430_ME_AxialWindowFan_Rectangular.rfa | 2026-09-09 | 2026-09-30 | 16 | handler_assign | confirm_note:stored_full | N | N
75783 | 430_ME_AirHandlingUnit_Geniox29H.rfa | 2026-09-09 | 2026-09-17 | 7 | handler_assign | confirm_note:stored_full | N | N
75782 | 430_ME_AirHandlingUnit_FloorStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75781 | 430_ME_AirHandlingUnit_2LayerForKitchen_FloorStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75780 | 430_ME_AirHandlingUnit_2LayerCompactSeries_FloorStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75779 | 430_ME_AirHandlingUnit_2LayerBowl_RoofStand.rfa | 2026-09-09 | 2026-09-11 | 3 | handler_assign | status_resolved | N | N
75778 | 430_ME_AirHandlingUnit_1LayerFlachSeries_CeilingStand.rfa | 2026-09-09 | 2026-09-29 | 15 | handler_assign | confirm_note:stored_full | N | N
75748 | 430_ME_AirHandlingUnit_Floor_Single_Aubenluft.rfa | 2026-09-07 | 2026-09-25 | 15 | handler_assign | confirm_note:stored_full | N | N
75747 | 430_ME_AirHandlingUnit_Single_Fortluft.rfa | 2026-09-07 | 2026-09-25 | 15 | handler_assign | confirm_note:stored_full | N | N
75746 | 2026Q4_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-09-07 |  |  | handler_assign | none | N | Y | missing_end
75712 | SAN Existing Schematic Diagrams Review and Update_ LPH3 and LPH5 in DCM_SAN Model | 2026-09-04 | 2026-09-25 | 16 | handler_assign | status_resolved | N | N
75711 | LPH5_SAN Existing Layout and Section Drawings Review and Update in DCM_SAN Model | 2026-09-04 | 2026-09-25 | 16 | handler_assign | status_resolved | N | N
75710 | MED_Producing layouts for LPH8 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | N | N
75709 | LPH3_SAN Existing Layout and Section Drawings Review and Update in DCM_SAN Model | 2026-09-03 | 2026-09-25 | 17 | handler_assign | status_resolved | N | N
75708 | MED_Producing layouts for LPH5 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | N | N
75707 | MED_Producing layouts for LPH3 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | N | N
75706 | SPR_Producing layouts for LPH8 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | N | N
75705 | SPR_Producing layouts for LPH5 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | N | N
75704 | SPR_Producing layouts for LPH3 | 2026-09-03 | 2026-09-30 | 20 | handler_assign | status_resolved | N | N
75700 | 491_NF_Steel_UnirodThreadedRod.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75699 | 491_NF_Steel_P5501_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75698 | 491_NF_Steel_P5500_Unistrut.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | N | N
75697 | 491_NF_Steel_P4003_Unistrut.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75696 | 491_NF_Steel_P40021_Unistrut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75695 | 491_NF_Steel_P4000_Unistrut.rfa | 2026-09-03 | 2026-09-15 | 9 | handler_assign | status_resolved | N | N
75694 | 491_NF_Steel_P3300_Unistrut.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | N | N
75693 | 491_NF_Steel_P2001C3_Unistrut.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | N | N
75692 | 491_NF_Steel_P2001B_Unistrut.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | N | N
75691 | 491_NF_Steel_P2001A_Unistrut.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | N | N
75690 | 491_NF_Steel_P1004A_Unistrut.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | N | N
75689 | 491_NF_Steel_P1003_Unistrut.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75688 | 491_NF_Steel_P1001_Unistrut.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | N | N
75687 | 491_NF_Steel_P1001D3_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75686 | 491_NF_Steel_P1001C3_Unistrut.rfa | 2026-09-03 | 2026-09-15 | 9 | handler_assign | status_resolved | N | N
75685 | 491_NF_Steel_P1001A_Unistrut.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75684 | 491_NF_Steel_P10013_Unistrut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75683 | 491_NF_Steel_P1000_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75682 | 491_NF_Steel_P1000C_Unistrut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75681 | 491_NF_Steel_P1000C41_Unistrut.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | N | N
75680 | 491_NF_Steel_P1000B_Unistrut.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75679 | 491_NF_Steel_HexagonNut_Threaded.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75678 | 491_NF_Steel_HexagonHeadScrew.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75677 | 491_NF_Steel_FlatWashers.rfa | 2026-09-03 | 2026-09-09 | 5 | handler_assign | status_resolved | N | N
75676 | 491_NF_Steel_CantileverBrackets_Triangle.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | N | N
75675 | 491_NF_Steel_AnchorScrew.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75674 | 491_NF_Steel_A1000_Unistrut.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | N | N
75673 | 491_NF_PipeClamp_StandOffBracket.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | N | N
75672 | 491_NF_PipeClamp_OnePiece.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75671 | 491_NF_PipeClampUBolt.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | N | N
75670 | 491_NF_PipeClampTwoPieceWithYoke.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | N | N
75669 | 491_NF_PipeClampTwoPiece.rfa | 2026-09-03 | 2026-09-28 | 18 | handler_assign | confirm_note:stored_full | N | N
75668 | 491_NF_PipeClampTwistClip.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75667 | 491_NF_PipeClampThreeBolt.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75666 | 491_NF_PipeClampSingleBoltStrut.rfa | 2026-09-03 | 2026-09-09 | 5 | handler_assign | status_resolved | N | N
75665 | 491_NF_PipeClampPearHanger.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75664 | 491_NF_PipeClampHangedSaddle.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75663 | 491_NF_PipeClampFourBolt.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75662 | 491_NF_PipeClampDoubleBoltStrut.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75661 | 491_NF_PipeClampBeamAttachments_SwivelCage.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75660 | 491_NF_PipeClampBeamAttachments_SphericalWasher.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75659 | 491_NF_PipeClampBeamAttachments_PipeBeamClip.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75658 | 491_NF_PipeClampBeamAttachments_FlangeClamp.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | N | N
75654 | 491_NF_PipeClampBeamAttachments_BeamClip.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | N | N
75653 | 491_NF_PipeClampBeamAttachments_AngleBracket.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75652 | 491_NF_PipeClampBeamAttachmentsWeldOnBracket.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75651 | 491_NF_PipeClampBeamAttachmentsUBracket.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75650 | 491_NF_PipeClampBeamAttachmentsSwivelFlangeClamp.rfa | 2026-09-03 | 2026-09-09 | 5 | handler_assign | status_resolved | N | N
75649 | 491_NF_PipeClampBeamAttachmentsPurlinClip.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | N | N
75648 | 491_NF_PipeClampAccessories_Turnbuckle.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | N | N
75647 | 491_NF_PipeClampAccessories_LinkPlate.rfa | 2026-09-03 | 2026-09-14 | 8 | handler_assign | status_resolved | N | N
75646 | 491_NF_PipeClampAccessories_HangerStrap.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75645 | 491_NF_PipeClampAccessories_EyeNut.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75644 | 491_NF_PipeClampAccessories_Clevis.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75643 | 491_NF_PipeClampAccessories_BladeEnd.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75642 | 491_NF_PipeClampAccessoriesSquareWasher.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | N | N
75641 | 491_NF_PipeClampAccessoriesPunchedAngle.rfa | 2026-09-03 | 2026-09-30 | 20 | handler_assign | confirm_note:stored_full | N | N
75640 | 491_NF_GussetPlate_StairTreadSupport.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | status_resolved | N | N
75639 | 491_NF_GussetPlateZShape.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75638 | 491_NF_GussetPlateWingShape.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | N | N
75637 | 491_NF_GussetPlateWShape.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75636 | 491_NF_GussetPlateUShape_Side.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | N | N
75635 | 491_NF_GussetPlateUShape_Omega.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75634 | 491_NF_GussetPlateUShape_Hanger.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75633 | 491_NF_GussetPlateUShape_2Layers.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75632 | 491_NF_GussetPlateUShape.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75631 | 491_NF_GussetPlateTrailingArmBrace.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75630 | 491_NF_GussetPlateTrailingArm.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | N | N
75629 | 491_NF_GussetPlateFlatT.rfa | 2026-09-03 | 2026-09-11 | 7 | handler_assign | status_resolved | N | N
75628 | 491_NF_GussetPlateFlatSemiCircle.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | N | N
75627 | 491_NF_GussetPlateFlatRectangular.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | N | N
75626 | 491_NF_GussetPlateFlatHexagon.rfa | 2026-09-03 | 2026-09-10 | 6 | handler_assign | status_resolved | N | N
75625 | 491_NF_GussetPlateCantileverBracket.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75624 | 491_NF_GussetPlateBase.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75623 | 491_NF_GussetPlateAngularSingleAdjustableBrace.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | confirm_note:stored_full | N | N
75622 | 491_NF_GussetPlateAngularRectangular.rfa | 2026-09-03 | 2026-09-18 | 12 | handler_assign | confirm_note:stored_full | N | N
75621 | 491_NF_GussetPlateAngularDoubleAdjustableBrace.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | N | N
75620 | 491_NF_GussetPlateAngularAxial.rfa | 2026-09-03 | 2026-10-01 | 21 | handler_assign | confirm_note:stored_full | N | N
75619 | 491_NF_GussetPlate90dTSide.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | N | N
75618 | 491_NF_GussetPlate90dTCenter.rfa | 2026-09-03 | 2026-09-29 | 19 | handler_assign | confirm_note:stored_full | N | N
75617 | 491_NF_GussetPlate90dRectangular.rfa | 2026-09-03 | 2026-09-17 | 11 | handler_assign | status_resolved | N | N
75616 | 491_NF_GussetPlate90dHexagon.rfa | 2026-09-03 | 2026-09-16 | 10 | handler_assign | status_resolved | N | N
75605 | LPH5_SAN Discipline Output Checklist Definition | 2026-08-31 | 2026-09-30 | 23 | handler_assign | status_resolved | N | N
75551 | MED_Update Equipment to DCM Revit Library Model | 2026-08-27 | 2026-08-28 | 2 | handler_assign | status_resolved | N | N
75550 | MED_Update Pipe Accessories to DCM Revit Library Model | 2026-08-27 | 2026-08-31 | 3 | handler_assign | status_resolved | N | N
75494 | SPR_Update Equipment to DCM Revit Library Model | 2026-08-24 | 2026-08-31 | 6 | handler_assign | status_resolved | N | N
75493 | SPR_Update Pipe Accessories to DCM Revit Library Model | 2026-08-24 | 2026-08-31 | 6 | handler_assign | status_resolved | N | N
75492 | DCMvn_Annotation_Update Families in Existing DCM_ELT_Model | 2026-08-24 |  |  | handler_assign | none | N | Y | missing_end
75403 | 491_SE_SlidesetFS.rfa | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full | N | N
75402 | 491_SE_SingleArmWithPlate.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75401 | 491_SE_SingleArmWithDoubleBracket.rfa | 2026-08-17 | 2026-08-25 | 7 | handler_assign | status_resolved | N | N
75400 | 491_SE_ShouderWithDoubleArm.rfa | 2026-08-17 | 2026-09-21 | 26 | handler_assign | confirm_note:stored_full | N | N
75399 | 491_SE_RoundDuctHanger_Standard.rfa | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full | N | N
75398 | 491_SE_RectangularDuctHanger_Standard.rfa | 2026-08-17 | 2026-08-21 | 5 | handler_assign | status_resolved | N | N
75397 | 491_SE_PipeTrapezeHangerSingleFrame.rfa | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full | N | N
75396 | 491_SE_PipeTrapezeHangerDoubleFrame.rfa | 2026-08-17 | 2026-09-30 | 33 | handler_assign | confirm_note:stored_full | N | N
75395 | 491_SE_PipeSupport_Riser_ClampType.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75394 | 491_SE_PipeSupport_RiserType.rfa | 2026-08-17 | 2026-08-24 | 6 | handler_assign | status_resolved | N | N
75393 | 491_SE_PipeSupport_FloorStandingType.rfa | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full | N | N
75392 | 491_SE_PipeStrapWithUType.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75391 | 491_SE_PipeClampWithShadeNut.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75390 | 491_SE_PipeClampWithRubberRing.rfa | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full | N | N
75389 | 491_SE_PillarWithPlate.rfa | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full | N | N
75388 | 491_SE_GuidingBracketFWF.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75387 | 491_SE_FrameHangerTopBase.rfa | 2026-08-17 | 2026-08-21 | 5 | handler_assign | status_resolved | N | N
75386 | 491_SE_FixedpointsetXS.rfa | 2026-08-17 | 2026-09-29 | 32 | handler_assign | confirm_note:stored_full | N | N
75385 | 491_SE_EndSupportSTAF80.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75384 | 491_SE_DouleClampWithFoundationPlate.rfa | 2026-08-17 | 2026-09-18 | 25 | handler_assign | confirm_note:stored_full | N | N
75383 | 491_SE_DoublePillarWithPlate.rfa | 2026-08-17 | 2026-08-20 | 4 | handler_assign | status_resolved | N | N
75382 | 491_SE_ClampDoublePiece.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75381 | 491_SE_CantileverBracketAKF80.rfa | 2026-08-17 | 2026-08-20 | 4 | handler_assign | status_resolved | N | N
75380 | 491_SE_BracingArmSKOF80.rfa | 2026-08-17 | 2026-09-16 | 23 | handler_assign | confirm_note:stored_full | N | N
75379 | 491_SE_ArmWithAngleBracket.rfa | 2026-08-17 | 2026-08-20 | 4 | handler_assign | status_resolved | N | N
75366 | 434_ME_FillsoftI.rfa | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full | N | N
75365 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBT2pipes.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | N | N
75364 | 434_ME_Fancoilunit_CeilingMounted_RoundflowcassetteFWCBF4pipes.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | N | N
75358 | 434_ME_Fancoilunit_CeilingMounted_4wayblowcassetteFWFBF4pipes.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | confirm_note:stored_full | N | N
75357 | 434_ME_FanCoilUnit_WallMounted_Standard.rfa | 2026-08-14 | 2026-08-26 | 9 | handler_assign | status_resolved | N | N
75356 | 434_ME_FanCoilUnit_WallMounted_FWBBT2pipe.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | N | N
75355 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermID.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full | N | N
75354 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHKE.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | N | N
75353 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK4Pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full | N | N
75352 | 434_ME_FanCoilUnit_UnderFloorTrench_KathermHK2Pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | confirm_note:stored_full | N | N
75351 | 434_ME_FanCoilUnit_FloorStanding_FWVDAT2Pipes.rfa | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full | N | N
75350 | 434_ME_FanCoilUnit_FloorStanding_FWVDAF4Pipes.rfa | 2026-08-14 | 2026-08-25 | 8 | handler_assign | status_resolved | N | N
75349 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAT2Pipes.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | N | N
75348 | 434_ME_FanCoilUnit_FlexiTypeUnitFWLDAF4Pipes.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | N | N
75347 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ4Pipes.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | N | N
75346 | 434_ME_FanCoilUnit_ConcealedCeiling_42BJ2Pipes.rfa | 2026-08-14 | 2026-09-16 | 24 | handler_assign | confirm_note:stored_full | N | N
75345 | 434_ME_FanCoilUnit_CeilingPlenum_Ultra.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | N | N
75344 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize1x.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | N | N
75343 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM4PipeSize0x.rfa | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full | N | N
75342 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize1x.rfa | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full | N | N
75341 | 434_ME_FanCoilUnit_CeilingPlenum_HydronicDucted42EM2PipeSize0x.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75340 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS4Pipe.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75339 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NS2Pipe.rfa | 2026-08-14 | 2026-09-15 | 23 | handler_assign | confirm_note:stored_full | N | N
75337 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE4Pipe.rfa | 2026-08-14 | 2026-09-17 | 25 | handler_assign | confirm_note:stored_full | N | N
75336 | 434_ME_FanCoilUnit_CeilingPlenum_HorizontalCabinet42NE2Pipe.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | N | N
75335 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAT2pipe.rfa | 2026-08-14 | 2026-09-14 | 22 | handler_assign | confirm_note:stored_full | N | N
75334 | 434_ME_FanCoilUnit_CeilingPlenum_FWSAF4pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | status_resolved | N | N
75333 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDT2pipe.rfa | 2026-08-14 | 2026-09-25 | 31 | handler_assign | status_resolved | N | N
75332 | 434_ME_FanCoilUnit_CeilingPlenum_FWMDF4pipe.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | N | N
75331 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAT2pipe.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | confirm_note:stored_full | N | N
75330 | 434_ME_FanCoilUnit_CeilingPlenum_FWDAF4pipe.rfa | 2026-08-14 | 2026-09-24 | 30 | handler_assign | confirm_note:stored_full | N | N
75329 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJT2pipe.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | N | N
75328 | 434_ME_FanCoilUnit_CeilingPlenum_FWBJF4pipe.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75327 | 491_SE_ArmFromDoublePerpendicularArm.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full | N | N
75326 | 420_ME_RadiatorBathroom_WallMounted_Credohalfround.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | N | N
75325 | 420_ME_RadiatorBathroom_WallMounted_Credohalf.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | N | N
75324 | 420_ME_RadiatorBathroom_WallMounted_Casteo.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75323 | 420_ME_RadiatorBathroom_WallMounted_BasicR.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75322 | 420_ME_RadiatorBathroom_WallMounted_Basic.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75321 | 420_ME_QuantumW500_DoubleCapacitor.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | N | N
75320 | 420_ME_Pump_WaterJetPump_3Way_Threaded.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75319 | 420_ME_Pump_WaterJetPump_3Way_Flanged.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | N | N
75318 | 420_ME_PlateHeatExchanger.rfa | 2026-08-14 | 2026-08-28 | 11 | handler_assign | status_resolved | N | N
75317 | 420_ME_MultiOutdoorUnit_SingleFan.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | N | N
75316 | 420_ME_MixedBecomixVessel_Vertical.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | N | N
75315 | 420_ME_ManifoldCabinet_UP110.rfa | 2026-08-14 | 2026-08-24 | 7 | handler_assign | status_resolved | N | N
75314 | 420_ME_Manifold12Connection_Custom.rfa | 2026-08-14 | 2026-08-24 | 7 | handler_assign | status_resolved | N | N
75313 | 420_ME_LargeBecomixVessel_Vertical.rfa | 2026-08-14 | 2026-09-17 | 25 | handler_assign | confirm_note:stored_full | N | N
75312 | 420_ME_KTS_ThermoBox.rfa | 2026-08-14 | 2026-09-08 | 18 | handler_assign | confirm_note:stored_full | N | N
75311 | 420_ME_HydraulicSeparator_Threaded.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | N | N
75310 | 420_ME_HydraulicSeparator_Flanged.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | confirm_note:stored_full | N | N
75309 | 420_ME_HotWaterTank.rfa | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full | N | N
75308 | 420_ME_HotWaterStorageTank_StorathermAquaSolarEEC.rfa | 2026-08-14 | 2026-08-27 | 10 | handler_assign | status_resolved | N | N
75307 | 420_ME_HotWaterStorageTank_StorathermAquaSolar.rfa | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full | N | N
75306 | 420_ME_HotWaterStorageTank_StorathermAquaLoad4Flange.rfa | 2026-08-14 | 2026-09-04 | 16 | handler_assign | confirm_note:stored_full | N | N
75305 | 420_ME_HotWaterStorageTank_StorathermAquaLoad3Flange.rfa | 2026-08-14 | 2026-09-09 | 19 | handler_assign | confirm_note:stored_full | N | N
75304 | 420_ME_HotWaterStorageTank_StorathermAquaLoad2Flange.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | N | N
75303 | 420_ME_HotWaterStorageTank_StorathermAquaLoad1Flange.rfa | 2026-08-14 | 2026-09-23 | 29 | handler_assign | confirm_note:stored_full | N | N
75302 | 420_ME_HotWaterStorageTank_StorathermAquaInox.rfa | 2026-08-14 | 2026-08-28 | 11 | handler_assign | status_resolved | N | N
75301 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump2Coil.rfa | 2026-08-14 | 2026-09-04 | 16 | handler_assign | confirm_note:stored_full | N | N
75300 | 420_ME_HotWaterStorageTank_StorathermAquaHeatPump1Coil.rfa | 2026-08-14 | 2026-09-11 | 21 | handler_assign | confirm_note:stored_full | N | N
75299 | 420_ME_HotWaterStorageTank_StorathermAquaEEC.rfa | 2026-08-14 | 2026-09-21 | 27 | handler_assign | confirm_note:stored_full | N | N
75298 | 420_ME_HotWaterStorageTank_StorathermAquaCompactWallHung.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | N | N
75297 | 420_ME_HotWaterStorageTank_StorathermAquaCompactHorizontal.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | status_resolved | N | N
75296 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil.rfa | 2026-08-14 | 2026-09-22 | 28 | handler_assign | confirm_note:stored_full | N | N
75295 | 420_ME_HotWaterStorageTank_StorathermAquaCompact1Coil&Electricheater.rfa | 2026-08-14 | 2026-09-10 | 20 | handler_assign | status_resolved | N | N
75294 | 420_ME_HotWaterStorageTank_StorathermAquaCompact&Electricheater.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | status_resolved | N | N
75293 | 420_ME_HotWaterStorageTank_StorathermAqua.rfa | 2026-08-14 | 2026-09-07 | 17 | handler_assign | status_resolved | N | N
75289 | 434_ME_FanCoilUnit_CeilingMounted_Standard.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | N | N
75288 | 434_ME_FanCoilUnit_CeilingMounted_LargeChassis42GW4Pipes.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | N | N
75287 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH4Pipe.rfa | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full | N | N
75286 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42NH2Pipe.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75285 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWD2Pipe.rfa | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full | N | N
75284 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC4Pipe.rfa | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full | N | N
75283 | 434_ME_FanCoilUnit_CeilingMounted_HydronicDucted42DWC2Pipe.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75282 | 434_ME_FanCoilUnit_CeilingMounted_HybridTerminal36XB.rfa | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full | N | N
75281 | 434_ME_FanCoilUnit_CeilingMounted_CompactChassis42GW4Pipes.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75280 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFCT2Pipes.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | N | N
75279 | 434_ME_FanCoilUnit_CeilingMounted_4WayBlowCassetteFWFBT2Pipes.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75278 | 434_ME_FanCoilUnit_CeilingCassette_Standard.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | N | N
75277 | 434_ME_FanCoilUnit_CeilingCassette_2pipes&42GW.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75276 | 434_ME_FanCoilUnit_AirTreatmentModules42GR4Pipes.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | N | N
75275 | 434_ME_FanCoilUnit_AirTreatmentModules42GR2Pipes.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75274 | 434_ME_FanCoilUnit_AirTreatmentModules42GM4Pipes.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75272 | 434_ME_FanCoilUnit_AirTreatmentModules42GM2Pipes.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | confirm_note:stored_full | N | N
75271 | 434_ME_ExpansionVessel_StaticoSU.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75270 | 434_ME_ExpansionVessel_StaticoSG.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | N | N
75269 | 434_ME_ExpansionVessel_StaticoSD.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | N | N
75268 | 434_ME_ExpansionVessel_Standard.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | N | N
75267 | 434_ME_ExpansionVessel_IntermediateDU.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | status_resolved | N | N
75266 | 434_ME_ExpansionVessel_IntermediateDG.rfa | 2026-08-13 | 2026-09-23 | 30 | handler_assign | confirm_note:stored_full | N | N
75265 | 434_ME_ExpansionVessel_IntermediateDD.rfa | 2026-08-13 |  |  | handler_assign | none | N | Y | missing_end
75264 | 434_ME_EndSuctionPump_Standard.rfa | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | N | N
75263 | 434_ME_Ductableaircooledliquidchillers_30RBSY_LeftConnection.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | N | N
75262 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY.rfa | 2026-08-13 | 2026-09-25 | 32 | handler_assign | status_resolved | N | N
75261 | 434_ME_DuctableAirCooledLiquidChillers_BehindConnection_30RBSY.rfa | 2026-08-13 | 2026-08-25 | 9 | handler_assign | status_closed | N | N
75260 | 434_ME_DuctableAirCooledLiquidChillers_30RBY.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | N | N
75259 | 434_ME_DegassingSystem.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | N | N
75258 | 434_ME_CyclonicVacuumDegasser_VentoVIEC.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | N | N
75257 | 434_ME_CyclonicVacuumDegasser_VentoVEC.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | N | N
75256 | 434_ME_Convector_UnderFloorTrench_Standard.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | N | N
75255 | 434_ME_ConvectionElementsCeillings_CeilingMounted_KN.rfa | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full | N | N
75254 | 434_ME_CirculatorPump_CronoTwinDL.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | status_resolved | N | N
75253 | 434_ME_AirCooledScrollChillers_30RBP.rfa | 2026-08-13 | 2026-08-26 | 10 | handler_assign | status_resolved | N | N
75252 | 434_ME_AirCooledLiquidChillers_HeatReclaimUnit30XAS.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | N | N
75251 | 434_ME_AirCooledLiquidChillers_30XAV.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75250 | 434_ME_AirCooledLiquidChillers_30XAS.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | N | N
75249 | 434_ME_AirCooledLiquidChillers_30XA.rfa | 2026-08-13 | 2026-09-07 | 18 | handler_assign | confirm_note:stored_full | N | N
75248 | 434_ME_AirCooledLiquidChillers_30RBS.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75247 | 434_ME_AirCooledLiquidChillers_30RB.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75246 | 434_ME_AirCooledCondensingUnits_38RBS_LeftConnector.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75244 | 434_ME_AirCooledCondensingUnits_38RBS_4Pipes.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75243 | 434_ME_AirCooledCondensingUnits_38RBS_2Pipes.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75242 | 434_ME_AirCooledChillers_30AWH.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75241 | 434_ME_ FanCoilUnit_CeilingPlemun_ Standard.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75240 | 420_ME_HotWaterStorageTank_Standard.rfa | 2026-08-13 | 2026-09-22 | 29 | handler_assign | confirm_note:stored_full | N | N
75239 | 420_ME_HotWaterBoiler.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | N | N
75238 | 420_ME_HomeStation_GHKFBH.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75237 | 420_ME_HomeStation_GHK.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | N | N
75236 | 420_ME_HomeStation_DHK.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | N | N
75235 | 420_ME_HeatingCoolingSails_Ceiling.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | N | N
75234 | 420_ME_HeatTransferStation_Custom.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75233 | 420_ME_HeatPump_PackageDrooftop_48And50UA&UH.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | N | N
75232 | 420_ME_HeatExchangerFreeCooling_Flange.rfa | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | N | N
75231 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_5Connector.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75230 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_4Connector.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75229 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_3Connector.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75228 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_2Connector.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75227 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQL_1Connector.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75226 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQKnano.rfa | 2026-08-13 | 2026-09-29 | 34 | handler_assign | confirm_note:stored_full | N | N
75225 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQK.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | N | N
75224 | 420_ME_Fancoilunit_UnderfloorTrench_KathermQE_NoSystem.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75223 | 420_ME_Fancoilunit_UnderfloorTrench_KathermNK.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | N | N
75222 | 420_ME_FacadeHeating_Standard.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75221 | 420_ME_FWTransfer.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75220 | 420_ME_ExpansionTank_Standard.rfa | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | N | N
75219 | 420_ME_ExpansionTank_FloorStand.rfa | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
75218 | 420_ME_EnergyDistributor_8Pairs.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | N | N
75217 | 420_ME_EnergyDistributor_6Pairs.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | N | N
75216 | 420_ME_Convector_FloorSurface.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75215 | 420_ME_ControlValveGroup.rfa | 2026-08-13 | 2026-09-21 | 28 | handler_assign | confirm_note:stored_full | N | N
75214 | 420_ME_CompressedAirTank.rfa | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full | N | N
75213 | 420_ME_ColdWaterTank.rfa | 2026-08-13 | 2026-09-04 | 17 | handler_assign | confirm_note:stored_full | N | N
75212 | 420_ME_CentrifugalPumpWithElectricMotor_Horizontal.rfa | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full | N | N
75211 | 420_ME_CeilingPanel_Standard.rfa | 2026-08-13 | 2026-09-23 | 30 | handler_assign | confirm_note:stored_full | N | N
75210 | 420_ME_BufferTank_StorathermHeatFlange&WithoutInsulation.rfa | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full | N | N
75209 | 420_ME_BufferTank_StorathermHeatFlange&WithInsulation.rfa | 2026-08-13 | 2026-08-25 | 9 | handler_assign | status_resolved | N | N
75208 | 420_ME_BufferTank_StorathermHeatCombi2Coil&WithInsulation.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75207 | 420_ME_BufferTank_StorathermHeatCombi1Coil&WithInsulation.rfa | 2026-08-13 | 2026-09-04 | 17 | handler_assign | confirm_note:stored_full | N | N
75206 | 420_ME_BufferTank_StorathermHeat2Coil&WithInsulation.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75205 | 420_ME_BufferTank_StorathermHeat1Coil&WithoutInsulation.rfa | 2026-08-13 | 2026-08-25 | 9 | handler_assign | status_resolved | N | N
75204 | 420_ME_BufferTank_StorathermHeat1Coil&WithInsulation.rfa | 2026-08-13 | 2026-08-27 | 11 | handler_assign | status_resolved | N | N
75203 | 420_ME_BufferTank_StorathermHeat&WithInsulation.rfa | 2026-08-13 | 2026-09-14 | 23 | handler_assign | confirm_note:stored_full | N | N
75202 | 420_ME_BufferTank_Standard.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75201 | 420_ME_BufferTank_Custom.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75200 | 420_ME_BufferHeatingTank.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75199 | 420_ME_AirSoureHeatPump.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75198 | 420_ME_AirHeater_Top.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | N | N
75197 | 420_ME_AirCurtain_WallMounted_Standard.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75196 | 420_ME_AirCurtain_WallMounted.rfa | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | N | N
75195 | 420_ME_AirCurtain_StandingType.rfa | 2026-08-13 | 2026-09-11 | 22 | handler_assign | confirm_note:stored_full | N | N
75194 | 420_ME_AirCoolHeatPump_MonoBlock.rfa | 2026-08-13 | 2026-09-10 | 21 | handler_assign | confirm_note:stored_full | N | N
75193 | 420_HeatExchangerTank_VerticalPump.rfa | 2026-08-13 | 2026-09-24 | 31 | handler_assign | confirm_note:stored_full | N | N
75192 | 430_ME_WindDrivenRoofVentilator_Standard.rfa | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | N | N
75191 | 430_ME_WallSmokeExhaustFans.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | N | N
75190 | 430_ME_WallMountedVentilator.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | N | N
75189 | 430_ME_Ventilator_VAM.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full | N | N
75188 | 430_ME_VentilationPlugFans_ERV.rfa | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | N | N
75187 | 430_ME_VentilationCentrifugalFans_RZH.rfa | 2026-08-13 | 2026-09-17 | 26 | handler_assign | confirm_note:stored_full | N | N
75186 | 430_ME_VentilationCentrifugalFans_REH.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | N | N
75185 | 430_ME_VentilationCentrifugalFans_KFB.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | N | N
75184 | 430_ME_VentilationAxialFans_ZAXN691256.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | N | N
75183 | 430_ME_VentilationAxialFans_GLDF.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | N | N
75182 | 430_ME_VentilationAxialFans_BVAXN_1256.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | N | N
75181 | 430_ME_VentilationAxialFans_AXO927.rfa | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | N | N
75180 | 430_ME_VentilationAxialFans_AXO1050.rfa | 2026-08-13 | 2026-09-09 | 20 | handler_assign | confirm_note:stored_full | N | N
75179 | 430_ME_VentilationAxialFans_AXO.rfa | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | N | N
75178 | 430_ME_VentilationAxialFans_AXN691256.rfa | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | N | N
75177 | 430_ME_VacuumPump.rfa | 2026-08-13 | 2026-09-16 | 25 | handler_assign | confirm_note:stored_full | N | N
75176 | 430_ME_SmokeExhaustPlugFans_BRERV.rfa | 2026-08-13 | 2026-08-19 | 5 | handler_assign | status_resolved | N | N
75175 | 430_ME_SmokeExhaustFan_WallMounted_BVW_A.rfa | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | N | N
75174 | 430_ME_SmokeExhaustCentrifugalFans_BVW-B.rfa | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | N | N
75168 | 430_ME_SmokeExhaustCentrifugalFans_BVREH.rfa | 2026-08-12 | 2026-08-17 | 4 | handler_assign | status_resolved | N | N
75167 | 430_ME_SmokeExhaustCentrifugalFans_BVRA.rfa | 2026-08-12 | 2026-09-24 | 32 | handler_assign | confirm_note:stored_full | N | N
75166 | 430_ME_SmokeExhaustAxialFans_BVAXO_F400.rfa | 2026-08-12 | 2026-09-16 | 26 | handler_assign | confirm_note:stored_full | N | N
75165 | 430_ME_SmokeExhaustAxialFans_BVAXO_F300.rfa | 2026-08-12 | 2026-08-14 | 3 | handler_assign | status_resolved | N | N
75164 | 430_ME_RoofVentilationFans_DRV_EC.rfa | 2026-08-12 | 2026-08-28 | 13 | handler_assign | confirm_note:stored_full | N | N
75163 | 430_ME_RoofVentilationFans_DRV_DRH.rfa | 2026-08-12 | 2026-08-14 | 3 | handler_assign | status_resolved | N | N
75162 | 430_ME_RoofVentilationFans_DRVFH.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75161 | 430_ME_RoofVentilationFans_DAX_NoSystem.rfa | 2026-08-12 | 2026-09-23 | 31 | handler_assign | confirm_note:stored_full | N | N
75160 | 430_ME_RoofVentilationFans_DAX.rfa | 2026-08-12 | 2026-08-14 | 3 | handler_assign | status_resolved | N | N
75159 | 430_ME_RoofTopUnits_ThermoVentD.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75155 | 430_ME_RoofFanDV_Return.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75154 | 430_ME_KitchenHoodMonoblock_Standard.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75151 | 430_ME_StartingSolution.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75150 | 430_ME_InlineCentrifugalFan_FRD.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75149 | 430_ME_RoofFanBendDHE_Supply.rfa | 2026-08-12 | 2026-08-12 | 1 | handler_assign | status_resolved | N | N
75148 | 430_ME_AirHandlingUnit_Single_Zuluft.rfa | 2026-08-12 | 2026-08-12 | 1 | handler_assign | status_resolved | N | N
75147 | 430_ME_Schleusenventilatoren.rfa | 2026-08-12 | 2026-08-13 | 2 | handler_assign | status_resolved | N | N
75146 | 430_ME_VentilationJetFans_GAXO_NoSystem.rfa | 2026-08-12 | 2026-09-17 | 27 | handler_assign | confirm_note:stored_full | N | N
75145 | 430_ME_KitchenExtractorHood.rfa | 2026-08-12 | 2026-09-24 | 32 | handler_assign | confirm_note:stored_full | N | N
75144 | 430_ME_SmokeExhaustJetFans_NoSystem.rfa | 2026-08-12 | 2026-09-16 | 26 | handler_assign | confirm_note:stored_full | N | N
75143 | 430_ME_MixingTank_Becomix.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75142 | 430_ME_JetFanCarPark_FloorSurface_NoSystem.rfa | 2026-08-12 | 2026-09-14 | 24 | handler_assign | confirm_note:stored_full | N | N
75141 | 430_ME_AirHandlingUnit_Single_Abluft.rfa | 2026-08-12 | 2026-09-15 | 25 | handler_assign | confirm_note:stored_full | N | N
75140 | 430_ME_IndoorUnitsThermoVentI.rfa | 2026-08-12 | 2026-09-14 | 24 | handler_assign | confirm_note:stored_full | N | N
75130 | 491_SE_PillarOnTopAndDoubleArmWithThread.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | N | N
75129 | 491_SE_SingleArmWithPillarOnTop.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | N | N
75128 | 491_SE_PillarOnTopAndSingleArmWithThread.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | N | N
75127 | Revise the RFA library for the HGR system. | 2026-08-11 |  |  | handler_assign | none | N | Y | missing_end
75126 | 491_SE_ConductorHolders_FloorStand.rfa | 2026-08-11 | 2026-09-09 | 22 | handler_assign | confirm_note:stored_full | N | N
75082 | MED_Update Pipe Fitting to DCM Revit Library Model | 2026-08-05 | 2026-08-31 | 19 | handler_assign | status_resolved | N | N
75081 | SPR_Update Pipe Fitting to DCM Revit Library Model | 2026-08-05 |  |  | handler_assign | none | N | Y | missing_end
75059 | 440_EE_FlatRoofSolarModule.rfa | 2026-08-04 | 2026-09-04 | 24 | handler_assign | confirm_note:stored_full | N | N
75015 | ELT_MSR_High Priority Audit Family List | 2026-07-30 | 2026-07-31 | 2 | handler_assign | status_resolved | N | N
74979 | 410_SE_CoverBox | 2026-08-04 | 2026-09-10 | 28 | handler_assign | confirm_note:stored_full | N | N
74978 | 410_SE_ConlitFireProtectionSleeve_NoSystem | 2026-08-04 | 2026-09-10 | 28 | handler_assign | confirm_note:stored_full | N | N
74977 | 410_SE_Conlit150U_NoSystem | 2026-08-04 | 2026-09-09 | 27 | handler_assign | confirm_note:stored_full | N | N
74976 | 410_ME_WaterSofteningTank | 2026-08-31 | 2026-09-09 | 8 | handler_assign | status_resolved | N | N
74975 | 410_ME_WaterHeater_WallMounted | 2026-08-31 | 2026-09-18 | 15 | handler_assign | confirm_note:stored_full | N | N
74974 | 410_ME_WaterHeaterWithTap_WallMounted | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | N | N
74973 | 410_ME_WaterHardnessMeter | 2026-08-31 | 2026-09-14 | 11 | handler_assign | confirm_note:stored_full | N | N
74972 | 410_ME_WaterFilterVertical | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | N | N
74971 | 410_ME_WaterFilterTank | 2026-08-31 | 2026-09-18 | 15 | handler_assign | confirm_note:stored_full | N | N
74970 | 410_ME_WaterDispenser_FloorStand | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | N | N
74969 | 410_ME_WasteWaterLift_Floor_WC3 | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | N | N
74968 | 410_ME_WasteWaterLift_Floor_WC1 | 2026-08-31 | 2026-09-24 | 19 | handler_assign | confirm_note:stored_full | N | N
74967 | 410_ME_WasteWaterLift_Floor_D2 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full | N | N
74966 | 410_ME_WasteWaterLift_Floor_CWC3 | 2026-08-31 | 2026-09-22 | 17 | handler_assign | confirm_note:stored_full | N | N
74965 | 410_ME_WasteWaterLift_Floor_C3 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full | N | N
74964 | 410_ME_WasteWaterLiftingStation_VerticalPump | 2026-08-31 | 2026-09-08 | 7 | handler_assign | status_resolved | N | N
74963 | 410_ME_WastewaterLiftingStation_Sinkamat_HW | 2026-08-31 | 2026-09-24 | 19 | handler_assign | confirm_note:stored_full | N | N
74962 | 410_ME_WastewaterLiftingStation_MuliStarMDP1&MWP1 | 2026-08-31 | 2026-09-17 | 14 | handler_assign | confirm_note:stored_full | N | N
74961 | 410_ME_WastewaterLiftingStation_MuliStarDDP | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | N | N
74960 | 410_ME_WastewaterLiftingStation_MuliProPENXLDuo | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | N | N
74959 | 410_ME_WastewaterLiftingStation_MuliProPEKParallel | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | N | N
74958 | 410_ME_WastewaterLiftingStation_MuliProPEKDuo | 2026-08-31 | 2026-09-07 | 6 | handler_assign | status_resolved | N | N
74957 | 410_ME_WastewaterLiftingStation_MuliPES&Mono | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | N | N
74956 | 410_ME_WasteWaterLiftingStation_KesselPump | 2026-08-31 | 2026-09-16 | 13 | handler_assign | confirm_note:stored_full | N | N
74955 | 410_ME_WastewaterLiftingStation_DouPump | 2026-08-27 | 2026-09-16 | 15 | handler_assign | confirm_note:stored_full | N | N
74954 | 410_ME_WasteWaterLiftingStationPump | 2026-08-26 | 2026-09-23 | 21 | handler_assign | confirm_note:stored_full | N | N
74953 | 410_ME_VerticaltubeHeatexchanger | 2026-08-26 | 2026-09-15 | 15 | handler_assign | confirm_note:stored_full | N | N
74952 | 410_ME_TWPressureBoosterSystem | 2026-08-26 | 2026-09-16 | 16 | handler_assign | confirm_note:stored_full | N | N
74951 | 410_ME_TripleSofteningSystem_DeltaP | 2026-08-26 | 2026-09-11 | 13 | handler_assign | confirm_note:stored_full | N | N
74950 | 410_ME_TresorCabinet_WallSurface | 2026-08-26 | 2026-09-16 | 16 | handler_assign | confirm_note:stored_full | N | N
74949 | 410_ME_TresorCabinet_InWall | 2026-08-26 | 2026-09-11 | 13 | handler_assign | confirm_note:stored_full | N | N
74948 | 410_ME_SubmergedPump_Vertical_SATVSeries | 2026-08-24 | 2026-09-28 | 26 | handler_assign | confirm_note:stored_full | N | N
74947 | 410_ME_SubmergedPump_Vertical_SATSeries | 2026-08-24 | 2026-09-04 | 10 | handler_assign | confirm_note:stored_full | N | N
74946 | 410_ME_SubmergedPump_SitaSeries | 2026-08-20 | 2026-09-15 | 19 | handler_assign | confirm_note:stored_full | N | N
74945 | 410_ME_SubmergedPump_Horizontal_SatSeries | 2026-08-20 | 2026-09-24 | 26 | handler_assign | confirm_note:stored_full | N | N
74944 | 410_ME_SubmergedPump_ACOSAT100DWithPoweliftMono | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | N | N
74943 | 410_ME_StratosPICOZPump_Vertical | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | N | N
74942 | 410_ME_StratosMAXOZPump_Vertical | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | N | N
74941 | 410_ME_SinglePressureBoosterSystem | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | N | N
74940 | 410_ME_Sicherheitstrennstation | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | N | N
74939 | 410_ME_ServiceStorageTank_Round | 2026-08-20 | 2026-09-11 | 17 | handler_assign | confirm_note:stored_full | N | N
74938 | 410_ME_SeparationStation | 2026-08-20 | 2026-08-21 | 2 | handler_assign | status_resolved | N | N
74937 | 410_ME_ReverseOsmosisSystem | 2026-08-20 | 2026-09-23 | 25 | handler_assign | confirm_note:stored_full | N | N
74936 | 410_ME_PureWaterTank | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | N | N
74935 | 410_ME_PumpGlandlessCirculator_TopZ | 2026-08-20 | 2026-09-30 | 30 | handler_assign | confirm_note:stored_full | N | N
74934 | 410_ME_PumpGlandlessCirculator_StarZD | 2026-08-20 | 2026-09-15 | 19 | handler_assign | confirm_note:stored_full | N | N
74933 | 410_ME_PumpGlandlessCirculator_StarZ | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full | N | N
74929 | 410_ME_Probenahmetopf | 2026-08-20 | 2026-09-09 | 15 | handler_assign | confirm_note:stored_full | N | N
74926 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith2PumP | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | N | N
74922 | 410_ME_PressurisationUnit_VariableSpeedUnitsWith1Pump | 2026-08-20 | 2026-09-18 | 22 | handler_assign | confirm_note:stored_full | N | N
74921 | 410_ME_PressurisationUnit_VariableSpeedUnits3Pump | 2026-08-20 | 2026-09-17 | 21 | handler_assign | confirm_note:stored_full | N | N
74920 | 410_ME_PressurisationUnit_FixedSpeedUnits3Pump | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full | N | N
74919 | 410_ME_PressurisationUnit_FixedSpeedUnits2Pump | 2026-08-20 | 2026-09-08 | 14 | handler_assign | confirm_note:stored_full | N | N
74918 | 410_ME_PressureBoosterPump | 2026-08-20 | 2026-09-16 | 20 | handler_assign | confirm_note:stored_full | N | N
74917 | 410_ME_PoolSandFilter_FloorStand_Round | 2026-08-13 | 2026-09-28 | 33 | handler_assign | confirm_note:stored_full | N | N
74916 | 410_ME_PoolHeatPump | 2026-08-13 | 2026-08-17 | 3 | handler_assign | status_resolved | N | N
74915 | 410_ME_PlasticInnerTankSeries | 2026-08-31 | 2026-09-21 | 16 | handler_assign | confirm_note:stored_full | N | N
74914 | 410_ME_PHController | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
74913 | 410_ME_MixingTank | 2026-08-13 | 2026-08-18 | 4 | handler_assign | status_resolved | N | N
74912 | 410_ME_MiniTresorCabinet_WallSurface | 2026-08-13 | 2026-08-21 | 7 | handler_assign | status_resolved | N | N
74911 | 410_ME_MiniTresorCabinet_InWall | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full | N | N
74910 | 410_ME_KHSTimer_WallSurface | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
74909 | 410_ME_KHSMiniControlSystem_WallSurface_Master | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | N | N
74907 | 410_ME_KHSMiniControlSystemSLAVE_WallSurface | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | N | N
74906 | 410_ME_KHSHygieneFlushBoxPURE_Wall_Threaded_FlowSensorDoublePort | 2026-08-13 | 2026-09-25 | 32 | handler_assign | confirm_note:stored_full | N | N
74905 | 410_ME_KHSHygieneFlushBoxPUREwithFlowSensorSinglePort_Threaded | 2026-08-13 | 2026-08-21 | 7 | handler_assign | status_resolved | N | N
74904 | 410_ME_KHSHygieneFlushBoxPRO_Wall_Threaded_FlowSensorDoublePort | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full | N | N
74903 | 410_ME_KHSHygieneFlushBoxPROwithFlowSensorSinglePort_Threaded | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | N | N
74901 | 410_ME_KHSHygieneFlushBoxLITE_Wall_Threaded_FlowSensorSinglePort | 2026-08-13 | 2026-08-21 | 7 | handler_assign | confirm_note:stored_full | N | N
74900 | 410_ME_KHSHygieneFlushBoxLITE_FlowSensorDoublePortwithThreaded | 2026-08-13 | 2026-08-21 | 7 | handler_assign | status_resolved | N | N
74899 | 410_ME_InstantaneousWaterHeater_WashBasin | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | N | N
74898 | 410_ME_InstantaneousWaterHeater_TeaKitchen | 2026-08-13 | 2026-09-15 | 24 | handler_assign | confirm_note:stored_full | N | N
74897 | 410_ME_InstantaneousWaterHeater_SinkAGB | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | N | N
74896 | 410_ME_InstantaneousWaterHeater_Shower | 2026-08-13 | 2026-09-18 | 27 | handler_assign | confirm_note:stored_full | N | N
74895 | 410_ME_iboxUniversalForShower_WallRecessed | 2026-08-13 | 2026-09-30 | 35 | handler_assign | confirm_note:stored_full | N | N
74894 | 410_ME_IBCTank | 2026-08-13 | 2026-08-20 | 6 | handler_assign | status_resolved | N | N
74893 | 410_ME_HygieneFlushingBox_CoverPanelSinglePortThreaded_KHSHS2 | 2026-08-13 | 2026-08-28 | 12 | handler_assign | confirm_note:stored_full | N | N
74892 | 410_ME_HygieneFlushingBox_CoverPanelDoublePortThreaded_KHSHS2 | 2026-08-13 | 2026-08-24 | 8 | handler_assign | confirm_note:stored_full | N | N
74891 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&SinglePortThreaded_KHSHS2 | 2026-08-13 | 2026-08-24 | 8 | handler_assign | confirm_note:stored_full | N | N
74890 | 410_ME_HygieneFlushingBox_CoverPanel&FlowSensor&DoublePortThreaded_KHSHS2 | 2026-08-13 | 2026-09-08 | 19 | handler_assign | confirm_note:stored_full | N | N
74889 | 410_ME_HotWaterStorageTank | 2026-08-11 | 2026-08-28 | 14 | handler_assign | confirm_note:stored_full | N | N
74888 | 410_ME_HighPerformanceIndustrialMixers | 2026-08-07 | 2026-09-15 | 28 | handler_assign | confirm_note:stored_full | N | N
74887 | 410_ME_GreaseSeparator_FloorStand | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | N | N
74886 | 410_ME_GreaseSeparatorFreeStandingInstallationNS10 | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | N | N
74885 | 410_ME_GlandlessCirculatorPump_Vertical_YonosPICOZ | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | N | N
74884 | 410_ME_GlandlessCirculatorPump_Vertical_YonosMAXOZ | 2026-08-07 | 2026-09-16 | 29 | handler_assign | confirm_note:stored_full | N | N
74883 | 410_ME_GlandlessCirculatorPump_Vertical_VeroLineIPZ | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full | N | N
74882 | 410_ME_FreshWaterStation | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | N | N
74881 | 410_ME_FettabscheiderNG2 | 2026-08-07 | 2026-08-27 | 15 | handler_assign | confirm_note:stored_full | N | N
74880 | 410_ME_ExpansionVessel_Reflex | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | N | N
74879 | 410_ME_ExpansionVessel | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | N | N
74878 | 410_ME_ElectricInstantaneousHeater_DLE | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | N | N
74877 | 410_ME_EKleindurchlauferhitzer_MCX | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | N | N
74876 | 410_ME_EKleindurchlauferhitzerCEX | 2026-08-07 | 2026-08-27 | 15 | handler_assign | confirm_note:stored_full | N | N
74875 | 410_ME_DuplexSofteningUnit_RondomatDuo | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | N | N
74874 | 410_ME_DualTank_WaterSofteners | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full | N | N
74873 | 410_ME_DrainLiftXL_Floor | 2026-08-07 | 2026-09-17 | 30 | handler_assign | confirm_note:stored_full | N | N
74872 | 410_ME_DrainLiftS_Floor | 2026-08-07 | 2026-09-09 | 24 | handler_assign | confirm_note:stored_full | N | N
74861 | 410_ME_DrainLiftM_Floor | 2026-08-07 | 2026-09-24 | 35 | handler_assign | confirm_note:stored_full | N | N
74860 | 410_ME_DrainLiftL_Floor | 2026-08-07 | 2026-09-08 | 23 | handler_assign | confirm_note:stored_full | N | N
74859 | 410_ME_DoublePressureBoosterSystem | 2026-08-07 | 2026-09-23 | 34 | handler_assign | confirm_note:stored_full | N | N
74858 | 410_ME_DoppelHebeanlageSchmutzwasser | 2026-08-07 | 2026-09-14 | 27 | handler_assign | confirm_note:stored_full | N | N
74857 | 410_ME_Desoftening | 2026-08-07 | 2026-09-11 | 26 | handler_assign | confirm_note:stored_full | N | N
74856 | 410_ME_CompactWaterHeater_WallMounted | 2026-08-06 | 2026-09-25 | 37 | handler_assign | confirm_note:stored_full | N | N
74855 | 410_ME_CompactPressureBoostingSystem_1MVISE | 2026-08-06 | 2026-09-17 | 31 | handler_assign | confirm_note:stored_full | N | N
74854 | 410_ME_CompactPressureBoostingSystem | 2026-07-30 | 2026-09-09 | 30 | handler_assign | confirm_note:stored_full | N | N
74853 | 410_ME_CentrifugalPump | 2026-07-30 | 2026-09-23 | 40 | handler_assign | confirm_note:stored_full | N | N
74719 | 420_ME_RadiatorBathroom_WallMounted_Credohalfflat.rfa | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full | N | N
74718 | 420_ME_RadiatorBathroom_WallMounted_Credoplus.rfa | 2026-07-22 | 2026-09-22 | 45 | handler_assign | confirm_note:stored_full | N | N
74717 | 420_ME_RadiatorBathroom_WallMounted_DecorArteLine.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | N | N
74716 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePlan.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | N | N
74715 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureHorizontal.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | N | N
74714 | 420_ME_RadiatorBathroom_WallMounted_DecorArtePureVertical.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | N | N
74713 | 420_ME_RadiatorBathroom_WallMounted_Diveo.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | N | N
74712 | 420_ME_RadiatorBathroom_WallMounted_Duett.rfa | 2026-07-22 | 2026-09-23 | 46 | handler_assign | confirm_note:stored_full | N | N
74711 | 420_ME_RadiatorBathroom_WallMounted_Elveo_NoSystem.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | N | N
74710 | 420_ME_RadiatorBathroom_WallMounted_Fineo.rfa | 2026-07-22 | 2026-09-10 | 37 | handler_assign | confirm_note:stored_full | N | N
74709 | 420_ME_RadiatorBathroom_WallMounted_Geneocircle.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | N | N
74708 | 420_ME_RadiatorBathroom_WallMounted_Geneoquadris.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | N | N
74707 | 420_ME_RadiatorBathroom_WallMounted_Icaro.rfa | 2026-07-22 | 2026-08-13 | 17 | handler_assign | status_resolved | N | N
74706 | 420_ME_RadiatorBathroom_WallMounted_Ideos.rfa | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full | N | N
74705 | 420_ME_RadiatorBathroom_WallMounted_Ineo.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | N | N
74704 | 420_ME_RadiatorBathroom_WallMounted_Leveo.rfa | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full | N | N
74703 | 420_ME_RadiatorBathroom_WallMounted_Pateo.rfa | 2026-07-22 | 2026-08-27 | 27 | handler_assign | confirm_note:stored_full | N | N
74702 | 420_ME_RadiatorBathroom_WallMounted_Pio1layer.rfa | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full | N | N
74701 | 434_ME_FlatCompactDryCooler.rfa | 2026-07-22 | 2026-09-10 | 37 | handler_assign | confirm_note:stored_full | N | N
74700 | 434_ME_HeatExchanger_Brazed&DoublePass&Flanged.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | N | N
74699 | 434_ME_HeatExchanger_BrazedSinglePass&Thread.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | N | N
74698 | 434_ME_HeatExchanger_Brazed_DoublePass.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | N | N
74697 | 434_ME_HeatExchanger_Brazed_SinglePass&Flanged.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | N | N
74696 | 434_ME_HeatExchanger_Gasketed&Flanged.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | N | N
74695 | 434_ME_HeatExchanger_Gasketed&Thread.rfa | 2026-07-22 | 2026-08-21 | 23 | handler_assign | status_resolved | N | N
74694 | 434_ME_HeatExchanger_Standard.rfa | 2026-07-22 | 2026-09-24 | 47 | handler_assign | confirm_note:stored_full | N | N
74693 | 434_ME_HeatedAndChilledBaffleCeilings_CeilingMounted_L608.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | N | N
74692 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD315.rfa | 2026-07-22 | 2026-08-10 | 14 | handler_assign | status_resolved | N | N
74691 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SD320.rfa | 2026-07-22 | 2026-08-11 | 15 | handler_assign | status_resolved | N | N
74690 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs125_NoSystem.rfa | 2026-07-22 | 2026-08-12 | 16 | handler_assign | status_resolved | N | N
74689 | 434_ME_HeatedAndChilledCanopyCeilings_CeilingMounted_SDTabs78_NoSystem.rfa | 2026-07-22 | 2026-09-23 | 46 | handler_assign | confirm_note:stored_full | N | N
74688 | 434_ME_HeatedAndChilledCorridorCeilings_CeilingMounted_E312.rfa | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full | N | N
74687 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E200.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | N | N
74686 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E210.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | N | N
74685 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E213.rfa | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full | N | N
74684 | 434_ME_HeatedAndChilledHookonCeilings_CeilingMounted_E214.rfa | 2026-07-22 | 2026-09-14 | 39 | handler_assign | confirm_note:stored_full | N | N
74683 | 434_ME_HeatedAndChilledHybridCeilings_CeilingMounted_DSTAS.rfa | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full | N | N
74682 | 434_ME_HeatedAndChilledPlasterboardCeilings_CeilingMounted_GKHEKDA2Pipes.rfa | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full | N | N
74681 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100.rfa | 2026-07-22 | 2026-09-15 | 40 | handler_assign | confirm_note:stored_full | N | N
74680 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B100SD.rfa | 2026-07-22 | 2026-09-08 | 35 | handler_assign | confirm_note:stored_full | N | N
74679 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B110.rfa | 2026-07-22 | 2026-09-11 | 38 | handler_assign | confirm_note:stored_full | N | N
74678 | 434_ME_HeatedAndChilledPostCapCeilings_CeilingMounted_B147SD.rfa | 2026-07-22 | 2026-09-25 | 48 | handler_assign | confirm_note:stored_full | N | N
74664 | 420_ME_RadiatorBathroom_WallMounted_Pio2layer.rfa | 2026-07-21 | 2026-09-11 | 39 | handler_assign | confirm_note:stored_full | N | N
74663 | 420_ME_RadiatorBathroom_WallMounted_PioPlus.rfa | 2026-07-21 | 2026-09-11 | 39 | handler_assign | confirm_note:stored_full | N | N
74662 | 420_ME_RadiatorBathroom_WallMounted_Rubeo.rfa | 2026-07-21 | 2026-08-20 | 23 | handler_assign | confirm_note:stored_full | N | N
74661 | 420_ME_RadiatorBathroom_WallMounted_Signo.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74660 | 420_ME_RadiatorBathroom_WallMounted_Tabeo.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | N | N
74659 | 420_ME_RadiatorBathroom_WallMounted_TabeoV.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | N | N
74657 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanHorizontal_NoSystem.rfa | 2026-07-21 | 2026-08-19 | 22 | handler_assign | confirm_note:stored_full | N | N
74656 | 420_ME_RadiatorElectricPanel_WallMounted_xThermPlanVertical_NoSystem.rfa | 2026-07-21 | 2026-08-10 | 15 | handler_assign | status_resolved | N | N
74655 | 420_ME_RadiatorElectricPanel_WallMounted_xThermProfileHorizontal_NoSystem.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74654 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanK.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | N | N
74653 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKHygiene.rfa | 2026-07-21 | 2026-09-09 | 37 | handler_assign | confirm_note:stored_full | N | N
74652 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanKReplacement.rfa | 2026-07-21 | 2026-09-10 | 38 | handler_assign | confirm_note:stored_full | N | N
74651 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74650 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVHygiene.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | N | N
74649 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlus.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74648 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanVPlusHygiene.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | N | N
74647 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileK.rfa | 2026-07-21 | 2026-08-20 | 23 | handler_assign | confirm_note:stored_full | N | N
74646 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKHygiene.rfa | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:passed_audit | N | N
74645 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileKReplacement.rfa | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:passed_audit | N | N
74644 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileV.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74643 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVHygiene.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | N | N
74642 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlus.rfa | 2026-07-22 | 2026-08-25 | 25 | handler_assign | confirm_note:stored_full | N | N
74641 | 420_ME_RadiatorFlatPanel_WallMounted_ThermX2ProfileVPlusHygiene.rfa | 2026-07-22 | 2026-08-20 | 22 | handler_assign | confirm_note:stored_full | N | N
74640 | 434_ME_InLinePump_Standard.rfa | 2026-07-21 | 2026-09-04 | 34 | handler_assign | confirm_note:stored_full | N | N
74639 | 434_ME_ManifoldWithFlowMeter_10Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74638 | 434_ME_ManifoldWithFlowMeter_11Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74637 | 434_ME_ManifoldWithFlowMeter_12Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74636 | 434_ME_ManifoldWithFlowMeter_2Circuits.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | N | N
74635 | 434_ME_ManifoldWithFlowMeter_3Circuits.rfa | 2026-07-21 | 2026-09-08 | 36 | handler_assign | confirm_note:stored_full | N | N
74634 | 434_ME_ManifoldWithFlowMeter_4Circuits.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | N | N
74633 | 434_ME_ManifoldWithFlowMeter_5Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | N | N
74632 | 434_ME_ManifoldWithFlowMeter_6Circuits.rfa | 2026-07-21 | 2026-09-15 | 41 | handler_assign | confirm_note:stored_full | N | N
74631 | 434_ME_ManifoldWithFlowMeter_7Circuits.rfa | 2026-07-21 | 2026-08-26 | 27 | handler_assign | confirm_note:stored_full | N | N
74630 | 434_ME_ManifoldWithFlowMeter_8Circuits.rfa | 2026-07-21 | 2026-08-27 | 28 | handler_assign | confirm_note:stored_full | N | N
74629 | 434_ME_ManifoldWithFlowMeter_9Circuits.rfa | 2026-07-21 | 2026-08-21 | 24 | handler_assign | confirm_note:stored_full | N | N
74628 | 434_ME_ManifoldWithPump_1Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | N | N
74627 | 434_ME_ManifoldWithPump_2Circuits.rfa | 2026-07-21 | 2026-08-13 | 18 | handler_assign | confirm_note:stored_full | N | N
74626 | 434_ME_ManifoldWithPump_3Circuits.rfa | 2026-07-21 | 2026-08-14 | 19 | handler_assign | confirm_note:stored_full | N | N
74625 | 434_ME_ManifoldWithPump_4Circuits.rfa | 2026-07-21 | 2026-08-14 | 19 | handler_assign | confirm_note:stored_full | N | N
74624 | 434_ME_ManifoldWithPump_5Circuits.rfa | 2026-07-21 | 2026-08-25 | 26 | handler_assign | confirm_note:stored_full | N | N
74623 | 434_ME_ManifoldWithPump_6Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | N | N
74622 | 434_ME_ManifoldWithPump_7Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | N | N
74621 | 434_ME_ManifoldWithPump_8Circuits.rfa | 2026-07-21 | 2026-08-24 | 25 | handler_assign | confirm_note:stored_full | N | N
74603 | RLT_Update RLT Update family to DCM Revit Library Model | 2026-07-21 |  |  | handler_assign | none | N | Y | missing_end
74592 | 430_ME_AirHandlingUnits_2Layer.rfa | 2026-07-20 | 2026-09-07 | 36 | handler_assign | confirm_note:stored_full | N | N
74591 | RLT_Test Family | 2026-07-20 | 2026-07-21 | 2 | handler_assign | status_resolved | N | N
74587 | DCMvn_Annotation_Update Families in Existing DCM_SAN_Model | 2026-08-07 | 2026-09-25 | 36 | handler_assign | status_resolved | N | N
74586 | 430_ME_AirHandlingUnits_PHE.rfa | 2026-07-17 | 2026-09-16 | 44 | handler_assign | confirm_note:stored_full | N | N
74585 | 430_ME_AirHandlingUnits_CF.rfa | 2026-07-17 | 2026-09-07 | 37 | handler_assign | confirm_note:stored_full | N | N
74577 | 430_ME_AirHandlingUnits_1Layer.rfa | 2026-07-17 | 2026-08-14 | 21 | handler_assign | confirm_note:stored_full | N | N
74552 | 430_ME_AirHandingUnit_RoundConnection_CeilingStand | 2026-07-15 | 2026-09-29 | 55 | handler_assign | confirm_note:stored_full | N | N
74541 | 440_NC_EmergencyPullCordSwitch_Wall.rfa | 2026-07-15 | 2026-09-04 | 38 | handler_assign | confirm_note:stored_full | N | N
74540 | 430_ME_AirHandingUnit_RectangularRightConnection_CeilingStand.rfa | 2026-07-15 | 2026-09-18 | 48 | handler_assign | confirm_note:stored_full | N | N
74539 | 430_ME_AirHandingUnit_RectangularLeftConnection_CeilingStand.rfa | 2026-07-15 | 2026-09-17 | 47 | handler_assign | confirm_note:stored_full | N | N
74538 | 430_ME_AirCompressors_Standard.rfa | 2026-07-15 | 2026-08-14 | 23 | handler_assign | confirm_note:stored_full | N | N
74537 | 430_ME_AirHandlingUnit_CeilingMounted_AIR1XC3200L.rfa | 2026-07-15 | 2026-08-28 | 33 | handler_assign | status_resolved | N | N
74521 | 455_DD_TVOutlet_WallMounted_1Gang.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | N | N
74520 | 451_DD_TelOutlet_WallMounted_2Gangs.rfa | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full | N | N
74519 | 457_DD_LanOutlet_WallMounted_2Gangs.rfa | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full | N | N
74518 | 457_DD_LanAndTelOutlet_WallSurface.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | N | N
74517 | 481_DD_BACnetGateway.rfa | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full | N | N
74516 | 442_SD_UPSBattery_FloorStand_Rectangular.rfa | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full | N | N
74515 | 456_SD_ThermalCamera.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74514 | 456_SD_SecurityAlarmBell.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | N | N
74513 | 456_SD_PTZCamera_Outdoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74512 | 456_SD_PTZCamera_Indoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74511 | 456_SD_Monitor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74510 | 456_SD_FixCameraIP_Outdoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74509 | 456_SD_FixCameraIP_Indoor.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74508 | 456_SD_FingerScanFace_WallMounted.rfa | 2026-07-14 | 2026-09-15 | 46 | handler_assign | confirm_note:stored_full | N | N
74507 | 456_SD_FingerScan.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74506 | 456_SD_ElectricalLock_DoorMounted.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74505 | 456_SD_DomeCamera_Outdoor.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | N | N
74504 | 456_SD_DomeCamera_Indoor.rfa | 2026-07-14 | 2026-08-25 | 31 | handler_assign | confirm_note:stored_full | N | N
74503 | 456_SD_CardReader.rfa | 2026-07-14 | 2026-08-24 | 30 | handler_assign | confirm_note:stored_full | N | N
74502 | 456_SD_CameraHub_8Port.rfa | 2026-07-14 | 2026-08-25 | 31 | handler_assign | confirm_note:stored_full | N | N
74501 | 456_SD_CameraHub_16Port.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | N | N
74500 | 456_SD_AnalogCamera.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | N | N
74499 | 456_CD_Siren.rfa | 2026-07-14 | 2026-09-29 | 56 | handler_assign | confirm_note:stored_full | N | N
74498 | 457_CD_Router_Indoor.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | N | N
74497 | 454_CD_Loudspeaker6W_CeilingRecessed.rfa | 2026-07-14 | 2026-08-27 | 33 | handler_assign | confirm_note:stored_full | N | N
74496 | 455_CD_IndoorAntenna_Ceiling.rfa | 2026-07-14 | 2026-09-17 | 48 | handler_assign | confirm_note:stored_full | N | N
74491 | 430_ME_AHU_BSF_Standard.rfa | 2026-07-14 | 2026-08-14 | 24 | handler_assign | confirm_note:stored_full | N | N
74490 | 430_ME_AHUProcess.rfa | 2026-07-14 | 2026-07-14 | 1 | handler_assign | status_resolved | N | N
74488 | 454_CD_HornLoudspeaker15W_WallMounted.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
74487 | 454_CD_FireDepartmentContactPoint_WallMounted.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | N | N
74486 | 456_CD_DeskIntercomStation.rfa | 2026-07-13 | 2026-09-21 | 51 | handler_assign | confirm_note:stored_full | N | N
74485 | 452_CD_CallButtonPullCord.rfa | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
74484 | 454_CD_CabinetLoudspeaker6W_WallMounted_Square.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
74483 | 454_CD_CabinetLoudspeaker6W_WallMounted_Rectangular.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
74482 | 454_CD_CabinetLoudspeaker6W_WallMounted_Circular.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
74481 | 484_EF_Transferbox.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | N | N
74480 | 452_EF_TouchButton_WallMounted.rfa | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full | N | N
74479 | 442_EF_SealedBatteries.rfa | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
74478 | 443_EF_OvervoltageProtection_WallFlush.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | N | N
74477 | 446_EF_LightningRod_NoSystem.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
74476 | 446_EF_LightningCounterDevice.rfa | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full | N | N
74475 | 444_CI_ABS_mIndustrialBox.rfa | 2026-07-13 | 2026-09-28 | 56 | handler_assign | confirm_note:stored_full | N | N
74472 | 480_EF_IndividualRoomController.rfa | 2026-07-13 | 2026-08-05 | 18 | handler_assign | status_resolved | N | N
74471 | 480_EE_WallControlPanel_WallMounted.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
74470 | 482_EE_SwitchCabinet_FloorStand_Rectangular.rfa | 2026-07-13 | 2026-09-18 | 50 | handler_assign | confirm_note:stored_full | N | N
74469 | 482_EE_RackCabinet_WallMounted.rfa | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
74468 | 454_EE_PublicAddressSystemPanel_FloorMounted.rfa | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
74467 | 456_EE_PowerSupplyUnitAccessControl_WallMounted.rfa | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
74457 | 482_EE_Distribution_FloorStanding_Outdoor.rfa | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full | N | N
74456 | 482_EE_Distribution_FloorStanding_Indoor.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74455 | 457_EE_DataServerCabinet_FloorStand_Rectangular.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | N | N
74454 | 457_EE_DataCabinet.rfa | 2026-07-10 | 2026-09-04 | 41 | handler_assign | confirm_note:stored_full | N | N
74453 | 456_EE_ConventionalControlPanel_WallSurface_Rectangular.rfa | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full | N | N
74452 | 482_EE_ControlDistribution_WallMounted.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74451 | 456_FA_WindandRainDetector_WallMounted_RWA.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | N | N
74450 | 454_FA_VandalResistantLoudSpeaker.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74449 | 480_FA_TransferUnit.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74448 | 456_FA_ManualCallPoint_WallMounted_Square_Waterproof.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74447 | 456_FA_ManualCallPoint_WallMounted_Square.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74446 | 456_FA_SmokeSensor_RaiseFloor.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74445 | 456_FA_SmokeSensor_Ceiling.rfa | 2026-07-10 | 2026-09-28 | 57 | handler_assign | confirm_note:stored_full | N | N
74444 | 456_FA_SmokeSensor_BottomSlab.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | N | N
74443 | 480_FA_SmokeDectectorOpticalSignal_Ceiling.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74442 | 456_FA_PushButton_WallMounted_RWA.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74441 | 456_FA_PresenceDetectorHTS_Ceiling.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | N | N
74440 | 456_FA_PresenceDetector24m_Ceiling.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74439 | 456_FA_PhotoThermalSensor_CeilingMouted_Round.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74438 | 456_FA_O2TMultisensordetector_BottomSlab.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74437 | 456_FA_PhotoelectricSmokeDetector.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | N | N
74436 | 456_FA_O2TMultisensordetector.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74435 | 456_FA_MultiSensorDetector_Ceiling.rfa | 2026-07-10 | 2026-09-18 | 51 | handler_assign | confirm_note:stored_full | N | N
74434 | 456_FA_LinearHeatDetector.rfa | 2026-07-10 | 2026-09-15 | 48 | handler_assign | confirm_note:stored_full | N | N
74433 | 480_FA_LEDIndicator_WallMounted.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74432 | 456_FA_HeatSensor.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74431 | 480_FA_FireDoorHolder.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74430 | 456_FA_FireDepartmentKeyDepot.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | N | N
74429 | 456_FA_FireBrigadeInformationCenter_WallMounted.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | N | N
74428 | 456_FA_FireAlarmZoneModuleControl.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74427 | 456_FA_FireAlarmControlPanel.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74426 | 456_FA_FireAlarmCenter.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | N | N
74425 | 456_FA_EmegencyDoorRelease_WallMounted.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74424 | 456_FA_Detector_CO1224TR.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | N | N
74423 | 456_FA_Detector_CO1224A.rfa | 2026-07-10 | 2026-09-17 | 50 | handler_assign | confirm_note:stored_full | N | N
74422 | 456_FA_DetectorWithHorn.rfa | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full | N | N
74421 | 456_FA_CouplerUnit.rfa | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full | N | N
74420 | 480_FA_Bell.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74419 | 410_PX_WaterTap | 2026-07-30 | 2026-08-20 | 16 | handler_assign | confirm_note:stored_full | N | N
74418 | 456_FA_BeamSensor_WallSurface_Rectangular.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74417 | 410_PX_TapWithMaleHose_Threaded_DN15 | 2026-07-30 | 2026-09-15 | 34 | handler_assign | confirm_note:stored_full | N | N
74416 | 456_FA_AspiratingSmokeDetector_WallMounted.rfa | 2026-07-10 | 2026-09-22 | 53 | handler_assign | confirm_note:stored_full | N | N
74415 | 410_PX_SumpPit_NoSystem | 2026-07-30 | 2026-09-15 | 34 | handler_assign | confirm_note:stored_full | N | N
74414 | 480_FA_AnnunciatorPanel.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74413 | 410_PX_RoadGully | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74412 | 410_PX_ReusedRainWaterTank | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full | N | N
74411 | 456_FA_AddressableSensor.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74410 | 410_PX_Manhole_Round | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full | N | N
74409 | 410_PX_ManholeTaper_EccentricalCones_NoSystem | 2026-07-30 | 2026-08-05 | 5 | handler_assign | status_resolved | N | N
74408 | 410_PX_ManholeReducingSlabs_Eccentrical_NoSystem | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74407 | 410_PX_ManholeCoverSlabs_Eccentrical_NoSystem | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74406 | 410_PX_ManholeChamberUnits_Round_NoSystem | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74405 | 480_FA_AddressableManualPullStation.rfa | 2026-07-10 | 2026-08-28 | 36 | handler_assign | confirm_note:stored_full | N | N
74404 | 410_PX_ManholeBase_CastIn | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | N | N
74403 | 410_PX_ManholeAdjustingUnits_Round_NoSystem | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | N | N
74402 | 410_PX_KitchenTap | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74401 | 410_PX_InspectionShaft_TwoPipe_Nosystem | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74400 | 410_PX_InspectionShaft_OnePipe_Nosystem | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | N | N
74399 | 410_PX_HorizontalFloorDrain | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74398 | 410_PX_GullyGrating | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74397 | 410_PX_GreaseDisposalPoint | 2026-07-30 | 2026-08-28 | 22 | handler_assign | confirm_note:stored_full | N | N
74396 | 410_PX_GardenWater_Kemper | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74395 | 410_PX_FloorDrain_Vertical_Coupling_StainlessSteel | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74394 | 410_PX_FloorDrain_Vertical_Coupling_Plastic | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | N | N
74393 | 410_PX_CastlronFloorDrain_Vertical_Coupling | 2026-07-30 | 2026-08-06 | 6 | handler_assign | status_resolved | N | N
74392 | 410_PX_FloorDrain_VerticalFinor2PartL15_Coupling_CastIron | 2026-07-30 | 2026-08-05 | 5 | handler_assign | status_resolved | N | N
74391 | 410_PX_FloorDrain_Horizontal_Coupling_StainlessSteel | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | N | N
74390 | 410_PX_FloorDrain_Horizontal_Coupling_Plastic | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | N | N
74389 | 410_PX_FloorDrain_Horizontal_Coupling_CastIron | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74388 | 410_PX_FloorDrainExtraInlet_Vertical_Coupling_Standard | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74387 | 410_PX_FlatRoofSingleDrain_Vertical_Coupling_CastIron | 2026-07-30 | 2026-09-28 | 43 | handler_assign | confirm_note:stored_full | N | N
74386 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_StainlessSteel | 2026-07-30 | 2026-08-28 | 22 | handler_assign | confirm_note:stored_full | N | N
74385 | 410_PX_FlatRoofSingleDrain_Horizontal_Coupling_CastIron | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74384 | 410_PX_FlatRoofCompleteDrainVariant_Vertical_Coupling_StainlessSteel | 2026-07-30 | 2026-09-11 | 32 | handler_assign | confirm_note:stored_full | N | N
74383 | 410_PX_FlatRoofCompleteDrainVariant_Horizontal_Coupling_StainlessSteel | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74382 | 410_PX_FaucetWithFlexibleHose | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74381 | 410_PX_DuofixTraverseForStandaloneFaucetKitchenSink | 2026-07-30 | 2026-08-19 | 15 | handler_assign | confirm_note:stored_full | N | N
74380 | 410_PX_DuofixSigmaToilet12cm_BarrierFree | 2026-07-30 | 2026-09-04 | 27 | handler_assign | confirm_note:stored_full | N | N
74379 | 410_PX_DuofixForUrinal_Universal | 2026-07-30 | 2026-09-14 | 33 | handler_assign | confirm_note:stored_full | N | N
74378 | 410_PX_DuofixForUrinal | 2026-07-30 | 2026-08-05 | 5 | handler_assign | status_resolved | N | N
74377 | 410_PX_DuofixForShower&Bathtub_WallFittingAP | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | N | N
74376 | 410_PX_DuofixForShower&Bathtub | 2026-07-30 | 2026-09-07 | 28 | handler_assign | confirm_note:stored_full | N | N
74375 | 410_PX_DuofixElementInsetWashbasin_PillarTap | 2026-07-30 | 2026-07-31 | 2 | handler_assign | status_resolved | N | N
74374 | 410_PX_DuofixElementForWashBasin_BarrierFree | 2026-07-28 | 2026-09-28 | 45 | handler_assign | confirm_note:stored_full | N | N
74373 | 410_PX_DuofixElementForWashbasin | 2026-07-28 | 2026-08-17 | 15 | handler_assign | confirm_note:stored_full | N | N
74371 | 410_PX_DuofixElementForWallHungWC | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full | N | N
74339 | Revise the RFA library for the MSR system. | 2026-07-09 |  |  | handler_assign | none | N | Y | missing_end
74338 | 440_CI_ST_mJunctionBox_Explosionproof.rfa | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full | N | N
74337 | 440_CI_SS_xFlatConductorCross.rfa | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full | N | N
74336 | 440_CI_SS_xCrossConductorFlatToRound.rfa | 2026-07-09 | 2026-08-18 | 29 | handler_assign | confirm_note:stored_full | N | N
74335 | 440_CI_SS_xConduitBodies_Threaded_TypeX.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | N | N
74334 | 440_CI_SS_uCFormConduitUnion_Threaded.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | N | N
74333 | 440_CI_SS_tConduitBodies_Threaded_TypeTB.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | N | N
74332 | 440_CI_SS_tConduitBodies_Threaded_TypeT.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | N | N
74331 | 440_CI_SS_FlatStrip_Standard.rfa | 2026-07-09 | 2026-09-18 | 52 | handler_assign | confirm_note:stored_full | N | N
74330 | 440_CI_SS_eInspectionElbow_Standard.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | N | N
74329 | 440_CI_SS_eFlatConductorsElbow_Standard.rfa | 2026-07-09 | 2026-09-18 | 52 | handler_assign | confirm_note:stored_full | N | N
74328 | 440_CI_SS_eConduitBodies_TypeLL_Threaded.rfa | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | N | N
74327 | 440_CI_SS_eConduitBodies_Threaded_TypeLU.rfa | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved | N | N
74326 | 440_CI_SS_eConduitBodies_Threaded_TypeLR.rfa | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved | N | N
74325 | 440_CI_SS_eConduitBodies_Threaded_TypeLB.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | N | N
74324 | 440_CI_SS_e90DegreeElbow_Threaded.rfa | 2026-07-09 | 2026-08-25 | 34 | handler_assign | confirm_note:stored_full | N | N
74323 | 440_CI_SS_e90DegreeElbow_Standard.rfa | 2026-07-09 | 2026-07-14 | 4 | handler_assign | status_resolved | N | N
74322 | 440_CI_SS_e45DegreeElbow_Threaded.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | N | N
74321 | 440_CI_SS_e45DegreeElbow_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | N | N
74320 | 440_CI_SS_cDeviceBoxes_Threaded.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | N | N
74319 | 440_CI_PVC_mYWayBox_Standard.rfa | 2026-07-09 | 2026-09-17 | 51 | handler_assign | confirm_note:stored_full | N | N
74318 | 440_CI_PVC_mUWayBox_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | N | N
74317 | 440_CI_PVC_uThroughTwoWayBox_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | N | N
74316 | 440_CI_PVC_cTerminalOneWayBox_Standard.rfa | 2026-07-09 | 2026-09-04 | 42 | handler_assign | confirm_note:stored_full | N | N
74315 | 440_CI_PVC_tTeeThreeWayBox_Standard.rfa | 2026-07-09 | 2026-08-26 | 35 | handler_assign | confirm_note:stored_full | N | N
74314 | 440_CI_PVC_rReducer_Standard.rfa | 2026-07-09 | 2026-08-24 | 33 | handler_assign | confirm_note:stored_full | N | N
74270 | 440_CI_PVC_mJunctionBox_Standard_ThreeWay.rfa | 2026-07-06 | 2026-09-28 | 61 | handler_assign | confirm_note:stored_full | N | N
74269 | 440_CI_PVC_uJunctionBox_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74268 | 440_CI_PVC_xIntersectionFourWayBox_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74267 | 440_CI_PVC_tInspectionTee_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74266 | 440_CI_PVC_e90DegreeInspectionElbow_Standard.rfa | 2026-07-06 | 2026-07-13 | 6 | handler_assign | status_resolved | N | N
74265 | 440_CI_PVC_eInspectionBend_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | N | N
74264 | 440_CI_PVC_mHWayJuntionBox_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | N | N
74263 | 440_CI_PVC_fCoupling_Standard.rfa | 2026-07-06 | 2026-08-25 | 37 | handler_assign | confirm_note:stored_full | N | N
74260 | 440_CI_PVC_ConduitSleeveCoupling_Standard.rfa | 2026-07-06 | 2026-07-10 | 5 | handler_assign | status_resolved | N | N
74259 | 440_CI_PVC_tConduitBodiesTypeT_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74258 | 440_CI_PVC_eConduitBodiesTypeLR_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74257 | 440_CI_PVC_eConduitBodiesTypeLL_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74256 | 440_CI_PVC_eConduitBodiesTypeLB_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | N | N
74255 | 440_CI_PVC_cConduitBodiesTypeE_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74254 | 440_CI_PVC_uConduitBodiesTypeC_Standard.rfa | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full | N | N
74253 | 440_CI_PVC_cMarkerforConnectionLugs.rfa | 2026-07-06 | 2026-09-24 | 59 | handler_assign | confirm_note:stored_full | N | N
74252 | 440_CI_PVC_eAngledTwoWayBox_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | N | N
74251 | 440_CI_PVC_e90DegreeElbow_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74249 | 440_CI_PVC_e45DegreeElbow_Standard.rfa | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full | N | N
74248 | 440_CI_PVC_e30DegreeElbow_Standard.rfa | 2026-07-06 | 2026-08-26 | 38 | handler_assign | confirm_note:stored_full | N | N
74247 | 440_CI_PC_mJunctionBox_Standard_Weatherproof.rfa | 2026-07-06 | 2026-09-30 | 63 | handler_assign | confirm_note:stored_full | N | N
74246 | 440_CI_CS_xExpansionPiecesRound_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | N | N
74243 | 440_CI_CS_xClamps_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | N | N
74240 | 440_CI_CS_tExpansionPiecesRound_Standard.rfa | 2026-07-06 | 2026-08-14 | 30 | handler_assign | confirm_note:stored_full | N | N
74239 | 440_CI_CS_tClamps_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | N | N
74230 | 440_CF_uWallFloorFlange_Busway.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | N | N
74229 | 440_CF_UnfusedReducer_Busway.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | N | N
74228 | 440_CF_uFlexibleLink_Busway.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | N | N
74227 | 440_CF_uEndClosure_Busway.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | N | N
74226 | 440_CF_uCableTapBoxEnd_Busway.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | N | N
74224 | 440_CF_uCableTapBoxCenter_Busway.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | N | N
74223 | 440_CF_ST_eoLadderVerticalOutsideBend_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | N | N
74222 | 440_CF_ST_eiLadderVerticalInsideBend_Standard.rfa | 2026-07-06 | 2026-08-20 | 34 | handler_assign | confirm_note:stored_full | N | N
74221 | 440_CF_ST_xvLadderVerticalCross_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | N | N
74220 | 440_CF_ST_tvLadderUTypeVerticalTee_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | N | N
74219 | 440_CF_ST_uLadderUnion_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | N | N
74218 | 440_CF_ST_rLadderTransition_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | N | N
74217 | 440_CF_ST_tLadderHorizontalTee_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | N | N
74216 | 440_CF_ST_xLadderHorizontalCross_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | N | N
74215 | 440_CF_ST_ehLadderHorizontalBend_Standard.rfa | 2026-07-06 | 2026-08-19 | 33 | handler_assign | confirm_note:stored_full | N | N
74214 | 440_CF_ST_eoChannelVerticalOutsideBend_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | N | N
74213 | 440_CF_ST_eiChannelVerticalInsideBend_Standard.rfa | 2026-07-06 | 2026-08-18 | 32 | handler_assign | confirm_note:stored_full | N | N
74212 | 440_CF_ST_tvChannelVerticalDownTee_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | N | N
74211 | 440_CF_ST_xvChannelVerticalCross_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | N | N
74210 | 440_CF_ST_uChannelUnion_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | N | N
74209 | 440_CF_ST_rChannelTransition_Standard.rfa | 2026-07-06 | 2026-08-28 | 40 | handler_assign | confirm_note:stored_full | N | N
74208 | 440_CF_ST_tChannelHorizontalTee_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | N | N
74190 | 440_CF_ST_ehChannelHorizontalMiteredBend_Standard.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | N | N
74189 | 440_CF_ST_xChannelHorizontalCross_Standard.rfa | 2026-07-06 | 2026-08-24 | 36 | handler_assign | confirm_note:stored_full | N | N
74188 | 440_CF_ST_ehChannelHorizontalBend_Standard.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | N | N
74187 | 440_CF_mStraightLength_Busway.rfa | 2026-07-06 | 2026-08-21 | 35 | handler_assign | confirm_note:stored_full | N | N
74185 | 440_CF_mPotentialEqualisationBusbar.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | N | N
74184 | 440_CF_mPhaseTransition_Busway.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | N | N
74183 | 440_CF_mFlatwiseTee_Busway.rfa | 2026-07-06 | 2026-08-17 | 31 | handler_assign | confirm_note:stored_full | N | N
74182 | 440_CF_ehFlatwiseElbowWithAngle_Busway.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | N | N
74181 | 440_CF_ehFlatwiseElbowFlangeEnd_Busway.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | N | N
74180 | 440_CF_CS_xCavityFloorBoxWithSquareFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | N | N
74179 | 440_CF_CS_xCavityFloorBoxWithRoundFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | N | N
74177 | ELT_Document for proposal of using Fill Region Text Nested to Detail Item | 2026-07-06 | 2026-07-07 | 2 | handler_assign | status_resolved | N | N
74176 | 2026Q3_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-07-06 | 2026-09-07 | 46 | handler_assign | status_closed | N | N
74175 | 430_AT_RoundLouver_Standard.rfa | 2026-07-06 | 2026-07-17 | 10 | handler_assign | confirm_note:stored_full | N | N
74174 | 430_AT_RoofHood.rfa | 2026-07-06 | 2026-07-17 | 10 | handler_assign | confirm_note:stored_full | N | N
74173 | 430_AT_Nozzle_Standard.rfa | 2026-07-08 | 2026-07-28 | 15 | handler_assign | confirm_note:stored_full | N | N
74172 | 430_AT_Nozzles_Supply.rfa | 2026-07-08 | 2026-07-28 | 15 | handler_assign | confirm_note:stored_full | N | N
74171 | 430_AT_Nozzles_Return.rfa | 2026-07-09 | 2026-07-28 | 14 | handler_assign | confirm_note:stored_full | N | N
74170 | 430_AT_Nozzles_Exhaust.rfa | 2026-07-09 | 2026-07-28 | 14 | handler_assign | confirm_note:stored_full | N | N
74169 | 430_AT_SchakoDisplacementDiffusers_Wall_WQA_Supply.rfa | 2026-07-09 | 2026-07-29 | 15 | handler_assign | confirm_note:stored_full | N | N
74168 | 430_AT_SlotDiffuserDSXXXLP2A_Return.rfa | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full | N | N
74167 | 430_AT_SlotDiffuserDSXXXLP2A_Supply.rfa | 2026-07-09 | 2026-08-07 | 22 | handler_assign | confirm_note:stored_full | N | N
74166 | 430_AT_SmokeExtractionAndVentilationHood_Roof_Rectangular_Exhaust.rfa | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full | N | N
74165 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Return.rfa | 2026-07-13 | 2026-07-31 | 15 | handler_assign | confirm_note:stored_full | N | N
74164 | 430_AT_SwirlDiffusers_Ceiling_Round_RFDV_Supply.rfa | 2026-07-13 | 2026-07-31 | 15 | handler_assign | confirm_note:stored_full | N | N
74163 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Return.rfa | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full | N | N
74162 | 430_AT_SwirlDiffuser_CeilingHorizontal_Rectangular_PerforatedMetalTiles_Supply.rfa | 2026-07-09 | 2026-07-31 | 17 | handler_assign | confirm_note:stored_full | N | N
74161 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Return.rfa | 2026-07-13 | 2026-08-10 | 21 | handler_assign | confirm_note:stored_full | N | N
74160 | 430_AT_SwirlDiffuser_CeilingHorizontal_Round_Supply.rfa | 2026-07-13 | 2026-08-10 | 21 | handler_assign | confirm_note:stored_full | N | N
74159 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Return.rfa | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full | N | N
74158 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_PerforatedMetalTiles_Supply.rfa | 2026-07-09 | 2026-08-10 | 23 | handler_assign | confirm_note:stored_full | N | N
74157 | 430_AT_SwirlDiffuser_CeilingVertical_Rectangular_Return.rfa | 2026-07-06 | 2026-07-27 | 16 | handler_assign | confirm_note:stored_full | N | N
74156 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Return.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | N | N
74155 | 430_AT_SwirlDiffuser4Ways_Ceiling_Rectangular_Supply.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | N | N
74154 | 440_CF_CS_xCavityFloorBoxWithHeatResistantSquareFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | N | N
74153 | 440_CF_CS_xCavityFloorBoxWithHeatResistantRoundFormworkBodyCross_Standard.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | N | N
74152 | 440_CF_CS_uCavityFloorBoxWithSquareFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | N | N
74151 | 440_CF_CS_uCavityFloorBoxWithRoundFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | N | N
74150 | 440_CF_CS_uCavityFloorBoxWithHeatResistantSquareFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-07-23 | 14 | handler_assign | confirm_note:stored_full | N | N
74149 | 440_CF_CS_uCavityFloorBoxWithHeatResistantRoundFormworkBodyEnd_Standard.rfa | 2026-07-06 | 2026-08-10 | 26 | handler_assign | confirm_note:stored_full | N | N
74148 | 440_CF_CS_tCavityFloorBoxWithSquareFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | N | N
74147 | 440_CF_CS_eScreedCovered_Standard_ChannelThreePartVerticalBend.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | N | N
74146 | 440_CF_CS_eCavityFloorBoxWithSquareFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | N | N
74145 | 440_CF_CS_tCavityFloorBoxWithRoundFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | N | N
74144 | 440_CF_CS_tCavityFloorBoxWithHeatResistantSquareFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | N | N
74143 | 440_CF_CS_tCavityFloorBoxWithHeatResistantRoundFormworkBodyTee_Standard.rfa | 2026-07-06 | 2026-08-07 | 25 | handler_assign | confirm_note:stored_full | N | N
74142 | 440_CF_CS_eScreedCovered_Standard_ChannelTwoPartVerticalBend.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | N | N
74141 | 440_CF_CS_eCavityFloorBoxWithRoundFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-05 | 23 | handler_assign | confirm_note:stored_full | N | N
74140 | 440_CF_CS_eCavityFloorBoxWithHeatResistantSquareFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | N | N
74139 | 440_CF_CS_eCavityFloorBoxWithHeatResistantRoundFormworkBodyElbow_Standard.rfa | 2026-07-06 | 2026-08-11 | 27 | handler_assign | confirm_note:stored_full | N | N
74138 | 440_CF_CO_uFlangedEnd_Busway.rfa | 2026-07-06 | 2026-08-03 | 21 | handler_assign | confirm_note:stored_full | N | N
74137 | 440_CF_CO_mChannelMultiPort_Standard_FeedUnitForDryTransformer.rfa | 2026-07-06 | 2026-08-06 | 24 | handler_assign | confirm_note:stored_full | N | N
74136 | 440_CF_CO_eFlatwise_Standard.rfa | 2026-07-06 | 2026-08-03 | 21 | handler_assign | confirm_note:stored_full | N | N
74129 | 410_PX_DuofixElementForWallHungWC_BarrierFree_SigmaConcealedCistern | 2026-07-28 | 2026-08-14 | 14 | handler_assign | confirm_note:stored_full | N | N
74128 | 410_PX_DuofixElementForWallHungWC_BarrierFree | 2026-07-28 | 2026-08-14 | 14 | handler_assign | confirm_note:stored_full | N | N
74127 | 410_PX_DuofixElementForSinkAGB | 2026-07-27 | 2026-07-30 | 4 | handler_assign | status_resolved | N | N
74126 | 410_PX_DrainageChannel_B125 | 2026-07-27 | 2026-07-30 | 4 | handler_assign | status_resolved | N | N
74125 | 410_PX_DoppelPumpStationPowerlift_ACO | 2026-07-27 | 2026-08-28 | 25 | handler_assign | confirm_note:stored_full | N | N
74124 | 410_PX_BoxGutters_Vertical_Coupling_StainlessSteel | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full | N | N
74123 | 410_PX_StainlessSteelBoxGutters_Horizontal_Coupling | 2026-08-24 | 2026-08-24 | 1 | handler_assign | status_resolved | N | N
74121 | 410_PX_BasementFloorDrain_Vertical_Coupling_CastIron | 2026-07-27 | 2026-09-09 | 33 | handler_assign | confirm_note:stored_full | N | N
74120 | 410_PX_BasementFloorDrain_Horizontal_Coupling_Plastic | 2026-07-27 | 2026-09-21 | 41 | handler_assign | confirm_note:stored_full | N | N
74119 | 410_PX_BasementFloorDrain_Horizontal_Coupling_CastIron | 2026-07-27 | 2026-08-28 | 25 | handler_assign | confirm_note:stored_full | N | N
74107 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Return.rfa | 2026-07-03 | 2026-09-23 | 59 | handler_assign | confirm_note:stored_full | N | N
74106 | 430_AT_SwirlDiffuser_CeilingVertical_Round_Supply.rfa | 2026-07-03 | 2026-09-21 | 57 | handler_assign | confirm_note:stored_full | N | N
74105 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Return.rfa | 2026-07-03 | 2026-07-22 | 14 | handler_assign | confirm_note:stored_full | N | N
74104 | 430_AT_SwirlDiffuser_HorizontalCeiling_Rectangular_Supply.rfa | 2026-07-03 | 2026-09-29 | 63 | handler_assign | confirm_note:stored_full | N | N
74103 | 430_AT_SwirlDiffuser_VerticalCeiling_Rectangular_Supply.rfa | 2026-07-03 | 2026-07-22 | 14 | handler_assign | confirm_note:stored_full | N | N
74102 | 430_AT_TextileDiffuser_Supply.rfa | 2026-07-03 | 2026-08-18 | 33 | handler_assign | confirm_note:stored_full | N | N
74101 | 430_AT_VentilationGrilles_DoorWall_AGS_Exhaust.rfa | 2026-07-03 | 2026-08-17 | 32 | handler_assign | confirm_note:stored_full | N | N
74100 | 430_AT_VentilationGrilles_DoorWall_AGS_Supply.rfa | 2026-07-03 | 2026-09-18 | 56 | handler_assign | confirm_note:stored_full | N | N
74099 | 430_AT_VentilationGrilles_Rectangular_Standard.rfa | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full | N | N
74098 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Return.rfa | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full | N | N
74097 | 430_AT_VentilationGrilles_RoundDuctHorizontal_TRSR_Supply.rfa | 2026-07-03 | 2026-09-15 | 53 | handler_assign | confirm_note:stored_full | N | N
74096 | 430_AT_VentilationGrilles_RoundDuct_Standard.rfa | 2026-07-03 | 2026-09-18 | 56 | handler_assign | confirm_note:stored_full | N | N
74077 | 2026Q3_Annotation Project_TL & TM Time allocation_Thuong Van Huynh | 2026-07-02 | 2026-09-30 | 65 | handler_assign | status_closed | N | N
74067 | 2026Q3_Annotation Project_TL & TM Time allocation_Nhut Minh Le | 2026-07-02 | 2026-09-30 | 65 | handler_assign | status_closed | N | N
74064 | PD Tasks_2026Q3 | 2026-07-02 |  |  | handler_assign | none | N | Y | missing_end
74035 | 440_CF_CO_eFlatwiseOffsetElbow_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | N | N
74034 | 440_CF_CO_eEdgewiseOffet_Standard.rfa | 2026-07-02 | 2026-08-03 | 23 | handler_assign | confirm_note:stored_full | N | N
74033 | 440_CF_CO_eEdgewiseElbow_Busway.rfa | 2026-07-02 | 2026-08-13 | 31 | handler_assign | confirm_note:stored_full | N | N
74032 | 440_CF_CO_eEdgewiseElbowWithAngle_Busway.rfa | 2026-07-02 | 2026-08-13 | 31 | handler_assign | confirm_note:stored_full | N | N
74031 | 440_CF_CO_eDoubleLeftElbow_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | N | N
74030 | 440_CF_wChannelHorizontalWye_Standard.rfa | 2026-07-02 | 2026-08-21 | 37 | handler_assign | confirm_note:stored_full | N | N
74029 | 440_CF_AL_uEndFlange_Busway.rfa | 2026-07-02 | 2026-07-31 | 22 | handler_assign | confirm_note:stored_full | N | N
74028 | 440_CF_AL_tVerticalTee_Busway.rfa | 2026-07-02 | 2026-07-29 | 20 | handler_assign | confirm_note:stored_full | N | N
74027 | 440_CF_AL_StraightLength_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | N | N
74026 | 440_CF_AL_mVerticalOffsetZShade_Busway.rfa | 2026-07-02 | 2026-08-07 | 27 | handler_assign | confirm_note:stored_full | N | N
74025 | 440_CF_AL_mHorizontalOffsetZShade_Busway.rfa | 2026-07-02 | 2026-08-04 | 24 | handler_assign | confirm_note:stored_full | N | N
74024 | 440_CF_AL_eVerticalOffsetElbow90Deg_Busway.rfa | 2026-07-02 | 2026-08-12 | 30 | handler_assign | confirm_note:stored_full | N | N
73996 | 440_CF_AL_eVerticalElbow90Deg_Busway.rfa | 2026-06-30 | 2026-08-03 | 25 | handler_assign | confirm_note:stored_full | N | N
73995 | 440_CF_AL_eHorizontalElbow_Busway.rfa | 2026-06-30 | 2026-07-31 | 24 | handler_assign | confirm_note:stored_full | N | N
73994 | 455_CD_IndoorAntenna_Ceiling.rfa | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full | N | N
73993 | 440_SE_Penetration_Curaflex.rfa | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full | N | N
73992 | 440_SE_AccessPanel_Ceiling.rfa | 2026-06-30 | 2026-09-28 | 65 | handler_assign | confirm_note:stored_full | N | N
73991 | 457_SD_DomeCamera_Outdoor.rfa | 2026-06-30 | 2026-08-17 | 35 | handler_assign | confirm_note:stored_full | N | N
73990 | 481_EE_SmartHomeAccessPoint_WLAN.rfa | 2026-06-30 | 2026-09-15 | 56 | handler_assign | confirm_note:stored_full | N | N
73989 | 440_LD_SingleSwitchSocket_WallMounted.rfa | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full | N | N
73988 | 440_LD_DoubleSwitchSocket_WallMounted.rfa | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full | N | N
73987 | 456_FA_SmokeSamplingHead_Ceiling.rfa | 2026-06-30 | 2026-09-04 | 49 | handler_assign | confirm_note:stored_full | N | N
73986 | 456_FA_AspiratingSmokesSystem2Channel_WallMounted.rfa | 2026-06-30 | 2026-09-28 | 65 | handler_assign | confirm_note:stored_full | N | N
73985 | ELT_MSR_Revise and update TIDP | 2026-06-30 |  |  | handler_assign | none | N | Y | missing_end
73969 | 2026Q3_DCMvn_Annotation Project_TL & TM Time allocation_Hanh Pham | 2026-06-30 | 2026-10-01 | 68 | handler_assign | status_closed | N | N
73899 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Supply.rfa | 2026-06-25 | 2026-07-16 | 16 | handler_assign | confirm_note:stored_full | N | N
73898 | 430_AT_SchakoDiffuser_HorizontalCeiling_Rectangular_Return.rfa | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full | N | N
73890 | 434_ME_Manifold_10Circuits.rfa | 2026-06-25 | 2026-08-26 | 45 | handler_assign | confirm_note:stored_full | N | N
73889 | 434_ME_Manifold_11Circuits.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | N | N
73888 | 434_ME_Manifold_12Circuits.rfa | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full | N | N
73887 | 434_ME_Manifold_2Circuits.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | N | N
73886 | 434_ME_Manifold_3Circuits.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | N | N
73885 | 434_ME_Manifold_4Circuits.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | N | N
73884 | 434_ME_Manifold_5Circuits.rfa | 2026-06-25 | 2026-09-23 | 65 | handler_assign | confirm_note:stored_full | N | N
73883 | 434_ME_Manifold_6Circuits.rfa | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | N | N
73882 | 434_ME_Manifold_7Circuits.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | status_resolved | N | N
73880 | 434_ME_Manifold_8Circuits.rfa | 2026-06-25 | 2026-08-21 | 42 | handler_assign | confirm_note:stored_full | N | N
73879 | 434_ME_Manifold_9Circuits.rfa | 2026-06-25 | 2026-07-10 | 12 | handler_assign | status_resolved | N | N
73878 | 434_ME_OutDoorUnit_VRV5HeatRecoveryREYA.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | N | N
73877 | 434_ME_PrecisionPressureMaintenance_TransferoTI.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | N | N
73876 | 434_ME_PrecisionPressureMaintenance_TransferoTV1.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73875 | 434_ME_PrecisionPressureMaintenance_TransferoTV2.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73874 | 434_ME_PrecisionPressureMaintenance_TransferoTVI1.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73873 | 434_ME_PrecisionPressuremaintenance_TransferoTVI2.rfa | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full | N | N
73872 | 434_ME_PrecisionPressurisation_CompressoC.rfa | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | N | N
73871 | 434_ME_PrecisionPressurisation_CompressoF.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73870 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9.rfa | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | N | N
73869 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9.rfa | 2026-06-25 | 2026-07-07 | 9 | handler_assign | status_closed | N | N
73868 | 434_ME_PressureMaintenanceMonitoring_PlenoPI9F.rfa | 2026-06-25 | 2026-07-09 | 11 | handler_assign | status_resolved | N | N
73867 | 434_ME_PressureMaintenanceMonitoring_PlenoPIX.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | N | N
73866 | 434_ME_PressureMaintenanceMonitoring_PlenoPX.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | N | N
73865 | 434_ME_PumpCirculator_FloorStand_Round_CronoLineILE.rfa | 2026-06-25 | 2026-07-10 | 12 | handler_assign | status_resolved | N | N
73864 | 434_ME_Pump_CirculatorAtmosGIGA&B.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | N | N
73863 | 434_ME_Pump_CirculatorStratosGIGA&B.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | N | N
73862 | 434_ME_Pump_CirculatorStratosGIGA.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73861 | 434_ME_Pump_CirculatorStratosGIGA20&D.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73860 | 434_ME_Pump_CirculatorStratosGIGA20&I.rfa | 2026-06-25 | 2026-07-02 | 6 | handler_assign | status_resolved | N | N
73859 | 434_ME_Pump_CirculatorStratosMAXO.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73858 | 434_ME_Pump_CirculatorStratosPICO.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full | N | N
73857 | 434_ME_Pump_CirculatorVeroLineIPL.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full | N | N
73856 | 434_ME_Pump_CirculatorYonosMAXO.rfa | 2026-06-25 | 2026-07-06 | 8 | handler_assign | confirm_note:stored_full | N | N
73855 | 434_ME_Pump_CirculatorYonosPICO.rfa | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full | N | N
73854 | 434_ME_Pump_Circulator_CronoTwin_DL_E.rfa | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full | N | N
73853 | 434_ME_Pump_Circulator_VeroTwinDPL_DN100.rfa | 2026-06-25 | 2026-10-01 | 71 | handler_assign | confirm_note:stored_full | N | N
73852 | 434_ME_Pump_Circulator_VeroTwinDPL_DN32.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | N | N
73851 | 434_ME_Pump_Circulator_VeroTwinDPL_DN40.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | N | N
73850 | 434_ME_Pump_Circulator_VeroTwinDPL_DN50.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | N | N
73849 | 434_ME_Pump_Circulator_VeroTwinDPL_DN65.rfa | 2026-07-08 | 2026-09-28 | 59 | handler_assign | confirm_note:stored_full | N | N
73848 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoPlan.rfa | 2026-06-25 | 2026-08-20 | 41 | handler_assign | confirm_note:stored_full | N | N
73847 | 420_ME_RadiatorFlatPanel_WallMounted_VerteoProfile.rfa | 2026-06-25 | 2026-08-20 | 41 | handler_assign | confirm_note:stored_full | N | N
73846 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanK.rfa | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full | N | N
73845 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanV.rfa | 2026-06-25 | 2026-09-14 | 58 | handler_assign | confirm_note:stored_full | N | N
73844 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairPlanVPlus.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | N | N
73843 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileK.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73842 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileV.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73841 | 420_ME_RadiatorFlatPanel_WallMounted_xFlairProfileVPlus.rfa | 2026-06-25 | 2026-08-31 | 48 | handler_assign | confirm_note:stored_full | N | N
73840 | 420_ME_RadiatorHeatingWall_WallMounted_Horizontal.rfa | 2026-06-25 | 2026-07-07 | 9 | handler_assign | confirm_note:stored_full | N | N
73839 | 420_ME_RadiatorHeatingWall_WallMounted_ValveHorizontal.rfa | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full | N | N
73838 | 420_ME_RadiatorHeatingWall_WallMounted_ValveVertical.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | N | N
73837 | 420_ME_RadiatorHeatingWall_WallMounted_Vertical.rfa | 2026-06-25 | 2026-09-03 | 51 | handler_assign | confirm_note:stored_full | N | N
73836 | 420_ME_Radiator_WallMounted_Standard.rfa | 2026-06-25 | 2026-09-08 | 54 | handler_assign | confirm_note:stored_full | N | N
73835 | 420_ME_RectangularTubeManifold_8Connection.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | N | N
73834 | 420_ME_SinglePassTubeHeatExchanger_Horizontal.rfa | 2026-06-25 | 2026-09-03 | 51 | handler_assign | confirm_note:stored_full | N | N
73833 | 420_ME_WaterHeater_Vertical.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | N | N
73832 | 420_PA_6WayValve_Thread.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | N | N
73831 | 420_PA_AirReleaseValve_Flanged_Standard.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | N | N
73830 | 420_PA_AirReleaseValve_Thread_Standard.rfa | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full | N | N
73829 | 420_PA_AirValve_Thread.rfa | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full | N | N
73828 | 420_PA_BalancingValve_Flanged.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | N | N
73827 | 420_PA_BalancingValve_Flanged_Standard.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | N | N
73826 | 420_PA_BalancingValve_Thread.rfa | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full | N | N
73825 | 420_PA_BalancingValve_Thread_Standard.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | N | N
73824 | 420_PA_BallValve3Way_LPort.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | N | N
73823 | 420_PA_BallValve3Way_TPort.rfa | 2026-06-25 | 2026-10-01 | 71 | handler_assign | confirm_note:stored_full | N | N
73822 | 420_PA_BallValve_Flanged.rfa | 2026-06-25 | 2026-09-25 | 67 | handler_assign | confirm_note:stored_full | N | N
73821 | 420_PA_BallValve_Flanged_LeverStandard | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | N | N
73820 | 420_PA_BallValve_Flanged_WheelStandard | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | N | N
73819 | 420_PA_BallValve_FullBore | 2026-06-25 | 2026-08-12 | 35 | handler_assign | confirm_note:stored_full | N | N
73818 | 420_PA_ButterflyValve_Flanged_Handle | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full | N | N
73817 | 445_LF_MoistureProofLuminaire_WallSurface_Rectangular.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73816 | 445_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full | N | N
73815 | 445_LF_LEDLuminaireMP_CeilingMounted_Rectangular.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | N | N
73814 | 445_LF_LEDDownlightSFNB_CeilingRecessed_Round.rfa | 2026-06-25 | 2026-09-15 | 59 | handler_assign | confirm_note:stored_full | N | N
73813 | 445_LF_LEDDownlightOP_CeilingRecessed_Round.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | N | N
73812 | 445_LF_InteriorLuminaireINDMP_CeilingRecessed_Round.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73811 | 445_LF_InteriorLuminaireBL_CeilingRecessed_Rectangular.rfa | 2026-06-25 | 2026-08-28 | 47 | handler_assign | confirm_note:stored_full | N | N
73810 | 445_LF_UVCAirDisinfectionLight_WallSurface.rfa | 2026-06-25 | 2026-08-24 | 43 | handler_assign | confirm_note:stored_full | N | N
73809 | 445_LF_TruelineLinearLuminaire_CeilingRecessed.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | N | N
73808 | 445_LF_TrackSpot_S_CeilingMounted.rfa | 2026-06-25 | 2026-09-28 | 68 | handler_assign | confirm_note:stored_full | N | N
73807 | 445_LF_OpticalLight_CeilingRecessed_Round_Outdoor.rfa | 2026-06-25 | 2026-08-27 | 46 | handler_assign | confirm_note:stored_full | N | N
73806 | 440_LF_MoistureProofLuminaire_WallSurface_Rectangular.rfa | 2026-06-25 | 2026-07-17 | 17 | handler_assign | status_resolved | N | N
73805 | 445_LF_MoistureProofLuminaire_CeilingSuspended_Rectangular.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | N | N
73803 | 445_LF_LuxSpaceDownlight_CeilingRecessed_Square.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73802 | 445_LF_LuxSpaceCompactAnbaudownlight_CeilingSuspended.rfa | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full | N | N
73801 | 445_LF_LuxSpaceAccentPerformanceSpotlightSwiveling_CeilingRecessed.rfa | 2026-06-25 | 2026-08-26 | 45 | handler_assign | confirm_note:stored_full | N | N
73800 | 445_LF_LED_HighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa | 2026-06-25 | 2026-07-16 | 16 | handler_assign | status_resolved | N | N
73799 | 445_LF_LEDUplight_FloorRecessed_Round.rfa | 2026-06-25 | 2026-09-24 | 66 | handler_assign | confirm_note:stored_full | N | N
73798 | 445_LF_LEDTwoHeadWaterProofIP65EmergencyLight_WallSurface.rfa | 2026-06-25 | 2026-08-25 | 44 | handler_assign | confirm_note:stored_full | N | N
73748 | 445_LF_LEDTwinSpotEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-07-17 | 20 | handler_assign | status_resolved | N | N
73747 | 445_LF_LEDTwinHeadsFastChargingIP30EmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73746 | 445_LF_LEDStripLight_WallSurface_Rectangular.rfa | 2026-06-22 | 2026-09-22 | 67 | handler_assign | confirm_note:stored_full | N | N
73745 | 445_LF_LEDStripLight_CeilingRecessed_Rectangular.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73744 | 445_LF_LEDStripLight_CeilingMounted_Rectangular.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73743 | 445_LF_LEDStairEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-11 | 37 | handler_assign | confirm_note:stored_full | N | N
73742 | 445_LF_LEDSpotEmergencyLightingLuminaire_WallMounted_Square_SQ5A.rfa | 2026-06-22 | 2026-08-24 | 46 | handler_assign | confirm_note:stored_full | N | N
73741 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Square.rfa | 2026-06-22 | 2026-09-25 | 70 | handler_assign | confirm_note:stored_full | N | N
73740 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingSuspended_Round.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73739 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Square_SQ5E.rfa | 2026-06-22 | 2026-06-30 | 7 | handler_assign | status_resolved | N | N
73738 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round_SQ6.rfa | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full | N | N
73737 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full | N | N
73736 | 440_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square_SQ5D.rfa | 2026-06-22 | 2026-08-12 | 38 | handler_assign | confirm_note:stored_full | N | N
73735 | 445_LF_LEDSpotEmergencyLightingLuminaire_CeilingMounted_Square.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73734 | 445_LF_LEDSpotEmergencyLightingLuminaireInFireResistantCeiling_CeilingRecessed.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73733 | 445_LF_LEDSignalLightForWC_WallMounted.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | N | N
73732 | 445_LF_LEDPendantRingLight.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | N | N
73731 | 445_LF_LEDPendantLightWithAdjustableRod_CeilingSuspended.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73730 | 445_LF_LEDPanel_CeilingRecessed.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73729 | 445_LF_LEDMasterEmergencyLightingLuminaire_WallMounted.rfa | 2026-06-22 | 2026-08-24 | 46 | handler_assign | confirm_note:stored_full | N | N
73728 | 440_LF_LEDLuminaireOP_CeilingMounted_Rectangular.rfa | 2026-06-22 | 2026-07-01 | 8 | handler_assign | status_resolved | N | N
73727 | 440_LF_LEDLuminaireMP_CeilingMounted_Rectangular.rfa | 2026-06-22 | 2026-07-01 | 8 | handler_assign | status_resolved | N | N
73726 | 445_LF_LedinaireSlimDownlight_CeilingSuspended.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73725 | 445_LF_LedinaireHighbayPendantLightWithAdjustableRod_CeilingSuspended.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73724 | 445_LF_LEDHighBayPendantLight_CeilingSuspended_GentleSpaceWithAdjustableRod.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | N | N
73723 | 445_LF_LEDDownlightSM_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-08-27 | 49 | handler_assign | confirm_note:stored_full | N | N
73722 | 440_LF_LEDDownlightSFNB_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_resolved | N | N
73721 | 440_LF_LEDDownlightOP_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_resolved | N | N
73720 | 445_LF_LEDDownlightForWC_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73719 | 445_LF_LEDDoubleHeadEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73718 | 445_LF_LEDDeckeneinbauMontage_CeilingMounted_LG6E.rfa | 2026-06-22 | 2026-08-26 | 48 | handler_assign | confirm_note:stored_full | N | N
73717 | 445_LF_LEDBAPPendantLightWithAdjustableRod_CeilingSuspended.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73716 | 445_LF_LEDAccentRigidlight_CeilingRecessed_Rectangular.rfa | 2026-06-22 | 2026-08-14 | 40 | handler_assign | confirm_note:stored_full | N | N
73715 | 440_LF_LEDAccentGridlight_CeilingRecessed.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_closed | N | N
73714 | 445_LF_LeadSacidTwinHeadEmergencyLight_WallSurface.rfa | 2026-06-22 | 2026-08-07 | 35 | handler_assign | confirm_note:stored_full | N | N
73713 | 445_LF_LaserBladeLightXS_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73712 | 445_LF_LaserBladeLightXSWallWasher_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73711 | 440_LF_InteriorLuminaireINDMP_CeilingRecessed_Round.rfa | 2026-06-22 | 2026-06-29 | 6 | handler_assign | status_resolved | N | N
73710 | 440_LF_InteriorLuminaireBL_CeilingRecessed_Rectangular.rfa | 2026-06-22 | 2026-06-25 | 4 | handler_assign | status_resolved | N | N
73709 | 445_LF_GreenSpaceAccentSpotlightRigid_CeilingRecessed.rfa | 2026-06-22 | 2026-08-11 | 37 | handler_assign | confirm_note:stored_full | N | N
73708 | 445_LF_FixedOpticSmallBodyIroundOutdoorlight_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73707 | 445_LF_ExitCube_Ceiling.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73706 | 445_LF_EscapeSign_WallMounted.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73705 | 445_LF_EscapeSign_CeilingRecessed.rfa | 2026-06-22 | 2026-09-22 | 67 | handler_assign | confirm_note:stored_full | N | N
73704 | 445_LF_EscapeSign_CeilingMounted.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | N | N
73703 | 445_LF_DownlightLEDSwivelling_CeilingRecessed.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | N | N
73702 | 445_LF_DownlightLEDrigid_CeilingRecessed.rfa | 2026-06-22 | 2026-09-07 | 56 | handler_assign | confirm_note:stored_full | N | N
73701 | 445_LF_CorelineSpotlight_CeilingRecessed.rfa | 2026-06-22 | 2026-08-21 | 45 | handler_assign | confirm_note:stored_full | N | N
73700 | 445_LF_CorelineSlimDownlight_CeilingRecessed.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | N | N
73699 | 445_LF_CorelineSlimDownlight_CeilingMounted.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | N | N
73698 | 445_LF_CoreLineLEDLight_WallSurface.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | N | N
73697 | 445_LF_CoreLineLEDLight_CeilingSuspended.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | N | N
73696 | 410_PA_ZBCapRoof_Standard | 2026-07-24 | 2026-09-18 | 41 | handler_assign | confirm_note:stored_full | N | N
73695 | 410_PA_YStrainer_Threaded | 2026-07-24 | 2026-08-21 | 21 | handler_assign | confirm_note:stored_full | N | N
73694 | 440_LF_BathroomLuminaire_WallMounted_Rectangular.rfa | 2026-06-22 | 2026-09-10 | 59 | handler_assign | confirm_note:stored_full | N | N
73693 | 410_PA_YStrainer_Flanged | 2026-07-24 | 2026-09-10 | 35 | handler_assign | confirm_note:stored_full | N | N
73692 | 445_LF_3FoldPendantLight_CeilingSuspended.rfa | 2026-06-22 | 2026-08-20 | 44 | handler_assign | confirm_note:stored_full | N | N
73691 | 410_PA_WaterMeter_Threaded | 2026-07-24 | 2026-08-17 | 17 | handler_assign | confirm_note:stored_full | N | N
73690 | 410_PA_WaterMeter_Flanged | 2026-07-24 | 2026-09-09 | 34 | handler_assign | confirm_note:stored_full | N | N
73689 | 410_PA_WaterMeterUNI | 2026-07-24 | 2026-08-21 | 21 | handler_assign | confirm_note:stored_full | N | N
73688 | 410_PA_WaterHammerArrestor_Threaded | 2026-07-24 | 2026-08-26 | 24 | handler_assign | confirm_note:stored_full | N | N
73687 | 410_PA_WaferButterflyValve_Flanged | 2026-07-24 | 2026-08-27 | 25 | handler_assign | confirm_note:stored_full | N | N
73686 | 410_PA_VentCowl | 2026-07-24 | 2026-08-17 | 17 | handler_assign | confirm_note:stored_full | N | N
73685 | 410_PA_VAVFullFlowShutOffValve_FemaleThreaded | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full | N | N
73684 | 410_PA_UPConcealedShutoffValve | 2026-07-16 | 2026-08-12 | 20 | handler_assign | confirm_note:stored_full | N | N
73683 | 410_PA_UPVSenkrecht | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full | N | N
73682 | 410_PA_UpPlusFlushMoutedStopValve_SanpressProfipress | 2026-07-16 | 2026-08-18 | 24 | handler_assign | confirm_note:stored_full | N | N
73681 | 410_PA_UpETATHERMThermostaticBalancingValve_Threaded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73680 | 410_PA_UpETATHERMThermostaticBalancingValve_SanpressProfipress | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73679 | 410_PA_TwoWayDiaphragmValve_Flanged | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full | N | N
73678 | 410_PA_TwoWayDiaphragmValve_Threaded | 2026-07-16 | 2026-08-18 | 24 | handler_assign | confirm_note:stored_full | N | N
73677 | 410_PA_ThreeWayMotorisedControlValve_Threaded | 2026-07-16 | 2026-09-18 | 47 | handler_assign | confirm_note:stored_full | N | N
73676 | 410_PA_ThreeWayMotorisedControlValve_Flanged | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73675 | 410_PA_ThreePiecesBallValve_Welded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73674 | 410_PA_ThermostaticBalancingValve_Mapress_UpEtaTherm | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73673 | 410_PA_THandleBallValve_Threaded | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full | N | N
73672 | 410_PA_TemperatureMeasuringValve_Threaded_KHS | 2026-07-16 | 2026-08-27 | 31 | handler_assign | confirm_note:stored_full | N | N
73671 | 410_PA_SystemSeparator_Threaded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73670 | 410_PA_SystemSeparator_Flanged | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73669 | 410_PA_SwingcheckValve_Threaded | 2026-07-16 | 2026-08-21 | 27 | handler_assign | confirm_note:stored_full | N | N
73668 | 410_PA_SwingcheckValve_Flanged | 2026-07-16 | 2026-08-17 | 23 | handler_assign | confirm_note:stored_full | N | N
73667 | 410_PA_StaticBalancingValve_UnionThreaded_MultiFixPlus | 2026-07-16 | 2026-08-12 | 20 | handler_assign | confirm_note:stored_full | N | N
73666 | 410_PA_StaticBalancingValve_Threaded_MultiFixPlus | 2026-07-16 | 2026-09-11 | 42 | handler_assign | confirm_note:stored_full | N | N
73665 | 410_PA_StraightSafetyValve_Threaded | 2026-07-16 | 2026-08-25 | 29 | handler_assign | confirm_note:stored_full | N | N
73664 | 410_PA_StainlessSteel_ShutoffValve_MapressGeberit | 2026-07-16 | 2026-07-17 | 2 | handler_assign | status_resolved | N | N
73663 | 410_PA_ShutoffValve_Mapress_WithDrainValve | 2026-07-15 | 2026-08-12 | 21 | handler_assign | confirm_note:stored_full | N | N
73662 | 410_PA_SolenoidControlValve_Flanged | 2026-07-15 | 2026-08-25 | 30 | handler_assign | confirm_note:stored_full | N | N
73661 | 410_PA_SingleInstallationRackWatermeter_Threaded | 2026-07-15 | 2026-09-21 | 49 | handler_assign | confirm_note:stored_full | N | N
73660 | 410_PA_ShutoffValve_WithDrainPlug_Threaded | 2026-07-15 | 2026-08-26 | 31 | handler_assign | confirm_note:stored_full | N | N
73659 | 410_PA_ShutoffValve_Threaded | 2026-07-15 | 2026-08-18 | 25 | handler_assign | confirm_note:stored_full | N | N
73658 | 410_PA_ShutoffValve_Flanged_DrainValve | 2026-07-15 | 2026-08-06 | 17 | handler_assign | confirm_note:stored_full | N | N
73657 | 410_PA_ShutoffValve_Flanged | 2026-07-10 | 2026-08-07 | 21 | handler_assign | confirm_note:stored_full | N | N
73656 | 410_PA_SamplingValve_Standard_SS | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | N | N
73655 | 410_PA_SamplingValve_Standard_Gunmetal | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | N | N
73654 | 410_PA_SamplingValveForWashBasinAngleValve_Standard_SS | 2026-07-10 | 2026-08-19 | 29 | handler_assign | status_resolved | N | N
73653 | 410_PA_PressureRegulator_Thread | 2026-07-10 | 2026-08-25 | 33 | handler_assign | confirm_note:stored_full | N | N
73652 | 410_PA_PressureReducingValve_Threaded | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | N | N
73650 | 410_PA_PressureReducingValve_Flanged | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | N | N
73649 | 410_PA_PressureReducingValveWithPressureGauge_FemaleThreaded | 2026-07-10 | 2026-09-09 | 44 | handler_assign | confirm_note:stored_full | N | N
73648 | 410_PA_PressureReducingValveFilterCombination_Threaded | 2026-07-10 | 2026-07-17 | 6 | handler_assign | status_resolved | N | N
73646 | 410_PA_PressureGauge_WithSiphon | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | N | N
73645 | 410_PA_StopValve_SocketFusion | 2026-07-10 | 2026-08-24 | 32 | handler_assign | confirm_note:stored_full | N | N
73644 | 410_PA_BallValve_SocketFusion | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | N | N
73641 | 430_AT_NozzlesElectricActuator_DUK_E_Supply.rfa | 2026-06-25 | 2026-09-21 | 63 | handler_assign | confirm_note:stored_full | N | N
73640 | 430_AT_NozzlesElectricActuator_DUK_E_Exhaust.rfa | 2026-06-25 | 2026-09-11 | 57 | handler_assign | confirm_note:stored_full | N | N
73639 | 430_AT_Louvre_Standard.rfa | 2026-06-24 | 2026-08-04 | 30 | handler_assign | confirm_note:stored_full | N | N
73638 | 430_AT_LourveCover_Roof.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | N | N
73637 | 430_AT_LamellarHood_Roof_Rectangular_FreshAirIntake.rfa | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full | N | N
73636 | 430_AT_LamellarHood_Roof_Rectangular_Exhaust.rfa | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | N | N
73635 | 430_AT_JetDiffuser_Round_Standard.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | N | N
73634 | 430_AT_InspectionOpenings_RoundDuctHorizontal_Oval.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73633 | 430_AT_InspectionOpenings_RecDuctHorizontal_Rectangular.rfa | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | N | N
73632 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Supply.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73631 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGAL_Exhaust.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73624 | 410_PA_PoolSkimmer_Threaded | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full | N | N
73623 | 410_PA_PoolReturnJet_Threaded | 2026-07-10 | 2026-08-14 | 26 | handler_assign | confirm_note:stored_full | N | N
73622 | 410_PA_PoolMainDrain_Threaded | 2026-07-10 | 2026-08-14 | 26 | handler_assign | confirm_note:stored_full | N | N
73621 | 410_PA_OutletValve_Threaded_WithHoseScrewConnection | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full | N | N
73620 | 410_PA_OutletValve_Threaded | 2026-07-10 | 2026-08-06 | 20 | handler_assign | confirm_note:stored_full | N | N
73618 | 410_PA_NozzleCheckValve_Flanged | 2026-07-10 | 2026-08-05 | 19 | handler_assign | confirm_note:stored_full | N | N
73616 | 410_PA_MotorButterflyValve_Flanged | 2026-07-09 | 2026-08-20 | 31 | handler_assign | confirm_note:stored_full | N | N
73615 | 410_PA_KugelSiphon_Standard | 2026-07-09 | 2026-08-24 | 33 | handler_assign | confirm_note:stored_full | N | N
73614 | 410_PA_KHSFlushPoint_Threaded_ControlPlus24V | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full | N | N
73613 | 410_PA_KHSFlushPoint_Threaded_ControlPlus230V | 2026-07-03 | 2026-08-25 | 38 | handler_assign | confirm_note:stored_full | N | N
73612 | 410_PA_KHSFlushPoint_Threaded_24V | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73611 | 410_PA_KHSFlushPoint_Threaded_230V | 2026-07-03 | 2026-08-03 | 22 | handler_assign | confirm_note:stored_full | N | N
73610 | 410_PA_GlobeValve_Threaded | 2026-07-03 | 2026-08-03 | 22 | handler_assign | confirm_note:stored_full | N | N
73609 | 410_PA_GlobeValve_Flanged | 2026-07-03 | 2026-08-14 | 31 | handler_assign | confirm_note:stored_full | N | N
73608 | 410_PA_GateValve_Threaded | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full | N | N
73607 | 410_PA_GateValve_Flanged | 2026-07-03 | 2026-08-06 | 25 | handler_assign | confirm_note:stored_full | N | N
73606 | 410_PA_GateValveWithDrain_Threaded | 2026-07-03 | 2026-08-25 | 38 | handler_assign | confirm_note:stored_full | N | N
73605 | 410_PA_GateValveSealingDirectionWithDrain_Threaded | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | N | N
73604 | 410_PA_FunnelSiphon_Horizontal | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73603 | 410_PA_FlushMoutedStopValve_Threaded_UpPlus | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | N | N
73600 | 410_PA_FlushMountedStopValve_Mapress_UpPlus | 2026-07-03 | 2026-07-10 | 6 | handler_assign | status_resolved | N | N
73599 | 410_PA_FlowTemperatureMeterValve_Threaded | 2026-07-24 | 2026-08-25 | 23 | handler_assign | confirm_note:stored_full | N | N
73598 | 410_PA_FlowSplitterUnit_Threaded_DynamicKHS | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73597 | 410_PA_FlowSplitterUnit_FlushMounted_Threaded_DynamicKHS | 2026-07-03 | 2026-09-08 | 48 | handler_assign | confirm_note:stored_full | N | N
73596 | 410_PA_FlowSplitterSet_Threaded_KHS | 2026-07-03 | 2026-09-21 | 57 | handler_assign | confirm_note:stored_full | N | N
73595 | 410_PA_FlowSplitterBox_Floor_Threaded_KHS | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full | N | N
73594 | 410_PA_FloatingValve_Threaded | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full | N | N
73593 | 410_PA_FlexibleConnection_Flanged | 2026-07-03 | 2026-08-10 | 27 | handler_assign | confirm_note:stored_full | N | N
73592 | 410_PA_FittingSpacerForWaterMeter_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73591 | 410_PA_Filter_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73590 | 410_PA_FillsoftHousing_Threaded | 2026-07-03 | 2026-07-31 | 21 | handler_assign | confirm_note:stored_full | N | N
73589 | 410_PA_FillSetStandardValve_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73588 | 410_PA_DrainValve_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73587 | 410_PA_DoubleInstallationRackWatermeter_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73586 | 410_PA_DiaphragmValve | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73585 | 410_PA_CombinationAngleValve_Standard | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | N | N
73584 | 410_PA_CoarseTrap | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | N | N
73583 | 410_PA_BallValve_Threaded | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | N | N
73582 | 410_PA_BackflowPreventer_Threaded | 2026-07-03 | 2026-08-05 | 24 | handler_assign | confirm_note:stored_full | N | N
73581 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Supply.rfa | 2026-06-22 | 2026-07-23 | 24 | handler_assign | confirm_note:stored_full | N | N
73580 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALWidthSubdivided_Exhaust.rfa | 2026-06-22 | 2026-07-23 | 24 | handler_assign | confirm_note:stored_full | N | N
73579 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdividedSupply.rfa | 2026-06-22 | 2026-06-25 | 4 | handler_assign | status_resolved | N | N
73578 | 430_AT_GrilleWeatherProtection_Wall_Rectangular_WGALHeightSubdividedExhaust.rfa | 2026-06-22 | 2026-07-16 | 19 | handler_assign | confirm_note:stored_full | N | N
73577 | 430_AT_Grilles_Wall_Rectangular_TRS_Supply.rfa | 2026-06-22 | 2026-09-21 | 66 | handler_assign | confirm_note:stored_full | N | N
73576 | 430_AT_Grilles_Wall_Rectangular_TRS_Return.rfa | 2026-06-22 | 2026-09-23 | 68 | handler_assign | confirm_note:stored_full | N | N
73575 | 430_AT_Grilles_Wall_Rectangular_TRS_FreshAirIntake.rfa | 2026-06-22 | 2026-07-09 | 14 | handler_assign | confirm_note:stored_full | N | N
73574 | 430_AT_ExternalRainProtectionGrill_Wall_Round.rfa | 2026-06-25 | 2026-07-22 | 20 | handler_assign | confirm_note:stored_full | N | N
73573 | 430_AT_EggCrateAirGrill_HorizontalCeiling_Rectangular_Return.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73572 | 430_AT_DoubleSlot_CeilingHorizontal_1ConnectionSymmetrical_Withbox.rfa | 2026-06-25 | 2026-09-11 | 57 | handler_assign | confirm_note:stored_full | N | N
73571 | 430_AT_DisplacementFlowDiffusers_Wall_QLV_Supply.rfa | 2026-06-25 | 2026-07-03 | 7 | handler_assign | status_resolved | N | N
73570 | 430_AT_DisplacementFlowDiffusers_Wall_QLF_Supply.rfa | 2026-06-25 | 2026-07-03 | 7 | handler_assign | status_resolved | N | N
73569 | 430_AT_DiscValvesSTVZ_Supply.rfa | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full | N | N
73568 | 430_AT_DiscValvesSTVA_Return.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | N | N
73567 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Supply.rfa | 2026-06-25 | 2026-07-15 | 15 | handler_assign | confirm_note:stored_full | N | N
73566 | 430_AT_Diffuser_FloorHorizontal_Rectangular_AH_Return.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73565 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Supply.rfa | 2026-06-25 | 2026-07-24 | 22 | handler_assign | confirm_note:stored_full | N | N
73564 | 430_AT_Diffuser_Ceiling_Round_AIRNAMIC_Exhaust.rfa | 2026-06-25 | 2026-07-31 | 27 | handler_assign | confirm_note:stored_full | N | N
73563 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Supply.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | N | N
73562 | 430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Return.rfa | 2026-06-25 | 2026-08-04 | 29 | handler_assign | confirm_note:stored_full | N | N
73561 | 410_PA_BallValve_Flanged | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | N | N
73559 | 410_PA_BackflowPreventerValve_Threaded | 2026-07-03 | 2026-07-30 | 20 | handler_assign | confirm_note:stored_full | N | N
73558 | 410_PA_AutomaticHygieneFlushingStationHS10_Geberit | 2026-07-03 | 2026-08-04 | 23 | handler_assign | confirm_note:stored_full | N | N
73557 | 410_PA_AutomaticCirculationRegulatingValve | 2026-07-03 | 2026-07-09 | 5 | handler_assign | status_resolved | N | N
73556 | 410_PA_AutomaticBackwashFilter_Flanged | 2026-07-03 | 2026-07-10 | 6 | handler_assign | status_resolved | N | N
73555 | 410_PA_AngleValve_Threaded_WithRegulatingFunction | 2026-07-03 | 2026-08-20 | 35 | handler_assign | confirm_note:stored_full | N | N
73554 | 410_PA_AngleSeatPistonValve_Threaded | 2026-07-02 | 2026-07-08 | 5 | handler_assign | confirm_note:stored_full | N | N
73553 | 420_PA_BallValve_Thread_LeverStandard | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full | N | N
73552 | 420_PA_BallValve_Thread_WheelStandard | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full | N | N
73551 | 420_PA_BallValve_Threaded | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full | N | N
73550 | 420_PA_BasketStrainerValve_Flanged_Standard | 2026-06-19 | 2026-07-10 | 16 | handler_assign | confirm_note:stored_full | N | N
73549 | 420_PA_BasketStrainerValve_Thread_Standard | 2026-06-19 | 2026-06-24 | 4 | handler_assign | status_resolved | N | N
73548 | 420_PA_ButterflyValveHandwheel_Flanged | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | N | N
73547 | 420_PA_ButterflyValve_Flanged_GearStandard | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | N | N
73546 | 420_PA_ButterflyValve_Flanged_LeverStandard | 2026-06-19 | 2026-08-05 | 34 | handler_assign | confirm_note:stored_full | N | N
73545 | 420_PA_ButterflyValve_Thread_GearStandard | 2026-06-19 | 2026-10-01 | 75 | handler_assign | confirm_note:stored_full | N | N
73544 | 420_PA_ButterflyValve_Thread_LeverStandard | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full | N | N
73543 | 420_PA_ButterflyvalveMotor_Flanged | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full | N | N
73542 | 420_PA_CapValve_Thread | 2026-06-19 | 2026-07-10 | 16 | handler_assign | confirm_note:stored_full | N | N
73541 | 420_PA_CheckValveWithThermometer_Thread | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | N | N
73540 | 420_PA_DifferentialPressureControlValve_Thread | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | N | N
73539 | 420_PA_DifferentialPressureGauge_Standard | 2026-06-19 | 2026-09-04 | 56 | handler_assign | confirm_note:stored_full | N | N
73538 | 420_PA_DifferentialPressureSensor | 2026-06-19 | 2026-06-25 | 5 | handler_assign | status_closed | N | N
73537 | 420_PA_DifferentialPressureSensor | 2026-06-19 | 2026-09-11 | 61 | handler_assign | confirm_note:stored_full | N | N
73536 | 420_PA_DifferentialPressureSensor_Standard | 2026-06-19 | 2026-08-14 | 41 | handler_assign | confirm_note:stored_full | N | N
73535 | 420_PA_DiscCheckValve_Flanged_Standard | 2026-06-19 | 2026-09-07 | 57 | handler_assign | confirm_note:stored_full | N | N
73534 | 420_PA_DrainValve_Thread_Standard | 2026-06-19 | 2026-09-28 | 72 | handler_assign | confirm_note:stored_full | N | N
73533 | 420_PA_DrainValve_Threaded | 2026-06-19 | 2026-06-25 | 5 | handler_assign | status_resolved | N | N
73532 | 420_PA_ExpansionJoint_Flanged | 2026-06-19 | 2026-09-03 | 55 | handler_assign | confirm_note:stored_full | N | N
73531 | 420_PA_ExpansionJoint_Threaded | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full | N | N
73530 | 420_PA_ExpansionJoint_Weld | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | N | N
73529 | 420_PA_FillAndDrainBallValve_Threaded | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | N | N
73528 | 420_PA_FilterValve_Flanged | 2026-06-19 | 2026-09-21 | 67 | handler_assign | confirm_note:stored_full | N | N
73527 | 420_PA_FilterValve_Thread | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full | N | N
73526 | 420_PA_FlexibleConnection_Flanged_Standard | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | N | N
73525 | 420_PA_ManifoldConnection_Thread | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | N | N
73524 | 420_PA_PICVValve_Thread | 2026-06-19 | 2026-08-07 | 36 | handler_assign | confirm_note:stored_full | N | N
73523 | 410_PA_AngleSeatPistonValve_Flanged | 2026-07-02 | 2026-08-20 | 36 | handler_assign | confirm_note:stored_full | N | N
73522 | 420_PA_PIQCVValve_Thread | 2026-06-25 | 2026-07-08 | 10 | handler_assign | status_resolved | N | N
73521 | 420_PA_ShutOffValveWithSafetyFunction_Flanged | 2026-06-25 | 2026-07-16 | 16 | handler_assign | confirm_note:stored_full | N | N
73520 | 420_PA_ShutoffValve_Motorized | 2026-06-25 | 2026-07-01 | 5 | handler_assign | status_resolved | N | N
73519 | 410_PA_AngleSafetyValve_Threaded | 2026-07-02 | 2026-08-03 | 23 | handler_assign | confirm_note:stored_full | N | N
73518 | 410_PA_AirReleaseValve_Threaded | 2026-07-02 | 2026-08-20 | 36 | handler_assign | confirm_note:stored_full | N | N
73517 | 420_PA_SixWayMotorisedControlValve_Threaded | 2026-06-25 | 2026-08-13 | 36 | handler_assign | confirm_note:stored_full | N | N
73516 | 420_PA_SmartForEnergyManagement_Flanged | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full | N | N
73515 | 420_PA_SmartForEnergyManagement_Thread | 2026-06-25 | 2026-09-07 | 53 | handler_assign | confirm_note:stored_full | N | N
73514 | 420_PA_TemperatureRegulatorValve_SelfOperated | 2026-06-25 | 2026-08-05 | 30 | handler_assign | confirm_note:stored_full | N | N
73513 | 420_PA_ThreeWayMotorisedControlValve_Flanged | 2026-06-25 | 2026-07-27 | 23 | handler_assign | confirm_note:stored_full | N | N
73512 | 420_PA_ThreeWayMotorisedControlValve_Thread | 2026-06-25 | 2026-06-30 | 4 | handler_assign | status_resolved | N | N
73511 | 420_PA_WaterMeter_Threaded_Standard | 2026-07-08 | 2026-08-17 | 29 | handler_assign | confirm_note:stored_full | N | N
73510 | 410_PA_AdapterAndExpansionPiece_Flanged | 2026-06-24 | 2026-06-30 | 5 | handler_assign | status_resolved | N | N
73509 | 420_PF_CO_rReducer_Soldered | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
73508 | 434_ME_Pump_Circulator_YonosGIGA20D | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full | N | N
73507 | 434_ME_Pump_SingleStageGlandedBM | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | N | N
73506 | 434_ME_Pump_SingleStageLowPressureBAC | 2026-06-19 | 2026-07-15 | 19 | handler_assign | confirm_note:stored_full | N | N
73505 | 434_ME_Pump_WaterSupplyAtmosGIGA&N | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | N | N
73504 | 434_ME_Pump_WaterSupplyAtmosI | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | N | N
73503 | 434_ME_Pump_WaterSupplyAtmosTERA&SCH | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | N | N
73502 | 434_ME_Pump_WaterSupplyCronoBlocBLE | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full | N | N
73501 | 434_ME_Pump_WaterSupplyCronoNorm&NLG | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full | N | N
73500 | 434_ME_Pump_WaterSupplySCP | 2026-06-19 | 2026-08-17 | 42 | handler_assign | confirm_note:stored_full | N | N
73499 | 434_ME_Pump_WaterSupplyVeroLineIPE | 2026-06-19 | 2026-08-27 | 50 | handler_assign | confirm_note:stored_full | N | N
73498 | 434_ME_Pump_WaterSupplyVeroTwinDPE | 2026-06-19 | 2026-08-17 | 42 | handler_assign | confirm_note:stored_full | N | N
73497 | 434_ME_Pump_WaterSupplyYonosGIGA&N | 2026-06-19 | 2026-08-27 | 50 | handler_assign | confirm_note:stored_full | N | N
73495 | 434_ME_VariableSpeedWaterCooledLiquidChiller_SingleCompressor30XW&V | 2026-06-19 | 2026-09-25 | 71 | handler_assign | confirm_note:stored_full | N | N
73494 | 434_ME_WateCooledCondenserlessLiquidChillers_WithHydraulicModule_30RW | 2026-06-19 | 2026-08-28 | 51 | handler_assign | confirm_note:stored_full | N | N
73493 | 434_ME_WaterCooledCondenserlessLiquidChillers_30WG | 2026-06-19 | 2026-06-23 | 3 | handler_assign | status_resolved | N | N
73492 | 434_ME_WaterCooledCondenserlessLiquidchillers_30WGA | 2026-06-19 | 2026-06-23 | 3 | handler_assign | status_resolved | N | N
73491 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC4Pipes | 2026-06-19 | 2026-07-30 | 30 | handler_assign | confirm_note:stored_full | N | N
73490 | 434_ME_WatercooledCondenserlessliquidchillers_30RW_WithoutHydraulicModule | 2026-06-19 | 2026-06-30 | 8 | handler_assign | status_resolved | N | N
73489 | 434_PF_CO_e90Elbow_ThreadAndMeplaFix | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | N | N
73488 | 434_PF_CO_eAdaptorBend_MapressAndFemaleThread_WithNut | 2026-06-19 | 2026-08-11 | 38 | handler_assign | confirm_note:stored_full | N | N
73487 | 434_PF_CO_eAdaptorBend_MapressAndMeplaFix | 2026-06-19 | 2026-07-13 | 17 | handler_assign | confirm_note:stored_full | N | N
73486 | 434_PF_CO_eDouble90ElbowMultiPort_Mapress | 2026-06-19 | 2026-07-22 | 24 | handler_assign | confirm_note:stored_full | N | N
73485 | 434_PF_CO_eElbow90Deg_MaleThread_MeplaFixAndPremounted | 2026-06-19 | 2026-07-29 | 29 | handler_assign | confirm_note:stored_full | N | N
73484 | 434_PF_CO_eElbowDouble90Deg_MaleThread_MeplaFixAndPremounted | 2026-06-19 | 2026-07-29 | 29 | handler_assign | confirm_note:stored_full | N | N
73483 | 434_PF_CO_fFlange_Mapress | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | N | N
73482 | 410_PF_CS_tTee_Welded | 2026-06-19 | 2026-09-16 | 64 | handler_assign | confirm_note:stored_full | N | N
73481 | 410_PF_CS_eRadiusReturnBends_Welded | 2026-06-19 | 2026-08-31 | 52 | handler_assign | confirm_note:stored_full | N | N
73468 | 457_EF_VideoModul.rfa | 2026-06-18 | 2026-08-07 | 37 | handler_assign | confirm_note:stored_full | N | N
73467 | 440_EF_WindowMotor_WallMounted.rfa | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full | N | N
73466 | 440_EF_TripleSocketOutlet_Wall.rfa | 2026-06-18 | 2026-08-12 | 40 | handler_assign | confirm_note:stored_full | N | N
73465 | 440_EF_TripleSocketOutlet_Floor.rfa | 2026-06-18 | 2026-08-25 | 49 | handler_assign | confirm_note:stored_full | N | N
73464 | 440_EF_TripleSocketOutlet_Ceiling.rfa | 2026-06-18 | 2026-08-07 | 37 | handler_assign | confirm_note:stored_full | N | N
73463 | 440_EF_TouchPanelRoomOperating_WallMounted.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | N | N
73462 | 440_EF_Thermosat.rfa | 2026-06-18 | 2026-08-26 | 50 | handler_assign | confirm_note:stored_full | N | N
73461 | 451_EF_TelephoneOutlet_Single.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | N | N
73460 | 440_EF_Switch_3Gang.rfa | 2026-06-18 | 2026-08-20 | 46 | handler_assign | confirm_note:stored_full | N | N
73459 | 440_EF_Switch_2Gang2Way.rfa | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full | N | N
73458 | 440_EF_Switch_2Gang.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | N | N
73457 | 440_EF_Switch_1Gang.rfa | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full | N | N
73456 | 440_EF_SwitchPushButton_FlushMounted.rfa | 2026-06-18 | 2026-08-20 | 46 | handler_assign | confirm_note:stored_full | N | N
73455 | 444_EF_SwitchableSocketOutlet_WallSurface.rfa | 2026-06-18 | 2026-08-21 | 47 | handler_assign | confirm_note:stored_full | N | N
73454 | 440_EF_SwitchableSocketOutlet_Floor.rfa | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full | N | N
73453 | 440_EF_SwitchableSocketOutlet_Ceiling.rfa | 2026-06-18 | 2026-08-14 | 42 | handler_assign | confirm_note:stored_full | N | N
73452 | 440_EF_SocketOutlet_Wall_Combination.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | N | N
73451 | 440_EF_SocketOutlet_Wall_4Gangs.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | N | N
73450 | 440_EF_SocketOutlet_Wall_3Phase.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | N | N
73449 | 440_EF_SocketOutlet_WallMounted_WaterProof.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | N | N
73448 | 440_EF_SocketOutlet_Wall.rfa | 2026-06-18 | 2026-08-13 | 41 | handler_assign | confirm_note:stored_full | N | N
73447 | 444_EF_SocketOutlet_VerticalWallSurface_4Gangs.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | N | N
73446 | 444_EF_USBSocketOutlet_WallFlush.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | N | N
73445 | 444_EF_SocketOutlet_Rec_Floor.rfa | 2026-06-18 | 2026-08-27 | 51 | handler_assign | confirm_note:stored_full | N | N
73444 | 440_EF_SocketOutlet_Horizontal_4Gangs_Wall.rfa | 2026-06-18 | 2026-08-11 | 39 | handler_assign | confirm_note:stored_full | N | N
73443 | 440_EF_SocketOutlet_FloorRecessed_Round.rfa | 2026-06-18 | 2026-08-11 | 39 | handler_assign | confirm_note:stored_full | N | N
73442 | 440_EF_SocketOutletRound_Floor.rfa | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full | N | N
73441 | 440_EF_SocketOutletCombination_Ceiling.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | N | N
73440 | 440_EF_SocketDistributionBox_Wall.rfa | 2026-06-18 | 2026-09-04 | 57 | handler_assign | confirm_note:stored_full | N | N
73439 | 440_EF_SocketDistributionBox_Ceiling.rfa | 2026-06-18 | 2026-09-23 | 70 | handler_assign | confirm_note:stored_full | N | N
73438 | 440_EF_ShaverSocketOutlet_Wall.rfa | 2026-06-18 | 2026-08-12 | 40 | handler_assign | confirm_note:stored_full | N | N
73437 | 440_EF_RotaryDimmer.rfa | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full | N | N
73436 | 440_EF_RoomSignallight.rfa | 2026-06-18 | 2026-08-19 | 45 | handler_assign | confirm_note:stored_full | N | N
73435 | 440_EF_Raumluftfühler.rfa | 2026-06-18 | 2026-08-17 | 43 | handler_assign | confirm_note:stored_full | N | N
73375 | 440_EF_PushButtonSensorKNX_4gang.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | N | N
73374 | 440_EF_PresenceDetector_Wall.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | N | N
73373 | 440_EF_PresenceDetector_Ceiling.rfa | 2026-06-15 | 2026-08-19 | 48 | handler_assign | confirm_note:stored_full | N | N
73372 | 440_EF_PanelBoard.rfa | 2026-06-15 | 2026-09-04 | 60 | handler_assign | confirm_note:stored_full | N | N
73371 | 440_EF_MotionDetector360_CeilingSurface.rfa | 2026-06-15 | 2026-06-29 | 11 | handler_assign | status_closed | N | N
73370 | 440_EF_MainEquipotentialBondingBar.rfa | 2026-06-15 | 2026-08-07 | 40 | handler_assign | confirm_note:stored_full | N | N
73369 | 440_EF_KNX_PushButtonSensor_2gang.rfa | 2026-06-15 | 2026-09-18 | 70 | handler_assign | confirm_note:stored_full | N | N
73368 | 440_EF_KNXPresenceDetection_Ceiling.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | N | N
73367 | 440_EF_KeySwitch_WallRecessed.rfa | 2026-06-15 | 2026-08-17 | 46 | handler_assign | confirm_note:stored_full | N | N
73366 | 440_EF_BasementVentilationControl.rfa | 2026-06-15 | 2026-08-13 | 44 | handler_assign | confirm_note:stored_full | N | N
73365 | 440_EF_JunctionBox_Floor_3Pole.rfa | 2026-06-15 | 2026-09-04 | 60 | handler_assign | confirm_note:stored_full | N | N
73364 | 440_EF_JunctionBox_Ceiling_3Pole.rfa | 2026-06-15 | 2026-09-28 | 76 | handler_assign | confirm_note:stored_full | N | N
73363 | 440_EF_Isolator_SinglePhase.rfa | 2026-06-15 | 2026-08-11 | 42 | handler_assign | confirm_note:stored_full | N | N
73362 | 440_EF_Isolator_3Phases.rfa | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full | N | N
73361 | 444_EF_InstallationTrunking.rfa | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full | N | N
73360 | 481_EF_Hygrostat.rfa | 2026-06-15 | 2026-08-27 | 54 | handler_assign | confirm_note:stored_full | N | N
73359 | 444_EF_GooseneckBushing_NoSystem.rfa | 2026-06-15 | 2026-08-28 | 55 | handler_assign | confirm_note:stored_full | N | N
73357 | 440_EF_FixedConnection_400V.rfa | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full | N | N
73356 | 440_EF_FixedConnection_1Pole.rfa | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full | N | N
73355 | 446_EF_EquipotentialBondingBusbars_WallMounted.rfa | 2026-06-15 | 2026-08-21 | 50 | handler_assign | confirm_note:stored_full | N | N
73354 | 440_EF_Equipotentialbondingbar.rfa | 2026-06-15 | 2026-06-17 | 3 | handler_assign | status_resolved | N | N
73353 | 440_EF_EnergyBollard.rfa | 2026-06-15 | 2026-08-18 | 47 | handler_assign | confirm_note:stored_full | N | N
73352 | 440_EF_EmergencyStopPushButtons.rfa | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full | N | N
73351 | 446_EF_EarthTestBox.rfa | 2026-06-15 | 2026-08-19 | 48 | handler_assign | confirm_note:stored_full | N | N
73350 | 440_EF_EarthRod.rfa | 2026-06-15 | 2026-08-31 | 56 | handler_assign | confirm_note:stored_full | N | N
73349 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-07-03 | 15 | handler_assign | confirm_note:stored_full | N | N
73348 | 430_AT_Diffuser_CeilingVertical_2ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-08-13 | 44 | handler_assign | confirm_note:stored_full | N | N
73347 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-07-09 | 19 | handler_assign | confirm_note:stored_full | N | N
73346 | 430_AT_Diffuser_CeilingVertical_1ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-07-09 | 19 | handler_assign | confirm_note:stored_full | N | N
73345 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-09-18 | 70 | handler_assign | confirm_note:stored_full | N | N
73343 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-09-23 | 73 | handler_assign | confirm_note:stored_full | N | N
73342 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Supply.rfa | 2026-06-15 | 2026-08-03 | 36 | handler_assign | confirm_note:stored_full | N | N
73341 | 430_AT_Diffuser_CeilingHorizontal_2ConnectionAsymmetrical_Return.rfa | 2026-06-15 | 2026-08-04 | 37 | handler_assign | confirm_note:stored_full | N | N
73340 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Return.rfa | 2026-06-15 | 2026-07-29 | 33 | handler_assign | confirm_note:stored_full | N | N
73339 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionSymmetrical_Supply.rfa | 2026-06-15 | 2026-09-28 | 76 | handler_assign | confirm_note:stored_full | N | N
73338 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Supply.rfa | 2026-06-15 | 2026-07-10 | 20 | handler_assign | confirm_note:stored_full | N | N
73337 | 430_AT_Diffuser_CeilingHorizontal_1ConnectionAsymmetrical_Return.rfa | 2026-06-15 | 2026-07-29 | 33 | handler_assign | confirm_note:stored_full | N | N
73336 | 430_AT_Diffusers_Wall_CHS_Supply.rfa | 2026-06-15 | 2026-07-10 | 20 | handler_assign | confirm_note:stored_full | N | N
73335 | 430_AT_Diffusers_Wall_CHM_Supply.rfa | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full | N | N
73334 | 430_AT_Diffusers_Floor_FBK_Supply.rfa | 2026-06-15 | 2026-08-24 | 51 | handler_assign | confirm_note:stored_full | N | N
73333 | 430_AT_Diffusers_Floor_FBK_Return.rfa | 2026-06-15 | 2026-08-10 | 41 | handler_assign | confirm_note:stored_full | N | N
73332 | 430_AT_DeflectorHood_Roof_Round_FreshAirIntake.rfa | 2026-06-15 | 2026-06-19 | 5 | handler_assign | status_resolved | N | N
73331 | 430_AT_DeflectorHood_Roof_Round_Exhaust.rfa | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full | N | N
73330 | 430_AT_DeflectorHood_Roof_Rectangular_FreshAirIntake.rfa | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full | N | N
73329 | 430_AT_CircularDiscValves_ZLVS_Supply.rfa | 2026-06-15 | 2026-07-28 | 32 | handler_assign | confirm_note:stored_full | N | N
73314 | 434_PF_CO_mBridgeBend_Mapress | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full | N | N
73313 | 434_PF_CO_mDouble90Elbow_Mapress_PreMounted | 2026-06-12 | 2026-06-19 | 6 | handler_assign | status_resolved | N | N
73312 | 434_PF_CO_mElbowOffset_MapressAndFemaleThread | 2026-06-12 | 2026-07-22 | 29 | handler_assign | confirm_note:stored_full | N | N
73311 | 434_PF_CO_mElbow_MapressAndFemaleThread | 2026-06-12 | 2026-09-14 | 67 | handler_assign | confirm_note:stored_full | N | N
73310 | 434_PF_CO_mTeeCrossing_Mapress | 2026-06-12 | 2026-09-07 | 62 | handler_assign | confirm_note:stored_full | N | N
73309 | 434_PF_CO_mTeeInletReturnUnion_Mapress | 2026-06-12 | 2026-09-11 | 66 | handler_assign | confirm_note:stored_full | N | N
73308 | 434_PF_CO_mTeeInletReturn_Mapress | 2026-06-12 | 2026-07-28 | 33 | handler_assign | confirm_note:stored_full | N | N
73307 | 434_PF_CO_mTeeReturn_Mapress | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full | N | N
73306 | 434_PF_CO_rReducerAdaptor_MaleThread_MeplaFix | 2026-06-12 | 2026-07-28 | 33 | handler_assign | confirm_note:stored_full | N | N
73305 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThreadFKMBlue_WithNut | 2026-06-19 | 2026-07-16 | 20 | handler_assign | confirm_note:stored_full | N | N
73304 | 434_PF_CO_rReducerAdaptor_MapressAndFemaleThread_WithNut | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | N | N
73303 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThreadFKMBlue_WithNut | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | N | N
73302 | 434_PF_CO_rReducerAdaptor_MapressAndMaleThread_WithNut | 2026-06-19 | 2026-08-04 | 33 | handler_assign | confirm_note:stored_full | N | N
73301 | 434_PF_CO_rReducerAdaptor_MapressAndThread | 2026-06-19 | 2026-07-14 | 18 | handler_assign | confirm_note:stored_full | N | N
73300 | 434_PF_CO_rReducerAdaptor_MapressAndThreadFKMBlue | 2026-06-19 | 2026-08-20 | 45 | handler_assign | confirm_note:stored_full | N | N
73299 | 434_PF_CO_rReducerAdaptor_MapressAndThreadGas | 2026-06-19 | 2026-07-17 | 21 | handler_assign | confirm_note:stored_full | N | N
73298 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFix | 2026-06-19 | 2026-07-17 | 21 | handler_assign | confirm_note:stored_full | N | N
73297 | 434_PF_CO_rReducerAdaptor_PlainEndAndThread | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | N | N
73296 | 434_PF_CO_rReducerAdaptor_PlainEndAndThreadGas | 2026-06-19 | 2026-07-27 | 27 | handler_assign | confirm_note:stored_full | N | N
73295 | 434_PF_CO_uAdaptorUnion_MaleThreadAndMeplaFix | 2026-07-08 | 2026-08-05 | 21 | handler_assign | confirm_note:stored_full | N | N
73294 | 434_PF_CO_uAdaptorUnion_MaleThread_MeplaFix | 2026-07-09 | 2026-07-29 | 15 | handler_assign | confirm_note:stored_full | N | N
73293 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThread_WithNut | 2026-07-09 | 2026-08-06 | 21 | handler_assign | confirm_note:stored_full | N | N
73292 | 434_PF_CO_uAdaptorUnion_MapressAndMaleThreadFKMBlue_WithNut | 2026-07-13 | 2026-08-10 | 21 | handler_assign | status_resolved | N | N
73291 | 434_PF_CO_uAdaptorUnion_MapressAndNutGas | 2026-07-13 | 2026-08-10 | 21 | handler_assign | status_resolved | N | N
73290 | 434_PF_CO_uAdaptorUnion_PlainEndAndClampingRing | 2026-07-13 | 2026-09-07 | 41 | handler_assign | confirm_note:stored_full | N | N
73289 | 434_PF_CO_uAdaptorUnion_PlainEndAndThread | 2026-07-13 | 2026-09-21 | 51 | handler_assign | confirm_note:stored_full | N | N
73288 | 434_PF_CO_uTap_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
73287 | 434_PF_CO_xOffsetCross_Mapress | 2026-07-13 | 2026-09-14 | 46 | handler_assign | confirm_note:stored_full | N | N
73243 | 430_AT_DeflectorHood_Roof_Rectangular_Exhaust Air.rfa | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full | N | N
73241 | 430_AT_CrossflowCFE_TPP_NoSystem.rfa | 2026-06-12 | 2026-07-08 | 19 | handler_assign | confirm_note:stored_full | N | N
73221 | 440_EF_EarthPit.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | N | N
73209 | 446_EF_Earthing_WallSurface.rfa | 2026-06-11 | 2026-08-11 | 44 | handler_assign | confirm_note:stored_full | N | N
73208 | 446_EF_EarthingFixedPoint_WallSurface.rfa | 2026-06-11 | 2026-09-16 | 70 | handler_assign | confirm_note:stored_full | N | N
73207 | 440_EF_DoubleSocketOutlet_Wall.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | N | N
73206 | 440_EF_DoubleSocketOutlet_Floor.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | N | N
73205 | 440_EF_DoubleSocketOutlet_Ceiling.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | N | N
73204 | 440_EF_DoubleSocketOutletVertical_WallFlush.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | N | N
73203 | 440_EF_DoubleSocketOutletVertical_Wall.rfa | 2026-06-11 | 2026-08-27 | 56 | handler_assign | confirm_note:stored_full | N | N
73202 | 440_EF_DoubleSocketOutletUSBTypeAC_WallSurface.rfa | 2026-06-11 | 2026-08-11 | 44 | handler_assign | confirm_note:stored_full | N | N
73201 | 440_EF_DoubleSocketOutletHorizontal_Wall.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | N | N
73200 | 440_EF_DoorbellPushButton_WallMounted.rfa | 2026-06-11 | 2026-08-31 | 58 | handler_assign | confirm_note:stored_full | N | N
73193 | 440_EF_DimmerSwitch_WallRecessed.rfa | 2026-06-10 | 2026-08-31 | 59 | handler_assign | confirm_note:stored_full | N | N
73192 | 440_EF_DaylightSensor_Wall.rfa | 2026-06-10 | 2026-08-31 | 59 | handler_assign | confirm_note:stored_full | N | N
73191 | 440_EF_DaylightSensor_Ceiling.rfa | 2026-06-10 | 2026-09-28 | 79 | handler_assign | confirm_note:stored_full | N | N
73190 | 440_EF_DataConnectionSocket_Wall.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | N | N
73189 | 440_EF_DataConnectionSocket_Floor.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | N | N
73188 | 457_EF_DataConnectionSocket_CeilingMounted_WaterProof.rfa | 2026-06-10 | 2026-09-16 | 71 | handler_assign | confirm_note:stored_full | N | N
73187 | 440_EF_DataConnectionSocket_Ceiling.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | N | N
73186 | 440_EF_DataConnectionSocket_Audio_Out_HDMI.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | N | N
73185 | 440_EF_DALIPresenceDetector_CeilingSurface.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | N | N
73184 | 440_EF_DALIPresenceDetectorCombineLightingSensor_CeilingSurface.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | N | N
73183 | 440_EF_ConnectionBrackets.rfa | 2026-06-10 | 2026-08-24 | 54 | handler_assign | confirm_note:stored_full | N | N
73182 | 440_EF_CableConnection_PluginSystem.rfa | 2026-06-10 | 2026-08-13 | 47 | handler_assign | confirm_note:stored_full | N | N
73174 | 430_AT_CircularDiscValves_LVS_Return.rfa | 2026-06-10 | 2026-08-13 | 47 | handler_assign | confirm_note:stored_full | N | N
73173 | 430_AT_AirDiffuser_Standard.rfa | 2026-06-10 | 2026-07-30 | 37 | handler_assign | confirm_note:stored_full | N | N
73168 | 481_EF_OutdoorAirTemperatureSensor.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | N | N
73167 | 440_EF_AL_TopFeedingUnitForTransformer_Busway.rfa | 2026-06-09 | 2026-08-11 | 46 | handler_assign | confirm_note:stored_full | N | N
73166 | 440_EF_AL_TakeOffUnitWithFuseSwitch_Busway.rfa | 2026-06-09 | 2026-08-24 | 55 | handler_assign | confirm_note:stored_full | N | N
73165 | 440_EF_AL_SideFeedingUnitForTransformer_Busway.rfa | 2026-06-09 | 2026-08-24 | 55 | handler_assign | confirm_note:stored_full | N | N
73164 | 446_EF_AirTerminationRods_FloorStand.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | N | N
73163 | 446_EF_AirTerminationRodsForMetalRoofs.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | N | N
73162 | 440_EF_360DegreeRadiusMotionDetector_CeilingMounted.rfa | 2026-06-09 | 2026-08-27 | 58 | handler_assign | confirm_note:stored_full | N | N
73147 | 434_ME_Pump_Circulator_VeroTwinDPL_DN80 | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | N | N
73146 | 420_PA_FlexibleConnection_Thread_Standard | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full | N | N
73145 | 420_PA_FlowSensor | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full | N | N
73144 | 420_PA_FlowSensor_Flanged_Standard | 2026-06-08 | 2026-08-10 | 46 | handler_assign | confirm_note:stored_full | N | N
73143 | 420_PA_FlowSensor_Thread_Standard | 2026-06-08 | 2026-09-10 | 69 | handler_assign | confirm_note:stored_full | N | N
73142 | 420_PA_GateValve_Flanged | 2026-06-08 | 2026-06-18 | 9 | handler_assign | status_resolved | N | N
73141 | 420_PA_GateValve_Flanged_Standard | 2026-06-08 | 2026-09-14 | 71 | handler_assign | confirm_note:stored_full | N | N
73140 | 420_PA_GateValve_Thread | 2026-06-08 | 2026-09-08 | 67 | handler_assign | confirm_note:stored_full | N | N
73139 | 420_PA_GateValve_Thread_Standard | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full | N | N
73138 | 420_PA_GlobeValve_Flanged | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full | N | N
73137 | 420_PA_GlobeValve_Flanged | 2026-06-08 | 2026-06-15 | 6 | handler_assign | confirm_note:confirm_other | N | N
73136 | 420_PA_GlobeValve_Flanged_Standard | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full | N | N
73135 | 420_PA_GlobeValve_Thread | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full | N | N
73134 | 420_PA_GlobeValve_Thread_Standard | 2026-06-08 | 2026-09-25 | 80 | handler_assign | confirm_note:stored_full | N | N
73133 | 420_PA_HeatMeter_Flanged | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full | N | N
73132 | 420_PA_HeatMeter_Flanged_Standard | 2026-06-08 | 2026-06-19 | 10 | handler_assign | status_resolved | N | N
73131 | 420_PA_HeatMeter_Thread_Standard | 2026-06-08 | 2026-06-19 | 10 | handler_assign | status_resolved | N | N
73130 | 420_PA_HeatingBallValve_Thread | 2026-06-08 | 2026-09-03 | 64 | handler_assign | confirm_note:stored_full | N | N
73129 | 420_PA_LiftCheckValve_Flanged_Standard | 2026-06-08 | 2026-09-21 | 76 | handler_assign | confirm_note:stored_full | N | N
73128 | 420_PA_LiftCheckValve_Thread_Standard | 2026-06-08 | 2026-09-11 | 70 | handler_assign | confirm_note:stored_full | N | N
73127 | 420_PA_MotorizedBallValve_Flanged_Standard | 2026-06-08 | 2026-08-25 | 57 | handler_assign | confirm_note:stored_full | N | N
73126 | 420_PA_MotorizedBallValve_Thread_Standard | 2026-06-08 | 2026-10-01 | 84 | handler_assign | confirm_note:stored_full | N | N
73125 | 420_PA_MotorizedButterflyValve_Flanged_Standard | 2026-06-08 | 2026-07-17 | 30 | handler_assign | confirm_note:stored_full | N | N
73124 | 420_PA_MotorizedGateValve_Flanged_Standard | 2026-06-08 | 2026-07-29 | 38 | handler_assign | confirm_note:stored_full | N | N
73123 | 420_PA_MotorizedGateValve_Thread_Standard | 2026-06-08 | 2026-07-31 | 40 | handler_assign | confirm_note:stored_full | N | N
73122 | 420_PA_MotorizedGlobeValve_Flanged_Standard | 2026-06-08 | 2026-07-31 | 40 | handler_assign | confirm_note:stored_full | N | N
73121 | 420_PA_MotorizedGlobeValve_Thread_Standard | 2026-06-08 | 2026-07-24 | 35 | handler_assign | confirm_note:stored_full | N | N
73120 | 420_PA_MotorizedThreeWayValve_Flanged_Standard | 2026-06-08 | 2026-09-16 | 73 | handler_assign | confirm_note:stored_full | N | N
73119 | 420_PA_MotorizedThreeWayvalve_Thread_Standard | 2026-06-12 | 2026-09-21 | 72 | handler_assign | confirm_note:stored_full | N | N
73118 | 420_PA_NonReturnFlap_Flanged | 2026-06-12 | 2026-06-19 | 6 | handler_assign | status_resolved | N | N
73117 | 420_PA_PICCV2WayValve_Thread | 2026-06-12 | 2026-07-24 | 31 | handler_assign | confirm_note:stored_full | N | N
73116 | 420_PA_PICCV3WayValve_Thread | 2026-06-12 | 2026-07-24 | 31 | handler_assign | confirm_note:stored_full | N | N
73115 | 420_PA_PIQCV6WayValve_Thread | 2026-06-12 | 2026-06-17 | 4 | handler_assign | status_resolved | N | N
73114 | 420_PA_PneumaticControlValve_Flanged | 2026-06-12 | 2026-06-18 | 5 | handler_assign | status_resolved | N | N
73113 | 420_PA_PneumaticGlobeControlValve_Flanged | 2026-06-12 | 2026-09-28 | 77 | handler_assign | confirm_note:stored_full | N | N
73112 | 420_PA_PneumaticGlobeControlValve_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
73111 | 420_PA_PressureGauge | 2026-07-13 | 2026-09-07 | 41 | handler_assign | confirm_note:stored_full | N | N
73110 | 420_PA_PressureGauge_2Connection | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
73109 | 420_PA_PressureGauge_Standard | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
73108 | 420_PA_PressureIndependentControlValveCompact_Threaded | 2026-07-13 | 2026-08-27 | 34 | handler_assign | confirm_note:stored_full | N | N
73107 | 420_PA_PressureIndependentControlValve_Flanged | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
73106 | 420_PA_PressureIndependentControlValve_Threaded | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
73105 | 420_PA_PressureReducingValveWithGauge_Thread | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
73104 | 434_ME_Pump_Circulator_YonosGIGA20_I | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full | N | N
73103 | 434_ME_Pump_SingleStageLowPressureBAC65 | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full | N | N
73102 | 434_ME_SplitCasePump_Standard | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full | N | N
73101 | 434_ME_TwoOutletPump_Flanged | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full | N | N
73100 | 434_ME_VRVInDoorUnit_CeilingMouted_FXFA&A | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full | N | N
73099 | 434_ME_VRVInDoorUnit_CeilingMouted_FXZA&A | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full | N | N
73098 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXHA&A | 2026-06-08 | 2026-09-04 | 65 | handler_assign | confirm_note:stored_full | N | N
73097 | 434_ME_VRVInDoorUnit_CeilingSuspended_FXUA&A | 2026-06-08 | 2026-08-27 | 59 | handler_assign | confirm_note:stored_full | N | N
73096 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXDA | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | N | N
73095 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | N | N
73094 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXMA200and250A | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | N | N
73093 | 434_ME_VRVInDoorUnit_ConcealedCeiling_FXSA | 2026-06-08 | 2026-06-12 | 5 | handler_assign | status_resolved | N | N
73092 | 434_ME_VRVInDoorUnit_WallMounted_FXAA&A | 2026-06-08 | 2026-09-22 | 77 | handler_assign | confirm_note:stored_full | N | N
73091 | 434_ME_VRVMultiBranchSelector_BS&10A14AV1B | 2026-06-08 | 2026-09-21 | 76 | handler_assign | confirm_note:stored_full | N | N
73090 | 434_ME_VRVMultiBranchSelector_BS&12A14AV1B | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | N | N
73089 | 434_ME_VRVMultiBranchSelector_BS&4A14AV1B | 2026-06-08 | 2026-06-17 | 8 | handler_assign | status_resolved | N | N
73088 | 434_ME_VRVMultiBranchSelector_BS&6A14AV1B | 2026-06-08 | 2026-06-16 | 7 | handler_assign | status_resolved | N | N
73087 | 434_ME_VRVMultiBranchSelector_BS&8A14AV1B | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full | N | N
73086 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA14&20A | 2026-06-08 | 2026-09-18 | 75 | handler_assign | confirm_note:stored_full | N | N
73085 | 434_ME_VRVOutDoorUnit_HeatPumpRXYA8&12A | 2026-06-08 | 2026-08-28 | 60 | handler_assign | confirm_note:stored_full | N | N
73084 | 434_ME_VRVOutDoorUnit_HeatPumpRXYSA&AV1&AY1 | 2026-06-08 | 2026-09-07 | 66 | handler_assign | confirm_note:stored_full | N | N
73083 | 434_ME_VRVShutOffValveBox_SV1A25AJV1B | 2026-06-08 | 2026-09-11 | 70 | handler_assign | confirm_note:stored_full | N | N
73082 | 434_ME_VRVShutOffValveBox_SV4A14AJV1B | 2026-06-08 | 2026-08-31 | 61 | handler_assign | confirm_note:stored_full | N | N
73081 | 434_ME_VRVShutOffValveBox_SV6A14AJV1B | 2026-06-08 | 2026-07-03 | 20 | handler_assign | confirm_note:stored_full | N | N
73080 | 434_ME_VRVShutOffValveBox_SV8A14AJV1B | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | N | N
73079 | 434_ME_WaterCooledLiquidChillers_30XW | 2026-06-08 | 2026-08-25 | 57 | handler_assign | confirm_note:stored_full | N | N
73078 | 434_ME_WaterCooledScrewCompressorLiquidChillers_30HXC5Pipes | 2026-06-08 | 2026-08-24 | 56 | handler_assign | confirm_note:stored_full | N | N
73077 | 430_DA_VolumeFlowRateMeasuringUnits_VMRK.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | N | N
73076 | 430_DA_RecFireDamperMechanism_FK2EU.rfa | 2026-06-08 | 2026-07-16 | 29 | handler_assign | confirm_note:stored_full | N | N
73075 | 430_DA_VolumeFlowRateMeasuringUnits_VMR.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | N | N
73074 | 430_DA_VolumeFlowRateMeasuringUnits_VMLK.rfa | 2026-06-08 | 2026-06-23 | 12 | handler_assign | confirm_note:stored_full | N | N
73073 | 430_DA_VolumeFlowRateMeasuringUnits_VME.rfa | 2026-06-08 | 2026-07-22 | 33 | handler_assign | confirm_note:stored_full | N | N
73072 | 430_DA_VariableVolumeFlowControl_Varycontrol_Round_TVRK.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | N | N
73071 | 430_DA_FlexibleConnection_Round.rfa | 2026-06-08 | 2026-06-30 | 17 | handler_assign | confirm_note:stored_full | N | N
73070 | 430_DA_VariableVolumeFlowControl_VaryControl_Round_TVR.rfa | 2026-06-08 | 2026-07-14 | 27 | handler_assign | confirm_note:stored_full | N | N
73069 | 430_DA_VariableVolumeFlowControl_VaryControl_Round_LVC.rfa | 2026-06-08 | 2026-09-09 | 68 | handler_assign | confirm_note:stored_full | N | N
73064 | Annotation_Model_Compare and markup for replacement rfa | 2026-06-05 |  |  | handler_assign | none | N | Y | missing_end
73063 | Annotation_Model_Upgrade LIB model to Revit 2023 | 2026-06-05 | 2026-06-09 | 3 | handler_assign | status_resolved | N | N
73024 | 456_EE_BMABusCoupler.rfa | 2026-06-05 | 2026-08-26 | 59 | handler_assign | confirm_note:stored_full | N | N
73023 | 440_EE_TransferDistributor.rfa | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full | N | N
73022 | 440_EE_SynchronizationPanel.rfa | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full | N | N
73021 | 440_EE_SwitchCabinet_SupplyPanel.rfa | 2026-06-05 | 2026-08-24 | 57 | handler_assign | confirm_note:stored_full | N | N
73020 | 440_EE_SwitchCabinet_OutgoingPanel.rfa | 2026-06-05 | 2026-08-19 | 54 | handler_assign | confirm_note:stored_full | N | N
73019 | 440_EE_SubmainSwitchBoard.rfa | 2026-06-05 | 2026-08-25 | 58 | handler_assign | confirm_note:stored_full | N | N
73018 | 440_EE_SpringVibration.rfa | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full | N | N
73017 | 440_EE_SinglePhase_Panel.rfa | 2026-06-05 | 2026-09-18 | 76 | handler_assign | confirm_note:stored_full | N | N
73016 | 440_EE_SilentDieselGenerator.rfa | 2026-06-05 | 2026-06-05 | 1 | handler_assign | status_resolved | N | N
73015 | 440_EE_PanelBoard.rfa | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full | N | N
73014 | 440_EE_OutdoorTransformer.rfa | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full | N | N
73012 | 440_EE_OilTransformer.rfa | 2026-06-05 | 2026-06-24 | 14 | handler_assign | confirm_note:stored_full | N | N
73011 | 440_EE_MotorControlCenter_SwitchBoard.rfa | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full | N | N
73009 | 440_EE_MediumVoltageSwitchgear.rfa | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full | N | N
73007 | 440_EE_Manhole_Standard.rfa | 2026-06-05 | 2026-09-18 | 76 | handler_assign | confirm_note:stored_full | N | N
73006 | 440_EE_MainSwitchBoard.rfa | 2026-06-05 | 2026-08-14 | 51 | handler_assign | confirm_note:stored_full | N | N
73005 | 440_EE_MainSupply_UPSmains.rfa | 2026-06-05 | 2026-08-17 | 52 | handler_assign | confirm_note:stored_full | N | N
73004 | 440_EE_MainSupply_GEVBnetwork.rfa | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full | N | N
73003 | 440_EE_MainDistributionBoard_WallMounted.rfa | 2026-06-05 | 2026-08-27 | 60 | handler_assign | confirm_note:stored_full | N | N
73002 | 440_EE_LowVoltageSwitchboard_NshvPV_HOST.rfa | 2026-06-05 | 2026-07-22 | 34 | handler_assign | confirm_note:stored_full | N | N
73001 | 440_EE_LowVoltageSwitchboard_NshvKälte_HOST.rfa | 2026-06-05 | 2026-08-31 | 62 | handler_assign | confirm_note:stored_full | N | N
73000 | 440_EE_LowVoltageSwitchboard_GHVSüd_HOST.rfa | 2026-06-05 | 2026-09-22 | 78 | handler_assign | confirm_note:stored_full | N | N
72999 | 440_EE_LowVoltageSwitchboard_GHVNord_HOST.rfa | 2026-06-05 | 2026-08-18 | 53 | handler_assign | confirm_note:stored_full | N | N
72940 | 430_DA_VariableVolumeFlowControl_Round_VaryControlTVREX.rfa | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full | N | N
72939 | 430_DA_VariableVolumeFlowControl_Round_VarycontrolTVLK.rfa | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full | N | N
72938 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTZSilenzio.rfa | 2026-06-04 | 2026-09-16 | 75 | handler_assign | confirm_note:stored_full | N | N
72937 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVZ.rfa | 2026-06-04 | 2026-09-24 | 81 | handler_assign | confirm_note:stored_full | N | N
72935 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVT.rfa | 2026-06-04 | 2026-06-30 | 19 | handler_assign | confirm_note:stored_full | N | N
72934 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVM.rfa | 2026-06-04 | 2026-08-05 | 45 | handler_assign | confirm_note:stored_full | N | N
72933 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVJ.rfa | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full | N | N
72932 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTVA.rfa | 2026-06-04 | 2026-07-08 | 25 | handler_assign | confirm_note:stored_full | N | N
72931 | 430_DA_VariableVolumeFlowControl_Rectangular_VaryControlTASilenzio.rfa | 2026-06-04 | 2026-09-14 | 73 | handler_assign | confirm_note:stored_full | N | N
72920 | 430_DA_VariableAirVolume_Round_MQTH.rfa | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full | N | N
72919 | 430_DA_VariableAirVolume_Rectangular_MQTH.rfa | 2026-06-04 | 2026-08-21 | 57 | handler_assign | confirm_note:stored_full | N | N
72917 | 430_DA_TunnelDampers_JF.rfa | 2026-06-04 | 2026-07-28 | 39 | handler_assign | confirm_note:stored_full | N | N
72899 | 430_DA_SmokeProtectionDamper_JZRS.rfa | 2026-06-03 | 2026-08-21 | 58 | handler_assign | confirm_note:stored_full | N | N
72898 | 410_PF_UPVC_xCross_Socket | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | N | N
72897 | 410_PF_UPVC_uSiphon_Socket | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | N | N
72896 | 410_PF_UPVC_uInspectionPort_Glue | 2026-06-23 | 2026-07-13 | 15 | handler_assign | confirm_note:stored_full | N | N
72895 | 410_PF_UPVC_uCoupling_Socket | 2026-06-17 | 2026-07-02 | 12 | handler_assign | confirm_note:stored_full | N | N
72894 | 410_PF_UPVC_uAdaptor_SpigotAndFemaleThreaded | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | N | N
72893 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThread_WithoutReinforced | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | N | N
72892 | 410_PF_UPVC_uAdaptor_SocketAndFemaleThreaded | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | N | N
72891 | 410_PF_UPVC_tTee_Socket | 2026-06-23 | 2026-07-30 | 28 | handler_assign | confirm_note:stored_full | N | N
72890 | 410_PF_UPVC_tTee90Deg_SocketAndFemaleThreaded | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | N | N
72889 | 410_PF_UPVC_tTee90Deg_FemaleThreaded | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | N | N
72888 | 410_PF_UPVC_tLateralTee90Deg_Socket | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | N | N
72887 | 410_PF_UPVC_rShortBushReducing_Socket | 2026-06-23 | 2026-07-14 | 16 | handler_assign | confirm_note:stored_full | N | N
72886 | 410_PF_UPVC_rLongBushReducing_Socket | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | N | N
72885 | 410_PF_UPVC_rBushReducing_Socket | 2026-06-30 | 2026-08-07 | 29 | handler_assign | confirm_note:stored_full | N | N
72884 | 410_PF_UPVC_eShortBend90Deg_Socket | 2026-06-25 | 2026-08-10 | 33 | handler_assign | confirm_note:stored_full | N | N
72883 | 410_PF_UPVC_eReducerElbow_Socket | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | N | N
72882 | 410_PF_UPVC_eElbow_Socket | 2026-06-25 | 2026-08-10 | 33 | handler_assign | confirm_note:stored_full | N | N
72881 | 410_PF_UPVC_eElbow90Deg_FemaleThreaded | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | N | N
72880 | 410_PF_UPVC_eElbow90DegAdaptor_SocketAndFemaleThreaded | 2026-06-25 | 2026-07-23 | 21 | handler_assign | confirm_note:stored_full | N | N
72879 | 410_PF_UPVC_eBend90Deg_Socket | 2026-06-25 | 2026-07-30 | 26 | handler_assign | confirm_note:stored_full | N | N
72878 | 410_PF_UPVC_cCap_Socket | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | N | N
72877 | 430_DA_RoundFireDampers_FKRS_EU.rfa | 2026-06-03 | 2026-09-14 | 74 | handler_assign | confirm_note:stored_full | N | N
72876 | 430_DA_RoundFireDampers_FKREU.rfa | 2026-06-03 | 2026-07-27 | 39 | handler_assign | confirm_note:stored_full | N | N
72875 | 410_PF_UPVC_cCap_FemaleThreaded | 2026-06-25 | 2026-07-30 | 26 | handler_assign | confirm_note:stored_full | N | N
72872 | 410_PF_ST_SanpressDoubleWallPane_Threaded_DN15 | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | N | N
72871 | 410_PF_SS_xReducingDoubleBranch87.5Degrees_SocketAndSpigot | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | N | N
72870 | 410_PF_SS_xDoubleBranch87_Socket | 2026-06-25 | 2026-07-15 | 15 | handler_assign | confirm_note:stored_full | N | N
72869 | 410_PF_SS_xDoubleBranch45Deg_SocketAndSpigot | 2026-06-25 | 2026-07-14 | 14 | handler_assign | confirm_note:stored_full | N | N
72868 | 410_PF_SS_xCornerBranch87Deg_SocketAndSpigot | 2026-06-25 | 2026-07-29 | 25 | handler_assign | confirm_note:stored_full | N | N
72867 | 410_PF_SS_wCleaningPipes | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | N | N
72865 | 410_PF_SS_uUnion_Mapress | 2026-06-23 | 2026-06-30 | 6 | handler_assign | status_resolved | N | N
72864 | 410_PF_SS_uStraightCoupling | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | N | N
72863 | 410_PF_SS_uSocketClamp_Twopiece | 2026-06-23 | 2026-07-15 | 17 | handler_assign | confirm_note:stored_full | N | N
72861 | 410_PF_SS_uSocketClamp_Special | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | N | N
72860 | 410_PF_SS_uRepairCoupling_Socket | 2026-06-23 | 2026-08-03 | 30 | handler_assign | confirm_note:stored_full | N | N
72859 | 410_PF_SS_uRatStop_SocketAndSpigot | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | N | N
72858 | 410_PF_SS_uPeakPressure_Standard | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | N | N
72857 | 410_PF_SS_uExpansionSocket | 2026-06-23 | 2026-07-22 | 22 | handler_assign | confirm_note:stored_full | N | N
72856 | 410_PF_SS_uCoupling_Mapress | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full | N | N
72855 | 410_PF_SS_uConnector_SocketAndThreaded | 2026-06-23 | 2026-07-29 | 27 | handler_assign | confirm_note:stored_full | N | N
72854 | 430_DA_RecFireDampers_FKEU.rfa | 2026-06-03 | 2026-09-16 | 76 | handler_assign | confirm_note:stored_full | N | N
72853 | 430_DA_PressureReliefDamper_Rectangular_Standard_NoSystem.rfa | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | N | N
72851 | 430_DA_NonReturnValves.rfa | 2026-06-03 | 2026-07-08 | 26 | handler_assign | confirm_note:stored_full | N | N
72841 | 410_PF_SS_uConnector_FlangedAndSpigot | 2026-06-23 | 2026-08-13 | 38 | handler_assign | confirm_note:stored_full | N | N
72840 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndMapress | 2026-06-23 | 2026-08-13 | 38 | handler_assign | confirm_note:stored_full | N | N
72839 | 410_PF_SS_uConnectionWithPlainEnd_FlangedAndWelded | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | N | N
72838 | 410_PF_SS_uBulkhead_Welded | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | N | N
72837 | 410_PF_SS_uAxialExpansion_PressingSockets | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full | N | N
72836 | 410_PF_SS_uAdaptorWithPlainEnd_MaleThreadAndMapress | 2026-06-23 | 2026-08-18 | 41 | handler_assign | confirm_note:stored_full | N | N
72835 | 410_PF_SS_uAdaptor_WithMaleThreadAndMapress | 2026-06-23 | 2026-07-17 | 19 | handler_assign | confirm_note:stored_full | N | N
72834 | 410_PF_SS_uAdaptor_WithFemaleThreadAndPlainEndLong_Mapress | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | N | N
72833 | 410_PF_SS_uAdaptor_WithFemaleThreadAndMapress | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full | N | N
72832 | 410_PF_SS_uAdaptorWithUnionNut_ThreadedAndMapress | 2026-06-23 | 2026-09-21 | 65 | handler_assign | confirm_note:stored_full | N | N
72831 | 410_PF_SS_uAdaptorUnion_MaleThreadAndMapress | 2026-06-23 | 2026-07-28 | 26 | handler_assign | confirm_note:stored_full | N | N
72830 | 410_PF_SS_uAdaptorUnion_FemaleThreadAndMapress | 2026-06-23 | 2026-07-27 | 25 | handler_assign | confirm_note:stored_full | N | N
72829 | 410_PF_SS_tPieceReducer_Mapress | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full | N | N
72828 | 410_PF_SS_tTeePiece_Mapress | 2026-06-23 | 2026-07-27 | 25 | handler_assign | confirm_note:stored_full | N | N
72827 | 410_PF_SS_tTeePiece_MaleThreadedAndMapress | 2026-06-23 | 2026-08-10 | 35 | handler_assign | confirm_note:stored_full | N | N
72826 | 410_PF_SS_tTeePiece_FemaleThreadedAndMapress | 2026-06-23 | 2026-08-21 | 44 | handler_assign | confirm_note:stored_full | N | N
72825 | 410_PF_SS_tSweptBranch87Deg_SocketAndSpigot | 2026-06-23 | 2026-08-07 | 34 | handler_assign | confirm_note:stored_full | N | N
72824 | 410_PF_SS_tSingleBranch45_SocketAndSpigot | 2026-06-23 | 2026-08-11 | 36 | handler_assign | confirm_note:stored_full | N | N
72823 | 410_PF_SS_tReducingSingleBranch87Deg_Socket | 2026-06-23 | 2026-08-24 | 45 | handler_assign | confirm_note:stored_full | N | N
72822 | 410_PF_SS_tReducingSingleBranch45Degree_Socket | 2026-06-23 | 2026-08-24 | 45 | handler_assign | confirm_note:stored_full | N | N
72821 | 410_PF_SS_tReducingDoubleBranch45_Socket | 2026-06-23 | 2026-07-24 | 24 | handler_assign | confirm_note:stored_full | N | N
72820 | 410_PF_SS_tTPiece_Mapress_Equal | 2026-06-23 | 2026-08-06 | 33 | handler_assign | confirm_note:stored_full | N | N
72819 | 430_DA_MultileafDamperRec_LowLeakage.rfa | 2026-06-02 | 2026-07-02 | 23 | handler_assign | confirm_note:stored_full | N | N
72818 | 440_EE_LowVoltagePanel.rfa | 2026-06-02 | 2026-06-04 | 3 | handler_assign | status_resolved | N | N
72817 | 440_EE_kwhMeter_3Phases.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | N | N
72816 | 440_EE_IndoorTransformer.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | N | N
72815 | 440_EE_Generator_Standard.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | N | N
72814 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSSud.rfa | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full | N | N
72813 | 410_PF_SS_tCornerDoubleBranch87_SocketAndSpigot | 2026-06-18 | 2026-07-03 | 12 | handler_assign | confirm_note:stored_full | N | N
72812 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSSud.rfa | 2026-06-02 | 2026-06-04 | 3 | handler_assign | status_closed | N | N
72811 | 410_PF_SS_rTransition_SocketAndFemaleThreaded | 2026-06-17 | 2026-07-03 | 13 | handler_assign | confirm_note:stored_full | N | N
72810 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MsPvAnlage.rfa | 2026-06-02 | 2026-06-04 | 3 | handler_assign | status_resolved | N | N
72809 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSNord.rfa | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full | N | N
72808 | 410_PF_SS_rReducerWithPlainEnd_Mapress | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full | N | N
72807 | 410_PF_SS_rReducerAdaptor_FemaleThreadedAndMapress_PlainEndLong | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full | N | N
72806 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSKälte.rfa | 2026-06-02 | 2026-09-22 | 81 | handler_assign | confirm_note:stored_full | N | N
72805 | 440_EE_GasInsulatedMediumVoltageSwitchgear_MSEVU.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | N | N
72804 | 430_DA_SmokeDetectorinDucts_RMOVSD.rfa | 2026-06-02 | 2026-09-14 | 75 | handler_assign | confirm_note:stored_full | N | N
72803 | 430_DA_SmokeDetectorinDucts_RMO3D.rfa | 2026-06-02 | 2026-09-25 | 84 | handler_assign | confirm_note:stored_full | N | N
72802 | 410_PF_SS_rEccentricIncreaserCoupling_SocketAndSpigot | 2026-06-17 | 2026-09-25 | 73 | handler_assign | confirm_note:stored_full | N | N
72800 | 410_PF_SS_rConnector_SocketAndThreaded | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full | N | N
72798 | 410_PF_SS_rConnector_Socket | 2026-06-17 | 2026-07-30 | 32 | handler_assign | confirm_note:stored_full | N | N
72797 | 410_PF_SS_rTransition_SocketAndFlanged | 2026-06-17 | 2026-09-30 | 76 | handler_assign | confirm_note:stored_full | N | N
72784 | 410_PF_SS_rConnectorInternal_ThreadSpigot | 2026-06-17 | 2026-07-01 | 11 | handler_assign | confirm_note:stored_full | N | N
72783 | 410_PF_SS_rConnectorExternalThreadSpigot | 2026-06-17 | 2026-07-28 | 30 | handler_assign | confirm_note:stored_full | N | N
72782 | 410_PF_SS_rConcentricIncreaserCoupling_Standard | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | N | N
72781 | 410_PF_SS_uRapid_Coupling | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full | N | N
72779 | 410_PF_SS_rAdaptorReducer_FemaleThreadedAndMapress | 2026-06-17 | 2026-08-04 | 35 | handler_assign | confirm_note:task_completed_closed | N | N
72777 | 410_PF_SS_mCornerElbow90Deg_Mapress | 2026-06-17 | 2026-06-23 | 5 | handler_assign | status_resolved | N | N
72776 | 410_PF_SS_eTElbowTapConnector90Deg_Mapress_Offset | 2026-06-17 | 2026-08-14 | 43 | handler_assign | confirm_note:stored_full | N | N
72769 | 440_EE_FlatRoofSolarFrame_NoSystem.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | N | N
72768 | 410_PF_SS_ePTrap_SocketAndSpigot | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | N | N
72767 | 410_PF_SS_eLongBend_1Socket | 2026-06-17 | 2026-07-03 | 13 | handler_assign | confirm_note:stored_full | N | N
72766 | 410_PF_SS_eElbow_Mapress | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | N | N
72764 | 410_PF_SS_eElbowTapConector90Degree_Mapress | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full | N | N
72763 | 410_PF_SS_eElbow90Deg_FemaleThreadAndMapress | 2026-06-17 | 2026-06-23 | 5 | handler_assign | status_resolved | N | N
72762 | 410_PF_SS_eElbow90DegTapConnector_Mapress | 2026-06-17 | 2026-07-22 | 26 | handler_assign | confirm_note:stored_full | N | N
72761 | 410_PF_SS_eElbow90DegAdaptor_MaleThreadAndMapress | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | N | N
72760 | 430_DA_SchakoConstantVolumeFlowControl_Round_ConstantFlowVLV.rfa | 2026-06-02 | 2026-07-03 | 24 | handler_assign | confirm_note:stored_full | N | N
72759 | 410_PF_SS_eElbow90DegAdaptor_FemaleThreadedAndPlainEndAndMapress | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full | N | N
72758 | 430_DA_SmokeControlDamper_EKJZ.rfa | 2026-06-02 | 2026-07-27 | 40 | handler_assign | confirm_note:stored_full | N | N
72757 | 410_PF_SS_eBend_30_1Socket | 2026-06-17 | 2026-08-10 | 39 | handler_assign | confirm_note:stored_full | N | N
72756 | 430_DA_SmokeControlDamper_EKEU.rfa | 2026-06-02 | 2026-06-23 | 16 | handler_assign | confirm_note:stored_full | N | N
72755 | 410_PF_SS_eBend_15_1Socket | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full | N | N
72754 | 410_PF_SS_eBendWith250mmOblong_Clamp | 2026-06-17 | 2026-08-17 | 44 | handler_assign | confirm_note:stored_full | N | N
72753 | 430_DA_IntumescentDamper_OverflowGrill_NoSystem.rfa | 2026-06-02 | 2026-07-15 | 32 | handler_assign | confirm_note:stored_full | N | N
72751 | 430_DA_FlowAdjustmentDampers.rfa | 2026-06-02 | 2026-07-07 | 26 | handler_assign | confirm_note:stored_full | N | N
72750 | 410_PF_SS_eBend87_Socket | 2026-06-17 | 2026-08-14 | 43 | handler_assign | confirm_note:stored_full | N | N
72748 | 430_DA_SilencersVAV_Rectangular_TX.rfa | 2026-06-02 | 2026-07-27 | 40 | handler_assign | confirm_note:stored_full | N | N
72747 | 410_PF_SS_eBend45Degrees_SocketAndStandard | 2026-06-17 | 2026-07-22 | 26 | handler_assign | confirm_note:stored_full | N | N
72746 | 430_DA_SilencersVAV_Rectangular_TS.rfa | 2026-06-02 | 2026-06-03 | 2 | handler_assign | status_resolved | N | N
72745 | 430_DA_SchakoSilencer_Round_RS.rfa | 2026-06-02 | 2026-07-07 | 26 | handler_assign | confirm_note:stored_full | N | N
72744 | 410_PF_SS_cVentCowl_Standard | 2026-06-17 | 2026-07-15 | 21 | handler_assign | confirm_note:stored_full | N | N
72743 | 430_DA_Silencer_Rectangular_Standard.rfa | 2026-06-02 | 2026-09-03 | 68 | handler_assign | confirm_note:stored_full | N | N
72742 | 410_PF_SS_cSocketPlugWithClamp | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full | N | N
72741 | 430_DA_Silencer_Round_Standard.rfa | 2026-06-02 | 2026-07-03 | 24 | handler_assign | confirm_note:stored_full | N | N
72740 | 410_PF_SS_cSocketPlug | 2026-06-17 | 2026-07-17 | 23 | handler_assign | confirm_note:stored_full | N | N
72739 | 410_PF_SS_cDrainplugWithScrewedPlug | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full | N | N
72738 | 430_DA_ShutOffDevices_AKK.rfa | 2026-06-02 | 2026-09-16 | 77 | handler_assign | confirm_note:stored_full | N | N
72737 | 410_PF_SS_cCap_Mapress | 2026-06-17 | 2026-07-23 | 27 | handler_assign | confirm_note:stored_full | N | N
72736 | 430_DA_ShutOffDevices_AKEx.rfa | 2026-06-02 | 2026-07-01 | 22 | handler_assign | confirm_note:stored_full | N | N
72735 | 410_PF_SS_uUnion_Coupling | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | N | N
72734 | 430_DA_ShutOffDevices_AK.rfa | 2026-06-02 | 2026-09-25 | 84 | handler_assign | confirm_note:stored_full | N | N
72733 | 410_PF_SilentPro_xCrossDoubleBranchFitting88DegSweptEntry_SocketAndSpigot | 2026-06-17 | 2026-07-13 | 19 | handler_assign | confirm_note:stored_full | N | N
72732 | 410_PF_PPMX_wParallelBrand45Deg_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-24 | 49 | handler_assign | confirm_note:stored_full | N | N
72731 | 410_PF_PPMX_uSlipCoupling_PushOnJoint_SilentPro | 2026-06-17 | 2026-08-17 | 44 | handler_assign | confirm_note:stored_full | N | N
72730 | 410_PF_PPMD_uAccessPipe90DegWithRoundServiceOpening_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-24 | 49 | handler_assign | confirm_note:stored_full | N | N
72729 | 410_PF_SilentPro_tTeeBranch_SocketSpigot | 2026-06-25 | 2026-07-27 | 23 | handler_assign | confirm_note:stored_full | N | N
72728 | 410_PF_SilentPro_tDuctBranch_SweptEntry88DegLeft_SocketAndSpigot | 2026-06-17 | 2026-07-28 | 30 | handler_assign | confirm_note:stored_full | N | N
72726 | 410_PF_SilentPro_tBranch_SocketAndSpigot_SweptEntry88Deg | 2026-06-17 | 2026-07-24 | 28 | handler_assign | confirm_note:stored_full | N | N
72725 | 410_PF_PPMX_rReducerEccentric_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-07 | 38 | handler_assign | confirm_note:stored_full | N | N
72724 | Annotation_Platform_Maintain the platform | 2026-06-02 |  |  | handler_assign | none | N | Y | missing_end
72723 | 410_PF_PPMD_mCornerBranch88Deg_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full | N | N
72722 | Annotation_Platform_Upgrade the function of feature | 2026-06-02 | 2026-06-05 | 4 | handler_assign | status_resolved | N | N
72721 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_SilentPro | 2026-06-17 | 2026-08-13 | 42 | handler_assign | confirm_note:stored_full | N | N
72720 | 410_PF_PPMX_eElbow_SocketAndSpigot_SilentPro | 2026-06-16 | 2026-08-17 | 45 | handler_assign | confirm_note:stored_full | N | N
72719 | 440_EE_FlatRoofSolarFrameWithRoot_NoSystem.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | N | N
72718 | 440_EE_FlatRoofSolar.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | N | N
72717 | 440_EE_ElectricalCabinet_Standard.rfa | 2026-06-02 | 2026-08-17 | 55 | handler_assign | confirm_note:stored_full | N | N
72716 | 440_EE_DryTransformer.rfa | 2026-06-02 | 2026-08-18 | 56 | handler_assign | confirm_note:stored_full | N | N
72715 | 440_EE_DistributionBox_DALI.rfa | 2026-06-02 | 2026-08-31 | 65 | handler_assign | confirm_note:stored_full | N | N
72710 | 410_PF_SilentPro_cCapEnd_Socket | 2026-06-15 | 2026-06-25 | 9 | handler_assign | confirm_note:stored_full | N | N
72707 | 410_PF_SilentPro_cCapEnd_Socket | 2026-06-17 | 2026-06-17 | 1 | handler_assign | confirm_note:will_be_closed | N | N
72705 | 410_PF_PP_uSlipCoupling_Silent | 2026-06-15 | 2026-06-16 | 2 | handler_assign | status_resolved | N | N
72700 | 410_PF_PP_rReducerEccentric_SocketAndSpigot_Silent | 2026-06-15 | 2026-09-16 | 68 | handler_assign | confirm_note:stored_full | N | N
72699 | 410_PF_PPMD_wParallelBrand45Deg_SocketAndSpigot_Silent | 2026-06-15 | 2026-06-16 | 2 | handler_assign | status_resolved | N | N
72697 | 410_PF_PP_mOdorTrapForSinkVerticalAndHorizontal_Standard | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full | N | N
72696 | 410_PF_PP_mOdorTrapForSinkVertical_Standard | 2026-06-12 | 2026-06-17 | 4 | handler_assign | status_resolved | N | N
72695 | 420_PA_PressureSensor | 2026-07-13 | 2026-08-12 | 23 | handler_assign | status_resolved | N | N
72694 | 420_PA_PressureSensor_Standard | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
72693 | 420_PA_RadiatorLockshield_Thread | 2026-07-13 | 2026-08-28 | 35 | handler_assign | confirm_note:stored_full | N | N
72692 | 410_PF_PP_mOdorTrapForSinkHorizontal_Standard | 2026-06-12 | 2026-06-16 | 3 | handler_assign | status_resolved | N | N
72691 | 420_PA_RadiatorShutOffValveAngle_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
72690 | 420_PA_RadiatorShutOffValveStraight_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
72689 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_SweptEntryAndSilent | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full | N | N
72688 | 420_PA_RadiatorThermostatic2PointAngleValve_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
72687 | 420_PA_RadiatorThermostaticAngleValve_Thread | 2026-07-13 | 2026-09-15 | 47 | handler_assign | confirm_note:stored_full | N | N
72686 | 420_PA_RadiatorThermostaticStraightValve_Thread | 2026-07-13 | 2026-07-29 | 13 | handler_assign | status_resolved | N | N
72684 | 420_PA_RegulatingValve_Flanged | 2026-07-13 | 2026-07-31 | 15 | handler_assign | status_resolved | N | N
72683 | 420_PA_RegulatingValve_Flanged_Standard | 2026-07-13 | 2026-07-31 | 15 | handler_assign | status_resolved | N | N
72682 | 410_PF_PP_xDoubleBranchFitting88Deg_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-13 | 45 | handler_assign | confirm_note:stored_full | N | N
72681 | 410_PF_PPMD_mCombinedCornerBranch_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-13 | 45 | handler_assign | confirm_note:stored_full | N | N
72680 | 410_PF_PPMD_cEndCap_Socket_Silent | 2026-06-12 | 2026-06-16 | 3 | handler_assign | status_resolved | N | N
72679 | 410_PF_PP_tBranch_SocketSpigot_Silent | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | N | N
72678 | 410_PF_PPMD_eBend_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-10 | 42 | handler_assign | confirm_note:stored_full | N | N
72676 | 410_PF_EPDM_mSleeveToCastlron_MechanicalJoint_Silent | 2026-06-12 | 2026-06-18 | 5 | handler_assign | status_resolved | N | N
72674 | 410_PF_PP_uAccessPipe90Deg_SocketAndSpigot_WithRoundServiceOpening&Silent | 2026-06-12 | 2026-07-14 | 23 | handler_assign | confirm_note:stored_full | N | N
72673 | 410_PF_PPMD_tDoubleConnectionBend90Deg_Extended_Silent | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full | N | N
72672 | 410_PF_PPMD_tBranchSweptEntry88Deg_SocketAndSpigot_Silent | 2026-06-12 | 2026-08-12 | 44 | handler_assign | confirm_note:stored_full | N | N
72671 | 410_PF_PPMD_xDuctBranchSweptEntry88DegLeft_SocketAndSpigot_Silent | 2026-06-12 | 2026-07-29 | 34 | handler_assign | confirm_note:passed_audit | N | N
72669 | 410_PF_PPR_uUnion_BushSocketFusion | 2026-06-25 | 2026-06-30 | 4 | handler_assign | status_resolved | N | N
72668 | 410_PF_PPR_uUnion_BushSocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | N | N
72667 | 410_PF_PPR_uCoupling_MaleThreadAndSocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | N | N
72666 | 410_PF_PPR_uCoupling_FemaleThreadAndSocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | N | N
72665 | 410_PF_PPR_tTee_SocketFusion | 2026-06-12 | 2026-07-17 | 26 | handler_assign | confirm_note:stored_full | N | N
72664 | 410_PF_PPR_tTee_MaleThreadedAndSocketFusion | 2026-06-10 | 2026-06-25 | 12 | handler_assign | confirm_note:stored_full | N | N
72663 | 420_PA_RegulatingValve_Thread_Standard | 2026-06-01 | 2026-08-11 | 52 | handler_assign | confirm_note:stored_full | N | N
72662 | 420_PA_RegulatingValve_Threaded | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full | N | N
72661 | 410_PF_PPR_tTee_FemaleThreadedAndSocketFusion | 2026-06-10 | 2026-06-24 | 11 | handler_assign | confirm_note:stored_full | N | N
72660 | 420_PA_SafetyReliefValveConer_Thread | 2026-06-01 | 2026-08-11 | 52 | handler_assign | confirm_note:stored_full | N | N
72659 | 420_PA_SafetyReliefValveCorner_Flanged | 2026-06-01 | 2026-08-12 | 53 | handler_assign | confirm_note:stored_full | N | N
72658 | 420_PA_SafetyReliefValveStraight_Flanged | 2026-06-01 | 2026-09-15 | 77 | handler_assign | confirm_note:stored_full | N | N
72657 | 420_PA_SafetyValveCorner_Flanged_Standard | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | N | N
72656 | 410_PF_PPR_rReducing_SocketFusion | 2026-06-10 | 2026-07-02 | 17 | handler_assign | confirm_note:stored_full | N | N
72655 | 420_PA_SafetyValveCorner_Thread_Standard | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | N | N
72654 | 420_PA_SpringCheckValve_Flanged_Standard | 2026-06-01 | 2026-07-13 | 31 | handler_assign | confirm_note:stored_full | N | N
72653 | 420_PA_SwingCheckValve_Flanged_Standard | 2026-06-01 | 2026-10-01 | 89 | handler_assign | confirm_note:stored_full | N | N
72652 | 420_PA_SwingCheckValve_Thread_Standard | 2026-06-01 | 2026-06-16 | 12 | handler_assign | confirm_note:stored_full | N | N
72651 | 410_PF_PPR_eElbow90Deg_MaleThreadAndSocketFusion | 2026-06-10 | 2026-07-30 | 37 | handler_assign | confirm_note:stored_full | N | N
72650 | 420_PA_SwingcheckValve_Flanged | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | N | N
72649 | 410_PF_PPR_mCoupling_MaleThreadAndSocketFusion | 2026-06-10 | 2026-06-17 | 6 | handler_assign | status_resolved | N | N
72648 | 410_PF_PPR_mCoupling_FemaleThreadAndSocketFusion | 2026-06-10 | 2026-08-21 | 53 | handler_assign | confirm_note:stored_full | N | N
72647 | 410_PF_PPR_eElbow_SocketFusion | 2026-06-10 | 2026-07-28 | 35 | handler_assign | confirm_note:stored_full | N | N
72646 | 410_PF_PPR_eElbow90Deg_FemaleThreadAndSocketFusion | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | N | N
72645 | 410_PF_PPR_eElbow90DegBracket_MaleThreadAndSocketFusion | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | N | N
72644 | 434_ME_Watercooled_Condenserlessliquidchillers_30RW_30RWA_VerticalConnection | 2026-06-01 | 2026-09-22 | 82 | handler_assign | confirm_note:stored_full | N | N
72643 | 434_PA_BranchProviderBox_BPMKS2Port | 2026-06-01 | 2026-06-30 | 22 | handler_assign | confirm_note:stored_full | N | N
72642 | 434_PA_BranchProviderBox_BPMKS3Port | 2026-06-01 | 2026-06-30 | 22 | handler_assign | confirm_note:stored_full | N | N
72641 | 410_PF_PPR_eElbow90DegBracket_FemaleThreadAndSocketFusion | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | N | N
72640 | 434_PA_MultiConnectionPipingKit1_BHFPGas | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | N | N
72639 | 434_PA_MultiConnectionPipingKit1_BHFPLiquid | 2026-06-01 | 2026-07-01 | 23 | handler_assign | confirm_note:stored_full | N | N
72638 | 410_PF_PPR_cEndCap_SocketFusion | 2026-06-10 | 2026-07-02 | 17 | handler_assign | confirm_note:stored_full | N | N
72637 | 434_PF_CO_eBend_MapressFKMBlue.rfa | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | N | N
72636 | 434_PA_MultiConnectionPipingKit2_BHFPLiquid | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | N | N
72635 | 434_PA_RefnetHeader_KHRPGas4Branches | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | N | N
72634 | 434_PA_RefnetHeader_KHRPGas8Branches | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | N | N
72633 | 434_PA_RefnetHeader_KHRPHP&LPGas | 2026-06-01 | 2026-09-10 | 74 | handler_assign | confirm_note:stored_full | N | N
72632 | 434_PA_RefnetHeader_KHRPLiquid4Branches | 2026-06-01 | 2026-07-02 | 24 | handler_assign | confirm_note:stored_full | N | N
72631 | 434_PA_RefnetHeader_KHRPLiquid8Branches | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | N | N
72630 | 434_PA_RefnetJoint_KHRPDischarge | 2026-06-01 | 2026-06-09 | 7 | handler_assign | status_resolved | N | N
72629 | 434_PA_RefnetJoint_KHRPGas | 2026-06-01 | 2026-06-09 | 7 | handler_assign | status_resolved | N | N
72628 | 434_PA_RefnetJoint_KHRPLiquid | 2026-06-01 | 2026-06-10 | 8 | handler_assign | status_resolved | N | N
72627 | 434_PF_CO_30Cross_Mapress | 2026-06-01 | 2026-07-06 | 26 | handler_assign | confirm_note:stored_full | N | N
72626 | 434_PF_CO_AdaptorMultiPort_MapressAndNut | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | N | N
72625 | 434_PF_CO_AdaptorUnion_FemaleThreadAndMeplaFix | 2026-06-01 | 2026-07-01 | 23 | handler_assign | confirm_note:stored_full | N | N
72624 | 434_PF_CO_AdaptorUnion_MapressAndFlangeGas | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | N | N
72623 | 434_PF_CO_AdaptorUnion_PlainEndAndFlange | 2026-06-01 | 2026-06-19 | 15 | handler_assign | confirm_note:stored_full | N | N
72622 | 434_PF_CO_Bend_Mapress | 2026-06-01 | 2026-07-22 | 38 | handler_assign | confirm_note:stored_full | N | N
72621 | 434_PF_CO_Bend_MapressFKMBlue | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | N | N
72618 | 410_PF_PE_eBendForWandWC | 2026-06-10 | 2026-08-04 | 40 | handler_assign | confirm_note:stored_full | N | N
72614 | 410_PF_mHDPE_PTrap | 2026-06-10 | 2026-08-04 | 40 | handler_assign | confirm_note:stored_full | N | N
72612 | 410_PF_GA_mPTrapGMX_Standard | 2026-06-10 | 2026-07-29 | 36 | handler_assign | confirm_note:stored_full | N | N
72611 | 410_PF_HDPE_xDoubleBrandFitting45Deg_Welded | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | N | N
72610 | 410_PF_HDPE_uUnionConnection_WeldingJoints | 2026-06-10 | 2026-07-29 | 36 | handler_assign | confirm_note:stored_full | N | N
72609 | 410_PF_HDPE_uUnion_FemaleThreadAndCompression | 2026-06-10 | 2026-08-12 | 46 | handler_assign | confirm_note:stored_full | N | N
72608 | 410_PF_HDPE_uStraightConnector_ForFloorStandingWC | 2026-06-10 | 2026-07-17 | 28 | handler_assign | confirm_note:stored_full | N | N
72607 | 410_PF_HDPE_uStraightConnectorForWC_ButtFusionAndPushOnJoint | 2026-06-10 | 2026-07-27 | 34 | handler_assign | confirm_note:stored_full | N | N
72606 | 410_PF_HDPE_uStraightAdapter_WithMaleThread&CompressionJoint_Standard | 2026-06-10 | 2026-08-03 | 39 | handler_assign | confirm_note:stored_full | N | N
72605 | 410_PF_HDPE_uStraightAdapter_CompressionAndSpigot | 2026-06-10 | 2026-08-11 | 45 | handler_assign | confirm_note:stored_full | N | N
72604 | 420_PA_SwingcheckValve_Threaded | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full | N | N
72603 | 420_PA_TemperatureGauge_Standard | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | N | N
72602 | 420_PA_TemperatureSensor | 2026-06-01 | 2026-07-03 | 25 | handler_assign | confirm_note:stored_full | N | N
72601 | 410_PF_HDPE_uStraightAdapterHDPEToPVC_ButtFusionAndPushOnJoint | 2026-06-10 | 2026-07-28 | 35 | handler_assign | confirm_note:stored_full | N | N
72600 | 420_PA_Thermometer | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | N | N
72599 | 420_PA_Thermometergauge | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full | N | N
72598 | 420_PA_ThreeWayvalve_Flanged_Standard | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | N | N
72597 | 420_PA_ThreeWayvalve_Thread_Standard | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | N | N
72596 | 410_PF_HDPE_uStraightAdapterToCastIronPipe | 2026-06-09 | 2026-07-07 | 21 | handler_assign | confirm_note:stored_full | N | N
72595 | 420_PA_WaferCheckValve_Flanged_Standard | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | N | N
72594 | 420_PA_WaterMeter_Flanged | 2026-06-01 | 2026-09-21 | 81 | handler_assign | confirm_note:stored_full | N | N
72593 | 420_PA_WaterMeter_Flanged_Standard | 2026-06-01 | 2026-09-25 | 85 | handler_assign | confirm_note:stored_full | N | N
72592 | 410_PF_HDPE_fFlangeSet_Standard | 2026-06-09 | 2026-06-09 | 1 | handler_assign | status_resolved | N | N
72591 | 420_PA_WaterMeter_Threaded | 2026-06-01 | 2026-06-19 | 15 | handler_assign | confirm_note:stored_full | N | N
72590 | 420_PA_YStrainerValve_Flanged_Standard | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full | N | N
72589 | 420_PA_YStrainerValve_Thread_Standard | 2026-06-01 | 2026-07-27 | 41 | handler_assign | confirm_note:stored_full | N | N
72588 | 420_PA_YStrainer_Flanged | 2026-06-01 | 2026-08-12 | 53 | handler_assign | confirm_note:stored_full | N | N
72587 | 420_PA_YStrainer_Thread | 2026-06-01 | 2026-07-27 | 41 | handler_assign | confirm_note:stored_full | N | N
72586 | 420_PF_CO_tTee_Soldered | 2026-06-01 | 2026-07-15 | 33 | handler_assign | confirm_note:stored_full | N | N
72585 | 420_PF_CO_uUnion_Soldered | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full | N | N
72584 | 420_PF_CO_xCross_Soldered | 2026-06-01 | 2026-07-08 | 28 | handler_assign | confirm_note:stored_full | N | N
72583 | 420_PF_CS_cCap_Welded | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full | N | N
72582 | 420_PF_CS_eElbow_Welded | 2026-06-01 | 2026-08-06 | 49 | handler_assign | confirm_note:stored_full | N | N
72581 | 434_PF_CO_Bend_MapressGas | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | N | N
72580 | 434_PF_CO_BridgeBendMultiPort_MapressGas | 2026-06-01 | 2026-08-20 | 59 | handler_assign | confirm_note:stored_full | N | N
72579 | 434_PF_CO_Cap_Mapress | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | N | N
72578 | 434_PF_CO_Cap_MapressFKMBlue | 2026-06-01 | 2026-07-28 | 42 | handler_assign | confirm_note:stored_full | N | N
72577 | 434_PF_CO_Cap_MapressGas | 2026-06-01 | 2026-06-09 | 7 | handler_assign | confirm_note:stored_full | N | N
72576 | 434_PF_CO_ReducerAdaptor_PlainEndAndClampingRing | 2026-06-01 | 2026-06-09 | 7 | handler_assign | confirm_note:stored_full | N | N
72575 | 434_PF_CO_Tee_Mapress&FemaleThread | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | N | N
72574 | 434_PF_CO_Tee_Mapress | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | N | N
72573 | 434_PF_CO_Tee_MapressFKMBlue&FemaleThread | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | N | N
72572 | 434_PF_CO_Tee_MapressFKMBlue | 2026-06-01 | 2026-06-15 | 11 | handler_assign | confirm_note:stored_full | N | N
72571 | 434_PF_CO_Tee_MapressGas&FemaleThread | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | N | N
72570 | 434_PF_CO_Tee_MapressGas | 2026-06-01 | 2026-07-29 | 43 | handler_assign | confirm_note:stored_full | N | N
72569 | 434_PF_CO_Transition_Mapress | 2026-06-01 | 2026-06-11 | 9 | handler_assign | confirm_note:stored_full | N | N
72568 | 434_PF_CO_Transition_MapressFKMBlue | 2026-06-01 | 2026-07-30 | 44 | handler_assign | confirm_note:stored_full | N | N
72567 | 434_PF_CO_Transition_MapressGas | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | N | N
72566 | 434_PF_CO_Union_Mapress | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | N | N
72565 | 434_PF_CO_Union_MapressFKMBlue | 2026-06-01 | 2026-07-23 | 39 | handler_assign | confirm_note:stored_full | N | N
72561 | 410_PF_HDPE_uFlangeBushing_Standard | 2026-06-09 | 2026-09-17 | 73 | handler_assign | confirm_note:stored_full | N | N
72560 | 410_PF_HDPE_uFlangeAdapter_Standard | 2026-06-09 | 2026-09-17 | 73 | handler_assign | confirm_note:stored_full | N | N
72559 | 410_PF_HDPE_uExpansion_Socket | 2026-06-25 | 2026-08-11 | 34 | handler_assign | confirm_note:stored_full | N | N
72558 | 410_PF_HDPE_uClampingConnector | 2026-06-10 | 2026-06-30 | 15 | handler_assign | confirm_note:stored_full | N | N
72557 | 410_PF_HDPE_rReducerAdaptor_MaleThreaded | 2026-06-10 | 2026-08-21 | 53 | handler_assign | confirm_note:stored_full | N | N
72556 | 410_PF_HDPE_uAdapterUnion_FemaleThreadAndCompressionJoint | 2026-06-03 | 2026-07-08 | 26 | handler_assign | confirm_note:stored_full | N | N
72555 | 410_PF_HDPE_uAdapterUnion_FemaleThreaded | 2026-06-03 | 2026-08-21 | 58 | handler_assign | confirm_note:stored_full | N | N
72554 | 410_PF_HDPE_uAccessPipe90Deg_RoundServiceOpening_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | N | N
72553 | 410_PF_HDPE_uAccessPipe90Deg_OvalServiceOpening_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | N | N
72552 | 410_PF_HDPE_uAccessPipe45Deg_RoundServiceOpening_Welded | 2026-06-03 | 2026-07-06 | 24 | handler_assign | confirm_note:stored_full | N | N
72551 | 410_PF_HDPE_tSilen_DB20BreechesBranchFitting90Deg_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | N | N
72550 | 410_PF_HDPE_tLateralTee_Welded | 2026-06-10 | 2026-07-15 | 26 | handler_assign | confirm_note:stored_full | N | N
72549 | 410_PF_HDPE_tBreechesBranchFitting2x30Deg_Welded | 2026-06-03 | 2026-06-19 | 13 | handler_assign | confirm_note:stored_full | N | N
72548 | 410_PF_HDPE_rStraightConnectorWithRingSealSocket_WC | 2026-06-03 | 2026-07-03 | 23 | handler_assign | confirm_note:stored_full | N | N
72547 | 410_PF_HDPE_mReducedRingSealSocket_Socket | 2026-06-03 | 2026-09-17 | 77 | handler_assign | confirm_note:stored_full | N | N
72546 | 410_PF_HDPE_rReducer_Welded | 2026-06-03 | 2026-07-16 | 32 | handler_assign | confirm_note:stored_full | N | N
72545 | 440_EE_DieselTankGenerator.rfa | 2026-05-29 | 2026-08-17 | 57 | handler_assign | confirm_note:stored_full | N | N
72544 | 410_PF_HDPE_rCompressionJoint_MechanicalJoint | 2026-06-03 | 2026-09-17 | 77 | handler_assign | confirm_note:stored_full | N | N
72543 | 440_EE_DieselGenerator.rfa | 2026-05-29 | 2026-09-18 | 81 | handler_assign | confirm_note:stored_full | N | N
72542 | 410_PF_HDPE_rAdaptorSocket_DN90xDN100 | 2026-06-03 | 2026-07-03 | 23 | handler_assign | confirm_note:stored_full | N | N
72541 | 410_PF_HDPE_mWasteManifold | 2026-06-03 | 2026-07-15 | 31 | handler_assign | confirm_note:stored_full | N | N
72540 | 440_EE_DCtoAC_Inverter.rfa | 2026-05-29 | 2026-08-14 | 56 | handler_assign | confirm_note:stored_full | N | N
72539 | 410_PF_HDPE_mUniversalTrap_WithFlangeBushing | 2026-06-03 | 2026-06-19 | 13 | handler_assign | confirm_note:stored_full | N | N
72538 | 440_EE_CircuitBreakerEnclosure.rfa | 2026-05-29 | 2026-09-18 | 81 | handler_assign | confirm_note:stored_full | N | N
72537 | 410_PF_HDPE_mSTrap_Standard | 2026-06-03 | 2026-06-22 | 14 | handler_assign | confirm_note:stored_full | N | N
72536 | 442_EE_ChargeController.rfa | 2026-05-29 | 2026-09-15 | 78 | handler_assign | confirm_note:stored_full | N | N
72535 | 440_EE_BatteryStorage.rfa | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | N | N
72534 | 440_EE_AutomaticTranferSwitchPanel.rfa | 2026-05-29 | 2026-08-18 | 58 | handler_assign | confirm_note:stored_full | N | N
72533 | 410_PF_HDPE_mSoventFitting_Welded | 2026-06-03 | 2026-07-14 | 30 | handler_assign | confirm_note:stored_full | N | N
72532 | 410_PF_HDPE_mRunningTrap_Standard | 2026-06-03 | 2026-08-14 | 53 | handler_assign | confirm_note:stored_full | N | N
72531 | 410_PF_HDPE_mQuadrupleDoubleBrandFitting88Deg_Welded | 2026-06-03 | 2026-08-14 | 53 | handler_assign | confirm_note:stored_full | N | N
72530 | 410_PF_HDPE_tDoubleConnectionBend90Deg_SlipJoint_VerticalForWallHungWC | 2026-06-02 | 2026-09-17 | 78 | handler_assign | confirm_note:stored_full | N | N
72529 | 410_PF_HDPE_mDoubleConnectionBend90Deg_HorizontalForWallHungWC | 2026-06-02 | 2026-06-16 | 11 | handler_assign | confirm_note:stored_full | N | N
72528 | 410_PF_HDPE_tDoubleConnectionBend90Deg_ForSleeve | 2026-06-02 | 2026-09-21 | 80 | handler_assign | confirm_note:stored_full | N | N
72527 | 410_PF_HDPE_eSegmentBend_Welded | 2026-06-02 | 2026-08-14 | 54 | handler_assign | confirm_note:stored_full | N | N
72526 | 410_PF_HDPE_eScrewCap | 2026-06-16 | 2026-07-14 | 21 | handler_assign | confirm_note:stored_full | N | N
72525 | 410_PF_HDPE_eRightOffsetBend90Deg_Standard_ForFloorStandingWC | 2026-06-02 | 2026-06-08 | 5 | handler_assign | status_resolved | N | N
72524 | 410_PF_HDPE_eConnectionBend90Deg_ForWallHungWC | 2026-06-02 | 2026-09-15 | 76 | handler_assign | confirm_note:stored_full | N | N
72523 | 410_PF_HDPE_eConnectionBend90Deg_Standard_ForSleeve | 2026-06-02 | 2026-06-05 | 4 | handler_assign | status_resolved | N | N
72522 | 410_PF_HDPE_eBend88DegWithLateralSupplementary_Standard_ForFloorStandingWC | 2026-06-02 | 2026-06-05 | 4 | handler_assign | status_resolved | N | N
72521 | 410_PF_HDPE_eConnectionBend88Deg_ForFloorStandingWC | 2026-06-02 | 2026-07-15 | 32 | handler_assign | confirm_note:stored_full | N | N
72519 | RLT_Symbol_Detail Item Setup | 2026-05-29 | 2026-06-04 | 5 | handler_assign | status_resolved | N | N
72496 | MEP_Revise 473_PF_CO_eShortRadiusFF_Soldered | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72495 | MEP_Revise 473_PF_CO_eOffset_M_F_Soldered | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | N | N
72494 | MEP_Revise 473_PF_CO_eLongRadius_Soldered | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72493 | MEP_Revise 473_PF_CO_eLongRadius_MFSoldered | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72492 | MEP_Revise 473_PF_CO_eElbowShortRadiusMF_Soldered | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | N | N
72491 | MEP_Revise 473_PF_CO_eElbowLongRadiusFF_Soldered | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:stored_full | N | N
72490 | MEP_Revise 473_PF_CO_eElbow180_Soldered | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:will_be_closed | N | N
72489 | MEP_Revise 473_PF_CO_eElbow45_MaleAndFemaleSoldered | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | N | N
72488 | MEP_Revise 473_PF_CO_eElbow45_FemaleAndFemaleSoldered | 2026-05-28 | 2026-07-16 | 36 | handler_assign | confirm_note:stored_full | N | N
72487 | MEP_Revise 473_PF_CO_eElbow_Reduce_Soldered | 2026-05-28 | 2026-06-29 | 23 | handler_assign | status_resolved | N | N
72486 | MEP_Revise 473_PF_CO_cEndCap_Soldered | 2026-05-28 | 2026-07-28 | 44 | handler_assign | confirm_note:stored_full | N | N
72485 | 434_PF_CO_Union_MapressGas | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | N | N
72484 | 434_PF_CO_eAdaptorBend_MapressAndThread | 2026-05-28 | 2026-06-09 | 9 | handler_assign | confirm_note:stored_full | N | N
72483 | 434_PF_CO_eAdaptorBend_MapressAndThreadFKMBlue | 2026-05-28 | 2026-07-29 | 45 | handler_assign | confirm_note:stored_full | N | N
72482 | 434_PF_CO_eAdaptorBend_MapressAndThreadGas | 2026-05-28 | 2026-06-24 | 20 | handler_assign | confirm_note:stored_full | N | N
72481 | 434_PF_CO_rReducerAdaptor_Mapress_WithMeplaFixAdaptor | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | N | N
72480 | 434_PF_CO_rReducerAdaptor_PlainEnd_WithMeplaFixAdaptor | 2026-05-28 | 2026-06-09 | 9 | handler_assign | confirm_note:stored_full | N | N
72479 | 434_PF_CO_uAdaptorUnion_Mapress | 2026-05-28 | 2026-08-20 | 61 | handler_assign | confirm_note:stored_full | N | N
72478 | 434_PF_CO_uAdaptorUnion_MapressAndFemaleThreadFKMBlue_WithNut | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | N | N
72471 | 434_PF_CO_uAdaptorUnion_MapressAndThread | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72468 | 434_PF_CO_uAdaptorUnion_MapressAndThreadFKMBlue | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | N | N
72467 | 434_PF_CO_uAdaptorUnion_MapressAndThreadGas | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full | N | N
72466 | 434_PF_CO_uAdaptorUnion_PlainEndAndThreadGas | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full | N | N
72465 | 434_PF_CO_uAdaptorUnion_PlainEnd_WithMeplaFix | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | N | N
72464 | 410_PF_GS_eAngleBend_1PushSocket_GMX | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | N | N
72461 | MEP_Revise 473_PA_WaterOilSeparators_WOSm | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full | N | N
72460 | MEP_Revise 473_PA_WaterOilSeparators_WOS | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72459 | MEP_Revise 473_PA_VAC_Outlet | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72458 | MEP_Revise 473_PA_SterileFilters_SFSeries_Flanged | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | N | N
72457 | MEP_Revise 473_PA_StainlessSteelFlexibleConnection | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | N | N
72456 | MEP_Revise 473_PA_StainlessSteel1WayValve | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | N | N
72455 | MEP_Revise 473_PA_SS_WeldedCondensateSeparators | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | N | N
72454 | MEP_Revise 473_PA_SS_PressureReducingValve_Flanged | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72453 | MEP_Revise 473_PA_SS_PressureGauge_AnalogueType | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72452 | MEP_Revise 473_PA_SS_HighPressureProcessFilters_Welded | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72451 | MEP_Revise 473_PA_SS_CouplingsFemale_Threaded | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72450 | MEP_Revise 473_PA_SS_AirHeader_6Connection | 2026-05-28 | 2026-07-24 | 42 | handler_assign | status_resolved | N | N
72449 | MEP_Revise 473_PA_SS_AirHeader_4Connection | 2026-05-28 | 2026-07-23 | 41 | handler_assign | status_resolved | N | N
72448 | MEP_Revise 473_PA_SingleZone_ValveBox | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72447 | MEP_Revise 473_PA_ShutOffValveBox_MultiConnection | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72446 | MEP_Revise 473_PA_SafetyValve | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72445 | MEP_Revise 473_PA_RectangularPressureRegulator | 2026-05-28 | 2026-08-25 | 64 | handler_assign | confirm_note:stored_full | N | N
72444 | MEP_Revise 473_PA_PressureGauge_ElectricalContactCodeA | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | N | N
72443 | MEP_Revise 473_PA_PneumaticManualDiaphragmValve | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | N | N
72442 | MEP_Revise 473_PA_PneumaticDiaphragmValveWithAlarm | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | N | N
72441 | MEP_Revise 473_PA_PneumaticButterflyValve_Welded | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | N | N
72440 | MEP_Revise 473_PA_PlasticBox_Air | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | N | N
72439 | MEP_Revise 473_PA_NRVValve | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | N | N
72438 | MEP_Revise 473_PA_N2OOutlet | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72436 | MEP_Revise 473_PA_MotorizedPneumaticDiaphragmValve_Welded | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72435 | MEP_Revise 473_PA_MembraneAirDryers | 2026-05-28 | 2026-08-24 | 63 | handler_assign | confirm_note:stored_full | N | N
72434 | MEP_Revise 473_PA_LockableLineBallValve_NIST | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72433 | MEP_Revise 473_PA_LockableLineBallValve_LVL20 | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72432 | MEP_Revise 473_PA_LockableLineBallValve_LVL10 | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72431 | MEP_Revise 473_PA_LineBallValve_LV10VF | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72430 | MEP_Revise 473_PA_LineBallValve_LV10_V | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72429 | MEP_Revise 473_PA_GasO2Outlet | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full | N | N
72428 | MEP_Revise 473_PA_GasN2_Outlet | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72427 | MEP_Revise 473_PA_Filters_Welded | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72426 | MEP_Revise 473_PA_Filters_Flanged | 2026-05-28 | 2026-08-17 | 58 | handler_assign | confirm_note:stored_full | N | N
72425 | MEP_Revise 473_PA_ElectronicMotorizedValve | 2026-05-28 | 2026-08-14 | 57 | handler_assign | confirm_note:stored_full | N | N
72424 | MEP_Revise 473_PA_ElectronicCondensateDrain | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | N | N
72422 | MEP_Revise 473_PA_CycloneSeparator_Standard | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full | N | N
72421 | MEP_Revise 473_PA_CS_PressureReducingValve_Flanged | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72420 | MEP_Revise 473_PA_CondensateDistributor12Branch_WOSCD | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72419 | MEP_Revise 473_PA_CondensateDistributor8Branch_WOSCD | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | N | N
72418 | MEP_Revise 473_PA_CondensateDistributor4Branch_WOSCD | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72417 | MEP_Revise 473_PA_CondensateDistributor2Branch_WOSCD | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72416 | MEP_Revise 473_PA_CompressedAirFilters_QDT | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72414 | MEP_Revise 473_PA_CompressedAirFilters_DDp | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72413 | MEP_Revise 473_PA_ClampedStraightSightGlass | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72412 | MEP_Revise 473_PA_Brass_CheckValve_Threaded | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72411 | MEP_Revise 473_PA_BR_AirReliefValve_Threaded | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72410 | MEP_Revise 473_PA_BR_3WayValveDN15toDN50_Threaded | 2026-05-28 | 2026-08-03 | 48 | handler_assign | confirm_note:stored_full | N | N
72409 | MEP_Revise 473_PA_BR_3WayMotorControlValve_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72408 | MEP_Revise 473_PA_BallValve_Threaded | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | N | N
72407 | MEP_Revise 473_PA_AutomaticMechanicalCondensateDrain | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:stored_full | N | N
72406 | MEP_Revise 473_PA_AutoDrainValve_FloatType_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72405 | MEP_Revise 473_PA_AirVentingFilters_Standard | 2026-05-28 | 2026-08-04 | 49 | handler_assign | confirm_note:stored_full | N | N
72404 | MEP_Revise 473_PA_AirRegulatorValve_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72403 | MEP_Revise 473_PA_AirPressureRegulator_Mapress | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72402 | MEP_Revise 473_PA_AirHeader_18Connection | 2026-05-28 | 2026-07-31 | 47 | handler_assign | confirm_note:will_be_closed | N | N
72401 | MEP_Revise 473_PA_AirHeader_16Connection | 2026-05-28 | 2026-07-31 | 47 | handler_assign | confirm_note:will_be_closed | N | N
72400 | MEP_Revise 473_PA_AirHeader_14Connection | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72399 | MEP_Revise 473_PA_AirHeader_12Connection | 2026-05-28 | 2026-07-30 | 46 | handler_assign | confirm_note:stored_full | N | N
72398 | MEP_Revise 473_PA_AirHeader_10Connection | 2026-05-28 | 2026-08-17 | 58 | handler_assign | confirm_note:stored_full | N | N
72397 | MEP_Revise 473_PA_AirHeader_8Connection | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72396 | MEP_Revise 473_PA_AGSSOutletType1L | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | N | N
72395 | MEP_Revise 473_PA_3WayMotorControlValve_Threaded | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | N | N
72394 | MEP_Revise 473_ME_ZoneWallUnit_HST200 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72393 | MEP_Revise 473_ME_ZoneWallUnit_HST100 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72392 | MEP_Revise 473_ME_ZoneWallUnit_CZ200 | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72391 | MEP_Revise 473_ME_VacuumPump | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72390 | MEP_Revise 473_ME_RefrigerationAirDryer_Threaded | 2026-05-28 | 2026-07-30 | 46 | handler_assign | status_resolved | N | N
72389 | MEP_Revise 473_ME_RefrigerationAirDryer_Flanged | 2026-05-28 | 2026-07-30 | 46 | handler_assign | status_resolved | N | N
72388 | MEP_Revise 473_ME_OxygenGenerators | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | N | N
72387 | MEP_Revise 473_ME_NitrogenGenerators | 2026-05-28 | 2026-07-28 | 44 | handler_assign | status_resolved | N | N
72386 | MEP_Revise 473_ME_MedicalAirCompressors_TankMounted | 2026-05-28 | 2026-07-27 | 43 | handler_assign | status_resolved | N | N
72385 | MEP_Revise 473_ME_MedicalAirCompressors_FloorMounted | 2026-05-28 | 2026-08-14 | 57 | handler_assign | confirm_note:stored_full | N | N
72384 | MEP_Revise 473_ME_IntensiveCareUnits_WallMounted_SMICareHD | 2026-05-28 | 2026-07-28 | 44 | handler_assign | status_resolved | N | N
72383 | MEP_Revise 473_ME_IntensiveCareUnits_WallMounted_SMICAREDS | 2026-05-28 | 2026-07-29 | 45 | handler_assign | status_resolved | N | N
72382 | MEP_Revise 473_ME_ICU_SMICAREDS | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72381 | MEP_Revise 473_ME_ICU_SMICare | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72380 | MEP_Revise 473_ME_ICU_EurocareD | 2026-05-28 | 2026-08-18 | 59 | handler_assign | confirm_note:stored_full | N | N
72379 | MEP_Revise 473_ME_ICU_Eurocare | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72378 | MEP_Revise 473_ME_HeatRegenerationAdsorptionDryers | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72377 | MEP_Revise 473_ME_HeatlessRegenerationAdsorptionDryers_ActivatedCarbonTower | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72376 | MEP_Revise 473_ME_HeatlessRegenerationAdsorptionDryers | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72375 | MEP_Revise 473_ME_ExternalHeatRecoveryUnits | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72374 | MEP_Revise 473_ME_DryVacuumPump | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72373 | MEP_Revise 473_ME_DesiccantAdsorptionCompressedAirDryers | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | N | N
72372 | MEP_Revise 473_ME_CylinderTank_NoSystem | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | N | N
72371 | MEP_Revise 473_ME_CompactH2O2DecontaminationAirlock | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | N | N
72370 | MEP_Revise 473_ME_BottleFillingPlant | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | N | N
72369 | MEP_Revise 473_ME_BHU_Vertical | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | N | N
72368 | MEP_Revise 473_ME_BHU_SC2015 | 2026-05-28 | 2026-08-12 | 55 | handler_assign | confirm_note:stored_full | N | N
72367 | MEP_Revise 473_ME_BHU_HY2017DS | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | N | N
72366 | MEP_Revise 473_ME_BHU_HY2017D | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | N | N
72365 | MEP_Revise 473_ME_BHU_HY2017 | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | N | N
72364 | MEP_Revise 473_ME_BHU_DK2014M | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | N | N
72363 | MEP_Revise 473_ME_BHU_DK2014 | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | N | N
72362 | MEP_Revise 473_ME_AutomatedH2O2AirlockAccessible | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | N | N
72361 | MEP_Revise 473_ME_AreaAlarmPanel | 2026-05-28 | 2026-07-31 | 47 | handler_assign | status_resolved | N | N
72360 | MEP_Revise 473_ME_AirReceiverTank | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | N | N
72359 | MEP_Revise 473_ME_AirPurifiers | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | N | N
72358 | MEP_Revise 473_ME_AirDryer_Vertical | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | N | N
72357 | MEP_Revise 473_ME_AirDryer | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full | N | N
72356 | MEP_Revise 473_ME_ActivatedCarbonTower | 2026-05-28 | 2026-08-27 | 66 | handler_assign | confirm_note:stored_full | N | N
72355 | MEP_Revise 473_EF_TableControlUnit | 2026-05-28 | 2026-07-08 | 30 | handler_assign | status_resolved | N | N
72354 | MEP_Revise 473_EF_SocketforHandPushButton | 2026-05-28 | 2026-08-28 | 67 | handler_assign | confirm_note:stored_full | N | N
72353 | MEP_Revise 473_EF_SocketForCordedPushButton_WallSurface | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | N | N
72352 | MEP_Revise 473_EF_RemoteControlModules | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | N | N
72351 | MEP_Revise 473_EF_ElectronicBuzzer_WallSurface | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | N | N
72350 | MEP_Revise 473_EF_DoorUnit | 2026-05-28 | 2026-08-06 | 51 | handler_assign | confirm_note:stored_full | N | N
72349 | MEP_Revise 473_EF_CallTranferUnitForCorridors | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72348 | MEP_Revise 473_EF_CallDisplayUnit | 2026-05-28 | 2026-07-09 | 31 | handler_assign | status_resolved | N | N
72347 | MEP_Revise 473_EF_BiomedicalCallPlugandSocket | 2026-05-28 | 2026-10-01 | 91 | handler_assign | confirm_note:stored_full | N | N
72346 | MEP_Revise 473_EF_BathroomCallUnit_PushButton | 2026-05-28 | 2026-08-19 | 60 | handler_assign | confirm_note:stored_full | N | N
72345 | MEP_Revise 473_EF_BathroomCallUnit_PullCord | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | N | N
72344 | MEP_Revise 473_PF_SS_uClampConnectorWithWeldedConnection | 2026-05-28 | 2026-06-30 | 24 | handler_assign | status_resolved | N | N
72343 | MEP_Revise 473_PF_SS_uClampConnector | 2026-05-28 | 2026-07-01 | 25 | handler_assign | status_resolved | N | N
72342 | MEP_Revise 473_PF_SS_tTee_Welded | 2026-05-28 | 2026-07-29 | 45 | handler_assign | confirm_note:stored_full | N | N
72341 | MEP_Revise 473_PF_CO_uOffsetFF_Soldered | 2026-05-28 | 2026-07-14 | 34 | handler_assign | confirm_note:stored_full | N | N
72340 | MEP_Revise 473_PF_CO_uCoupling_Soldered | 2026-05-28 | 2026-08-07 | 52 | handler_assign | confirm_note:will_be_closed | N | N
72339 | MEP_Revise 473_PF_CO_tTee_Reducing_FemaleSoldered | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | N | N
72338 | MEP_Revise 473_PF_CO_tEqualTee_FemaleSoldered | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | N | N
72337 | MEP_Revise 473_PF_CO_rReducerMF_Soldered | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72336 | MEP_Revise 473_PF_CO_rReducer_FemaleSoldered | 2026-05-28 | 2026-06-29 | 23 | handler_assign | status_resolved | N | N
72335 | Revise the RFA library for the MED system. | 2026-05-28 |  |  | handler_assign | none | N | Y | missing_end
72334 | MEP_Revise 474_SP_GE_UprightCover | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | N | N
72333 | MEP_Revise 474_SP_GE_Upright | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | N | N
72332 | MEP_Revise 474_SP_GE_SprayNozzles | 2026-05-28 | 2026-08-13 | 56 | handler_assign | confirm_note:stored_full | N | N
72331 | MEP_Revise 474_SP_GE_PendentCover | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | N | N
72330 | MEP_Revise 474_SP_GE_Pendent | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | N | N
72329 | MEP_Revise 474_SP_GE_HVSprayNozzles | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | N | N
72328 | MEP_Revise 474_SP_GE_HorizontalSideWall | 2026-05-28 | 2026-07-27 | 43 | handler_assign | confirm_note:stored_full | N | N
72327 | MEP_Revise 474_SP_GE_DoubleSprinkler | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | N | N
72326 | MEP_Revise 474_SP_FoamNozzle_Upright | 2026-05-28 | 2026-08-11 | 54 | handler_assign | confirm_note:stored_full | N | N
72325 | MEP_Revise 474_SP_FoamNozzle_Pendent | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | N | N
72324 | MEP_Revise 474_SP_FM200_DischargeNozzle | 2026-05-28 | 2026-08-10 | 53 | handler_assign | confirm_note:stored_full | N | N
72323 | MEP_Revise 474_SP_FM200_360RadialNozzle_4Port | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | N | N
72322 | MEP_Revise 474_SP_FM200_360RadialNozzle_1Port | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | N | N
72321 | MEP_Revise 474_SP_FM200_180RadialNozzle_2Port | 2026-05-28 | 2026-08-05 | 50 | handler_assign | confirm_note:stored_full | N | N
72320 | MEP_Revise 474_SP_DischargeNozzle_CO2 | 2026-05-28 | 2026-07-13 | 33 | handler_assign | confirm_note:stored_full | N | N
72319 | MEP_Revise 474_PROMAT_Vertical_WallMount | 2026-05-28 | 2026-06-25 | 21 | handler_assign | status_resolved | N | N
72318 | MEP_Revise 474_PROMAT_Horizontal_WallMount | 2026-05-28 | 2026-06-25 | 21 | handler_assign | status_resolved | N | N
72317 | MEP_Revise 474_PROMAT_Horizontal_Vertical_WallMount | 2026-05-28 | 2026-08-31 | 68 | handler_assign | confirm_note:stored_full | N | N
72316 | MEP_Revise 474_PROMAT_4Sided_Vertical_CeilingMount | 2026-05-28 | 2026-06-23 | 19 | handler_assign | status_resolved | N | N
72315 | MEP_Revise 474_PROMAT_4Sided_Horizontal_Vertical_CeilingMount | 2026-05-28 | 2026-06-23 | 19 | handler_assign | status_resolved | N | N
72313 | MEP_Revise 474_PROMAT_4Sided_Horizontal_CeilingMount | 2026-05-28 | 2026-06-24 | 20 | handler_assign | status_resolved | N | N
72302 | MEP_Revise 474_PA_WaterMeter | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | N | N
72301 | MEP_Revise 474_PA_WaterflowSwitches | 2026-05-27 | 2026-09-11 | 78 | handler_assign | confirm_note:stored_full | N | N
72300 | MEP_Revise 474_PA_SwingCheckValve_Grooved | 2026-05-27 | 2026-06-18 | 17 | handler_assign | status_resolved | N | N
72299 | MEP_Revise 474_PA_StoneCatcher | 2026-05-27 | 2026-08-17 | 59 | handler_assign | confirm_note:stored_full | N | N
72298 | MEP_Revise 474_PA_SS_CompoundPressureGauge | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | N | N
72297 | MEP_Revise 474_PA_SolenoidValve | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | N | N
72296 | MEP_Revise 474_PA_SightGlasses | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | N | N
72295 | MEP_Revise 474_PA_ShutoffValve_Motorized | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | N | N
72294 | MEP_Revise 474_PA_SelectorValve_CO2 | 2026-05-27 | 2026-08-11 | 55 | handler_assign | confirm_note:stored_full | N | N
72293 | MEP_Revise 474_PA_SafetyValve | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | N | N
72292 | MEP_Revise 474_PA_SafertyReliefValve_CO2 | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | N | N
72290 | MEP_Revise 474_PA_RubberExpansionJoint_Threaded | 2026-05-27 | 2026-08-25 | 65 | handler_assign | confirm_note:stored_full | N | N
72289 | MEP_Revise 474_PA_RubberExpansionJoint_Flanged | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | N | N
72288 | MEP_Revise 474_PA_RiserCheckValve | 2026-05-27 | 2026-09-03 | 72 | handler_assign | confirm_note:stored_full | N | N
72287 | MEP_Revise 474_PA_PressureSwitch_FM200 | 2026-05-27 | 2026-08-05 | 51 | handler_assign | confirm_note:stored_full | N | N
72286 | MEP_Revise 474_PA_PressureSensor | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | N | N
72285 | MEP_Revise 474_PA_PressureReliefValve | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | N | N
72284 | MEP_Revise 474_PA_PressureReliefControlValve | 2026-05-27 | 2026-06-19 | 18 | handler_assign | status_resolved | N | N
72283 | MEP_Revise 474_PA_PressureReducingControlValve_Groove | 2026-05-27 | 2026-08-13 | 57 | handler_assign | confirm_note:stored_full | N | N
72282 | MEP_Revise 474_PA_PressureOperatedDirectionalValve_CO2 | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | N | N
72281 | MEP_Revise 474_PA_PressureMeter | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72280 | MEP_Revise 474_PA_PressureGauge_withBallValve | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72279 | MEP_Revise 474_PA_OS&YGateValves_GrooveAndFlange | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | N | N
72277 | MEP_Revise 474_PA_NRSOS&YGateValvesGrooveandFlange | 2026-05-27 | 2026-09-11 | 78 | handler_assign | confirm_note:stored_full | N | N
72276 | MEP_Revise 474_PA_ManualPneumaticActuator_FM200 | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72275 | MEP_Revise 474_PA_ManuallyActuatedBallValve_CO2 | 2026-05-27 | 2026-06-25 | 22 | handler_assign | status_resolved | N | N
72274 | MEP_Revise 474_PA_ManifoldCheckValve_FM200 | 2026-05-27 | 2026-06-25 | 22 | handler_assign | status_resolved | N | N
72273 | MEP_Revise 474_PA_LevelControlValves_Grooved | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:will_be_closed | N | N
72272 | MEP_Revise 474_PA_LevelControlValves_Flange | 2026-05-27 | 2026-07-17 | 38 | handler_assign | confirm_note:stored_full | N | N
72271 | MEP_Revise 474_PA_HydrantGateValve | 2026-05-27 | 2026-06-23 | 20 | handler_assign | status_resolved | N | N
72270 | MEP_Revise 474_PA_HighPressureRiserCheckValve | 2026-05-27 | 2026-06-25 | 22 | handler_assign | status_resolved | N | N
72269 | MEP_Revise 474_PA_HighPressureCheckValve | 2026-05-27 | 2026-06-24 | 21 | handler_assign | status_resolved | N | N
72268 | MEP_Revise 474_PA_GateValve | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:will_be_closed | N | N
72267 | MEP_Revise 474_PA_FootValve | 2026-05-27 | 2026-06-24 | 21 | handler_assign | status_resolved | N | N
72266 | MEP_Revise 474_PA_FM200_DischagePressureSwitch | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72265 | MEP_Revise 474_PA_FireLockAlarmCheckValve | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72264 | MEP_Revise 474_PA_FireLockBallValve | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72263 | MEP_Revise 474_PA_DryPilotActuator_ | 2026-05-27 | 2026-07-28 | 45 | handler_assign | confirm_note:stored_full | N | N
72262 | MEP_Revise 474_PA_DryAccelerator | 2026-05-27 | 2026-07-22 | 41 | handler_assign | confirm_note:stored_full | N | N
72261 | MEP_Revise 474_PA_DoubleDoorCheckValve | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | N | N
72260 | MEP_Revise 474_PA_FireHoseAngleValveWithCap | 2026-05-27 | 2026-08-13 | 57 | handler_assign | confirm_note:stored_full | N | N
72259 | MEP_Revise 474_PA_CurrentDetector_ZoneCheck | 2026-05-27 | 2026-08-12 | 56 | handler_assign | confirm_note:stored_full | N | N
72258 | MEP_Revise 474_PA_WaterFlowDetector | 2026-05-27 | 2026-06-11 | 12 | handler_assign | status_resolved | N | N
72257 | MEP_Revise 474_PA_CS_GateValveWithElectricActuator | 2026-05-27 | 2026-08-21 | 63 | handler_assign | confirm_note:stored_full | N | N
72256 | MEP_Revise 474_PA_CS_BalancingValve_Flanged | 2026-05-27 | 2026-06-15 | 14 | handler_assign | status_resolved | N | N
72255 | MEP_Revise 474_PA_CheckValveAlternateWetDrySystem | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | N | N
72254 | MEP_Revise 474_PA_CheckValve | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | N | N
72253 | MEP_Revise 474_PA_ButterflyValve | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | N | N
72252 | MEP_Revise 474_PA_BrassBodyBallValves_Threaded | 2026-05-27 | 2026-07-02 | 27 | handler_assign | confirm_note:stored_full | N | N
72251 | MEP_Revise 474_PA_BallValvesThreadandThread | 2026-05-27 | 2026-07-31 | 48 | handler_assign | confirm_note:stored_full | N | N
72250 | MEP_Revise 474_PA_BallValves_GrooveAndGroove | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | N | N
72249 | MEP_Revise 474_PA_BallValve | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | N | N
72248 | MEP_Revise 474_PA_AutomaticConcentrateControlValve_Foam | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72247 | MEP_Revise 474_PA_AlarmTestModuleGrooveEnd | 2026-05-27 | 2026-07-24 | 43 | handler_assign | confirm_note:stored_full | N | N
72246 | MEP_Revise 474_PA_AlarmCheckValve_Preaction | 2026-05-27 | 2026-08-14 | 58 | handler_assign | confirm_note:stored_full | N | N
72245 | MEP_Revise 474_PA_AlarmCheckValve_European | 2026-05-27 | 2026-08-21 | 63 | handler_assign | confirm_note:stored_full | N | N
72244 | MEP_Revise 474_PA_AlarmCheckValve_Dry | 2026-05-27 | 2026-06-11 | 12 | handler_assign | status_resolved | N | N
72243 | MEP_Revise 474_PF_StainlessSteel_FlexibleCoupling_Grooved | 2026-05-27 | 2026-08-07 | 53 | handler_assign | confirm_note:stored_full | N | N
72242 | MEP_Revise 474_PF_SS_sHaftCoupling | 2026-05-27 | 2026-06-09 | 10 | handler_assign | status_resolved | N | N
72241 | MEP_Revise 474_PF_SS_eUnionElbow_Threaded | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | N | N
72240 | MEP_Revise 474_PF_GalvanizedSteel_NippleReducer_Threaded | 2026-05-27 | 2026-06-04 | 7 | handler_assign | status_resolved | N | N
72239 | MEP_Revise 474_PF_DuctileIron_SmallReducer_Thread | 2026-05-27 | 2026-06-05 | 8 | handler_assign | status_resolved | N | N
72238 | MEP_Revise 474_PF_DuctileIron_DrainElbow_Grooved | 2026-05-27 | 2026-06-05 | 8 | handler_assign | status_resolved | N | N
72237 | MEP_Revise 474_PF_DuctileIron_CapFemale_Thread | 2026-05-27 | 2026-06-04 | 7 | handler_assign | status_resolved | N | N
72236 | MEP_Revise 474_PF_CS_xCross_Grooved | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | N | N
72235 | MEP_Revise 474_PF_CS_wTrueWye_Grooved | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | N | N
72234 | MEP_Revise 474_PF_CS_uAdaptorNipple_Grooved | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | N | N
72233 | MEP_Revise 474_PF_CS_tTee_Grooved | 2026-05-27 | 2026-06-03 | 6 | handler_assign | status_resolved | N | N
72232 | MEP_Revise 474_PF_CS_tSprinkerTeeCoupling_Grooved_Threaded | 2026-05-27 | 2026-06-02 | 5 | handler_assign | status_resolved | N | N
72231 | MEP_Revise 474_PF_CS_tOutletReducingCouplingTee_Grooved | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | N | N
72229 | MEP_Revise 474_PF_CS_rEccentricReducer_Grooved | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | N | N
72228 | MEP_Revise 474_PF_CS_rConcentricReducer_Grooved | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | N | N
72227 | MEP_Revise 474_PF_CS_fConnection_Coupling_FireLockRigid | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | N | N
72226 | MEP_Revise 474_PF_CS_fConnection_Coupling_FireLockEZRigid | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | N | N
72225 | MEP_Revise 474_PF_CS_eElbowEndOfRun_Grooved | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | N | N
72224 | MEP_Revise 474_PF_CS_eElbow_Grooved | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | N | N
72223 | MEP_Revise 474_PF_CS_cCap_Grooved | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | N | N
72222 | MEP_Revise 474_PF_CI_uUnion_Threaded | 2026-05-27 | 2026-07-14 | 35 | handler_assign | confirm_note:stored_full | N | N
72221 | MEP_Revise 474_PF_CastIron_TeeReducing_Thread | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full | N | N
72220 | MEP_Revise 474_PF_CastIron_Tee_Thread | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full | N | N
72219 | MEP_Revise 474_PF_CastIron_SocketUnion_Threaded | 2026-05-27 | 2026-07-06 | 29 | handler_assign | confirm_note:stored_full | N | N
72218 | MEP_Revise 474_PF_CastIron_Reducer_Threaded | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | N | N
72217 | MEP_Revise 474_PF_Castiron_HexNipple | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | N | N
72216 | MEP_Revise 474_PF_CastIron_Elbow_Threaded_ShortBend | 2026-05-27 | 2026-07-13 | 34 | handler_assign | confirm_note:stored_full | N | N
72215 | MEP_Revise 474_PF_Castiron_Cross_Thread | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | N | N
72214 | MEP_Revise 474_PF_CastIron_Cap_Threaded | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | N | N
72213 | MEP_Revise 474_PF_CarbonSteel_TeeReducing_Grooved | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | N | N
72212 | MEP_Revise 474_PF_CarbonSteel_TeeGroovedEnd_Standard | 2026-05-27 | 2026-09-15 | 80 | handler_assign | confirm_note:stored_full | N | N
72211 | MEP_Revise 474_PF_CS_tReducingLateralTee_Grooved | 2026-05-27 | 2026-07-03 | 28 | handler_assign | confirm_note:stored_full | N | N
72210 | MEP_Revise 474_PF_CarbonSteel_OutletTeeReducing_Threaded | 2026-05-27 | 2026-06-23 | 20 | handler_assign | confirm_note:stored_full | N | N
72209 | MEP_Revise 474_PF_CarbonSteel_OutletTeeReducing_Coupling | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full | N | N
72208 | MEP_Revise 474_PF_CarbonSteel_LateralThread_Standard | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full | N | N
72207 | MEP_Revise 474_PF_CarbonSteel_LateralTee_Grooved | 2026-05-27 | 2026-07-23 | 42 | handler_assign | confirm_note:stored_full | N | N
72206 | MEP_Revise 474_PF_CarbonSteel_AdapterNipple_Flanged | 2026-05-27 | 2026-07-16 | 37 | handler_assign | confirm_note:stored_full | N | N
72205 | MEP_Revise 474_PF_CarbonSteel_LowProfileSprinklerTee_Threaded | 2026-05-27 | 2026-07-15 | 36 | handler_assign | confirm_note:stored_full | N | N
72204 | 420_PF_CS_fConnectionFlanged_Welded | 2026-05-28 | 2026-06-04 | 6 | handler_assign | confirm_note:stored_full | N | N
72203 | 420_PF_CS_rReducer_Welded | 2026-05-28 | 2026-06-03 | 5 | handler_assign | confirm_note:stored_full | N | N
72202 | 420_PF_CS_sTap_Welded | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | N | N
72201 | 420_PF_CS_tTee_Welded | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | N | N
72200 | 420_PF_CS_uUnion_Welded | 2026-05-28 | 2026-06-01 | 3 | handler_assign | status_resolved | N | N
72199 | 420_PF_CS_xCross_Welded | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | N | N
72198 | 420_PF_CO_eElbow_Soldered | 2026-05-28 | 2026-06-08 | 8 | handler_assign | confirm_note:stored_full | N | N
72196 | 420_PF_CO_cCap_Soldered | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | N | N
72195 | 420_PF_Brass_ThreeWayEqualTee_Compression | 2026-05-28 | 2026-06-19 | 17 | handler_assign | confirm_note:stored_full | N | N
72177 | 420_PF_Copper_Elbow.rfa | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | N | N
72176 | 420_PF_MapressCarbonSteel_Cap_SlipJoin | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full | N | N
72175 | 420_PF_MapressCarbonSteel_Cross_SlipJoin | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full | N | N
72174 | 420_PF_MapressCarbonSteel_Elbow_SlipJoin | 2026-05-28 | 2026-09-10 | 76 | handler_assign | confirm_note:stored_full | N | N
72173 | 420_PF_MapressCarbonSteel_FlangeAdaptor_SlipJoin | 2026-05-28 | 2026-07-17 | 37 | handler_assign | confirm_note:stored_full | N | N
72172 | 420_PF_MapressCarbonSteel_SocketAdaptor_SlipJoin | 2026-05-28 | 2026-07-23 | 41 | handler_assign | confirm_note:stored_full | N | N
72171 | 420_PF_MapressCarbonSteel_SocketFlangeAdaptor_SlipJoin | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | N | N
72170 | 420_PF_MapressCarbonSteel_Tee_SlipJoin | 2026-05-28 | 2026-06-22 | 18 | handler_assign | confirm_note:stored_full | N | N
72169 | 420_PF_MapressCarbonSteel_Transition_SlipJoin | 2026-05-28 | 2026-07-17 | 37 | handler_assign | confirm_note:stored_full | N | N
72168 | 420_PF_MapressCarbonSteel_Union_SlipJoin | 2026-05-28 | 2026-07-22 | 40 | handler_assign | confirm_note:stored_full | N | N
72167 | 420_PF_PE_eElbow.rfa | 2026-05-28 | 2026-06-15 | 13 | handler_assign | confirm_note:stored_full | N | N
72158 | Revise the RFA library for the HGR system | 2026-05-27 | 2026-10-01 | 92 | handler_assign | status_closed | N | N
72157 | Revise the RFA library for the KLT system | 2026-05-27 | 2026-10-01 | 92 | handler_assign | status_closed | N | N
72156 | Revise the RFA library for the HZG system | 2026-05-27 | 2026-10-01 | 92 | handler_assign | status_closed | N | N
72136 | Revise the RFA library for the ELT system. | 2026-05-25 |  |  | handler_assign | none | N | Y | missing_end
72130 | Annotation_Platform_Deploy the Upload and Download Feature | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | N | N
72129 | Annotation_Platform_Integrate the change proposal | 2026-05-25 | 2026-05-27 | 3 | handler_assign | status_resolved | N | N
72116 | KLT_LPH8_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | N | N
72115 | KLT_LPH5_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | N | N
72114 | KLT_LPH3_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | N | N
72113 | HZG_LPH3_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | N | N
72112 | HZG_LPH5_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | N | N
72111 | HZG_LPH8_Sample Layout_Multiple Scales | 2026-05-25 | 2026-05-29 | 5 | handler_assign | status_resolved | N | N
72106 | 410_PF_HDPE_eBend_Welded | 2026-06-02 | 2026-08-14 | 54 | handler_assign | confirm_note:stored_full | N | N
72105 | 410_PF_HDPE_eBend90Deg_Reducer_Welded | 2026-05-29 | 2026-07-15 | 34 | handler_assign | confirm_note:stored_full | N | N
72104 | 410_PF_HDPE_cThreadedConnectorWithScrewCap | 2026-05-29 | 2026-07-14 | 33 | handler_assign | confirm_note:stored_full | N | N
72103 | 410_PF_HDPE_cProtectionCapForPipeEnd_Standard | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | N | N
72102 | 410_PF_HDPE_cProtectionCap | 2026-05-29 | 2026-07-14 | 33 | handler_assign | confirm_note:stored_full | N | N
72101 | 410_PF_GS_xReducingDoubleBranches_3PushSocket_GMX | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | N | N
72100 | 410_PF_GS_xDoubleCorrnerBranches_3PushSocket_GMX | 2026-05-29 | 2026-07-27 | 42 | handler_assign | confirm_note:stored_full | N | N
72099 | Annotation_General_BEP_Aquire and Signoff V000_Hanh Pham | 2026-05-22 | 2026-06-05 | 11 | handler_assign | status_resolved | N | N
72098 | Annotation_General_BEP_Aquire and Signoff V000_Sang Duong | 2026-05-22 | 2026-06-05 | 11 | handler_assign | status_resolved | N | N
72097 | Annotation_General_BEP_Aquire and Signoff V000_Nhut Le | 2026-05-22 | 2026-06-01 | 7 | handler_assign | status_resolved | N | N
72096 | Annotation_General_BEP_Aquire and Signoff V000_Thuong Huynh | 2026-05-22 | 2026-05-29 | 6 | handler_assign | status_resolved | N | N
72095 | 410_PF_GS_uUnion_2PushSocket_GMX | 2026-05-29 | 2026-07-27 | 42 | handler_assign | confirm_note:stored_full | N | N
72094 | Annotation_General_BEP_Aquire and Signoff V000_Lam Truong | 2026-05-22 | 2026-06-04 | 10 | handler_assign | status_resolved | N | N
72093 | 410_PF_GS_uTranstiontoCastIron_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | N | N
72092 | 410_PF_GS_uTransitionSMLtoGMX_1PushSocket | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | N | N
72091 | 410_PF_GS_uSpigottoPlastic_1PushSocket_GMX | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | N | N
72090 | 410_PF_GS_uLongCleaningOpening_NoSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | N | N
72089 | 410_PF_GS_uLongUnion_1PushSocket_GMX | 2026-05-29 | 2026-07-07 | 28 | handler_assign | confirm_note:stored_full | N | N
72088 | 410_PF_GS_uLongCleaningOpening_1PushSocket_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | N | N
72087 | 410_PF_GS_uGutterPipes_1PushSocket_GMX | 2026-06-17 | 2026-07-14 | 20 | handler_assign | confirm_note:stored_full | N | N
72086 | 410_PF_GS_uBends_1PushSocket_GMX | 2026-06-01 | 2026-06-15 | 11 | handler_assign | confirm_note:stored_full | N | N
72085 | 410_PF_GS_tTransitionBranch45DegTee_2PushSocket_GMX | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full | N | N
72084 | 410_PF_GS_tTeeBranches_2PushSocket_GMX | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | N | N
72083 | 410_PF_GS_tSingleBranches_45Deg_NoSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | N | N
72082 | 410_PF_GS_tSingleBranchesTee_2PushSocketAndSpigot_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | N | N
72081 | 410_PF_GS_tReducingSingleBranches45Deg_1BushSocket_GMX | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | N | N
72080 | 410_PF_GS_rTransitiontoCastIron_PushSocket_GMX | 2026-05-29 | 2026-08-17 | 57 | handler_assign | confirm_note:stored_full | N | N
72079 | 410_PF_GS_rConcentricOptimiser_1PushSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | N | N
72078 | 410_PF_GS_rAdapterEccentric_1PushSocket_GMX | 2026-05-29 | 2026-09-30 | 89 | handler_assign | confirm_note:stored_full | N | N
72077 | 410_PF_GS_rAdapterConcentric_1PushSocket_GMX | 2026-05-29 | 2026-06-10 | 9 | handler_assign | confirm_note:stored_full | N | N
72076 | 410_PF_GS_rAdapterConcentricSpigot_1PushSocket_GMX | 2026-05-29 | 2026-08-19 | 59 | handler_assign | confirm_note:task_completed_closed | N | N
72074 | 430_DA_FlexibleConnection_Rectangular.rfa | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full | N | N
72073 | 430_DA_FireProtectionDamper_Round_FLIVE.rfa | 2026-05-26 | 2026-07-13 | 35 | handler_assign | confirm_note:stored_full | N | N
72072 | 430_DA_FireInsulationSheets_Promat_L90.rfa | 2026-05-26 | 2026-06-19 | 19 | handler_assign | confirm_note:stored_full | N | N
72071 | 430_DA_FireInsulationSheets_Fitting_Promat_L90.rfa | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full | N | N
72070 | 430_DA_FireDampers_FireProtectionValve_FV_EU.rfa | 2026-05-25 | 2026-07-23 | 44 | handler_assign | confirm_note:stored_full | N | N
72069 | 430_DA_FireDampers_CommercialKitchens_KA_EU.rfa | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full | N | N
72068 | 430_DA_FireDampersForCeiling_KU_K30.rfa | 2026-05-25 | 2026-07-08 | 33 | handler_assign | confirm_note:stored_full | N | N
72067 | 430_DA_PressureOverflowElements.rfa | 2026-05-26 | 2026-08-31 | 70 | handler_assign | confirm_note:stored_full | N | N
72066 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFC | 2026-05-25 | 2026-09-18 | 85 | handler_assign | confirm_note:stored_full | N | N
72065 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowVFL.rfa | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full | N | N
72064 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRNEx.rfa | 2026-05-25 | 2026-07-09 | 34 | handler_assign | confirm_note:stored_full | N | N
72063 | 430_DA_ConstantVolumeFlowControl_Round_ConstantFlowRN.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | N | N
72062 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowENEx.rfa | 2026-05-25 | 2026-07-06 | 31 | handler_assign | confirm_note:stored_full | N | N
72061 | 430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowEN.rfa | 2026-05-25 | 2026-07-01 | 28 | handler_assign | confirm_note:stored_full | N | N
72060 | 430_DA_CircularSilencers_CS.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | N | N
72059 | 410_PF_GS_mSBendTrap_1PushSocket_GMX | 2026-06-17 | 2026-06-19 | 3 | handler_assign | status_resolved | N | N
72058 | 430_DA_CircularSilencers_CB.rfa | 2026-05-25 | 2026-07-13 | 36 | handler_assign | confirm_note:stored_full | N | N
72057 | 430_DA_CircularSilencers_CA_100.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | N | N
72056 | 430_DA_CircularSilencers_CA_050.rfa | 2026-05-25 | 2026-07-10 | 35 | handler_assign | confirm_note:stored_full | N | N
72055 | 430_DA_AirtightLouverDamper.rfa | 2026-05-25 | 2026-06-24 | 23 | handler_assign | confirm_note:stored_full | N | N
72054 | 430_ME_FanCoilUnit_WithPlenumBox_ThreeConnector_Standard.rfa | 2026-05-22 | 2026-05-26 | 3 | handler_assign | status_resolved | N | N
72053 | 410_PF_GS_mOptimisationPart_1PushSocket | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | N | N
72052 | 410_PF_GS_uGutterRound_SocketAndStandard | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full | N | N
72051 | 410_PF_GS_eReductionAngleBend_1PushSocket_GMX | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | N | N
72050 | 410_PF_GS_eReductionAngleBendShort_1PushSocket_GMX | 2026-06-17 | 2026-07-08 | 16 | handler_assign | confirm_note:stored_full | N | N
72049 | 410_PF_GS_eNarrowBend_1PushSocketAndTightRadius_GMX | 2026-06-17 | 2026-08-03 | 34 | handler_assign | confirm_note:stored_full | N | N
72048 | 410_PF_GS_eBend_NoSocket_GMX | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | N | N
72046 | 410_PF_GS_eBend_1PushSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | N | N
72043 | 410_PF_GS_eBendWithCalm_1PushSocket_GMX | 2026-05-29 | 2026-07-06 | 27 | handler_assign | confirm_note:stored_full | N | N
72042 | 410_PF_GS_eBasinConnector_1PushSocket_GMX | 2026-05-29 | 2026-06-04 | 5 | handler_assign | confirm_note:stored_full | N | N
72041 | 410_PF_GS_eAngleBend_1PushShortSocket_GMX | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | N | N
72040 | 410_PF_GS_cSealingPlugsWithVentilationSlots_PushOnJoint | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | N | N
72039 | 410_SE_FireCollar_Vertical | 2026-05-29 | 2026-06-08 | 7 | handler_assign | status_resolved | N | N
72038 | Revise the RFA library for the RLT system | 2026-05-22 |  |  | handler_assign | none | N | Y | missing_end
72037 | 410_SE_FireCollar_Horizontal | 2026-05-29 | 2026-09-15 | 78 | handler_assign | confirm_note:stored_full | N | N
72035 | 410_PF_GS_cFrogFlap_Socket_GMX | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | N | N
72032 | 410_PF_fHDPE_LooseFlange | 2026-06-17 | 2026-07-27 | 29 | handler_assign | confirm_note:stored_full | N | N
72025 | 410_PF_eSweptBendLong_Medium_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
72024 | 410_PF_EPDM_mKonfixConnector_PushOnJoint | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | N | N
72023 | 410_PF_DI_tDoubleSocketTee_PushOnJoint_WithLevelInvertFlangedBranch | 2026-05-29 | 2026-08-12 | 54 | handler_assign | confirm_note:stored_full | N | N
72022 | 410_PF_DI_uUnion_Socket | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | N | N
72021 | 410_PF_DI_uUnionFlange_RFType | 2026-05-29 | 2026-07-07 | 28 | handler_assign | confirm_note:will_be_closed | N | N
72020 | 410_PF_DI_uFlangeAdaptor | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | N | N
72019 | 410_PF_DI_uAdaptorRestrained_Flanged | 2026-06-01 | 2026-06-22 | 16 | handler_assign | confirm_note:stored_full | N | N
72018 | 410_PF_DI_tTee_Socket | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
72017 | 410_PF_DI_tTee_Flanged | 2026-05-29 | 2026-08-13 | 55 | handler_assign | confirm_note:stored_full | N | N
72016 | 410_PF_DI_tTee_SocketAndLevelInvertFlangedBranch | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
72015 | 410_PF_DI_tTee_SocketAndFlangedBranch | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | N | N
72014 | 410_PF_DI_tLevelInvertTee_Flanged | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | N | N
72013 | 410_PF_DI_rTapper_Socket | 2026-05-29 | 2026-07-03 | 26 | handler_assign | confirm_note:stored_full | N | N
72012 | 410_PF_DI_rTapper_Flanged | 2026-05-29 | 2026-07-28 | 43 | handler_assign | confirm_note:stored_full | N | N
72011 | 410_PF_DI_fFlange_Spigot | 2026-05-29 | 2026-06-05 | 6 | handler_assign | status_resolved | N | N
72010 | 410_PF_DI_uConnector_FlangedAndSocket | 2026-05-29 | 2026-06-05 | 6 | handler_assign | status_resolved | N | N
72009 | 410_PF_DI_rFlangedCover | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | N | N
72008 | 410_PF_DI_fFlange_RFType | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full | N | N
72007 | 410_PF_DI_eDuckfoodBend90Deg_Flanged | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
72006 | 410_PF_DI_eBend_Socket | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
72005 | 410_PF_DI_eBend_Flange | 2026-05-29 | 2026-06-17 | 14 | handler_assign | confirm_note:stored_full | N | N
72003 | 410_PF_DI_cPlug_TType | 2026-05-29 | 2026-06-22 | 17 | handler_assign | confirm_note:stored_full | N | N
72002 | 410_PF_DI_cCap_KType | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | N | N
72001 | 410_PF_DI_cBlind_Flanged | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | N | N
72000 | 410_PF_DI_cBellmouth_Flanged | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | N | N
71999 | 410_PF_CS_uConnector_MapressAndFemaleThread | 2026-05-29 | 2026-06-09 | 8 | handler_assign | confirm_note:stored_full | N | N
71998 | 410_PF_CS_rConnector_MapressAndFemaleThread | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full | N | N
71997 | 410_PF_CS_rConcentricReducers_Welded | 2026-05-29 | 2026-06-29 | 22 | handler_assign | confirm_note:stored_full | N | N
71996 | 410_PF_CS_fPlaneFlange_Flanged | 2026-05-29 | 2026-06-19 | 16 | handler_assign | confirm_note:stored_full | N | N
71994 | 410_PF_CS_eRadiusElbows_Welded | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | N | N
71992 | 410_PF_CS_eLongRadiusReturnBends_Welded | 2026-05-29 | 2026-06-15 | 12 | handler_assign | confirm_note:stored_full | N | N
71991 | 410_PF_CS_eLongRadiusElbows_Welded | 2026-06-17 | 2026-08-25 | 50 | handler_assign | confirm_note:stored_full | N | N
71990 | 410_PF_CS_cEndCaps_Welded | 2026-05-29 | 2026-06-01 | 2 | handler_assign | status_resolved | N | N
71989 | 410_PF_CO_mDoubleElbowTapConnector90Degree_Mapress | 2026-05-29 | 2026-06-23 | 18 | handler_assign | confirm_note:stored_full | N | N
71988 | 410_PF_CI_xDoubleBranch70Deg_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
71931 | 410_PF_CI_xDoubleBranch45_Clamp | 2026-05-29 | 2026-06-02 | 3 | handler_assign | confirm_note:stored_full | N | N
71930 | 410_PF_CI_uTrapHorizontal_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
71929 | 410_PF_CI_uShortPipeRoundAccessDoor_Clamp | 2026-05-29 | 2026-06-16 | 13 | handler_assign | confirm_note:stored_full | N | N
71928 | 410_PF_CI_tSweptEntryBranch88_Spigot_Clamp | 2026-05-29 | 2026-06-01 | 2 | handler_assign | status_resolved | N | N
71927 | 410_PF_CI_tCornerBranch88_Clamp | 2026-05-29 | 2026-07-01 | 24 | handler_assign | confirm_note:stored_full | N | N
71926 | 410_PF_CI_tCombinationBranch90_Standard | 2026-05-28 | 2026-06-10 | 10 | handler_assign | confirm_note:stored_full | N | N
71925 | 410_PF_CI_tBranch88_Clamp | 2026-05-28 | 2026-05-29 | 2 | handler_assign | status_resolved | N | N
71924 | 410_PF_CI_tBranch88Long_Spigot_Clamp | 2026-05-28 | 2026-06-04 | 6 | handler_assign | confirm_note:stored_full | N | N
71923 | 410_PF_CI_tBranch88Deg_Coupling_HOST | 2026-05-26 | 2026-07-01 | 27 | handler_assign | confirm_note:stored_full | N | N
71922 | 410_PF_CI_tBranch88Deg_Coupling | 2026-05-26 | 2026-05-29 | 4 | handler_assign | status_resolved | N | N
71921 | 410_PF_CI_tBranch70_Clamp | 2026-05-26 | 2026-06-04 | 8 | handler_assign | confirm_note:stored_full | N | N
71920 | 410_PF_CI_tBranch45_Clamp | 2026-05-26 | 2026-06-05 | 9 | handler_assign | confirm_note:stored_full | N | N
71919 | 410_PF_CI_rReducingEccentric_Clamp | 2026-05-26 | 2026-05-27 | 2 | handler_assign | status_resolved | N | N
71918 | 410_PF_CI_rEccentricReducer_Coupling_HOST | 2026-05-26 | 2026-06-08 | 10 | handler_assign | confirm_note:stored_full | N | N
71902 | Annotation_General_Integrate the TIDP to MIDP | 2026-05-19 | 2026-05-20 | 2 | handler_assign | status_resolved | N | N
71899 | Annotation_Platform_Deploy the feature | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved | N | N
71877 | 430_DF_GS_sRoundTaps_Spigot.rfa | 2026-05-18 | 2026-06-04 | 14 | handler_assign | confirm_note:stored_full | N | N
71876 | 430_DF_GS_rUbergangRechteckRund_Flanged_SlipJoint.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71875 | 430_DF_GS_rUbergang_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71874 | 430_DF_GS_rReducer_Spigot_Round.rfa | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | N | N
71873 | 430_DF_GS_rEtage_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71872 | 430_DF_GS_eTransitionElbow_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71871 | 430_DF_GS_eRoundElbow_Spigot.rfa | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | N | N
71870 | 430_DF_GS_eEckbogen_Flanged.rfa | 2026-05-18 | 2026-07-09 | 39 | handler_assign | confirm_note:stored_full | N | N
71869 | 430_DF_GS_eBogen_Flanged.rfa | 2026-05-18 | 2026-09-18 | 90 | handler_assign | confirm_note:stored_full | N | N
71868 | 430_DF_GS_cCapEnd_Spigot_Round.rfa | 2026-05-18 | 2026-06-02 | 12 | handler_assign | confirm_note:stored_full | N | N
71867 | 430_DF_GS_cBoden_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71866 | 430_DF_GS_sUbergangsstutzen_Flanged.rfa | 2026-05-18 | 2026-09-18 | 90 | handler_assign | confirm_note:stored_full | N | N
71865 | 430_DF_GS_xKreuzstuck_Flanged.rfa | 2026-05-18 | 2026-06-19 | 25 | handler_assign | confirm_note:stored_full | N | N
71864 | 430_DF_GS_wHosenStuck_Flanged.rfa | 2026-05-18 | 2026-06-19 | 25 | handler_assign | confirm_note:stored_full | N | N
71863 | 430_DF_GS_uUnion_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71862 | 430_DF_GS_uCoupling_Spigot_Round.rfa | 2026-05-18 | 2026-06-05 | 15 | handler_assign | confirm_note:stored_full | N | N
71861 | 430_DF_GS_tTStuck_Flanged.rfa | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71860 | 430_DF_GS_tTee_Spigot_Round.rfa | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | N | N
71858 | LPH3_SAN Discipline Output Checklist Definition | 2026-05-18 | 2026-09-22 | 92 | handler_assign | status_resolved | N | N
71857 | MSR_LPH8_Sample Schematic | 2026-05-18 | 2026-05-29 | 10 | handler_assign | status_resolved | N | N
71856 | MSR_LPH5_Sample Schematic | 2026-05-18 | 2026-05-29 | 10 | handler_assign | status_resolved | N | N
71855 | ELT_LPH8_Sample Schematic | 2026-05-18 | 2026-05-26 | 7 | handler_assign | status_resolved | N | N
71854 | ELT_LPH5_Sample Schematic | 2026-05-18 | 2026-05-29 | 10 | handler_assign | status_resolved | N | N
71853 | ELT_Cable tray_LPH8_Sample Layout_Multiple Scales | 2026-05-18 | 2026-05-21 | 4 | handler_assign | status_resolved | N | N
71852 | ELT_Cable tray_LPH5_Sample Layout_Multiple Scales | 2026-05-18 | 2026-05-26 | 7 | handler_assign | status_resolved | N | N
71851 | ELT_LES_LPH8_Sample Layout_Multiple Scales | 2026-05-18 | 2026-05-21 | 4 | handler_assign | status_resolved | N | N
71850 | 410_PF_CI_uDownPipeBracket_Coupling | 2026-05-15 | 2026-06-17 | 24 | handler_assign | confirm_note:stored_full | N | N
71847 | 410_PF_CI_rEccentricReducer_WithoutCoupling | 2026-05-26 | 2026-08-12 | 57 | handler_assign | confirm_note:stored_full | N | N
71846 | 410_PF_CI_mVerticalTrap_Standard | 2026-05-26 | 2026-06-09 | 11 | handler_assign | confirm_note:stored_full | N | N
71843 | 410_PF_CI_mShortPipeRectangularAccessDoor_Standard | 2026-05-26 | 2026-06-09 | 11 | handler_assign | confirm_note:stored_full | N | N
71842 | 410_PF_CI_GutterUnionConnector | 2026-05-26 | 2026-06-19 | 19 | handler_assign | confirm_note:stored_full | N | N
71834 | 410_PF_CI_tGutterTee_RunningOutlet | 2026-05-26 | 2026-08-13 | 58 | handler_assign | confirm_note:stored_full | N | N
71833 | 410_PF_CI_GutterHalfRound | 2026-05-25 | 2026-06-18 | 19 | handler_assign | confirm_note:stored_full | N | N
71832 | 410_PF_CI_eGutterElbow_InternalDropEndOutlet | 2026-05-25 | 2026-06-18 | 19 | handler_assign | confirm_note:stored_full | N | N
71831 | 410_PF_CI_eGutterElbow_ExternalDropEndOutlet | 2026-05-25 | 2026-06-19 | 20 | handler_assign | confirm_note:stored_full | N | N
71830 | 410_PF_CI_cGutterCap_InternalStopEnd | 2026-05-25 | 2026-06-17 | 18 | handler_assign | confirm_note:stored_full | N | N
71828 | 410_PF_CI_cGutterCap_ExternalStopEnd | 2026-05-25 | 2026-06-17 | 18 | handler_assign | confirm_note:stored_full | N | N
71826 | 410_PF_CI_eGutterAngleUniversal | 2026-05-22 | 2026-06-10 | 14 | handler_assign | confirm_note:stored_full | N | N
71825 | 410_PF_CI_eVentilationBend88DegreesRadial_Standard_Clamp | 2026-05-22 | 2026-06-18 | 20 | handler_assign | confirm_note:stored_full | N | N
71824 | 410_PF_CI_eVentilationBend88Axial_Clamp | 2026-05-22 | 2026-05-29 | 6 | handler_assign | status_resolved | N | N
71823 | 410_PF_CI_eRestBend88_Clamp | 2026-05-22 | 2026-05-26 | 3 | handler_assign | status_resolved | N | N
71822 | 410_PF_CI_eRecirculatedAirBend135Degrees_Standard_Clamp | 2026-05-22 | 2026-06-05 | 11 | handler_assign | confirm_note:stored_full | N | N
71821 | 410_PF_CI_ePlainTrap_Clamp | 2026-05-22 | 2026-06-01 | 7 | handler_assign | confirm_note:stored_full | N | N
71820 | 410_PF_CI_eOffsetBend65_Clamp | 2026-05-22 | 2026-06-01 | 7 | handler_assign | confirm_note:stored_full | N | N
71808 | 410_PF_CI_eOffsetBend200_Clamp | 2026-05-22 | 2026-05-25 | 2 | handler_assign | status_resolved | N | N
71807 | 410_PF_CI_eOffsetBend130_Clamp | 2026-05-22 | 2026-06-04 | 10 | handler_assign | confirm_note:stored_full | N | N
71806 | 410_PF_CI_eDoubleBend88Deg_Coupling | 2026-05-21 | 2026-06-05 | 12 | handler_assign | confirm_note:stored_full | N | N
71805 | 410_PF_CI_xDoubleBend88Degrees_Standard_Clamp | 2026-05-21 | 2026-05-26 | 4 | handler_assign | status_resolved | N | N
71799 | MEP_Revise 474_PA_PressureReducingValve_Flanged | 2026-05-14 | 2026-06-19 | 27 | handler_assign | status_resolved | N | N
71798 | MEP_Revise 474_PA_PressureReducingControlValveThread | 2026-05-14 | 2026-08-14 | 67 | handler_assign | confirm_note:stored_full | N | N
71797 | MEP_Revise 474_PA_PressureGauge_AnalogueType | 2026-05-14 | 2026-06-24 | 30 | handler_assign | status_resolved | N | N
71796 | MEP_Revise 474_PA_OS&YGateValves_GrooveAndGroove | 2026-05-14 | 2026-07-08 | 40 | handler_assign | confirm_note:stored_full | N | N
71795 | MEP_Revise 474_PA_NRSOS&YGateValvesGrooveandGroove | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:will_be_closed | N | N
71794 | MEP_Revise 474_PA_NRSOS&YGateValves_GrooveAndGroove | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | N | N
71793 | MEP_Revise 474_PA_MeasuringOrificeAssembly | 2026-05-14 | 2026-07-17 | 47 | handler_assign | confirm_note:will_be_closed | N | N
71792 | MEP_Revise 474_PA_ManifoldCheckValve_Threaded | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | N | N
71791 | MEP_Revise 474_PA_ManifoldCheckValve_Grooved | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | N | N
71790 | MEP_Revise 474_PA_LevelControlValves_Flange | 2026-05-14 | 2026-09-30 | 100 | handler_assign | confirm_note:will_be_closed | N | N
71789 | MEP_Revise 474_PA_InlineCheckValve_CO2 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | N | N
71788 | MEP_Revise 474_PA_FoamLineProportioner | 2026-05-14 | 2026-06-24 | 30 | handler_assign | status_resolved | N | N
71787 | MEP_Revise 474_PA_Foam_InLineBalancedPressureProportioners | 2026-05-14 | 2026-08-03 | 58 | handler_assign | confirm_note:stored_full | N | N
71786 | MEP_Revise 474_PA_Foam_DuctileIron_DelugeValve_AngleStype | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | N | N
71785 | MEP_Revise 474_PA_Foam_AutomaticControlValve_Flanged | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | N | N
71784 | MEP_Revise 474_PA_Foam_AutomaticConcentrateControlValve | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | N | N
71783 | MEP_Revise 474_PA_FM200_SolenoidValve | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | N | N
71782 | MEP_Revise 474_PA_FM200_SectorValve_Threaded | 2026-05-14 | 2026-08-14 | 67 | handler_assign | confirm_note:stored_full | N | N
71781 | MEP_Revise 474_PA_FM200_SectorValve_Flanged | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | N | N
71780 | MEP_Revise 474_PA_FM200_ManualPneumaticActuator | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | N | N
71779 | MEP_Revise 474_PA_FM200_Manifold_CheckValve | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | N | N
71778 | MEP_Revise 474_PA_FM200_DischargePressureSwitch | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:will_be_closed | N | N
71777 | MEP_Revise 474_PA_FM200_ActuatorBox | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | N | N
71774 | MEP_Revise 474_PA_Flushing_Connection | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | N | N
71773 | MEP_Revise 474_PA_FlowTestMeter_Flange | 2026-05-14 | 2026-08-21 | 72 | handler_assign | confirm_note:stored_full | N | N
71772 | MEP_Revise 474_PA_FlexibleMetalHose | 2026-05-14 | 2026-07-27 | 53 | handler_assign | confirm_note:stored_full | N | N
71771 | MEP_Revise 474_PA_AerationVentilationValve | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | N | N
71770 | MEP_Revise 474_PA_3WayBronzeGlobeValve | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | N | N
71769 | MEP_Revise 474_PA_DuplexPressureGauges | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | N | N
71768 | MEP_Revise 474_PA_DiaphragmValves | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | N | N
71767 | MEP_Revise 474_ME_MasterCylinderWithTopValveOfActuator_CO2 | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | N | N
71766 | MEP_Revise 474_ME_CylinderWithCylinderValve_CO2 | 2026-05-14 | 2026-07-23 | 51 | handler_assign | confirm_note:stored_full | N | N
71765 | MEP_Revise 474_ME_ControlBox_CO2 | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | N | N
71764 | MEP_Revise 474_ME_Compressor | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | N | N
71763 | MEP_Revise 474_ME_Cabinet_FlushMountedWall | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | N | N
71762 | MEP_Revise 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | N | N
71761 | MEP_Revise 474_ME_AirSamplingPump | 2026-05-14 | 2026-07-16 | 46 | handler_assign | confirm_note:stored_full | N | N
71760 | MEP_Revise 474_PA_ButterflyValveSupervisedOpen | 2026-05-14 | 2026-08-04 | 59 | handler_assign | confirm_note:stored_full | N | N
71759 | MEP_Revise 474_SP_GE_WindowOpenNozzle | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | N | N
71758 | MEP_Revise 474_PA_AutoDrainValve_FloatType_Threaded | 2026-05-14 | 2026-07-27 | 53 | handler_assign | confirm_note:stored_full | N | N
71757 | MEP_Revise 474_PA_AutoConvertAssembly | 2026-05-14 | 2026-08-20 | 71 | handler_assign | confirm_note:stored_full | N | N
71756 | MEP_Revise 474_PA_AngleHoseValve | 2026-05-14 | 2026-07-02 | 36 | handler_assign | confirm_note:stored_full | N | N
71755 | MEP_Revise 474_PA_AlarmTestModuleThreadEnd | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | N | N
71754 | MEP_Revise 474_PA_AlarmTestModulePressureReliefValve_ThreadEnd | 2026-05-14 | 2026-08-20 | 71 | handler_assign | confirm_note:stored_full | N | N
71753 | MEP_Revise 474_ME_JunctionBox_VESDA | 2026-05-14 | 2026-10-01 | 101 | handler_assign | confirm_note:stored_full | N | N
71752 | MEP_Revise 474_PA_AlarmPressureSwitch | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | N | N
71751 | MEP_Revise 474_ME_FireExtinguisherPortable_Foam | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full | N | N
71750 | MEP_Revise 474_PA_AirVentValve | 2026-05-14 | 2026-07-01 | 35 | handler_assign | confirm_note:stored_full | N | N
71749 | MEP_Revise 474_ME_FireExtinguisherCarbonDioxide | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full | N | N
71748 | MEP_Revise 474_PA_AirMaintenanceCompressorAssembly | 2026-05-14 | 2026-07-09 | 41 | handler_assign | confirm_note:stored_full | N | N
71747 | MEP_Revise 474_ME_VerticalFirePump | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | N | N
71746 | MEP_Revise 474_ME_SolventTank | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | N | N
71745 | MEP_Revise 474_ME_ReceiverTank | 2026-05-14 | 2026-06-11 | 21 | handler_assign | status_resolved | N | N
71744 | MEP_Revise 474_ME_ProtectiveCabinetWithVentilationValve | 2026-05-14 | 2026-06-11 | 21 | handler_assign | status_resolved | N | N
71743 | MEP_Revise 474_ME_CylinderTank_FM200 | 2026-05-14 | 2026-07-09 | 41 | handler_assign | confirm_note:stored_full | N | N
71742 | MEP_Revise 474_ME_NitrogenPilotCylinderWithTopValve | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | N | N
71741 | MEP_Revise 474_ME_Cabinet_ExtinguishingWaterSupplyAndVentilationValve | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:will_be_closed | N | N
71740 | MEP_Revise 474_ME_DieselPump_FloorSurface_AURORA481 | 2026-05-14 | 2026-06-12 | 22 | handler_assign | status_resolved | N | N
71739 | MEP_Revise 474_ME_JockeyPump | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | N | N
71738 | MEP_Revise 474_ME_HorizontalPresssureTank | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | N | N
71737 | MEP_Revise 474_ME_FoamPump | 2026-05-14 | 2026-08-27 | 76 | handler_assign | confirm_note:stored_full | N | N
71736 | MEP_Revise 474_ME_FoamBladderTank_VerticalType | 2026-05-14 | 2026-05-22 | 7 | handler_assign | status_resolved | N | N
71735 | MEP_Revise 474_ME_FoamBladderTank_HorizontalType | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | N | N
71734 | MEP_Revise 474_ME_FM200_CylinderTank | 2026-05-14 | 2026-08-19 | 70 | handler_assign | confirm_note:stored_full | N | N
71733 | MEP_Revise 474_ME_FireValveBox | 2026-05-14 | 2026-08-12 | 65 | handler_assign | confirm_note:stored_full | N | N
71732 | MEP_Revise 474_ME_FirePump_Horizontal_SplitCase | 2026-05-14 | 2026-08-18 | 69 | handler_assign | confirm_note:stored_full | N | N
71731 | MEP_Revise 474_PA_ZoneControlRiserModule_Residential | 2026-05-14 | 2026-08-21 | 72 | handler_assign | confirm_note:stored_full | N | N
71729 | MEP_Revise 474_ME_FireHoseReel_WallSurface | 2026-05-14 | 2026-07-13 | 43 | handler_assign | confirm_note:stored_full | N | N
71728 | MEP_Revise 474_ME_FireExtinguisherPortable_Powder | 2026-05-14 | 2026-06-25 | 31 | handler_assign | confirm_note:stored_full | N | N
71727 | MEP_Revise 474_ME_FE_AutomaticDryPowerCeiling_HFC17_NoSystem | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | N | N
71726 | MEP_Revise 474_ME_EndSuctionFirePump | 2026-05-14 | 2026-07-10 | 42 | handler_assign | confirm_note:stored_full | N | N
71725 | MEP_Revise 474_ME_SlaveCylinderWithTopOfValve_CO2 | 2026-05-14 | 2026-05-27 | 10 | handler_assign | status_resolved | N | N
71724 | MEP_Revise 474_PA_DelugeValve | 2026-05-14 | 2026-08-07 | 62 | handler_assign | confirm_note:stored_full | N | N
71723 | MEP_Revise 474_PA_CylinderValve_CO2 | 2026-05-14 | 2026-08-19 | 70 | handler_assign | confirm_note:stored_full | N | N
71722 | MEP_Revise 474_ME_CO2_CylinderAssemblies | 2026-05-14 | 2026-05-19 | 4 | handler_assign | status_resolved | N | N
71721 | MEP_Revise 474_ME_CO2_ControlBox | 2026-05-14 | 2026-05-19 | 4 | handler_assign | status_resolved | N | N
71720 | MEP_Revise 474_ME_Cabinet_ExtinguishingWaterSupply | 2026-05-14 | 2026-05-19 | 4 | handler_assign | status_resolved | N | N
71719 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC8kg | 2026-05-14 | 2026-08-06 | 61 | handler_assign | confirm_note:stored_full | N | N
71718 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC4d5kg | 2026-05-14 | 2026-05-25 | 8 | handler_assign | status_resolved | N | N
71717 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_HFC14kg | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | N | N
71716 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC6kg | 2026-05-14 | 2026-06-29 | 33 | handler_assign | confirm_note:stored_full | N | N
71715 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC3kg | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | N | N
71714 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC1kg | 2026-05-14 | 2026-08-13 | 66 | handler_assign | confirm_note:stored_full | N | N
71713 | MEP_Revise 474_ME_AutomaticDryPowderCeilingFireExtinguiser_ABC12kg | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | N | N
71712 | Revise the RFA library for the MED system. | 2026-05-14 |  |  | handler_assign | none | N | Y | missing_end
71711 | Revise the RFA library for the SPR system. | 2026-05-14 |  |  | handler_assign | none | N | Y | missing_end
71709 | RLT_LPH3_5_8_Sample Schematic_Multiple Scales | 2026-05-14 | 2026-05-18 | 3 | handler_assign | status_resolved | N | N
71706 | 410_PF_CI_eDoubleBend45Deg_Coupling_HOST | 2026-05-21 | 2026-05-29 | 7 | handler_assign | confirm_note:stored_full | N | N
71705 | 410_PF_CI_eConectionBend_Clamp | 2026-05-19 | 2026-05-22 | 4 | handler_assign | status_resolved | N | N
71704 | 410_PF_CI_eBend_Coupling_HOST | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved | N | N
71703 | 410_PF_CI_eBend_Coupling | 2026-05-19 | 2026-06-01 | 10 | handler_assign | confirm_note:stored_full | N | N
71702 | 410_PF_CI_eBend_Clamp | 2026-05-19 | 2026-06-02 | 11 | handler_assign | confirm_note:stored_full | N | N
71701 | 410_PF_CI_eBendWC_Clamp_Standard | 2026-05-19 | 2026-05-25 | 5 | handler_assign | status_resolved | N | N
71700 | 410_PF_CI_eBend88Deg_Clamp | 2026-05-19 | 2026-05-29 | 9 | handler_assign | confirm_note:stored_full | N | N
71699 | 410_PF_CI_eBend88Degree_SpigotAndClamp | 2026-05-19 | 2026-05-28 | 8 | handler_assign | confirm_note:stored_full | N | N
71698 | 410_PF_CI_eBend68Degree_Clamp | 2026-05-19 | 2026-06-03 | 12 | handler_assign | confirm_note:stored_full | N | N
71697 | 410_PF_CI_eBend30Degrees_Standard_Clamp | 2026-05-19 | 2026-05-29 | 9 | handler_assign | confirm_note:stored_full | N | N
71696 | 410_PF_CI_eBend15Degrees_Standard_Clamp | 2026-05-19 | 2026-06-03 | 12 | handler_assign | confirm_note:stored_full | N | N
71695 | 410_PF_CI_eAccessBendShort_Clamp | 2026-05-19 | 2026-06-10 | 17 | handler_assign | confirm_note:stored_full | N | N
71694 | 410_PF_CI_eAccessBendLong_Clamp | 2026-05-19 | 2026-06-18 | 23 | handler_assign | confirm_note:stored_full | N | N
71693 | 410_PF_CI_DoubleBranch_Coupling | 2026-05-19 | 2026-05-28 | 8 | handler_assign | confirm_note:stored_full | N | N
71692 | 410_PF_CI_cPushinPlug_Clamp | 2026-05-19 | 2026-05-22 | 4 | handler_assign | status_resolved | N | N
71691 | 410_PF_CI_tBranch45Deg_Coupling_HOST | 2026-05-18 | 2026-06-09 | 17 | handler_assign | confirm_note:stored_full | N | N
71689 | 410_PF_CI_tBranch45Deg_Coupling | 2026-05-18 | 2026-06-09 | 17 | handler_assign | confirm_note:stored_full | N | N
71688 | 410_PF_CI_Bearing | 2026-05-18 | 2026-05-20 | 3 | handler_assign | status_resolved | N | N
71687 | 410_PF_CI_fAngleDoubleBranch88Degree_Coupling | 2026-05-18 | 2026-06-18 | 24 | handler_assign | confirm_note:stored_full | N | N
71686 | 410_PF_cHDPE_BlindFlange_Flanged | 2026-05-18 | 2026-06-16 | 22 | handler_assign | confirm_note:stored_full | N | N
71685 | 410_PF_CI_uSMLRainwaterSiphonVertical_Coupling | 2026-05-18 | 2026-06-01 | 11 | handler_assign | confirm_note:stored_full | N | N
71684 | 410_CI_eRainwaterSiphon_Coupling | 2026-05-18 | 2026-06-02 | 12 | handler_assign | confirm_note:stored_full | N | N
71683 | 410_PF_CI_cPlug_Coupling | 2026-05-15 | 2026-05-21 | 5 | handler_assign | status_resolved | N | N
71682 | 410_PF_CI_rEccentricReducer_Coupling | 2026-05-15 | 2026-05-18 | 2 | handler_assign | status_resolved | N | N
71681 | 410_PF_CastIron_DownPipeBracket_Coupling | 2026-05-26 | 2026-05-26 | 1 | handler_assign | status_closed | N | N
71680 | 410_PF_CI_xCombinationBranch88Degree_Coupling | 2026-05-15 | 2026-06-17 | 24 | handler_assign | confirm_note:stored_full | N | N
71679 | 410_PF_CI_uCleaningPipeWithRoundCover_Coupling | 2026-05-15 | 2026-05-28 | 10 | handler_assign | confirm_note:stored_full | N | N
71666 | Revise the RFA library for the SAN system. | 2026-05-13 |  |  | handler_assign | none | N | Y | missing_end
71660 | Annotation_General_TIDP Set up and creation_Digital Coordinator_Danh Nguyen | 2026-05-13 | 2026-05-18 | 4 | handler_assign | status_resolved | N | N
71659 | 440_EF_EmergencyStopPushButtons | 2026-05-13 | 2026-05-13 | 1 | handler_assign | status_resolved | N | N
71634 | ELT_LES_LPH5_Sample Layout_Multiple Scales | 2026-05-13 | 2026-05-18 | 4 | handler_assign | status_resolved | N | N
71633 | MSR_LPH8_Sample Layout_Multiple Scales | 2026-05-13 | 2026-05-18 | 4 | handler_assign | status_resolved | N | N
71632 | Annotation_General_TIDP Set up and creation_SRP & MED systems_Sang Duong | 2026-05-12 | 2026-05-19 | 6 | handler_assign | status_resolved | N | N
71622 | MSR_LPH5_Sample Layout_Multiple Scales | 2026-05-12 | 2026-05-18 | 5 | handler_assign | status_resolved | N | N
71604 | DCMvn_Annotation_SAN Detail Item and model lines Symbol Proposal | 2026-05-11 | 2026-05-15 | 5 | handler_assign | status_resolved | N | N
71603 | RLT_LPH5_Sample Layout_Multiple Scales | 2026-05-11 | 2026-05-18 | 6 | handler_assign | status_resolved | N | N
71602 | RLT_LPH3_Sample Layout_Multiple Scales | 2026-05-11 | 2026-05-18 | 6 | handler_assign | status_resolved | N | N
71601 | RLT_LPH8_Sample Layout_Multiple Scales | 2026-05-11 | 2026-05-18 | 6 | handler_assign | status_resolved | N | N
71599 | 410_PF_CI_uCleaningPipeWithRectangularcover_Coupling | 2026-05-15 | 2026-05-19 | 3 | handler_assign | status_resolved | N | N
71598 | 410_PF_CI_tBranch68Deg_Coupling | 2026-05-15 | 2026-05-26 | 8 | handler_assign | confirm_note:stored_full | N | N
71597 | MEP_Revise 474_PA_DischargeValve. | 2026-05-11 | 2026-09-04 | 85 | handler_assign | confirm_note:stored_full | N | N
71596 | MEP_Revise 474_PA_MaintenanceUnit. | 2026-05-11 | 2026-08-21 | 75 | handler_assign | confirm_note:stored_full | N | N
71595 | MEP_474_PA_AlarmCheckValve | 2026-05-11 | 2026-05-14 | 4 | handler_assign | status_resolved | N | N
71594 | MEP_Revise 474_PA_GateValve. | 2026-05-11 | 2026-08-14 | 70 | handler_assign | confirm_note:stored_full | N | N
71593 | MEP_Revise 474_PA_ShutoffValve_Motorized. | 2026-05-11 | 2026-09-30 | 103 | handler_assign | confirm_note:will_be_closed | N | N
71592 | MEP_474_PA_ShutoffValve_Motorized. | 2026-05-11 | 2026-07-15 | 48 | handler_assign | confirm_note:will_be_closed | N | N
71591 | MEP_Revise 474_PA_CS_YStrainer_Grooved. | 2026-05-11 | 2026-05-14 | 4 | handler_assign | status_resolved | N | N
71590 | 440_EF_AirTerminationRods_FloorStand | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | N | N
71589 | 440_EF_AirTerminationRodsForMetalRoofs | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | N | N
71588 | 440_EF_EarthingFixedPoint_WallSurface | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | N | N
71587 | 440_EF_DataConnectionSocket_Wall | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | N | N
71586 | 440_EF_Thermosat | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | N | N
71584 | 440_EF_SocketOutlet_Wall | 2026-05-11 | 2026-05-13 | 3 | handler_assign | status_resolved | N | N
71582 | Test_Revised family | 2026-05-11 | 2026-09-07 | 86 | handler_assign | status_resolved | N | N
71581 | Test_Update_430_DA_CircularSilencers_CA_100 | 2026-05-11 | 2026-05-22 | 10 | handler_assign | status_closed | N | N
71576 | Annotation_General_Ticket Template | 2026-05-08 |  |  | handler_assign | none | N | Y | missing_end
71544 | MEP_Revise RFA_430_DA_FireDampersForCeiling_KU_K30 | 2026-05-08 | 2026-05-11 | 2 | handler_assign | status_resolved | N | N
71543 | MEP_Revise RFA_430_DA_ConstantVolumeFlowControl_Rectangular_ConstantFlowEN | 2026-05-08 | 2026-05-11 | 2 | handler_assign | status_resolved | N | N
71542 | MEP_Revise RFA_430_DA_CircularSilencers_CA_100 | 2026-05-08 | 2026-05-08 | 1 | handler_assign | status_resolved | N | N
71541 | MEP_Revise RFA_30_AT_CircularDiscValves_ZLVS_Supply | 2026-05-08 | 2026-05-20 | 9 | handler_assign | status_closed | N | N
71540 | MEP_Revise RFA_430_AT_CircularDiscValves_LVS_Return | 2026-05-08 | 2026-05-11 | 2 | handler_assign | status_resolved | N | N
71520 | MEP_Revise RFA_30_ME_Fan_Axial | 2026-05-07 | 2026-05-07 | 1 | handler_assign | status_resolved | N | N
71496 | Annotation_ELT_MSR_Execution Planning | 2026-05-06 | 2026-05-08 | 3 | handler_assign | status_resolved | N | N
71484 | MEP_Revise RFA_430_AT_Test | 2026-05-06 | 2026-05-08 | 3 | handler_assign | status_resolved | N | N
71483 | MEP_Revise RFA_430_AT_Diffuser_Ceiling_Rectangular_AIRNAMIC_Return | 2026-05-06 | 2026-05-11 | 4 | handler_assign | status_resolved | N | N
71482 | MEP_Revise RFA_430_DF_GS_rUbergang_Flanged | 2026-05-06 | 2026-05-06 | 1 | handler_assign | status_closed | N | N
71481 | MEP_Revise RFA_430_DF_GS_rReducer_Spigot_Round. | 2026-05-06 | 2026-05-08 | 3 | handler_assign | status_resolved | N | N
71456 | ELT_Cable tray_LPH3_Sample Layout_Multiple Scales | 2026-05-04 | 2026-05-11 | 6 | handler_assign | status_resolved | N | N
71437 | SAN_Inspecting Drainage System for LPH3 + LPH5 + LPH8 | 2026-05-04 | 2026-05-15 | 10 | handler_assign | status_resolved | N | N
71435 | SAN_Inspecting Water Supply System for LPH3 + LPH5 + LPH8 | 2026-05-04 | 2026-05-15 | 10 | handler_assign | status_resolved | N | N
71432 | ELT_Installations_LPH8_Sample Layout_Multiple Scales | 2026-05-04 | 2026-05-08 | 5 | handler_assign | status_resolved | N | N
71431 | ELT_LES_LPH3_Sample Layout_Multiple Scales | 2026-05-04 | 2026-05-08 | 5 | handler_assign | status_resolved | N | N
71349 | MEP_Revise 420_PA_CheckValveWithThermometer_Thread. | 2026-04-23 | 2026-06-18 | 41 | handler_assign | status_closed | N | N
71348 | MEP_Revise 420_PA_CapValve_Thread. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | N | N
71347 | MEP_Revise 420_PA_ButterflyvalveMotor_Flanged. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | N | N
71345 | MEP_Revise 420_PA_ButterflyValveHandwheel_Flanged. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | N | N
71344 | MEP_Revise 420_PA_ButterflyValve_Thread_LeverStandard. | 2026-04-23 | 2026-05-07 | 11 | handler_assign | status_resolved | N | N
71343 | MEP_Revise 420_PA_ButterflyValve_Thread_GearStandard. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | N | N
71342 | MEP_Revise 420_PA_ButterflyValve_Flanged_LeverStandard. | 2026-04-23 | 2026-05-08 | 12 | handler_assign | status_resolved | N | N
71229 | MEP_Revise 420_PA_ButterflyValve_Flanged_Handle. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | N | N
71228 | MEP_Revise 420_PA_ButterflyValve_Flanged_GearStandard. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | N | N
71227 | MEP_Revise 420_PA_BasketStrainerValve_Thread_Standard. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | N | N
71226 | MEP_Revise 420_PA_BasketStrainerValve_Flanged_Standard. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | N | N
71225 | MEP_Revise 420_PA_BallValve3Way_TPort. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | N | N
71224 | MEP_Revise 420_PA_BallValve3Way_LPort. | 2026-04-20 | 2026-04-24 | 5 | handler_assign | status_resolved | N | N
71208 | 2026Q2_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-04-17 | 2026-07-06 | 57 | handler_assign | status_closed | N | N
71143 | HZG_Inspecting system for LPH3 + LPH5 + LPH8 | 2026-04-14 | 2026-04-24 | 9 | handler_assign | status_resolved | N | N
71142 | KLT_Inspecting system for LPH3 + LPH5 + LPH8 | 2026-04-14 | 2026-04-24 | 9 | handler_assign | status_resolved | N | N
71063 | 2026Q2_Annotation Project_TL & TM Time allocation_Thuong Van Huynh | 2026-04-10 | 2026-07-02 | 60 | handler_assign | status_closed | N | N
70988 | PD Tasks_2026Q2 | 2026-04-07 | 2026-07-02 | 63 | handler_assign | status_closed | N | N
70900 | 2026Q2_Annotation Project_TL & TM Time allocation_Nhut Minh Le | 2026-04-01 | 2026-07-02 | 67 | handler_assign | status_closed | N | N
70869 | 2026Q2_DCMvn_Annotation Project_TL & TM Time allocation_Hanh Pham | 2026-03-31 | 2026-06-30 | 66 | handler_assign | status_resolved | N | N
69618 | Annotation_DIG_BEP Creation | 2026-03-10 | 2026-04-29 | 37 | handler_assign | status_resolved | N | N
69617 | Annotation_DIG_Confirm the database and project material | 2026-03-10 | 2026-04-10 | 24 | handler_assign | status_resolved | N | N
68897 | MEP_Revise RFA_430_AT_DeflectorHood_Roof_Round_Exhaust | 2026-03-05 | 2026-05-19 | 54 | handler_assign | status_resolved | N | N
68896 | MEP_Revise RFA_430_AT_Test | 2026-03-05 | 2026-05-11 | 48 | handler_assign | status_resolved | N | N
68757 | MEP_Revise RFA_430_DF_GS_xKreuzstuck_Flanged | 2026-03-02 | 2026-05-06 | 48 | handler_assign | status_resolved | N | N
68755 | MEP_Revise RFA_430_DF_GS_wHosenStuck_Flanged | 2026-03-03 | 2026-03-04 | 2 | handler_assign | status_resolved | N | N
68754 | MEP_Revise RFA_430_DF_GS_uUnion_Flanged | 2026-03-02 | 2026-03-04 | 3 | handler_assign | status_resolved | N | N
68753 | MEP_Revise RFA_430_DF_GS_uCoupling_Spigot_Round | 2026-03-02 | 2026-03-03 | 2 | handler_assign | status_resolved | N | N
68752 | MEP_Revise RFA_430_DF_GS_tTStuck_Flanged | 2026-03-02 | 2026-03-04 | 3 | handler_assign | status_resolved | N | N
68750 | MEP_Revise RFA_430_DF_GS_Tee_Spigot_Round | 2026-03-02 | 2026-03-04 | 3 | handler_assign | status_resolved | N | N
68749 | MEP_Revise RFA_430_DF_GS_sRoundTaps_Spigot | 2026-03-04 | 2026-03-05 | 2 | handler_assign | status_resolved | N | N
68748 | MEP_Revise RFA_430_DF_GS_rUbergangRechteckRund_Flanged_SlipJoint | 2026-03-04 | 2026-03-05 | 2 | handler_assign | status_resolved | N | N
68747 | MEP_Revise RFA_430_DF_GS_rUbergang_Flanged | 2026-03-03 | 2026-03-04 | 2 | handler_assign | status_resolved | N | N
68746 | MEP_Revise RFA_430_DF_GS_rUbergang_Flanged | 2026-03-04 | 2026-03-09 | 4 | handler_assign | status_resolved | N | N
68745 | MEP_Revise RFA_430_DF_GS_rReducer_Spigot_Round. | 2026-03-04 | 2026-04-29 | 41 | handler_assign | status_resolved | N | N
68744 | MEP_Revise RFA_430_DF_GS_eTransitionElbow_Flanged | 2026-03-05 | 2026-05-07 | 46 | handler_assign | status_resolved | N | N
68659 | MEP_Revise RFA_430_DF_GS_eRoundElbow_Spigot | 2026-02-26 | 2026-03-02 | 3 | handler_assign | status_resolved | N | N
68658 | MEP_Revise RFA_430_DF_GS_eEckbogen_Flanged | 2026-02-26 | 2026-02-27 | 2 | handler_assign | status_resolved | N | N
68657 | MEP_Revise RFA_430_DF_GS_eBogen_Flanged | 2026-02-25 | 2026-03-02 | 4 | handler_assign | status_resolved | N | N
68656 | MEP_Revise RFA_430_DF_GS_cCapEnd_Spigot_Round | 2026-02-27 | 2026-03-02 | 2 | handler_assign | status_resolved | N | N
68655 | MEP_Revise RFA_430_DF_GS_cBoden_Flanged | 2026-02-26 | 2026-05-06 | 50 | handler_assign | status_resolved | N | N
68654 | MEP_Revise RFA_430_DF_GalvanizedSteel_Ubergangsstutzen_Flanged | 2026-02-26 | 2026-05-07 | 51 | handler_assign | status_resolved | N | N
68617 | MEP_Revise RFA_480_FA_PushButton_WallMounted_RWA_Part 2 | 2026-02-23 | 2026-02-25 | 3 | handler_assign | status_resolved | N | N
68615 | MEP_Revise RFA_440_CI_PVC_cMarkerforConnectionLugs_Part 2 | 2026-02-23 | 2026-02-24 | 2 | handler_assign | status_resolved | N | N
68554 | MEP_Revise RFA_440_LF_EscapeSign_CeilingRecessed.rfa_Part 2 | 2026-02-11 | 2026-02-24 | 10 | handler_assign | status_resolved | N | N
68553 | MEP_Revise RFA_480_FA_Bell.rfa_Part 2 | 2026-02-11 | 2026-02-23 | 9 | handler_assign | status_resolved | N | N
68552 | MEP_Revise RFA_440_LF_CoreLineLEDLight_CeilingSuspended.rfa_Part 2 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | N | N
68551 | MEP_Revise RFA_440_EF_EquipotentialBondingBusbars_WallMounted.rfa_Part 2 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | N | N
68550 | MEP_Revise RFA_440_NC_EmergencyPullCordSwitch_Wall_Part 2 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | N | N
68542 | 630_Annotation_General_Populate the graphical expectation for Layout_Part 1 | 2026-02-11 | 2026-02-13 | 3 | handler_assign | status_resolved | N | N
68493 | Annotation_General_Assess and Populate the data requirement | 2026-02-09 |  |  | handler_assign | none | N | Y | missing_end
68489 | ELT_Installations_LPH5_Sample Layout_Multiple Scales | 2026-02-09 | 2026-02-11 | 3 | handler_assign | status_resolved | N | N
68484 | MSR_LPH3_Sample Schematic | 2026-02-09 | 2026-02-11 | 3 | handler_assign | status_resolved | N | N
68476 | 2026_Annotation Project_TL & TM Time allocation_Sang Xui Duong | 2026-02-06 |  |  | handler_assign | none | N | Y | missing_end
68450 | Revising Family_410_ME_PumpGlandlessCirculator_StarZD._Part 1 | 2026-02-05 | 2026-04-10 | 47 | handler_assign | status_closed | N | N
68438 | ELT_LPH3_Sample Schematic | 2026-02-04 | 2026-02-06 | 3 | handler_assign | status_resolved | N | N
68436 | Annotation_General_Create RACI Table | 2026-02-04 | 2026-02-06 | 3 | handler_assign | status_resolved | N | N
68400 | Annotation_DIG_Revise RFA_Implement and Debate | 2026-02-02 | 2026-02-04 | 3 | handler_assign | status_resolved | N | N
68340 | Annotation_General_Verify the family name and ticket summary matching | 2026-01-29 | 2026-05-15 | 77 | handler_assign | status_resolved | N | N
68325 | Revising Family_410_ME_CompactPressureBoostingSystem_Part 1 | 2026-01-29 | 2026-04-10 | 52 | handler_assign | confirm_note:task_completed_closed | N | N
68323 | MSR_LPH3_Sample Layout_Multiple Scales | 2026-01-29 | 2026-02-03 | 4 | handler_assign | status_resolved | N | N
68322 | Revising Family_480_FA_PushButton_WallMounted_RWA_Part 1 | 2026-01-29 | 2026-01-30 | 2 | handler_assign | status_resolved | N | N
68300 | Revising Family_440_EF_MotionDetector360_CeilingSurface.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | N | N
68299 | Revising Family_440_EF_EquipotentialBondingBusbars_WallMounted.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | N | N
68298 | Revising Family_440_CI_PVC_cMarkerforConnectionLugs.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | N | N
68297 | Revising Family_440_EE_Generator_Standard.rfa_Part 1 | 2026-01-28 | 2026-01-29 | 2 | handler_assign | status_resolved | N | N
68288 | Annotation_General_Exchange Information Requirement Creation | 2026-01-27 | 2026-02-05 | 8 | handler_assign | status_resolved | N | N
68287 | ELT_Installations_LPH3_Sample Layout_Multiple Scales | 2026-01-27 | 2026-01-30 | 4 | handler_assign | status_resolved | N | N
68281 | KLT_Inspecting system for LPH3 + LPH5 + LPH8 output | 2026-01-28 | 2026-03-06 | 28 | handler_assign | status_closed | N | N
68280 | HZG_Inspecting system for LPH3 + LPH5 + LPH8 output | 2026-01-28 | 2026-03-06 | 28 | handler_assign | status_closed | N | N
68279 | KLT_Propose Drawing List_LPH3 + LPH5 + LPH8 | 2026-01-28 | 2026-02-02 | 4 | handler_assign | status_resolved | N | N
68278 | HZG_Propose Drawing List_LPH3 + LPH5 + LPH8 | 2026-01-28 | 2026-02-02 | 4 | handler_assign | status_resolved | N | N
68277 | KLT_Detail Item_Symbol Proposal | 2026-01-28 | 2026-02-04 | 6 | handler_assign | status_resolved | N | N
68276 | HZG_Detail Item_Symbol Proposal | 2026-01-27 | 2026-02-04 | 7 | handler_assign | status_resolved | N | N
68263 | Revising Family_480_FA_Bell.rfa_Part 1 | 2026-01-26 | 2026-01-28 | 3 | handler_assign | status_resolved | N | N
68250 | KLT_Create sample layout + schematic | 2026-01-26 | 2026-01-27 | 2 | handler_assign | status_resolved | N | N
68249 | HZG_Create sample layout + schematic | 2026-01-26 | 2026-01-27 | 2 | handler_assign | status_resolved | N | N
68227 | Revising Family_473_PA_CondensateDistributor2Branch_WOSCD.rfa_Part 1 | 2026-01-23 | 2026-01-30 | 6 | handler_assign | status_resolved | N | N
68223 | Revising Family_473_ME_HeatlessRegenerationAdsorptionDryers_ActivatedCarbonTower.rfa_Part 1 | 2026-01-23 | 2026-01-30 | 6 | handler_assign | status_resolved | N | N
68202 | Annotation_DIG_Create the testing and confirming environment_SubTask03and04 | 2026-01-22 | 2026-01-28 | 5 | handler_assign | status_resolved | N | N
68201 | Annotation_DIG_Create the testing and confirming environment_SubTask01and02 | 2026-01-22 | 2026-01-22 | 1 | handler_assign | status_resolved | N | N
68199 | Test update error | 2026-01-22 | 2026-01-22 | 1 | handler_assign | status_closed | N | N
68192 | Annotation_DIG_Set up and config the Database of information | 2026-01-22 | 2026-05-18 | 83 | handler_assign | status_resolved | N | N
68190 | Annotation_General_TIDP Set up and creation_Hanh Pham | 2026-01-22 | 2026-01-22 | 1 | handler_assign | status_closed | N | N
68182 | DCMvn_Annotation_MSR_Detail Item_Symbol Proposal | 2026-01-21 | 2026-01-27 | 5 | handler_assign | status_resolved | N | N
68181 | DCMvn_Annotation_ELT_Detail Item_Symbol Proposal | 2026-01-21 | 2026-01-27 | 5 | handler_assign | status_resolved | N | N
68180 | RLT_Revising Family_430_DA_FireDampers_FireProtectionValve_FV_EU.rfa _Part 1 | 2026-01-22 | 2026-01-29 | 6 | handler_assign | status_resolved | N | N
68179 | RLT_Revising Family_430_AT_DisplacementFlowDiffusers_Wall_QLV_Supply.rfa _Part 1 | 2026-01-22 | 2026-01-30 | 7 | handler_assign | status_resolved | N | N
68173 | Revising Family_420_ME_AirCurtain_WallMounted.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68172 | Revising Family_491_SE_ArmWithAngleBracket.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68171 | Revising Family_491_NF_GussetPlateBase.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68167 | Revising Family_434_PF_CO_Bend_Mapress.rfa_Part 1 | 2026-01-21 | 2026-01-22 | 2 | handler_assign | status_resolved | N | N
68166 | Revising Family_434_PA_RefnetJoint_KHRPGas.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68165 | Revising Family_434_ME_FanCoilUnit_CeilingCassette_Standard.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68164 | Revising Family_420_PF_Copper_Elbow.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68163 | Revising Family_420_PA_BalancingValve_Flanged.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68162 | Revising Family_420_ME_RadiatorFlatPanel_WallMounted_ThermX2PlanV.rfa_Part 1 | 2026-01-21 | 2026-01-23 | 3 | handler_assign | status_resolved | N | N
68161 | DCMvn_Annotation_SPR_Detail Item_Symbol Proposal | 2026-01-21 | 2026-04-10 | 58 | handler_assign | confirm_note:task_completed_closed | N | N
68160 | DCMvn_Annotation_SAN_Detail Item_Symbol Proposal | 2026-01-21 | 2026-04-10 | 58 | handler_assign | confirm_note:task_completed_closed | N | N
68153 | Revising Family_410_PA_StainlessSteel_ShutoffValve_MapressGeberit.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | N | N
68152 | Revising Family_410_PX_FloorDrain_Horizontal_QuickCoupling_Plastic_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | N | N
68151 | Revising Family_410_ME_WastewaterLiftingStation_DouPump.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | N | N
68150 | Revising Family_410_ME_CentrifugalPump.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | N | N
68149 | Revising Family_474_SP_Pendent.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | N | N
68148 | Revising Family_474_PA_AlarmCheckValve_European.rfa_Part 1 | 2026-01-20 | 2026-04-10 | 59 | handler_assign | confirm_note:task_completed_closed | N | N
68146 | Annotation_General_TIDP Set up and creation_Hanh Pham | 2026-01-20 | 2026-02-09 | 15 | handler_assign | status_resolved | N | N
68145 | Annotation_General_TIDP Set up and creation_Sang Duong | 2026-01-20 | 2026-05-11 | 80 | handler_assign | status_resolved | N | N
68144 | Annotation_General_TIDP Set up and creation_Nhut Le | 2026-01-20 | 2026-02-06 | 14 | handler_assign | status_resolved | N | N
68143 | Annotation_General_TIDP Set up and creation_Thuong Huynh | 2026-01-20 | 2026-02-03 | 11 | handler_assign | status_resolved | N | N
68142 | Annotation_General_TIDP Set up and creation_Lam Truong | 2026-01-20 | 2026-02-27 | 29 | handler_assign | status_resolved | N | N
68140 | Annotation_General_TIDP Set up and creation_Digital Coordinator | 2026-01-20 | 2026-01-21 | 2 | handler_assign | status_resolved | N | N
68139 | Annotation_DIG_Create the testing and confirming environment | 2026-01-20 | 2026-01-28 | 7 | handler_assign | status_resolved | N | N
68138 | Annotation_DIG_Confirm the possibility of reflection data by native Revit Parameter | 2026-01-20 | 2026-02-02 | 10 | handler_assign | status_resolved | N | N
68132 | MED_Detail Item_Symbol Proposal | 2026-01-27 | 2026-02-06 | 9 | handler_assign | status_resolved | N | N
68131 | RLT_Detail Item_Symbol Proposal | 2026-01-27 | 2026-02-25 | 22 | handler_assign | status_resolved | N | N
68109 | Revising Family_480_CD_CabinetLoudspeaker6W_WallMounted_Circular.rfa_Part 1 | 2026-01-19 | 2026-01-20 | 2 | handler_assign | status_resolved | N | N
68108 | Revising Family_440_NC_EmergencyPullCordSwitch_Wall.rfa_Part 1 | 2026-01-19 | 2026-01-20 | 2 | handler_assign | status_resolved | N | N
68107 | Revising Family_440_LF_EscapeSign_CeilingRecessed.rfa_Part 1 | 2026-01-19 | 2026-01-22 | 4 | handler_assign | status_resolved | N | N
68106 | Revising Family_440_LF_CoreLineLEDLight_CeilingSuspended.rfa_Part 1 | 2026-01-19 | 2026-01-22 | 4 | handler_assign | status_resolved | N | N
68105 | Revising Family_440_EF_DataConnectionSocket_Wall.rfa_Part 1 | 2026-01-19 | 2026-01-21 | 3 | handler_assign | status_resolved | N | N
68061 | Annotation_DIG_Create the Revit sample file | 2026-01-14 | 2026-01-21 | 6 | handler_assign | status_resolved | N | N
68054 | Annotation_Data Requirement Framework_Row 4_All System_Data Information Proposal | 2026-01-14 | 2026-01-19 | 4 | handler_assign | status_resolved | N | N
68032 | Annotation_MSR_General_Assess and Populate the data requirement_Part 2 | 2026-01-13 | 2026-01-16 | 4 | handler_assign | status_resolved | N | N
68031 | Annotation_ELT_General_Assess and Populate the data requirement_Part 2 | 2026-01-13 | 2026-01-16 | 4 | handler_assign | status_resolved | N | N
68018 | Annotation_HGR_General_Assess and Populate the data requirement | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | N | N
68017 | HGR_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-15 | 4 | handler_assign | status_resolved | N | N
68016 | KLT_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-04-10 | 65 | handler_assign | confirm_note:confirm_other | N | N
68015 | HZG_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-04-10 | 65 | handler_assign | confirm_note:confirm_other | N | N
68014 | SPR_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-16 | 5 | handler_assign | status_resolved | N | N
68013 | SAN_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-16 | 5 | handler_assign | status_resolved | N | N
68012 | System Family_Annotation_General_Populate the graphical expectation for Layout_Part 1 | 2026-01-12 | 2026-01-13 | 2 | handler_assign | status_resolved | N | N
68011 | Data Requirement Proposal for SPR discipline through LPH3,LPH5 and LPH8 | 2026-01-12 | 2026-02-02 | 16 | handler_assign | status_resolved | N | N
68010 | Data Requirement Proposal for SAN discipline through LPH3,LPH5 and LPH8 | 2026-01-12 | 2026-02-02 | 16 | handler_assign | status_resolved | N | N
68009 | ELT_Annotation_General_Populate the graphical expectation for Layout_Remaining Items | 2026-01-12 | 2026-01-12 | 1 | handler_assign | status_resolved | N | N
68008 | MSR_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | N | N
68007 | ELT_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | N | N
68005 | MED_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | N | N
68004 | RLT_Annotation_General_Populate the graphical expectation for Layout_Part 2 | 2026-01-12 | 2026-01-14 | 3 | handler_assign | status_resolved | N | N
67971 | Annotation_Row 3_Data Requirement Proposal for TGA System Elements | 2026-01-08 | 2026-01-09 | 2 | handler_assign | status_resolved | N | N
67944 | Annotation_Data Requirement Framework_Row 3_All System_Data Information Proposal | 2026-01-07 | 2026-01-13 | 5 | handler_assign | status_resolved | N | N
67935 | Annotation_General_MIDP | 2026-01-07 | 2026-01-21 | 11 | handler_assign | status_resolved | N | N
67927 | 2026Q1_Annotation Project_TL & TM Time allocation_Nhut Minh Le | 2026-01-06 | 2026-04-01 | 62 | handler_assign | status_closed | N | N
67921 | Annotation_ELE_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | N | N
67920 | Annotation_SAN_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | N | N
67919 | Annotation_RLT_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | N | N
67918 | Annotation_HZG/KLT_Proposed Data Requirement | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | N | N
67914 | HRG_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-01-09 | 4 | handler_assign | status_resolved | N | N
67910 | SE_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-03-04 | 42 | handler_assign | confirm_note:confirm_other | N | N
67909 | KIT_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-01-08 | 3 | handler_assign | status_resolved | N | N
67908 | BOS_Annotation_General_Populate the graphical expectation for Layout | 2026-01-06 | 2026-01-07 | 2 | handler_assign | status_resolved | N | N
67890 | PD Tasks_2026Q1 | 2026-01-05 | 2026-04-07 | 67 | handler_assign | status_closed | N | N
67855 | 2026Q1_Annotation Project_TL & TM Time allocation_Thuong Van Huynh | 2026-01-02 | 2026-04-10 | 71 | handler_assign | status_closed | N | N
67839 | 2026Q1_Annotation Project_TL & TM Time allocation_Lam Van Truong | 2026-01-02 | 2026-04-17 | 76 | handler_assign | status_closed | N | N
67838 | 2026Q1_DCMvn_Annotation Project_TL & TM Time allocation_Hanh Pham | 2026-01-02 | 2026-03-31 | 63 | handler_assign | status_resolved | N | N
67815 | ELT_Annotation_General_Populate the graphical expectation for Layout_EE | 2025-12-31 | 2026-01-09 | 8 | handler_assign | status_resolved | N | N
67814 | ELT_Annotation_General_Populate the graphical expectation for Layout_LF | 2025-12-31 | 2026-01-09 | 8 | handler_assign | status_resolved | N | N
67812 | ELT_Annotation_General_Populate the graphical expectation for Layout_EF | 2025-12-30 | 2026-01-09 | 9 | handler_assign | status_resolved | N | N
67745 | Annotation_RLT_ME_PowerSupplyUnitAccessControl_WallMounted | 2025-12-25 | 2025-12-31 | 5 | handler_assign | status_resolved | N | N
67744 | Annotation_RLT_ME_Fan_Roof_Exhaust | 2025-12-25 | 2025-12-31 | 5 | handler_assign | status_resolved | N | N
67743 | Annotation_SPR_FA_FireAlarmZoneModuleControl | 2025-12-25 | 2026-04-28 | 89 | handler_assign | status_resolved | N | N
67741 | Annotation_SPR_PA_YStrainer_Grooved | 2025-12-25 | 2026-01-06 | 9 | handler_assign | status_resolved | N | N
67737 | Annotation_General_Link the ticket number to family as recommendation | 2025-12-25 | 2025-12-30 | 4 | handler_assign | status_resolved | N | N
67736 | ELT_Annotation_General_Populate the graphical expectation for Layout_CI | 2025-12-25 | 2026-01-02 | 7 | handler_assign | status_resolved | N | N
67716 | Annotation_DIG_Tracking and backup the file | 2025-12-24 | 2025-12-31 | 6 | handler_assign | status_resolved | N | N
67713 | ELT_Annotation_General_Populate the graphical expectation for Layout_CF | 2025-12-24 | 2025-12-30 | 5 | handler_assign | status_resolved | N | N
67691 | 2025_TL & TM Time allocation_Hanh Pham | 2025-12-24 | 2026-01-02 | 8 | handler_assign | status_closed | N | N
67672 | Annotation_RLT_DA_VolumeFlowRateMeasuringUnits_VMLK | 2025-12-23 | 2025-12-25 | 3 | handler_assign | status_resolved | N | N
67567 | EDV_Annotation_General_Populate the graphical expectation for Layout | 2025-12-22 | 2025-12-23 | 2 | handler_assign | status_resolved | N | N
67566 | Lighting_Annotation_General_Populate the graphical expectation for Layout | 2025-12-22 | 2025-12-23 | 2 | handler_assign | status_resolved | N | N
67565 | BMA_Annotation_General_Populate the graphical expectation for Layout | 2025-12-22 | 2025-12-23 | 2 | handler_assign | status_resolved | N | N
67375 | Annotation_DIG_Pilot the process to integrate the symbol to 3D object | 2025-12-12 | 2025-12-23 | 8 | handler_assign | status_resolved | N | N
67343 | Annotation_MED_General_Assess and Populate the data requirement | 2026-01-02 | 2026-01-07 | 4 | handler_assign | status_resolved | N | N
67342 | Annotation_MSR_General_Assess and Populate the data requirement | 2026-01-02 | 2026-01-07 | 4 | handler_assign | status_resolved | N | N
67341 | Annotation_SPR_General_Assess and Populate the data requirement | 2025-12-15 | 2025-12-26 | 10 | handler_assign | status_resolved | N | N
67340 | Annotation_RLT_General_Assess and Populate the data requirement | 2025-12-12 | 2026-01-30 | 36 | handler_assign | confirm_note:confirm_other | N | N
67308 | Annotation_HZG_General_Assess and Populate the data requirement | 2025-12-16 | 2026-05-27 | 117 | handler_assign | confirm_note:confirm_other | N | N
67307 | Annotation_KLT_General_Assess and Populate the data requirement | 2025-12-16 | 2025-12-26 | 9 | handler_assign | status_resolved | N | N
67305 | Annotation_General_Assess and Populate the data requirement | 2025-12-10 | 2026-09-10 | 197 | handler_assign | status_resolved | N | N
67303 | SAN_Annotation_General_Populate the graphical expectation for Layout_Pipe Fitting | 2025-12-10 | 2025-12-19 | 8 | handler_assign | status_resolved | N | N
67300 | 2025_TL & TM Time allocation_Thuong Huynh | 2025-12-10 | 2026-01-02 | 18 | handler_assign | status_closed | N | N
67262 | Annotation_DIG_Create the checklist and Template report for Detail Item Creation | 2025-12-09 | 2025-12-15 | 5 | handler_assign | status_resolved | N | N
67259 | SAN_Annotation_General_Populate the graphical expectation for Layout | 2025-12-10 | 2025-12-26 | 13 | handler_assign | status_resolved | N | N
67242 | 2025_TL & TM Time allocation_Sang Duong | 2025-12-08 | 2026-02-09 | 46 | handler_assign | status_closed | N | N
67214 | Annotation_DIG_Prepare the workshop material | 2025-12-05 | 2025-12-12 | 6 | handler_assign | status_resolved | N | N
67116 | Annotation_DIG_Question and Answer Meeting Support | 2025-12-04 |  |  | handler_assign | none | N | Y | missing_end
67108 | Annotation_General_Graphical expectation for Layout | 2025-12-02 | 2025-12-04 | 3 | handler_assign | status_resolved | N | N
67010 | Anotation_DIG_Devlope the guideline and process to implement the rfa adjustment | 2025-11-27 | 2025-12-05 | 7 | handler_assign | status_resolved | N | N
66985 | MED_Accessing Revit families | 2025-11-27 | 2026-01-23 | 42 | handler_assign | confirm_note:confirm_other | N | N
66984 | MSR_Accessing Revit families | 2025-12-01 | 2026-01-23 | 40 | handler_assign | confirm_note:confirm_other | N | N
66927 | MSR_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2026-02-04 | 52 | handler_assign | confirm_note:will_be_closed | N | N
66926 | MED_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2026-01-30 | 49 | handler_assign | confirm_note:confirm_other | N | N
66924 | SPR_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-11 | 13 | handler_assign | status_resolved | N | N
66922 | RLT_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-04 | 8 | handler_assign | status_resolved | N | N
66919 | ELE_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-11-25 | 1 | handler_assign | status_closed | N | N
66918 | SAN_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-12 | 14 | handler_assign | status_closed | N | N
66917 | KLT_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-04 | 8 | handler_assign | confirm_note:confirm_other | N | N
66916 | HZG_Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2025-12-11 | 13 | handler_assign | confirm_note:confirm_other | N | N
66904 | SPR_Accessing Revit families | 2025-11-25 | 2026-01-23 | 44 | handler_assign | confirm_note:confirm_other | N | N
66901 | Annotation_General_Populate the graphical expectation for Layout | 2025-11-25 | 2026-05-21 | 128 | handler_assign | status_resolved | N | N
66900 | ELE_Accessing Revit families | 2025-11-25 | 2025-12-03 | 7 | handler_assign | status_resolved | N | N
66899 | SAN_Accessing Revit families | 2025-11-25 | 2025-12-03 | 7 | handler_assign | status_resolved | N | N
66898 | ELE_Revit family and required information list | 2025-11-25 | 2025-11-26 | 2 | handler_assign | confirm_note:confirm_other | N | N
66897 | SPR_Revit family and required information list | 2025-11-25 | 2025-11-25 | 1 | handler_assign | status_resolved | N | N
66896 | SAN_Revit family and required information list | 2025-11-25 | 2025-11-26 | 2 | handler_assign | confirm_note:confirm_other | N | N
66855 | RLT_Accessing Revit families | 2025-11-25 | 2026-01-23 | 44 | handler_assign | confirm_note:confirm_other | N | N
66854 | HZG/KLT_Revit family and required information list | 2025-11-24 | 2025-11-24 | 1 | handler_assign | status_resolved | N | N
66853 | HZG/KLT_Accessing Revit families | 2025-11-24 | 2025-12-03 | 8 | handler_assign | confirm_note:confirm_other | N | N
66840 | PD Tasks | 2025-11-24 | 2026-01-05 | 31 | handler_assign | status_closed | N | N
66785 | RLT_Anotation_Update layout based on new family | 2025-11-20 | 2025-11-24 | 3 | handler_assign | status_resolved | N | N
66709 | Annotation_DIG_Propose process to integrate the the symbol to rfa_DA | 2025-11-18 | 2025-11-28 | 9 | handler_assign | status_resolved | N | N
66706 | O1_Creating detailed items | 2025-11-18 | 2025-11-25 | 6 | handler_assign | confirm_note:confirm_other | N | N
66678 | RLT_Anotation_Creation View Template | 2025-11-18 | 2025-11-24 | 5 | handler_assign | status_resolved | N | N
66677 | RLT_Anotation_Legend Creation | 2025-11-18 | 2025-11-24 | 5 | handler_assign | status_resolved | N | N
66676 | RLT_Anotation_Update RLT Equipment family | 2025-11-18 | 2025-11-20 | 3 | handler_assign | status_resolved | N | N
66675 | RLT_Anotation_Update Air Terminal family | 2025-11-18 | 2025-11-24 | 5 | handler_assign | status_resolved | N | N
66674 | RLT_Anotation_Update DA family | 2025-11-18 | 2025-11-21 | 4 | handler_assign | status_resolved | N | N
66673 | RLT_Anotation_Update DF family | 2025-11-18 | 2025-11-21 | 4 | handler_assign | status_resolved | N | N
66659 | RLT_Creation Sheet List of Proposal | 2025-11-17 | 2025-11-18 | 2 | handler_assign | status_resolved | N | N
66617 | O1_Creating RLT Legend | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | N | N
66616 | O1_Creating 3D Views | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | N | N
66615 | O1_3D_Creating View Template | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | N | N
66614 | O1_Floor Plan_Creating View Template | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | N | N
66613 | O1_Creating Floor Plan | 2025-11-14 | 2025-11-25 | 8 | handler_assign | status_resolved | N | N
66601 | Anotation_DIG_Assess the symbol of rfa | 2025-11-13 | 2025-11-17 | 3 | handler_assign | status_resolved | N | N
66600 | Anotation_DIG_Upgrade Library to Revit Version 2022 | 2025-11-13 | 2025-11-14 | 2 | handler_assign | status_resolved | N | N
66599 | Anotation_General_Create the target drawing for set out layout_RLT_HG | 2025-11-13 | 2026-05-11 | 128 | handler_assign | status_resolved | N | N
66598 | Anotation_General_Create the target drawing for set out layout_RLT_O1 | 2025-11-13 | 2026-01-30 | 57 | handler_assign | confirm_note:confirm_other | N | N
66592 | RLT_Creation Sheet | 2025-11-13 | 2025-11-17 | 3 | handler_assign | status_resolved | N | N
66578 | 2025_TL & TM Time allocation_Nhut Le | 2025-11-12 | 2026-01-06 | 40 | handler_assign | status_closed | N | N
66575 | 2025_TL & TM Time allocation | 2025-11-12 | 2026-01-02 | 38 | handler_assign | status_closed | N | N

## Summary
Key | Value
Generated_ICT | 2026-10-01 15:32:49 ICT
Matrix_rows | 2703
Family_rows | 2043
Unique_Ticket_IDs_union | 2745
Matrix_only | 701
Family_only | 42
Overlap | 2002
Loaded_from_cache | 2309
Fetched_new_ok | 436
Fetch_failed | 0
No_issue_record | 0
Has_Start | 2744
Missing_Start | 1
Start_coverage_pct | 99.96
Has_End | 2695
Missing_End | 50
End_coverage_pct | 98.18
Has_Start_End_Duration | 2695
Both_coverage_pct | 98.18
End_before_Start | 0
Duration_computed | 2695
Family_with_primary | 2043
Family_missing_Start_or_End | 0
Weekend_rule | Duration = inclusive working days Mon–Fri; Sat+Sun excluded; Asia/Bangkok date part
Start_def | earliest of first handler→real assignee OR first status→assigned; not created_at alone
End_def | last confirm-done note after Start (prefer stored_full); else first status→resolved/closed after Start
NOT_merged_into_Checked | YES — draft only; await parent/user merge approval
Start_Method | Count
handler_assign | 2744
none | 1
End_Method | Count
confirm_note:stored_full | 2004
status_resolved | 601
none | 50
status_closed | 39
confirm_note:will_be_closed | 19
confirm_note:confirm_other | 18
confirm_note:task_completed_closed | 11
confirm_note:passed_audit | 3